## Rollout summary
Rollout | On-air window | Sites | DU | U | SU | Rural | Highway | Sectors | Hubs | Access fiber km | Agg fiber km | Backbone km | Indoor venues | Cum. sites | Cum. pop. covered % | Cum. 1 Gbps km² | Sites / month | Main areas
RO-01 | Apr 2027 – Jun 2027 | 306 | 293 | 13 | 0 | 0 | 0 | 918 | 6 | 228 | 32 | 87 | 0 | 306 | 8.6 | 40 | 102 | Amman-Zarqa Metro (306)
RO-02 | Jul 2027 – Sep 2027 | 465 | 176 | 289 | 0 | 0 | 0 | 1395 | 10 | 381 | 64 | 194 | 18 | 771 | 18.4 | 117 | 155 | Amman-Zarqa Metro (375), Irbid (90)
RO-03 | Oct 2027 – Dec 2027 | 617 | 8 | 589 | 20 | 0 | 0 | 1851 | 15 | 537 | 108 | 340 | 5 | 1388 | 28.5 | 236 | 206 | Amman-Zarqa Metro (456), Aqaba (123), Irbid (38)
RO-04 | Jan 2028 – Mar 2028 | 719 | 0 | 625 | 61 | 0 | 33 | 2124 | 16 | 611 | 108 | 337 | 14 | 2107 | 39.3 | 376 | 240 | Amman-Zarqa Metro (466), Irbid (168), Aqaba (52), Desert Highway (R15) Amman-Aqaba (33)
RO-05 | Apr 2028 – Jun 2028 | 769 | 0 | 561 | 176 | 0 | 32 | 2275 | 19 | 697 | 109 | 278 | 1 | 2876 | 50.1 | 550 | 256 | Amman-Zarqa Metro (618), Wadi Musa / Petra (65), Irbid (35), Dead Sea - Wadi Araba (R65) Amman-Aqaba (32), Dead Sea (19)
RO-06 | Jul 2028 – Sep 2028 | 770 | 0 | 455 | 308 | 0 | 7 | 2303 | 19 | 810 | 106 | 174 | 9 | 3646 | 60.3 | 755 | 257 | Irbid (283), Amman-Zarqa Metro (144), Madaba (122), Mafraq (75), Tafilah (42)
RO-07 | Oct 2028 – Dec 2028 | 766 | 0 | 264 | 191 | 311 | 0 | 2298 | 13 | 463 | 53 | 185 | 0 | 4412 | 73.9 | 878 | 255 | Jerash (117), Ma'an (102), Salt (101), Mafraq (71), Karak governorate (rural) (40)
RO-08 | Jan 2029 – Mar 2029 | 718 | 0 | 166 | 415 | 126 | 11 | 2142 | 18 | 667 | 107 | 471 | 2 | 5130 | 83.4 | 1071 | 239 | Amman-Zarqa Metro (288), Ajloun (81), Amman governorate (rural) (40), Salt (36), Madaba (36)
RO-09 | Apr 2029 – Jun 2029 | 669 | 0 | 2 | 609 | 7 | 51 | 1956 | 17 | 764 | 121 | 0 | 0 | 5799 | 88.9 | 1309 | 223 | Amman-Zarqa Metro (550), Irbid (61), Mafraq-Safawi-Ruwaished (R10) (34), Zarqa-Azraq-Safawi (13), Amman governorate (rural) (7)
RO-10 | Jul 2029 – Sep 2029 | 471 | 0 | 6 | 465 | 0 | 0 | 1413 | 17 | 579 | 80 | 0 | 2 | 6270 | 93 | 1491 | 157 | Amman-Zarqa Metro (208), Irbid (71), Mutah-Mazar (36), Aqaba (34), Azraq (32)

## BoQ by rollout
Item | RO-01 | RO-02 | RO-03 | RO-04 | RO-05 | RO-06 | RO-07 | RO-08 | RO-09 | RO-10 | Total
Macro sites | 306 | 465 | 617 | 719 | 769 | 770 | 766 | 718 | 669 | 471 | 6270
– rooftop | 306 | 452 | 487 | 385 | 359 | 225 | 132 | 181 | 83 | 42 | 2652
– monopole / greenfield | 0 | 13 | 130 | 301 | 378 | 538 | 323 | 400 | 528 | 429 | 3040
– lattice tower 45 m | 0 | 0 | 0 | 33 | 32 | 7 | 311 | 137 | 58 | 0 | 578
Sectors | 918 | 1395 | 1851 | 2124 | 2275 | 2303 | 2298 | 2142 | 1956 | 1413 | 18675
n78 64T64R AAU (3×100 MHz) | 918 | 1395 | 1851 | 2058 | 2211 | 2289 | 1365 | 1743 | 1833 | 1413 | 17076
n78 8T8R radio + antenna (rural) | 0 | 0 | 0 | 0 | 0 | 0 | 933 | 377 | 21 | 0 | 1331
Passive multiband antenna 2L4H + RET | 918 | 1395 | 1851 | 2124 | 2275 | 2303 | 2298 | 2142 | 1956 | 1413 | 18675
n28 RRU | 918 | 1395 | 1851 | 2124 | 2275 | 2303 | 2298 | 2142 | 1956 | 1413 | 18675
n1/n3 dual-band RRU | 918 | 1395 | 1851 | 2124 | 2275 | 2303 | 2298 | 2142 | 1956 | 1413 | 18675
n258 street small cells | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 960
DU (pooled, C-RAN hub) | 230 | 349 | 453 | 515 | 513 | 448 | 320 | 99 | 0 | 0 | 2927
DU (at site, D-RAN) | 0 | 0 | 14 | 33 | 85 | 173 | 340 | 586 | 669 | 471 | 2371
Cell-site router 25GE (D-RAN sites) | 0 | 0 | 14 | 33 | 85 | 173 | 340 | 586 | 669 | 471 | 2371
Fronthaul gateway / passive WDM (C-RAN sites) | 306 | 465 | 603 | 686 | 684 | 597 | 426 | 132 | 0 | 0 | 3899
Hubs (DU hotel / pre-agg) commissioned | 6 | 10 | 15 | 16 | 19 | 19 | 13 | 18 | 17 | 17 | 150
Hub aggregation routers 100GE | 12 | 20 | 30 | 32 | 38 | 38 | 26 | 36 | 34 | 34 | 300
Microwave hops | 0 | 0 | 0 | 0 | 0 | 0 | 246 | 107 | 7 | 0 | 360
Access-ring fiber (route km) | 228 | 381 | 537 | 611 | 697 | 810 | 463 | 667 | 764 | 579 | 5737
Aggregation-ring fiber (route km) | 32 | 64 | 108 | 108 | 109 | 106 | 53 | 107 | 121 | 80 | 888
Backbone / metro-core fiber lit (route km) | 87 | 194 | 340 | 337 | 278 | 174 | 185 | 471 | 0 | 0 | 2066
Backbone add/drop spurs (km) | 0 | 0 | 0 | 30 | 30 | 6 | 60 | 28 | 47 | 0 | 201
Indoor venues | 0 | 18 | 5 | 14 | 1 | 9 | 0 | 2 | 0 | 2 | 51
Indoor n78 pRRU | 0 | 1740 | 573 | 1545 | 88 | 650 | 0 | 319 | 0 | 424 | 5339
Indoor n258 heads | 0 | 58 | 38 | 47 | 4 | 28 | 0 | 4 | 0 | 17 | 196

## Schedule (Gantt)
Rollout | Activity | M1 Jan 2027 | M2 Feb 2027 | M3 Mar 2027 | M4 Apr 2027 | M5 May 2027 | M6 Jun 2027 | M7 Jul 2027 | M8 Aug 2027 | M9 Sep 2027 | M10 Oct 2027 | M11 Nov 2027 | M12 Dec 2027 | M13 Jan 2028 | M14 Feb 2028 | M15 Mar 2028 | M16 Apr 2028 | M17 May 2028 | M18 Jun 2028 | M19 Jul 2028 | M20 Aug 2028 | M21 Sep 2028 | M22 Oct 2028 | M23 Nov 2028 | M24 Dec 2028 | M25 Jan 2029 | M26 Feb 2029 | M27 Mar 2029 | M28 Apr 2029 | M29 May 2029 | M30 Jun 2029 | M31 Jul 2029 | M32 Aug 2029 | M33 Sep 2029 | M34 Oct 2029 | M35 Nov 2029 | M36 Dec 2029
RO-01 | Nominal release, TSSR surveys, site acquisition & permits
RO-01 | Detailed RF / transport design freeze, material call-off
RO-01 | Civil works, power, fiber build to hubs and rings
RO-01 | Hub / DU-hotel and router commissioning
RO-01 | Radio install, commissioning, integration to 5GC
RO-01 | Single-site verification (SSV)
RO-01 | Cluster optimisation & acceptance (1 Gbps drive test)
RO-01 | Commercial launch of rollout area / hand-over to operations
RO-02 | Nominal release, TSSR surveys, site acquisition & permits
RO-02 | Detailed RF / transport design freeze, material call-off
RO-02 | Civil works, power, fiber build to hubs and rings
RO-02 | Hub / DU-hotel and router commissioning
RO-02 | Radio install, commissioning, integration to 5GC
RO-02 | Single-site verification (SSV)
RO-02 | Cluster optimisation & acceptance (1 Gbps drive test)
RO-02 | Commercial launch of rollout area / hand-over to operations
RO-03 | Nominal release, TSSR surveys, site acquisition & permits
RO-03 | Detailed RF / transport design freeze, material call-off
RO-03 | Civil works, power, fiber build to hubs and rings
RO-03 | Hub / DU-hotel and router commissioning
RO-03 | Radio install, commissioning, integration to 5GC
RO-03 | Single-site verification (SSV)
RO-03 | Cluster optimisation & acceptance (1 Gbps drive test)
RO-03 | Commercial launch of rollout area / hand-over to operations
RO-04 | Nominal release, TSSR surveys, site acquisition & permits
RO-04 | Detailed RF / transport design freeze, material call-off
RO-04 | Civil works, power, fiber build to hubs and rings
RO-04 | Hub / DU-hotel and router commissioning
RO-04 | Radio install, commissioning, integration to 5GC
RO-04 | Single-site verification (SSV)
RO-04 | Cluster optimisation & acceptance (1 Gbps drive test)
RO-04 | Commercial launch of rollout area / hand-over to operations
RO-05 | Nominal release, TSSR surveys, site acquisition & permits
RO-05 | Detailed RF / transport design freeze, material call-off
RO-05 | Civil works, power, fiber build to hubs and rings
RO-05 | Hub / DU-hotel and router commissioning
RO-05 | Radio install, commissioning, integration to 5GC
RO-05 | Single-site verification (SSV)
RO-05 | Cluster optimisation & acceptance (1 Gbps drive test)
RO-05 | Commercial launch of rollout area / hand-over to operations
RO-06 | Nominal release, TSSR surveys, site acquisition & permits
RO-06 | Detailed RF / transport design freeze, material call-off
RO-06 | Civil works, power, fiber build to hubs and rings
RO-06 | Hub / DU-hotel and router commissioning
RO-06 | Radio install, commissioning, integration to 5GC
RO-06 | Single-site verification (SSV)
RO-06 | Cluster optimisation & acceptance (1 Gbps drive test)
RO-06 | Commercial launch of rollout area / hand-over to operations
RO-07 | Nominal release, TSSR surveys, site acquisition & permits
RO-07 | Detailed RF / transport design freeze, material call-off
RO-07 | Civil works, power, fiber build to hubs and rings
RO-07 | Hub / DU-hotel and router commissioning
RO-07 | Radio install, commissioning, integration to 5GC
RO-07 | Single-site verification (SSV)
RO-07 | Cluster optimisation & acceptance (1 Gbps drive test)
RO-07 | Commercial launch of rollout area / hand-over to operations
RO-08 | Nominal release, TSSR surveys, site acquisition & permits
RO-08 | Detailed RF / transport design freeze, material call-off
RO-08 | Civil works, power, fiber build to hubs and rings
RO-08 | Hub / DU-hotel and router commissioning
RO-08 | Radio install, commissioning, integration to 5GC
RO-08 | Single-site verification (SSV)
RO-08 | Cluster optimisation & acceptance (1 Gbps drive test)
RO-08 | Commercial launch of rollout area / hand-over to operations
RO-09 | Nominal release, TSSR surveys, site acquisition & permits
RO-09 | Detailed RF / transport design freeze, material call-off
RO-09 | Civil works, power, fiber build to hubs and rings
RO-09 | Hub / DU-hotel and router commissioning
RO-09 | Radio install, commissioning, integration to 5GC
RO-09 | Single-site verification (SSV)
RO-09 | Cluster optimisation & acceptance (1 Gbps drive test)
RO-09 | Commercial launch of rollout area / hand-over to operations
RO-10 | Nominal release, TSSR surveys, site acquisition & permits
RO-10 | Detailed RF / transport design freeze, material call-off
RO-10 | Civil works, power, fiber build to hubs and rings
RO-10 | Hub / DU-hotel and router commissioning
RO-10 | Radio install, commissioning, integration to 5GC
RO-10 | Single-site verification (SSV)
RO-10 | Cluster optimisation & acceptance (1 Gbps drive test)
RO-10 | Commercial launch of rollout area / hand-over to operations

## Work packages
Rollout | Work package | Type | Cluster / route | Sites
RO-01 | HUB-AMM-28 | Hub cluster | Amman-Zarqa Metro | 61
RO-01 | HUB-AMM-69 | Hub cluster | Amman-Zarqa Metro | 55
RO-01 | HUB-AMM-14 | Hub cluster | Amman-Zarqa Metro | 51
RO-01 | HUB-AMM-82 | Hub cluster | Amman-Zarqa Metro | 48
RO-01 | HUB-AMM-13 | Hub cluster | Amman-Zarqa Metro | 47
RO-01 | HUB-AMM-38 | Hub cluster | Amman-Zarqa Metro | 44
RO-02 | HUB-AMM-52 | Hub cluster | Amman-Zarqa Metro | 54
RO-02 | HUB-IRB-15 | Hub cluster | Irbid | 52
RO-02 | HUB-AMM-57 | Hub cluster | Amman-Zarqa Metro | 51
RO-02 | HUB-AMM-41 | Hub cluster | Amman-Zarqa Metro | 50
RO-02 | HUB-AMM-45 | Hub cluster | Amman-Zarqa Metro | 46
RO-02 | HUB-AMM-59 | Hub cluster | Amman-Zarqa Metro | 45
RO-02 | HUB-AMM-23 | Hub cluster | Amman-Zarqa Metro | 43
RO-02 | HUB-AMM-64 | Hub cluster | Amman-Zarqa Metro | 43
RO-02 | HUB-AMM-35 | Hub cluster | Amman-Zarqa Metro | 43
RO-02 | HUB-IRB-01 | Hub cluster | Irbid | 38
RO-03 | HUB-AQB-05 | Hub cluster | Aqaba | 57
RO-03 | HUB-AQB-06 | Hub cluster | Aqaba | 52
RO-03 | HUB-AMM-56 | Hub cluster | Amman-Zarqa Metro | 49
RO-03 | HUB-AMM-83 | Hub cluster | Amman-Zarqa Metro | 48
RO-03 | HUB-AMM-47 | Hub cluster | Amman-Zarqa Metro | 48
RO-03 | HUB-AMM-44 | Hub cluster | Amman-Zarqa Metro | 44
RO-03 | HUB-AMM-79 | Hub cluster | Amman-Zarqa Metro | 41
RO-03 | HUB-AMM-05 | Hub cluster | Amman-Zarqa Metro | 40
RO-03 | HUB-AMM-02 | Hub cluster | Amman-Zarqa Metro | 39
RO-03 | HUB-IRB-05 | Hub cluster | Irbid | 38
RO-03 | HUB-AMM-49 | Hub cluster | Amman-Zarqa Metro | 38
RO-03 | HUB-AMM-11 | Hub cluster | Amman-Zarqa Metro | 37
RO-03 | HUB-AMM-27 | Hub cluster | Amman-Zarqa Metro | 36
RO-03 | HUB-AMM-04 | Hub cluster | Amman-Zarqa Metro | 36
RO-03 | HUB-AQB-07 | Hub cluster | Aqaba | 14
RO-04 | HUB-AMM-40 | Hub cluster | Amman-Zarqa Metro | 54
RO-04 | HUB-AMM-03 | Hub cluster | Amman-Zarqa Metro | 53
RO-04 | HUB-AQB-03 | Hub cluster | Aqaba | 52
RO-04 | HUB-AMM-07 | Hub cluster | Amman-Zarqa Metro | 48
RO-04 | HUB-IRB-11 | Hub cluster | Irbid | 44
RO-04 | HUB-IRB-17 | Hub cluster | Irbid | 42
RO-04 | HUB-AMM-01 | Hub cluster | Amman-Zarqa Metro | 42
RO-04 | HUB-AMM-29 | Hub cluster | Amman-Zarqa Metro | 42
RO-04 | HUB-AMM-24 | Hub cluster | Amman-Zarqa Metro | 42
RO-04 | HUB-IRB-08 | Hub cluster | Irbid | 41
RO-04 | HUB-IRB-07 | Hub cluster | Irbid | 41
RO-04 | HUB-AMM-39 | Hub cluster | Amman-Zarqa Metro | 41
RO-04 | HUB-AMM-15 | Hub cluster | Amman-Zarqa Metro | 41
RO-04 | HUB-AMM-54 | Hub cluster | Amman-Zarqa Metro | 38
RO-04 | HUB-AMM-51 | Hub cluster | Amman-Zarqa Metro | 36
RO-04 | HW¦Desert Highway (R15) Amman-Aqaba | Highway corridor | Desert Highway (R15) Amman-Aqaba | 33
RO-04 | HUB-AMM-36 | Hub cluster | Amman-Zarqa Metro | 29
RO-05 | HUB-AMM-33 | Hub cluster | Amman-Zarqa Metro | 52
RO-05 | HUB-AMM-70 | Hub cluster | Amman-Zarqa Metro | 48
RO-05 | HUB-AMM-46 | Hub cluster | Amman-Zarqa Metro | 48
RO-05 | HUB-AMM-86 | Hub cluster | Amman-Zarqa Metro | 47
RO-05 | HUB-AMM-62 | Hub cluster | Amman-Zarqa Metro | 46
RO-05 | HUB-AMM-66 | Hub cluster | Amman-Zarqa Metro | 42
RO-05 | HUB-AMM-77 | Hub cluster | Amman-Zarqa Metro | 41
RO-05 | HUB-AMM-19 | Hub cluster | Amman-Zarqa Metro | 41
RO-05 | HUB-AMM-61 | Hub cluster | Amman-Zarqa Metro | 39
RO-05 | HUB-AMM-72 | Hub cluster | Amman-Zarqa Metro | 39
RO-05 | HUB-AMM-65 | Hub cluster | Amman-Zarqa Metro | 37
RO-05 | HUB-AMM-22 | Hub cluster | Amman-Zarqa Metro | 37
RO-05 | HUB-AMM-85 | Hub cluster | Amman-Zarqa Metro | 35
RO-05 | HUB-IRB-03 | Hub cluster | Irbid | 35
RO-05 | HUB-WAD-01 | Hub cluster | Wadi Musa / Petra | 34
RO-05 | HUB-AMM-63 | Hub cluster | Amman-Zarqa Metro | 33
RO-05 | HUB-AMM-42 | Hub cluster | Amman-Zarqa Metro | 33
RO-05 | HW¦Dead Sea - Wadi Araba (R65) Amman-Aqaba | Highway corridor | Dead Sea - Wadi Araba (R65) Amman-Aqaba | 32
RO-05 | HUB-WAD-02 | Hub cluster | Wadi Musa / Petra | 31
RO-05 | HUB-DEA-01 | Hub cluster | Dead Sea | 19
RO-06 | HUB-IRB-13 | Hub cluster | Irbid | 71
RO-06 | HUB-IRB-06 | Hub cluster | Irbid | 60
RO-06 | HUB-IRB-18 | Hub cluster | Irbid | 42
RO-06 | HUB-TAF-02 | Hub cluster | Tafilah | 42
RO-06 | HUB-MAD-04 | Hub cluster | Madaba | 42
RO-06 | HUB-AMM-81 | Hub cluster | Amman-Zarqa Metro | 41
RO-06 | HUB-MAD-02 | Hub cluster | Madaba | 41
RO-06 | HUB-MAF-05 | Hub cluster | Mafraq | 39
RO-06 | HUB-MAD-03 | Hub cluster | Madaba | 39
RO-06 | HUB-IRB-04 | Hub cluster | Irbid | 38
RO-06 | HUB-KAR-03 | Hub cluster | Karak | 38
RO-06 | HUB-IRB-09 | Hub cluster | Irbid | 37
RO-06 | HUB-AMM-60 | Hub cluster | Amman-Zarqa Metro | 37
RO-06 | HUB-MAF-02 | Hub cluster | Mafraq | 36
RO-06 | HUB-MA-02 | Hub cluster | Ma'an | 35
RO-06 | HUB-IRB-19 | Hub cluster | Irbid | 35
RO-06 | HUB-AMM-76 | Hub cluster | Amman-Zarqa Metro | 33
RO-06 | HUB-AMM-06 | Hub cluster | Amman-Zarqa Metro | 33
RO-06 | HUB-AQB-02 | Hub cluster | Aqaba | 24
RO-06 | HW¦King's Highway Madaba-Karak-Tafilah-Petra-Ma'an | Highway corridor | King's Highway Madaba-Karak-Tafilah-Petra-Ma'an | 7
RO-07 | RUR¦Karak¦1 | Rural package | Karak governorate (rural) | 40
RO-07 | RUR¦Amman¦1 | Rural package | Amman governorate (rural) | 40
RO-07 | RUR¦Madaba¦1 | Rural package | Madaba governorate (rural) | 40
RO-07 | RUR¦Mafraq¦1 | Rural package | Mafraq governorate (rural) | 40
RO-07 | RUR¦Irbid¦1 | Rural package | Irbid governorate (rural) | 40
RO-07 | HUB-JER-02 | Hub cluster | Jerash | 40
RO-07 | HUB-JER-03 | Hub cluster | Jerash | 39
RO-07 | HUB-JER-01 | Hub cluster | Jerash | 38
RO-07 | HUB-MAF-03 | Hub cluster | Mafraq | 36
RO-07 | RUR¦Tafilah¦1 | Rural package | Tafilah governorate (rural) | 35
RO-07 | HUB-MA-03 | Hub cluster | Ma'an | 35
RO-07 | HUB-SAL-01 | Hub cluster | Salt | 35
RO-07 | HUB-SAL-02 | Hub cluster | Salt | 35
RO-07 | HUB-MA-01 | Hub cluster | Ma'an | 35
RO-07 | HUB-MAF-04 | Hub cluster | Mafraq | 35
RO-07 | HUB-KAR-02 | Hub cluster | Karak | 35
RO-07 | HUB-MA-04 | Hub cluster | Ma'an | 32
RO-07 | HUB-SAL-03 | Hub cluster | Salt | 31
RO-07 | HUB-AMM-71 | Hub cluster | Amman-Zarqa Metro | 29
RO-07 | RUR¦Balqa¦1 | Rural package | Balqa governorate (rural) | 28
RO-07 | RUR¦Ajloun¦1 | Rural package | Ajloun governorate (rural) | 19
RO-07 | RUR¦Jerash¦1 | Rural package | Jerash governorate (rural) | 16
RO-07 | RUR¦Zarqa¦1 | Rural package | Zarqa governorate (rural) | 13
RO-08 | HUB-AMM-37 | Hub cluster | Amman-Zarqa Metro | 48
RO-08 | HUB-AMM-73 | Hub cluster | Amman-Zarqa Metro | 46
RO-08 | RUR¦Amman¦2 | Rural package | Amman governorate (rural) | 40
RO-08 | HUB-SAL-04 | Hub cluster | Salt | 36
RO-08 | HUB-MAD-01 | Hub cluster | Madaba | 36
RO-08 | HUB-AMM-58 | Hub cluster | Amman-Zarqa Metro | 36
RO-08 | RUR¦Karak¦2 | Rural package | Karak governorate (rural) | 35
RO-08 | HUB-AMM-21 | Hub cluster | Amman-Zarqa Metro | 35
RO-08 | HUB-KAR-01 | Hub cluster | Karak | 34
RO-08 | HUB-AMM-50 | Hub cluster | Amman-Zarqa Metro | 34
RO-08 | HUB-AMM-20 | Hub cluster | Amman-Zarqa Metro | 33
RO-08 | HUB-MAF-01 | Hub cluster | Mafraq | 31
RO-08 | HUB-TAF-01 | Hub cluster | Tafilah | 30
RO-08 | HUB-AMM-84 | Hub cluster | Amman-Zarqa Metro | 30
RO-08 | RUR¦Mafraq¦2 | Rural package | Mafraq governorate (rural) | 29
RO-08 | HUB-AJL-02 | Hub cluster | Ajloun | 29
RO-08 | HUB-AJL-03 | Hub cluster | Ajloun | 27
RO-08 | HUB-IRB-12 | Hub cluster | Irbid | 27
RO-08 | HUB-AMM-74 | Hub cluster | Amman-Zarqa Metro | 26
RO-08 | HUB-AJL-01 | Hub cluster | Ajloun | 25
RO-08 | RUR¦Irbid¦2 | Rural package | Irbid governorate (rural) | 21
RO-08 | HUB-AQB-04 | Hub cluster | Aqaba | 18
RO-08 | HW¦Amman-Azraq (R40) | Highway corridor | Amman-Azraq (R40) | 9
RO-08 | HW¦Karak-Qatraneh | Highway corridor | Karak-Qatraneh | 1
RO-08 | HW¦Tafilah-Jurf | Highway corridor | Tafilah-Jurf | 1
RO-08 | RUR¦Madaba¦2 | Rural package | Madaba governorate (rural) | 1
RO-09 | HUB-AMM-78 | Hub cluster | Amman-Zarqa Metro | 55
RO-09 | HUB-AMM-16 | Hub cluster | Amman-Zarqa Metro | 49
RO-09 | HUB-AMM-30 | Hub cluster | Amman-Zarqa Metro | 47
RO-09 | HUB-AMM-32 | Hub cluster | Amman-Zarqa Metro | 42
RO-09 | HUB-AMM-55 | Hub cluster | Amman-Zarqa Metro | 40
RO-09 | HUB-AMM-25 | Hub cluster | Amman-Zarqa Metro | 39
RO-09 | HUB-AMM-53 | Hub cluster | Amman-Zarqa Metro | 37
RO-09 | HUB-AMM-34 | Hub cluster | Amman-Zarqa Metro | 36
RO-09 | HUB-AMM-43 | Hub cluster | Amman-Zarqa Metro | 36
RO-09 | HUB-AMM-31 | Hub cluster | Amman-Zarqa Metro | 35
RO-09 | HW¦Mafraq-Safawi-Ruwaished (R10) | Highway corridor | Mafraq-Safawi-Ruwaished (R10) | 34
RO-09 | HUB-IRB-16 | Hub cluster | Irbid | 33
RO-09 | HUB-AMM-68 | Hub cluster | Amman-Zarqa Metro | 33
RO-09 | HUB-AMM-67 | Hub cluster | Amman-Zarqa Metro | 32
RO-09 | HUB-AMM-10 | Hub cluster | Amman-Zarqa Metro | 28
RO-09 | HUB-IRB-02 | Hub cluster | Irbid | 28
RO-09 | HUB-AMM-26 | Hub cluster | Amman-Zarqa Metro | 22
RO-09 | HUB-AMM-18 | Hub cluster | Amman-Zarqa Metro | 19
RO-09 | HW¦Zarqa-Azraq-Safawi | Highway corridor | Zarqa-Azraq-Safawi | 13
RO-09 | RUR¦Amman¦3 | Rural package | Amman governorate (rural) | 7
RO-09 | HW¦Quweira-Wadi Rum | Highway corridor | Quweira-Wadi Rum | 4
RO-10 | HUB-AMM-80 | Hub cluster | Amman-Zarqa Metro | 50
RO-10 | HUB-AMM-75 | Hub cluster | Amman-Zarqa Metro | 37
RO-10 | HUB-MUT-01 | Hub cluster | Mutah-Mazar | 36
RO-10 | HUB-AMM-48 | Hub cluster | Amman-Zarqa Metro | 35
RO-10 | HUB-AQB-01 | Hub cluster | Aqaba | 34
RO-10 | HUB-AZR-01 | Hub cluster | Azraq | 32
RO-10 | HUB-IRB-20 | Hub cluster | Irbid | 26
RO-10 | HUB-IRB-14 | Hub cluster | Irbid | 24
RO-10 | HUB-AMM-08 | Hub cluster | Amman-Zarqa Metro | 24
RO-10 | HUB-DEI-01 | Hub cluster | Deir Alla | 24
RO-10 | HUB-GHO-01 | Hub cluster | Ghor Safi | 23
RO-10 | HUB-SOU-01 | Hub cluster | South Shuna | 23
RO-10 | HUB-AMM-17 | Hub cluster | Amman-Zarqa Metro | 22
RO-10 | HUB-AMM-12 | Hub cluster | Amman-Zarqa Metro | 21
RO-10 | HUB-IRB-10 | Hub cluster | Irbid | 21
RO-10 | HUB-NOR-01 | Hub cluster | North Shuna | 20
RO-10 | HUB-AMM-09 | Hub cluster | Amman-Zarqa Metro | 19

## Sites
Rollout | Site | Class | Type | Cluster | Governorate | Lat | Lon | Ant. height m | Sectors | Hub | Ring | Backhaul
RO-01 | AMM-DU-0001 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9313 | 35.9381 | 25 | 3 | HUB-AMM-38 | HUB-AMM-38-R02 | Fiber ring
RO-01 | AMM-DU-0004 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9336 | 35.9164 | 25 | 3 | HUB-AMM-38 | HUB-AMM-38-R01 | Fiber ring
RO-01 | AMM-DU-0005 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9339 | 35.92 | 30 | 3 | HUB-AMM-38 | HUB-AMM-38-R01 | Fiber ring
RO-01 | AMM-DU-0006 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9343 | 35.9251 | 30 | 3 | HUB-AMM-38 | HUB-AMM-38-R01 | Fiber ring
RO-01 | AMM-DU-0007 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9339 | 35.9286 | 30 | 3 | HUB-AMM-38 | HUB-AMM-38-R02 | Fiber ring
RO-01 | AMM-DU-0008 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9336 | 35.9322 | 30 | 3 | HUB-AMM-38 | HUB-AMM-38-R02 | Fiber ring
RO-01 | AMM-DU-0009 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9343 | 35.9361 | 25 | 3 | HUB-AMM-38 | HUB-AMM-38-R03 | Fiber ring
RO-01 | AMM-DU-0010 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9346 | 35.9397 | 25 | 3 | HUB-AMM-38 | HUB-AMM-38-R03 | Fiber ring
RO-01 | AMM-DU-0016 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9379 | 35.9145 | 25 | 3 | HUB-AMM-38 | HUB-AMM-38-R06 | Fiber ring
RO-01 | AMM-DU-0017 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9365 | 35.9184 | 27 | 3 | HUB-AMM-38 | HUB-AMM-38-R01 | Fiber ring
RO-01 | AMM-DU-0018 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9372 | 35.9216 | 29 | 3 | HUB-AMM-38 | HUB-AMM-38-R07 | Fiber ring
RO-01 | AMM-DU-0019 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9372 | 35.9271 | 30 | 3 | HUB-AMM-38 | HUB-AMM-38-R06 | Fiber ring
RO-01 | AMM-DU-0020 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9369 | 35.9298 | 31 | 3 | HUB-AMM-38 | HUB-AMM-38-R01 | Fiber ring
RO-01 | AMM-DU-0021 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9365 | 35.9342 | 28 | 3 | HUB-AMM-38 | HUB-AMM-38-R03 | Fiber ring
RO-01 | AMM-DU-0022 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9372 | 35.9381 | 26 | 3 | HUB-AMM-38 | HUB-AMM-38-R03 | Fiber ring
RO-01 | AMM-DU-0023 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9372 | 35.9412 | 26 | 3 | HUB-AMM-38 | HUB-AMM-38-R03 | Fiber ring
RO-01 | AMM-DU-0032 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.9157 | 25 | 3 | HUB-AMM-38 | HUB-AMM-38-R06 | Fiber ring
RO-01 | AMM-DU-0033 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.9196 | 29 | 3 | HUB-AMM-38 | HUB-AMM-38-R06 | Fiber ring
RO-01 | AMM-DU-0034 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.9251 | 29 | 3 | HUB-AMM-38 | HUB-AMM-38-R06 | Fiber ring
RO-01 | AMM-DU-0035 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.9275 | 28 | 3 | HUB-AMM-38 | HUB-AMM-38-R05 | Fiber ring
RO-01 | AMM-DU-0036 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.933 | 31 | 3 | HUB-AMM-38 | HUB-AMM-38-R04 | Fiber ring
RO-01 | AMM-DU-0037 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9405 | 35.9365 | 25 | 3 | HUB-AMM-38 | HUB-AMM-38-R03 | Fiber ring
RO-01 | AMM-DU-0038 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.9401 | 26 | 3 | HUB-AMM-38 | HUB-AMM-38-R03 | Fiber ring
RO-01 | AMM-DU-0051 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9424 | 35.9184 | 30 | 3 | HUB-AMM-38 | HUB-AMM-38-R06 | Fiber ring
RO-01 | AMM-DU-0052 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9431 | 35.9216 | 30 | 3 | HUB-AMM-38 | HUB-AMM-38-R06 | Fiber ring
RO-01 | AMM-DU-0053 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9431 | 35.9263 | 31 | 3 | HUB-AMM-38 | HUB-AMM-38-R05 | Fiber ring
RO-01 | AMM-DU-0054 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9427 | 35.9306 | 31 | 3 | HUB-AMM-38 | HUB-AMM-38-R05 | Fiber ring
RO-01 | AMM-DU-0055 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9427 | 35.9346 | 31 | 3 | HUB-AMM-38 | HUB-AMM-38-R04 | Fiber ring
RO-01 | AMM-DU-0056 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9431 | 35.9389 | 27 | 3 | HUB-AMM-38 | HUB-AMM-38-R04 | Fiber ring
RO-01 | AMM-DU-0073 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9453 | 35.9164 | 30 | 3 | HUB-AMM-82 | HUB-AMM-82-R02 | Fiber ring
RO-01 | AMM-DU-0074 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9467 | 35.9204 | 30 | 3 | HUB-AMM-82 | HUB-AMM-82-R02 | Fiber ring
RO-01 | AMM-DU-0075 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9467 | 35.9243 | 31 | 3 | HUB-AMM-38 | HUB-AMM-38-R05 | Fiber ring
RO-01 | AMM-DU-0076 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9467 | 35.9283 | 33 | 3 | HUB-AMM-38 | HUB-AMM-38-R05 | Fiber ring
RO-01 | AMM-DU-0077 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9467 | 35.9322 | 31 | 3 | HUB-AMM-38 | HUB-AMM-38-R05 | Fiber ring
RO-01 | AMM-DU-0078 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.946 | 35.9369 | 32 | 3 | HUB-AMM-38 | HUB-AMM-38-R04 | Fiber ring
RO-01 | AMM-DU-0079 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9453 | 35.9401 | 25 | 3 | HUB-AMM-38 | HUB-AMM-38-R04 | Fiber ring
RO-01 | AMM-DU-0096 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9496 | 35.9105 | 25 | 3 | HUB-AMM-82 | HUB-AMM-82-R01 | Fiber ring
RO-01 | AMM-DU-0097 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9496 | 35.9145 | 27 | 3 | HUB-AMM-82 | HUB-AMM-82-R02 | Fiber ring
RO-01 | AMM-DU-0098 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9489 | 35.9184 | 30 | 3 | HUB-AMM-82 | HUB-AMM-82-R02 | Fiber ring
RO-01 | AMM-DU-0099 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9489 | 35.9224 | 28 | 3 | HUB-AMM-82 | HUB-AMM-82-R02 | Fiber ring
RO-01 | AMM-DU-0100 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9489 | 35.9263 | 29 | 3 | HUB-AMM-82 | HUB-AMM-82-R03 | Fiber ring
RO-01 | AMM-DU-0101 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9486 | 35.9298 | 33 | 3 | HUB-AMM-38 | HUB-AMM-38-R05 | Fiber ring
RO-01 | AMM-DU-0102 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9489 | 35.9334 | 30 | 3 | HUB-AMM-38 | HUB-AMM-38-R04 | Fiber ring
RO-01 | AMM-DU-0103 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9483 | 35.9381 | 32 | 3 | HUB-AMM-38 | HUB-AMM-38-R04 | Fiber ring
RO-01 | AMM-DU-0110 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9519 | 35.8613 | 26 | 3 | HUB-AMM-13 | HUB-AMM-13-R02 | Fiber ring
RO-01 | AMM-DU-0111 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9526 | 35.8653 | 27 | 3 | HUB-AMM-13 | HUB-AMM-13-R02 | Fiber ring
RO-01 | AMM-DU-0112 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9519 | 35.8692 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R02 | Fiber ring
RO-01 | AMM-DU-0113 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9519 | 35.8731 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R03 | Fiber ring
RO-01 | AMM-DU-0114 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9519 | 35.8763 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R03 | Fiber ring
RO-01 | AMM-DU-0115 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9519 | 35.881 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R03 | Fiber ring
RO-01 | AMM-DU-0116 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9519 | 35.8841 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R04 | Fiber ring
RO-01 | AMM-DU-0122 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9526 | 35.9086 | 27 | 3 | HUB-AMM-82 | HUB-AMM-82-R01 | Fiber ring
RO-01 | AMM-DU-0123 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9526 | 35.9125 | 32 | 3 | HUB-AMM-82 | HUB-AMM-82-R01 | Fiber ring
RO-01 | AMM-DU-0124 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9519 | 35.9164 | 27 | 3 | HUB-AMM-82 | HUB-AMM-82-R02 | Fiber ring
RO-01 | AMM-DU-0125 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9519 | 35.9204 | 32 | 3 | HUB-AMM-82 | HUB-AMM-82-R02 | Fiber ring
RO-01 | AMM-DU-0126 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9519 | 35.9235 | 32 | 3 | HUB-AMM-82 | HUB-AMM-82-R03 | Fiber ring
RO-01 | AMM-DU-0127 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9526 | 35.9283 | 30 | 3 | HUB-AMM-82 | HUB-AMM-82-R03 | Fiber ring
RO-01 | AMM-DU-0128 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9512 | 35.9322 | 30 | 3 | HUB-AMM-82 | HUB-AMM-82-R03 | Fiber ring
RO-01 | AMM-DU-0129 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9526 | 35.9361 | 28 | 3 | HUB-AMM-82 | HUB-AMM-82-R03 | Fiber ring
RO-01 | AMM-DU-0130 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9512 | 35.9401 | 34 | 3 | HUB-AMM-28 | HUB-AMM-28-R02 | Fiber ring
RO-01 | AMM-DU-0131 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9512 | 35.944 | 32 | 3 | HUB-AMM-28 | HUB-AMM-28-R02 | Fiber ring
RO-01 | AMM-DU-0139 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9548 | 35.8601 | 28 | 3 | HUB-AMM-13 | HUB-AMM-13-R01 | Fiber ring
RO-01 | AMM-DU-0140 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9548 | 35.8641 | 29 | 3 | HUB-AMM-13 | HUB-AMM-13-R02 | Fiber ring
RO-01 | AMM-DU-0141 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9555 | 35.8672 | 29 | 3 | HUB-AMM-13 | HUB-AMM-13-R02 | Fiber ring
RO-01 | AMM-DU-0142 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9548 | 35.8712 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R03 | Fiber ring
RO-01 | AMM-DU-0143 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9548 | 35.8751 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R03 | Fiber ring
RO-01 | AMM-DU-0144 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9548 | 35.8782 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R03 | Fiber ring
RO-01 | AMM-DU-0145 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9548 | 35.883 | 33 | 3 | HUB-AMM-13 | HUB-AMM-13-R04 | Fiber ring
RO-01 | AMM-DU-0146 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9555 | 35.8869 | 33 | 3 | HUB-AMM-14 | HUB-AMM-14-R02 | Fiber ring
RO-01 | AMM-DU-0147 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9555 | 35.8908 | 27 | 3 | HUB-AMM-14 | HUB-AMM-14-R02 | Fiber ring
RO-01 | AMM-DU-0148 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9545 | 35.8944 | 28 | 3 | HUB-AMM-14 | HUB-AMM-14-R02 | Fiber ring
RO-01 | AMM-DU-0149 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9555 | 35.8987 | 29 | 3 | HUB-AMM-14 | HUB-AMM-14-R03 | Fiber ring
RO-01 | AMM-DU-0150 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9548 | 35.9027 | 26 | 3 | HUB-AMM-14 | HUB-AMM-14-R03 | Fiber ring
RO-01 | AMM-DU-0151 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9548 | 35.9066 | 29 | 3 | HUB-AMM-82 | HUB-AMM-82-R01 | Fiber ring
RO-01 | AMM-DU-0152 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9548 | 35.9105 | 34 | 3 | HUB-AMM-82 | HUB-AMM-82-R01 | Fiber ring
RO-01 | AMM-DU-0153 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9541 | 35.9145 | 35 | 3 | HUB-AMM-82 | HUB-AMM-82-R01 | Fiber ring
RO-01 | AMM-DU-0154 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9555 | 35.9184 | 35 | 3 | HUB-AMM-82 | HUB-AMM-82-R01 | Fiber ring
RO-01 | AMM-DU-0155 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9555 | 35.9224 | 32 | 3 | HUB-AMM-82 | HUB-AMM-82-R03 | Fiber ring
RO-01 | AMM-DU-0156 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9548 | 35.9263 | 32 | 3 | HUB-AMM-82 | HUB-AMM-82-R03 | Fiber ring
RO-01 | AMM-DU-0157 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9548 | 35.9294 | 32 | 3 | HUB-AMM-82 | HUB-AMM-82-R04 | Fiber ring
RO-01 | AMM-DU-0158 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9548 | 35.9346 | 31 | 3 | HUB-AMM-82 | HUB-AMM-82-R04 | Fiber ring
RO-01 | AMM-DU-0159 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9545 | 35.9385 | 37 | 3 | HUB-AMM-28 | HUB-AMM-28-R02 | Fiber ring
RO-01 | AMM-DU-0160 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9541 | 35.942 | 37 | 3 | HUB-AMM-28 | HUB-AMM-28-R02 | Fiber ring
RO-01 | AMM-DU-0161 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9555 | 35.946 | 29 | 3 | HUB-AMM-28 | HUB-AMM-28-R03 | Fiber ring
RO-01 | AMM-DU-0162 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9555 | 35.9499 | 28 | 3 | HUB-AMM-28 | HUB-AMM-28-R03 | Fiber ring
RO-01 | AMM-DU-0163 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9541 | 35.9539 | 28 | 3 | HUB-AMM-28 | HUB-AMM-28-R03 | Fiber ring
RO-01 | AMM-DU-0164 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9541 | 35.9578 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R04 | Fiber ring
RO-01 | AMM-DU-0165 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9545 | 35.9613 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R04 | Fiber ring
RO-01 | AMM-DU-0167 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9578 | 35.8582 | 29 | 3 | HUB-AMM-13 | HUB-AMM-13-R01 | Fiber ring
RO-01 | AMM-DU-0168 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9578 | 35.8613 | 29 | 3 | HUB-AMM-13 | HUB-AMM-13-R01 | Fiber ring
RO-01 | AMM-DU-0169 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9571 | 35.8653 | 29 | 3 | HUB-AMM-13 | HUB-AMM-13-R02 | Fiber ring
RO-01 | AMM-DU-0170 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9578 | 35.8692 | 28 | 3 | HUB-AMM-13 | HUB-AMM-13-R02 | Fiber ring
RO-01 | AMM-DU-0171 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9584 | 35.8731 | 31 | 3 | HUB-AMM-13 | HUB-AMM-13-R03 | Fiber ring
RO-01 | AMM-DU-0172 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9584 | 35.8771 | 45 | 3 | HUB-AMM-13 | HUB-AMM-13-R04 | Fiber ring
RO-01 | AMM-DU-0173 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9584 | 35.881 | 45 | 3 | HUB-AMM-13 | HUB-AMM-13-R04 | Fiber ring
RO-01 | AMM-DU-0174 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9578 | 35.8849 | 31 | 3 | HUB-AMM-14 | HUB-AMM-14-R01 | Fiber ring
RO-01 | AMM-DU-0175 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9578 | 35.8889 | 30 | 3 | HUB-AMM-14 | HUB-AMM-14-R02 | Fiber ring
RO-01 | AMM-DU-0176 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9578 | 35.8928 | 29 | 3 | HUB-AMM-14 | HUB-AMM-14-R02 | Fiber ring
RO-01 | AMM-DU-0177 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9578 | 35.8967 | 45 | 3 | HUB-AMM-14 | HUB-AMM-14-R03 | Fiber ring
RO-01 | AMM-DU-0178 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9574 | 35.9003 | 49 | 3 | HUB-AMM-14 | HUB-AMM-14-R03 | Fiber ring
RO-01 | AMM-DU-0179 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9571 | 35.9046 | 27 | 3 | HUB-AMM-14 | HUB-AMM-14-R03 | Fiber ring
RO-01 | AMM-DU-0180 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9584 | 35.9086 | 32 | 3 | HUB-AMM-82 | HUB-AMM-82-R07 | Fiber ring
RO-01 | AMM-DU-0181 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9581 | 35.9121 | 34 | 3 | HUB-AMM-82 | HUB-AMM-82-R07 | Fiber ring
RO-01 | AMM-DU-0182 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9578 | 35.9164 | 33 | 3 | HUB-AMM-82 | HUB-AMM-82-R07 | Fiber ring
RO-01 | AMM-DU-0183 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9571 | 35.9204 | 34 | 3 | HUB-AMM-82 | HUB-AMM-82-R01 | Fiber ring
RO-01 | AMM-DU-0184 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9571 | 35.9243 | 29 | 3 | HUB-AMM-82 | HUB-AMM-82-R04 | Fiber ring
RO-01 | AMM-DU-0185 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9571 | 35.9283 | 33 | 3 | HUB-AMM-82 | HUB-AMM-82-R04 | Fiber ring
RO-01 | AMM-DU-0186 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9581 | 35.9318 | 33 | 3 | HUB-AMM-82 | HUB-AMM-82-R04 | Fiber ring
RO-01 | AMM-DU-0187 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9584 | 35.9361 | 32 | 3 | HUB-AMM-28 | HUB-AMM-28-R01 | Fiber ring
RO-01 | AMM-DU-0188 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9578 | 35.9401 | 35 | 3 | HUB-AMM-28 | HUB-AMM-28-R01 | Fiber ring
RO-01 | AMM-DU-0189 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9581 | 35.9436 | 35 | 3 | HUB-AMM-28 | HUB-AMM-28-R02 | Fiber ring
RO-01 | AMM-DU-0190 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9584 | 35.9479 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R03 | Fiber ring
RO-01 | AMM-DU-0191 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9584 | 35.9519 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R03 | Fiber ring
RO-01 | AMM-DU-0192 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9578 | 35.9558 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R04 | Fiber ring
RO-01 | AMM-DU-0193 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9574 | 35.9594 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R04 | Fiber ring
RO-01 | AMM-DU-0195 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9607 | 35.8554 | 26 | 3 | HUB-AMM-13 | HUB-AMM-13-R01 | Fiber ring
RO-01 | AMM-DU-0196 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9607 | 35.8593 | 28 | 3 | HUB-AMM-13 | HUB-AMM-13-R01 | Fiber ring
RO-01 | AMM-DU-0197 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9607 | 35.8633 | 27 | 3 | HUB-AMM-13 | HUB-AMM-13-R01 | Fiber ring
RO-01 | AMM-DU-0198 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9607 | 35.868 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R01 | Fiber ring
RO-01 | AMM-DU-0199 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9614 | 35.8712 | 37 | 3 | HUB-AMM-13 | HUB-AMM-13-R01 | Fiber ring
RO-01 | AMM-DU-0200 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9614 | 35.8751 | 37 | 3 | HUB-AMM-13 | HUB-AMM-13-R04 | Fiber ring
RO-01 | AMM-DU-0201 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9607 | 35.879 | 49 | 3 | HUB-AMM-13 | HUB-AMM-13-R04 | Fiber ring
RO-01 | AMM-DU-0202 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.961 | 35.8826 | 49 | 3 | HUB-AMM-13 | HUB-AMM-13-R04 | Fiber ring
RO-01 | AMM-DU-0203 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9603 | 35.8865 | 28 | 3 | HUB-AMM-14 | HUB-AMM-14-R01 | Fiber ring
RO-01 | AMM-DU-0204 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9607 | 35.8901 | 29 | 3 | HUB-AMM-14 | HUB-AMM-14-R02 | Fiber ring
RO-01 | AMM-DU-0205 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9614 | 35.8948 | 31 | 3 | HUB-AMM-14 | HUB-AMM-14-R02 | Fiber ring
RO-01 | AMM-DU-0206 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9614 | 35.8987 | 49 | 3 | HUB-AMM-14 | HUB-AMM-14-R03 | Fiber ring
RO-01 | AMM-DU-0207 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9607 | 35.9019 | 49 | 3 | HUB-AMM-14 | HUB-AMM-14-R04 | Fiber ring
RO-01 | AMM-DU-0208 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9607 | 35.9066 | 31 | 3 | HUB-AMM-14 | HUB-AMM-14-R04 | Fiber ring
RO-01 | AMM-DU-0209 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9614 | 35.9105 | 31 | 3 | HUB-AMM-82 | HUB-AMM-82-R07 | Fiber ring
RO-01 | AMM-DU-0210 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.961 | 35.9141 | 35 | 3 | HUB-AMM-82 | HUB-AMM-82-R07 | Fiber ring
RO-01 | AMM-DU-0211 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9614 | 35.9184 | 33 | 3 | HUB-AMM-82 | HUB-AMM-82-R06 | Fiber ring
RO-01 | AMM-DU-0212 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9614 | 35.9224 | 33 | 3 | HUB-AMM-82 | HUB-AMM-82-R05 | Fiber ring
RO-01 | AMM-DU-0213 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9607 | 35.9263 | 33 | 3 | HUB-AMM-82 | HUB-AMM-82-R05 | Fiber ring
RO-01 | AMM-DU-0214 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9607 | 35.9302 | 32 | 3 | HUB-AMM-82 | HUB-AMM-82-R04 | Fiber ring
RO-01 | AMM-DU-0215 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9607 | 35.9334 | 30 | 3 | HUB-AMM-82 | HUB-AMM-82-R04 | Fiber ring
RO-01 | AMM-DU-0216 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9607 | 35.9381 | 29 | 3 | HUB-AMM-28 | HUB-AMM-28-R01 | Fiber ring
RO-01 | AMM-DU-0217 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9607 | 35.9412 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R01 | Fiber ring
RO-01 | AMM-DU-0218 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.96 | 35.946 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R02 | Fiber ring
RO-01 | AMM-DU-0219 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9607 | 35.9491 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R03 | Fiber ring
RO-01 | AMM-DU-0220 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9607 | 35.9539 | 27 | 3 | HUB-AMM-28 | HUB-AMM-28-R04 | Fiber ring
RO-01 | AMM-DU-0221 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9607 | 35.957 | 27 | 3 | HUB-AMM-28 | HUB-AMM-28-R04 | Fiber ring
RO-01 | AMM-DU-0222 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9607 | 35.9625 | 31 | 3 | HUB-AMM-28 | HUB-AMM-28-R04 | Fiber ring
RO-01 | AMM-DU-0224 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9636 | 35.8574 | 27 | 3 | HUB-AMM-13 | HUB-AMM-13-R07 | Fiber ring
RO-01 | AMM-DU-0225 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9636 | 35.8613 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R07 | Fiber ring
RO-01 | AMM-DU-0226 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9636 | 35.866 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R07 | Fiber ring
RO-01 | AMM-DU-0227 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9636 | 35.8692 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R06 | Fiber ring
RO-01 | AMM-DU-0228 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9633 | 35.8735 | 37 | 3 | HUB-AMM-13 | HUB-AMM-13-R05 | Fiber ring
RO-01 | AMM-DU-0229 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9633 | 35.8767 | 37 | 3 | HUB-AMM-13 | HUB-AMM-13-R05 | Fiber ring
RO-01 | AMM-DU-0230 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9633 | 35.8806 | 49 | 3 | HUB-AMM-13 | HUB-AMM-13-R05 | Fiber ring
RO-01 | AMM-DU-0231 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9633 | 35.8845 | 49 | 3 | HUB-AMM-14 | HUB-AMM-14-R01 | Fiber ring
RO-01 | AMM-DU-0232 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9636 | 35.8897 | 30 | 3 | HUB-AMM-14 | HUB-AMM-14-R01 | Fiber ring
RO-01 | AMM-DU-0233 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9636 | 35.892 | 30 | 3 | HUB-AMM-14 | HUB-AMM-14-R01 | Fiber ring
RO-01 | AMM-DU-0234 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9633 | 35.8964 | 31 | 3 | HUB-AMM-14 | HUB-AMM-14-R03 | Fiber ring
RO-01 | AMM-DU-0235 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9636 | 35.8999 | 31 | 3 | HUB-AMM-14 | HUB-AMM-14-R04 | Fiber ring
RO-01 | AMM-DU-0236 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9636 | 35.9046 | 36 | 3 | HUB-AMM-14 | HUB-AMM-14-R04 | Fiber ring
RO-01 | AMM-DU-0237 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9636 | 35.9078 | 36 | 3 | HUB-AMM-14 | HUB-AMM-14-R04 | Fiber ring
RO-01 | AMM-DU-0238 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9636 | 35.9125 | 35 | 3 | HUB-AMM-82 | HUB-AMM-82-R06 | Fiber ring
RO-01 | AMM-DU-0239 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.964 | 35.9168 | 35 | 3 | HUB-AMM-82 | HUB-AMM-82-R06 | Fiber ring
RO-01 | AMM-DU-0240 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9643 | 35.9204 | 25 | 3 | HUB-AMM-82 | HUB-AMM-82-R06 | Fiber ring
RO-01 | AMM-DU-0241 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9636 | 35.9235 | 25 | 3 | HUB-AMM-82 | HUB-AMM-82-R05 | Fiber ring
RO-01 | AMM-DU-0242 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9643 | 35.9283 | 25 | 3 | HUB-AMM-82 | HUB-AMM-82-R05 | Fiber ring
RO-01 | AMM-DU-0243 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9633 | 35.9326 | 29 | 3 | HUB-AMM-82 | HUB-AMM-82-R05 | Fiber ring
RO-01 | AMM-DU-0244 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.964 | 35.9365 | 29 | 3 | HUB-AMM-28 | HUB-AMM-28-R01 | Fiber ring
RO-01 | AMM-DU-0245 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9633 | 35.9397 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R01 | Fiber ring
RO-01 | AMM-DU-0246 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9636 | 35.944 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R01 | Fiber ring
RO-01 | AMM-DU-0247 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9636 | 35.9479 | 30 | 3 | HUB-AMM-28 | HUB-AMM-28-R02 | Fiber ring
RO-01 | AMM-DU-0248 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9636 | 35.9511 | 35 | 3 | HUB-AMM-28 | HUB-AMM-28-R03 | Fiber ring
RO-01 | AMM-DU-0249 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9643 | 35.9558 | 35 | 3 | HUB-AMM-28 | HUB-AMM-28-R05 | Fiber ring
RO-01 | AMM-DU-0250 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9636 | 35.959 | 28 | 3 | HUB-AMM-28 | HUB-AMM-28-R05 | Fiber ring
RO-01 | AMM-DU-0252 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9666 | 35.8593 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R07 | Fiber ring
RO-01 | AMM-DU-0253 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9666 | 35.8641 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R06 | Fiber ring
RO-01 | AMM-DU-0254 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9662 | 35.8676 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R06 | Fiber ring
RO-01 | AMM-DU-0255 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9666 | 35.8712 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R06 | Fiber ring
RO-01 | AMM-DU-0256 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9666 | 35.8751 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R05 | Fiber ring
RO-01 | AMM-DU-0257 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9666 | 35.8782 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R05 | Fiber ring
RO-01 | AMM-DU-0258 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9672 | 35.883 | 26 | 3 | HUB-AMM-14 | HUB-AMM-14-R08 | Fiber ring
RO-01 | AMM-DU-0259 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9666 | 35.8861 | 29 | 3 | HUB-AMM-14 | HUB-AMM-14-R01 | Fiber ring
RO-01 | AMM-DU-0260 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9666 | 35.8908 | 29 | 3 | HUB-AMM-14 | HUB-AMM-14-R01 | Fiber ring
RO-01 | AMM-DU-0261 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9672 | 35.8948 | 38 | 3 | HUB-AMM-14 | HUB-AMM-14-R01 | Fiber ring
RO-01 | AMM-DU-0262 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9672 | 35.8987 | 38 | 3 | HUB-AMM-14 | HUB-AMM-14-R05 | Fiber ring
RO-01 | AMM-DU-0263 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9666 | 35.9019 | 33 | 3 | HUB-AMM-14 | HUB-AMM-14-R04 | Fiber ring
RO-01 | AMM-DU-0264 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9669 | 35.9066 | 34 | 3 | HUB-AMM-14 | HUB-AMM-14-R05 | Fiber ring
RO-01 | AMM-DU-0265 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9666 | 35.9105 | 34 | 3 | HUB-AMM-14 | HUB-AMM-14-R04 | Fiber ring
RO-01 | AMM-DU-0266 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9666 | 35.9145 | 30 | 3 | HUB-AMM-82 | HUB-AMM-82-R06 | Fiber ring
RO-01 | AMM-DU-0267 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9666 | 35.9184 | 30 | 3 | HUB-AMM-82 | HUB-AMM-82-R06 | Fiber ring
RO-01 | AMM-DU-0268 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9666 | 35.9216 | 25 | 3 | HUB-AMM-82 | HUB-AMM-82-R06 | Fiber ring
RO-01 | AMM-DU-0269 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9666 | 35.9255 | 25 | 3 | HUB-AMM-82 | HUB-AMM-82-R05 | Fiber ring
RO-01 | AMM-DU-0270 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9666 | 35.9294 | 25 | 3 | HUB-AMM-82 | HUB-AMM-82-R05 | Fiber ring
RO-01 | AMM-DU-0271 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9672 | 35.9342 | 26 | 3 | HUB-AMM-28 | HUB-AMM-28-R09 | Fiber ring
RO-01 | AMM-DU-0272 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9666 | 35.9381 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R09 | Fiber ring
RO-01 | AMM-DU-0273 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9669 | 35.9417 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R09 | Fiber ring
RO-01 | AMM-DU-0274 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9662 | 35.9464 | 28 | 3 | HUB-AMM-28 | HUB-AMM-28-R09 | Fiber ring
RO-01 | AMM-DU-0275 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9662 | 35.9495 | 32 | 3 | HUB-AMM-28 | HUB-AMM-28-R01 | Fiber ring
RO-01 | AMM-DU-0276 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9666 | 35.9539 | 34 | 3 | HUB-AMM-28 | HUB-AMM-28-R05 | Fiber ring
RO-01 | AMM-DU-0277 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9666 | 35.9578 | 33 | 3 | HUB-AMM-28 | HUB-AMM-28-R05 | Fiber ring
RO-01 | AMM-DU-0281 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9695 | 35.87 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R06 | Fiber ring
RO-01 | AMM-DU-0282 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9695 | 35.8731 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R06 | Fiber ring
RO-01 | AMM-DU-0283 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9695 | 35.8763 | 25 | 3 | HUB-AMM-13 | HUB-AMM-13-R06 | Fiber ring
RO-01 | AMM-DU-0284 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9695 | 35.881 | 27 | 3 | HUB-AMM-13 | HUB-AMM-13-R05 | Fiber ring
RO-01 | AMM-DU-0285 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9695 | 35.8841 | 27 | 3 | HUB-AMM-14 | HUB-AMM-14-R07 | Fiber ring
RO-01 | AMM-DU-0286 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9702 | 35.8889 | 25 | 3 | HUB-AMM-14 | HUB-AMM-14-R07 | Fiber ring
RO-01 | AMM-DU-0287 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9695 | 35.8928 | 32 | 3 | HUB-AMM-14 | HUB-AMM-14-R07 | Fiber ring
RO-01 | AMM-DU-0288 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9692 | 35.8964 | 38 | 3 | HUB-AMM-14 | HUB-AMM-14-R06 | Fiber ring
RO-01 | AMM-DU-0289 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9695 | 35.9007 | 33 | 3 | HUB-AMM-14 | HUB-AMM-14-R05 | Fiber ring
RO-01 | AMM-DU-0290 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9695 | 35.9046 | 39 | 3 | HUB-AMM-14 | HUB-AMM-14-R05 | Fiber ring
RO-01 | AMM-DU-0291 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9692 | 35.9082 | 39 | 3 | HUB-AMM-14 | HUB-AMM-14-R05 | Fiber ring
RO-01 | AMM-DU-0292 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9695 | 35.9133 | 29 | 3 | HUB-AMM-69 | HUB-AMM-69-R01 | Fiber ring
RO-01 | AMM-DU-0293 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9698 | 35.916 | 29 | 3 | HUB-AMM-69 | HUB-AMM-69-R02 | Fiber ring
RO-01 | AMM-DU-0294 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9695 | 35.9204 | 27 | 3 | HUB-AMM-69 | HUB-AMM-69-R02 | Fiber ring
RO-01 | AMM-DU-0295 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9695 | 35.9235 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R02 | Fiber ring
RO-01 | AMM-DU-0296 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9695 | 35.929 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R03 | Fiber ring
RO-01 | AMM-DU-0297 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9695 | 35.9322 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R03 | Fiber ring
RO-01 | AMM-DU-0298 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9692 | 35.9357 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R08 | Fiber ring
RO-01 | AMM-DU-0299 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9688 | 35.9401 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R08 | Fiber ring
RO-01 | AMM-DU-0300 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9702 | 35.944 | 26 | 3 | HUB-AMM-28 | HUB-AMM-28-R08 | Fiber ring
RO-01 | AMM-DU-0301 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9695 | 35.9472 | 30 | 3 | HUB-AMM-28 | HUB-AMM-28-R08 | Fiber ring
RO-01 | AMM-DU-0302 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9698 | 35.9523 | 30 | 3 | HUB-AMM-28 | HUB-AMM-28-R06 | Fiber ring
RO-01 | AMM-DU-0303 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9695 | 35.955 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R05 | Fiber ring
RO-01 | AMM-DU-0304 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9702 | 35.9598 | 27 | 3 | HUB-AMM-28 | HUB-AMM-28-R05 | Fiber ring
RO-01 | AMM-DU-0311 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9724 | 35.879 | 26 | 3 | HUB-AMM-13 | HUB-AMM-13-R05 | Fiber ring
RO-01 | AMM-DU-0312 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9728 | 35.8826 | 28 | 3 | HUB-AMM-14 | HUB-AMM-14-R07 | Fiber ring
RO-01 | AMM-DU-0313 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9724 | 35.8877 | 29 | 3 | HUB-AMM-14 | HUB-AMM-14-R07 | Fiber ring
RO-01 | AMM-DU-0314 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9728 | 35.8905 | 25 | 3 | HUB-AMM-14 | HUB-AMM-14-R07 | Fiber ring
RO-01 | AMM-DU-0315 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9724 | 35.8948 | 25 | 3 | HUB-AMM-14 | HUB-AMM-14-R06 | Fiber ring
RO-01 | AMM-DU-0316 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9724 | 35.8987 | 25 | 3 | HUB-AMM-14 | HUB-AMM-14-R06 | Fiber ring
RO-01 | AMM-DU-0317 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9731 | 35.9027 | 33 | 3 | HUB-AMM-14 | HUB-AMM-14-R05 | Fiber ring
RO-01 | AMM-DU-0318 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9724 | 35.9066 | 39 | 3 | HUB-AMM-14 | HUB-AMM-14-R05 | Fiber ring
RO-01 | AMM-DU-0319 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9724 | 35.9105 | 30 | 3 | HUB-AMM-69 | HUB-AMM-69-R01 | Fiber ring
RO-01 | AMM-DU-0320 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9724 | 35.9145 | 28 | 3 | HUB-AMM-69 | HUB-AMM-69-R01 | Fiber ring
RO-01 | AMM-DU-0321 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9724 | 35.9184 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R02 | Fiber ring
RO-01 | AMM-DU-0322 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9724 | 35.9216 | 26 | 3 | HUB-AMM-69 | HUB-AMM-69-R02 | Fiber ring
RO-01 | AMM-DU-0323 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9731 | 35.9263 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R02 | Fiber ring
RO-01 | AMM-DU-0324 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9724 | 35.9302 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R03 | Fiber ring
RO-01 | AMM-DU-0325 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9724 | 35.9334 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R03 | Fiber ring
RO-01 | AMM-DU-0326 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9731 | 35.9381 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R08 | Fiber ring
RO-01 | AMM-DU-0327 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9724 | 35.942 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R08 | Fiber ring
RO-01 | AMM-DU-0328 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9718 | 35.946 | 26 | 3 | HUB-AMM-28 | HUB-AMM-28-R07 | Fiber ring
RO-01 | AMM-DU-0329 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9724 | 35.9499 | 29 | 3 | HUB-AMM-28 | HUB-AMM-28-R06 | Fiber ring
RO-01 | AMM-DU-0330 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9724 | 35.9539 | 28 | 3 | HUB-AMM-28 | HUB-AMM-28-R06 | Fiber ring
RO-01 | AMM-DU-0331 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9724 | 35.9578 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R06 | Fiber ring
RO-01 | AMM-DU-0340 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9747 | 35.8889 | 29 | 3 | HUB-AMM-14 | HUB-AMM-14-R07 | Fiber ring
RO-01 | AMM-DU-0341 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9747 | 35.8928 | 25 | 3 | HUB-AMM-14 | HUB-AMM-14-R06 | Fiber ring
RO-01 | AMM-DU-0342 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9747 | 35.8967 | 26 | 3 | HUB-AMM-14 | HUB-AMM-14-R06 | Fiber ring
RO-01 | AMM-DU-0343 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.9007 | 25 | 3 | HUB-AMM-14 | HUB-AMM-14-R06 | Fiber ring
RO-01 | AMM-DU-0344 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9747 | 35.9046 | 34 | 3 | HUB-AMM-14 | HUB-AMM-14-R06 | Fiber ring
RO-01 | AMM-DU-0345 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.9086 | 34 | 3 | HUB-AMM-69 | HUB-AMM-69-R01 | Fiber ring
RO-01 | AMM-DU-0346 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.9125 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R01 | Fiber ring
RO-01 | AMM-DU-0347 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.9164 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R01 | Fiber ring
RO-01 | AMM-DU-0348 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.9196 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R01 | Fiber ring
RO-01 | AMM-DU-0349 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.9243 | 26 | 3 | HUB-AMM-69 | HUB-AMM-69-R02 | Fiber ring
RO-01 | AMM-DU-0350 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.9275 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R03 | Fiber ring
RO-01 | AMM-DU-0351 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.9322 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R03 | Fiber ring
RO-01 | AMM-DU-0352 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9747 | 35.9361 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R03 | Fiber ring
RO-01 | AMM-DU-0353 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9761 | 35.9401 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R08 | Fiber ring
RO-01 | AMM-DU-0354 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9761 | 35.944 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R07 | Fiber ring
RO-01 | AMM-DU-0355 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9761 | 35.9479 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R07 | Fiber ring
RO-01 | AMM-DU-0356 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9761 | 35.9519 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R06 | Fiber ring
RO-01 | AMM-DU-0357 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9761 | 35.9558 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R06 | Fiber ring
RO-01 | AMM-DU-0369 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9783 | 35.9098 | 29 | 3 | HUB-AMM-69 | HUB-AMM-69-R08 | Fiber ring
RO-01 | AMM-DU-0370 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9783 | 35.9145 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R08 | Fiber ring
RO-01 | AMM-DU-0371 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9783 | 35.9192 | 27 | 3 | HUB-AMM-69 | HUB-AMM-69-R08 | Fiber ring
RO-01 | AMM-DU-0372 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9783 | 35.9224 | 27 | 3 | HUB-AMM-69 | HUB-AMM-69-R01 | Fiber ring
RO-01 | AMM-DU-0373 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9783 | 35.9255 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R04 | Fiber ring
RO-01 | AMM-DU-0374 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.979 | 35.9302 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R04 | Fiber ring
RO-01 | AMM-DU-0375 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9783 | 35.9334 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R04 | Fiber ring
RO-01 | AMM-DU-0376 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9783 | 35.9381 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R04 | Fiber ring
RO-01 | AMM-DU-0377 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.979 | 35.942 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R07 | Fiber ring
RO-01 | AMM-DU-0378 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9783 | 35.9452 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R07 | Fiber ring
RO-01 | AMM-DU-0379 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.978 | 35.9495 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R07 | Fiber ring
RO-01 | AMM-DU-0389 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9819 | 35.9125 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R08 | Fiber ring
RO-01 | AMM-DU-0390 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9812 | 35.9157 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R08 | Fiber ring
RO-01 | AMM-DU-0391 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9819 | 35.9204 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R07 | Fiber ring
RO-01 | AMM-DU-0392 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9812 | 35.9243 | 27 | 3 | HUB-AMM-69 | HUB-AMM-69-R05 | Fiber ring
RO-01 | AMM-DU-0393 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9812 | 35.9283 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R05 | Fiber ring
RO-01 | AMM-DU-0394 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9812 | 35.9314 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R04 | Fiber ring
RO-01 | AMM-DU-0395 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9819 | 35.9361 | 31 | 3 | HUB-AMM-69 | HUB-AMM-69-R04 | Fiber ring
RO-01 | AMM-DU-0396 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9812 | 35.9401 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R04 | Fiber ring
RO-01 | AMM-DU-0397 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9812 | 35.9432 | 25 | 3 | HUB-AMM-28 | HUB-AMM-28-R07 | Fiber ring
RO-01 | AMM-DU-0403 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9842 | 35.9113 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R07 | Fiber ring
RO-01 | AMM-DU-0404 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9842 | 35.9145 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R07 | Fiber ring
RO-01 | AMM-DU-0405 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9842 | 35.9192 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R06 | Fiber ring
RO-01 | AMM-DU-0406 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9842 | 35.9224 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R06 | Fiber ring
RO-01 | AMM-DU-0407 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9842 | 35.9263 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R06 | Fiber ring
RO-01 | AMM-DU-0408 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9842 | 35.9294 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R05 | Fiber ring
RO-01 | AMM-DU-0409 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9842 | 35.9342 | 31 | 3 | HUB-AMM-69 | HUB-AMM-69-R05 | Fiber ring
RO-01 | AMM-DU-0410 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9842 | 35.9381 | 31 | 3 | HUB-AMM-69 | HUB-AMM-69-R05 | Fiber ring
RO-01 | AMM-DU-0412 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9871 | 35.9133 | 27 | 3 | HUB-AMM-69 | HUB-AMM-69-R07 | Fiber ring
RO-01 | AMM-DU-0413 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9871 | 35.9157 | 27 | 3 | HUB-AMM-69 | HUB-AMM-69-R07 | Fiber ring
RO-01 | AMM-DU-0414 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9878 | 35.9204 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R06 | Fiber ring
RO-01 | AMM-DU-0415 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9878 | 35.9243 | 28 | 3 | HUB-AMM-69 | HUB-AMM-69-R06 | Fiber ring
RO-01 | AMM-DU-0416 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9871 | 35.9275 | 27 | 3 | HUB-AMM-69 | HUB-AMM-69-R06 | Fiber ring
RO-01 | AMM-DU-0417 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9871 | 35.9314 | 25 | 3 | HUB-AMM-69 | HUB-AMM-69-R05 | Fiber ring
RO-01 | AMM-U-0667 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.926 | 35.9353 | 30 | 3 | HUB-AMM-38 | HUB-AMM-38-R02 | Fiber ring
RO-01 | AMM-U-0668 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.926 | 35.9401 | 30 | 3 | HUB-AMM-38 | HUB-AMM-38-R02 | Fiber ring
RO-01 | AMM-U-0696 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9296 | 35.915 | 30 | 3 | HUB-AMM-38 | HUB-AMM-38-R01 | Fiber ring
RO-01 | AMM-U-0697 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9296 | 35.9179 | 30 | 3 | HUB-AMM-38 | HUB-AMM-38-R01 | Fiber ring
RO-01 | AMM-U-0698 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9288 | 35.9235 | 30 | 3 | HUB-AMM-38 | HUB-AMM-38-R01 | Fiber ring
RO-01 | AMM-U-0699 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9288 | 35.9283 | 31 | 3 | HUB-AMM-38 | HUB-AMM-38-R02 | Fiber ring
RO-01 | AMM-U-0700 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9296 | 35.9339 | 32 | 3 | HUB-AMM-38 | HUB-AMM-38-R02 | Fiber ring
RO-01 | AMM-U-0994 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9715 | 35.9609 | 30 | 3 | HUB-AMM-28 | HUB-AMM-28-R05 | Fiber ring
RO-01 | AMM-U-1047 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9789 | 35.9566 | 30 | 3 | HUB-AMM-28 | HUB-AMM-28-R06 | Fiber ring
RO-01 | AMM-U-1150 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.9127 | 30 | 3 | HUB-AMM-69 | HUB-AMM-69-R07 | Fiber ring
RO-01 | AMM-U-1151 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9891 | 35.916 | 30 | 3 | HUB-AMM-69 | HUB-AMM-69-R07 | Fiber ring
RO-01 | AMM-U-1152 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.9212 | 30 | 3 | HUB-AMM-69 | HUB-AMM-69-R06 | Fiber ring
RO-01 | AMM-U-1153 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.9353 | 30 | 3 | HUB-AMM-69 | HUB-AMM-69-R05 | Fiber ring
RO-02 | AMM-DU-0002 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9317 | 35.9424 | 25 | 3 | HUB-AMM-52 | HUB-AMM-52-R01 | Fiber ring
RO-02 | AMM-DU-0003 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9313 | 35.9452 | 25 | 3 | HUB-AMM-52 | HUB-AMM-52-R01 | Fiber ring
RO-02 | AMM-DU-0011 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9336 | 35.944 | 25 | 3 | HUB-AMM-52 | HUB-AMM-52-R01 | Fiber ring
RO-02 | AMM-DU-0012 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9343 | 35.9487 | 28 | 3 | HUB-AMM-52 | HUB-AMM-52-R01 | Fiber ring
RO-02 | AMM-DU-0013 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9365 | 35.9027 | 25 | 3 | HUB-AMM-41 | HUB-AMM-41-R02 | Fiber ring
RO-02 | AMM-DU-0014 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9365 | 35.9066 | 30 | 3 | HUB-AMM-41 | HUB-AMM-41-R03 | Fiber ring
RO-02 | AMM-DU-0015 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9372 | 35.9113 | 30 | 3 | HUB-AMM-41 | HUB-AMM-41-R03 | Fiber ring
RO-02 | AMM-DU-0024 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9379 | 35.946 | 28 | 3 | HUB-AMM-52 | HUB-AMM-52-R08 | Fiber ring
RO-02 | AMM-DU-0025 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9372 | 35.9491 | 28 | 3 | HUB-AMM-52 | HUB-AMM-52-R08 | Fiber ring
RO-02 | AMM-DU-0026 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.8928 | 28 | 3 | HUB-AMM-41 | HUB-AMM-41-R01 | Fiber ring
RO-02 | AMM-DU-0027 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9398 | 35.8964 | 28 | 3 | HUB-AMM-41 | HUB-AMM-41-R01 | Fiber ring
RO-02 | AMM-DU-0028 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9408 | 35.9007 | 25 | 3 | HUB-AMM-41 | HUB-AMM-41-R01 | Fiber ring
RO-02 | AMM-DU-0029 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9408 | 35.9046 | 26 | 3 | HUB-AMM-41 | HUB-AMM-41-R04 | Fiber ring
RO-02 | AMM-DU-0030 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.9094 | 30 | 3 | HUB-AMM-41 | HUB-AMM-41-R03 | Fiber ring
RO-02 | AMM-DU-0031 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.9133 | 29 | 3 | HUB-AMM-41 | HUB-AMM-41-R03 | Fiber ring
RO-02 | AMM-DU-0039 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.9432 | 25 | 3 | HUB-AMM-52 | HUB-AMM-52-R08 | Fiber ring
RO-02 | AMM-DU-0040 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.9472 | 28 | 3 | HUB-AMM-52 | HUB-AMM-52-R08 | Fiber ring
RO-02 | AMM-DU-0041 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.9511 | 27 | 3 | HUB-AMM-52 | HUB-AMM-52-R07 | Fiber ring
RO-02 | AMM-DU-0042 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9431 | 35.883 | 25 | 3 | HUB-AMM-45 | HUB-AMM-45-R03 | Fiber ring
RO-02 | AMM-DU-0043 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9424 | 35.8869 | 25 | 3 | HUB-AMM-41 | HUB-AMM-41-R07 | Fiber ring
RO-02 | AMM-DU-0044 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9431 | 35.8901 | 28 | 3 | HUB-AMM-41 | HUB-AMM-41-R07 | Fiber ring
RO-02 | AMM-DU-0045 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9438 | 35.8948 | 31 | 3 | HUB-AMM-41 | HUB-AMM-41-R07 | Fiber ring
RO-02 | AMM-DU-0046 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9438 | 35.8987 | 26 | 3 | HUB-AMM-41 | HUB-AMM-41-R06 | Fiber ring
RO-02 | AMM-DU-0047 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9431 | 35.9019 | 25 | 3 | HUB-AMM-41 | HUB-AMM-41-R05 | Fiber ring
RO-02 | AMM-DU-0048 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9431 | 35.9058 | 27 | 3 | HUB-AMM-41 | HUB-AMM-41-R04 | Fiber ring
RO-02 | AMM-DU-0049 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9424 | 35.9105 | 26 | 3 | HUB-AMM-41 | HUB-AMM-41-R04 | Fiber ring
RO-02 | AMM-DU-0050 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9431 | 35.9145 | 28 | 3 | HUB-AMM-41 | HUB-AMM-41-R04 | Fiber ring
RO-02 | AMM-DU-0057 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9438 | 35.942 | 25 | 3 | HUB-AMM-52 | HUB-AMM-52-R07 | Fiber ring
RO-02 | AMM-DU-0058 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9438 | 35.946 | 25 | 3 | HUB-AMM-52 | HUB-AMM-52-R07 | Fiber ring
RO-02 | AMM-DU-0059 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9427 | 35.9495 | 26 | 3 | HUB-AMM-52 | HUB-AMM-52-R07 | Fiber ring
RO-02 | AMM-DU-0060 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9431 | 35.9546 | 29 | 3 | HUB-AMM-52 | HUB-AMM-52-R06 | Fiber ring
RO-02 | AMM-DU-0061 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9424 | 35.9578 | 28 | 3 | HUB-AMM-52 | HUB-AMM-52-R05 | Fiber ring
RO-02 | AMM-DU-0062 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9467 | 35.8731 | 25 | 3 | HUB-AMM-45 | HUB-AMM-45-R05 | Fiber ring
RO-02 | AMM-DU-0063 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.946 | 35.8771 | 25 | 3 | HUB-AMM-45 | HUB-AMM-45-R04 | Fiber ring
RO-02 | AMM-DU-0064 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.946 | 35.881 | 25 | 3 | HUB-AMM-45 | HUB-AMM-45-R04 | Fiber ring
RO-02 | AMM-DU-0065 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.946 | 35.8841 | 25 | 3 | HUB-AMM-45 | HUB-AMM-45-R03 | Fiber ring
RO-02 | AMM-DU-0066 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9467 | 35.8889 | 25 | 3 | HUB-AMM-41 | HUB-AMM-41-R07 | Fiber ring
RO-02 | AMM-DU-0067 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.946 | 35.8928 | 25 | 3 | HUB-AMM-41 | HUB-AMM-41-R07 | Fiber ring
RO-02 | AMM-DU-0068 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.946 | 35.8967 | 25 | 3 | HUB-AMM-41 | HUB-AMM-41-R06 | Fiber ring
RO-02 | AMM-DU-0069 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.946 | 35.9007 | 25 | 3 | HUB-AMM-41 | HUB-AMM-41-R05 | Fiber ring
RO-02 | AMM-DU-0070 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.946 | 35.9038 | 25 | 3 | HUB-AMM-41 | HUB-AMM-41-R05 | Fiber ring
RO-02 | AMM-DU-0071 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9467 | 35.9086 | 27 | 3 | HUB-AMM-41 | HUB-AMM-41-R04 | Fiber ring
RO-02 | AMM-DU-0072 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9453 | 35.9125 | 30 | 3 | HUB-AMM-41 | HUB-AMM-41-R04 | Fiber ring
RO-02 | AMM-DU-0080 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9453 | 35.944 | 25 | 3 | HUB-AMM-52 | HUB-AMM-52-R07 | Fiber ring
RO-02 | AMM-DU-0081 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.946 | 35.9479 | 26 | 3 | HUB-AMM-52 | HUB-AMM-52-R07 | Fiber ring
RO-02 | AMM-DU-0082 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9467 | 35.9519 | 28 | 3 | HUB-AMM-52 | HUB-AMM-52-R06 | Fiber ring
RO-02 | AMM-DU-0083 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.946 | 35.9566 | 29 | 3 | HUB-AMM-52 | HUB-AMM-52-R05 | Fiber ring
RO-02 | AMM-DU-0084 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.946 | 35.9598 | 25 | 3 | HUB-AMM-52 | HUB-AMM-52-R05 | Fiber ring
RO-02 | AMM-DU-0085 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9489 | 35.8672 | 25 | 3 | HUB-AMM-45 | HUB-AMM-45-R05 | Fiber ring
RO-02 | AMM-DU-0086 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9489 | 35.8712 | 25 | 3 | HUB-AMM-45 | HUB-AMM-45-R05 | Fiber ring
RO-02 | AMM-DU-0087 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9489 | 35.8751 | 25 | 3 | HUB-AMM-45 | HUB-AMM-45-R04 | Fiber ring
RO-02 | AMM-DU-0088 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9489 | 35.879 | 25 | 3 | HUB-AMM-45 | HUB-AMM-45-R04 | Fiber ring
RO-02 | AMM-DU-0089 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9496 | 35.883 | 25 | 3 | HUB-AMM-45 | HUB-AMM-45-R04 | Fiber ring
RO-02 | AMM-DU-0090 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9489 | 35.8869 | 25 | 3 | HUB-AMM-41 | HUB-AMM-41-R07 | Fiber ring
RO-02 | AMM-DU-0091 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9496 | 35.8908 | 25 | 3 | HUB-AMM-41 | HUB-AMM-41-R06 | Fiber ring
RO-02 | AMM-DU-0092 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9489 | 35.8948 | 25 | 3 | HUB-AMM-41 | HUB-AMM-41-R06 | Fiber ring
RO-02 | AMM-DU-0093 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9489 | 35.8979 | 25 | 3 | HUB-AMM-41 | HUB-AMM-41-R06 | Fiber ring
RO-02 | AMM-DU-0094 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9489 | 35.9019 | 28 | 3 | HUB-AMM-41 | HUB-AMM-41-R05 | Fiber ring
RO-02 | AMM-DU-0095 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9493 | 35.9062 | 28 | 3 | HUB-AMM-41 | HUB-AMM-41-R04 | Fiber ring
RO-02 | AMM-DU-0104 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9489 | 35.9428 | 31 | 3 | HUB-AMM-52 | HUB-AMM-52-R07 | Fiber ring
RO-02 | AMM-DU-0105 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9483 | 35.946 | 28 | 3 | HUB-AMM-52 | HUB-AMM-52-R06 | Fiber ring
RO-02 | AMM-DU-0106 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9483 | 35.9499 | 25 | 3 | HUB-AMM-52 | HUB-AMM-52-R06 | Fiber ring
RO-02 | AMM-DU-0107 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9486 | 35.9535 | 26 | 3 | HUB-AMM-52 | HUB-AMM-52-R06 | Fiber ring
RO-02 | AMM-DU-0108 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9496 | 35.9578 | 26 | 3 | HUB-AMM-52 | HUB-AMM-52-R05 | Fiber ring
RO-02 | AMM-DU-0109 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9483 | 35.9617 | 29 | 3 | HUB-AMM-52 | HUB-AMM-52-R04 | Fiber ring
RO-02 | AMM-DU-0117 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9519 | 35.8881 | 26 | 3 | HUB-AMM-41 | HUB-AMM-41-R06 | Fiber ring
RO-02 | AMM-DU-0118 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9526 | 35.8928 | 28 | 3 | HUB-AMM-41 | HUB-AMM-41-R06 | Fiber ring
RO-02 | AMM-DU-0119 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9526 | 35.8967 | 29 | 3 | HUB-AMM-41 | HUB-AMM-41-R05 | Fiber ring
RO-02 | AMM-DU-0120 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9526 | 35.9007 | 29 | 3 | HUB-AMM-41 | HUB-AMM-41-R05 | Fiber ring
RO-02 | AMM-DU-0121 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9519 | 35.9046 | 28 | 3 | HUB-AMM-41 | HUB-AMM-41-R05 | Fiber ring
RO-02 | AMM-DU-0132 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9512 | 35.9479 | 29 | 3 | HUB-AMM-52 | HUB-AMM-52-R06 | Fiber ring
RO-02 | AMM-DU-0133 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9512 | 35.9519 | 27 | 3 | HUB-AMM-52 | HUB-AMM-52-R06 | Fiber ring
RO-02 | AMM-DU-0134 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9512 | 35.9558 | 26 | 3 | HUB-AMM-52 | HUB-AMM-52-R05 | Fiber ring
RO-02 | AMM-DU-0135 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9519 | 35.959 | 25 | 3 | HUB-AMM-52 | HUB-AMM-52-R05 | Fiber ring
RO-02 | AMM-DU-0137 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9548 | 35.8515 | 25 | 3 | HUB-AMM-64 | HUB-AMM-64-R03 | Fiber ring
RO-02 | AMM-DU-0138 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9548 | 35.8554 | 28 | 3 | HUB-AMM-64 | HUB-AMM-64-R03 | Fiber ring
RO-02 | AMM-DU-0166 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9578 | 35.8534 | 26 | 3 | HUB-AMM-64 | HUB-AMM-64-R03 | Fiber ring
RO-02 | AMM-DU-0194 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9607 | 35.8515 | 25 | 3 | HUB-AMM-64 | HUB-AMM-64-R04 | Fiber ring
RO-02 | AMM-DU-0223 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9643 | 35.8534 | 31 | 3 | HUB-AMM-64 | HUB-AMM-64-R04 | Fiber ring
RO-02 | AMM-DU-0251 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9666 | 35.8554 | 31 | 3 | HUB-AMM-59 | HUB-AMM-59-R01 | Fiber ring
RO-02 | AMM-DU-0278 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9695 | 35.8574 | 29 | 3 | HUB-AMM-59 | HUB-AMM-59-R02 | Fiber ring
RO-02 | AMM-DU-0279 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9695 | 35.8613 | 25 | 3 | HUB-AMM-59 | HUB-AMM-59-R02 | Fiber ring
RO-02 | AMM-DU-0280 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9695 | 35.866 | 25 | 3 | HUB-AMM-59 | HUB-AMM-59-R02 | Fiber ring
RO-02 | AMM-DU-0305 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9724 | 35.8554 | 27 | 3 | HUB-AMM-59 | HUB-AMM-59-R01 | Fiber ring
RO-02 | AMM-DU-0306 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9724 | 35.8586 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R02 | Fiber ring
RO-02 | AMM-DU-0307 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9724 | 35.8633 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R02 | Fiber ring
RO-02 | AMM-DU-0308 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9724 | 35.868 | 25 | 3 | HUB-AMM-59 | HUB-AMM-59-R02 | Fiber ring
RO-02 | AMM-DU-0309 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9721 | 35.8712 | 25 | 3 | HUB-AMM-59 | HUB-AMM-59-R03 | Fiber ring
RO-02 | AMM-DU-0310 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9724 | 35.8751 | 25 | 3 | HUB-AMM-59 | HUB-AMM-59-R03 | Fiber ring
RO-02 | AMM-DU-0332 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.8574 | 34 | 3 | HUB-AMM-59 | HUB-AMM-59-R01 | Fiber ring
RO-02 | AMM-DU-0333 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.8613 | 36 | 3 | HUB-AMM-59 | HUB-AMM-59-R02 | Fiber ring
RO-02 | AMM-DU-0334 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9761 | 35.8653 | 33 | 3 | HUB-AMM-59 | HUB-AMM-59-R03 | Fiber ring
RO-02 | AMM-DU-0335 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.8692 | 25 | 3 | HUB-AMM-59 | HUB-AMM-59-R03 | Fiber ring
RO-02 | AMM-DU-0336 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.8739 | 25 | 3 | HUB-AMM-59 | HUB-AMM-59-R03 | Fiber ring
RO-02 | AMM-DU-0337 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9761 | 35.8771 | 25 | 3 | HUB-AMM-59 | HUB-AMM-59-R03 | Fiber ring
RO-02 | AMM-DU-0338 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.881 | 28 | 3 | HUB-AMM-23 | HUB-AMM-23-R01 | Fiber ring
RO-02 | AMM-DU-0339 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.8841 | 28 | 3 | HUB-AMM-23 | HUB-AMM-23-R01 | Fiber ring
RO-02 | AMM-DU-0358 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9783 | 35.868 | 28 | 3 | HUB-AMM-59 | HUB-AMM-59-R03 | Fiber ring
RO-02 | AMM-DU-0359 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9786 | 35.8708 | 25 | 3 | HUB-AMM-59 | HUB-AMM-59-R04 | Fiber ring
RO-02 | AMM-DU-0360 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9783 | 35.8759 | 28 | 3 | HUB-AMM-59 | HUB-AMM-59-R04 | Fiber ring
RO-02 | AMM-DU-0361 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9783 | 35.8782 | 28 | 3 | HUB-AMM-59 | HUB-AMM-59-R04 | Fiber ring
RO-02 | AMM-DU-0362 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9783 | 35.883 | 25 | 3 | HUB-AMM-23 | HUB-AMM-23-R01 | Fiber ring
RO-02 | AMM-DU-0363 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.979 | 35.8869 | 25 | 3 | HUB-AMM-23 | HUB-AMM-23-R01 | Fiber ring
RO-02 | AMM-DU-0364 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9783 | 35.8908 | 25 | 3 | HUB-AMM-23 | HUB-AMM-23-R02 | Fiber ring
RO-02 | AMM-DU-0365 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.978 | 35.8944 | 26 | 3 | HUB-AMM-23 | HUB-AMM-23-R02 | Fiber ring
RO-02 | AMM-DU-0366 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9783 | 35.8987 | 25 | 3 | HUB-AMM-23 | HUB-AMM-23-R02 | Fiber ring
RO-02 | AMM-DU-0367 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9776 | 35.9027 | 25 | 3 | HUB-AMM-23 | HUB-AMM-23-R02 | Fiber ring
RO-02 | AMM-DU-0368 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9783 | 35.9066 | 29 | 3 | HUB-AMM-23 | HUB-AMM-23-R03 | Fiber ring
RO-02 | AMM-DU-0380 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9812 | 35.8771 | 28 | 3 | HUB-AMM-59 | HUB-AMM-59-R04 | Fiber ring
RO-02 | AMM-DU-0381 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9819 | 35.881 | 29 | 3 | HUB-AMM-23 | HUB-AMM-23-R01 | Fiber ring
RO-02 | AMM-DU-0382 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9812 | 35.8849 | 28 | 3 | HUB-AMM-23 | HUB-AMM-23-R01 | Fiber ring
RO-02 | AMM-DU-0383 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9812 | 35.8881 | 28 | 3 | HUB-AMM-23 | HUB-AMM-23-R01 | Fiber ring
RO-02 | AMM-DU-0384 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9812 | 35.8928 | 25 | 3 | HUB-AMM-23 | HUB-AMM-23-R02 | Fiber ring
RO-02 | AMM-DU-0385 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9812 | 35.8967 | 25 | 3 | HUB-AMM-23 | HUB-AMM-23-R02 | Fiber ring
RO-02 | AMM-DU-0386 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9812 | 35.9007 | 25 | 3 | HUB-AMM-23 | HUB-AMM-23-R02 | Fiber ring
RO-02 | AMM-DU-0387 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9812 | 35.9054 | 25 | 3 | HUB-AMM-23 | HUB-AMM-23-R03 | Fiber ring
RO-02 | AMM-DU-0388 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9812 | 35.9078 | 25 | 3 | HUB-AMM-23 | HUB-AMM-23-R03 | Fiber ring
RO-02 | AMM-DU-0398 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9849 | 35.8908 | 29 | 3 | HUB-AMM-23 | HUB-AMM-23-R06 | Fiber ring
RO-02 | AMM-DU-0399 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9849 | 35.8948 | 26 | 3 | HUB-AMM-23 | HUB-AMM-23-R01 | Fiber ring
RO-02 | AMM-DU-0400 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9835 | 35.8987 | 25 | 3 | HUB-AMM-23 | HUB-AMM-23-R03 | Fiber ring
RO-02 | AMM-DU-0401 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9842 | 35.9027 | 25 | 3 | HUB-AMM-23 | HUB-AMM-23-R03 | Fiber ring
RO-02 | AMM-DU-0402 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9842 | 35.9066 | 25 | 3 | HUB-AMM-23 | HUB-AMM-23-R03 | Fiber ring
RO-02 | AMM-DU-0411 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9871 | 35.9078 | 25 | 3 | HUB-AMM-23 | HUB-AMM-23-R03 | Fiber ring
RO-02 | AMM-U-0444 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8978 | 35.8928 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R02 | Fiber ring
RO-02 | AMM-U-0445 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8978 | 35.8975 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R02 | Fiber ring
RO-02 | AMM-U-0461 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9014 | 35.8848 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R01 | Fiber ring
RO-02 | AMM-U-0462 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9014 | 35.8905 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R02 | Fiber ring
RO-02 | AMM-U-0463 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9022 | 35.8952 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R02 | Fiber ring
RO-02 | AMM-U-0464 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9014 | 35.8999 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R03 | Fiber ring
RO-02 | AMM-U-0465 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9014 | 35.9037 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R03 | Fiber ring
RO-02 | AMM-U-0469 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9014 | 35.9235 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R02 | Fiber ring
RO-02 | AMM-U-0470 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9014 | 35.9283 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R02 | Fiber ring
RO-02 | AMM-U-0482 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9049 | 35.8834 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R01 | Fiber ring
RO-02 | AMM-U-0483 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9049 | 35.8881 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R02 | Fiber ring
RO-02 | AMM-U-0484 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9049 | 35.8928 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R02 | Fiber ring
RO-02 | AMM-U-0485 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9053 | 35.898 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R03 | Fiber ring
RO-02 | AMM-U-0486 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9049 | 35.9032 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R03 | Fiber ring
RO-02 | AMM-U-0487 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9049 | 35.907 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R03 | Fiber ring
RO-02 | AMM-U-0488 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9049 | 35.9117 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R01 | Fiber ring
RO-02 | AMM-U-0489 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9049 | 35.9174 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R01 | Fiber ring
RO-02 | AMM-U-0490 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9049 | 35.9202 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R02 | Fiber ring
RO-02 | AMM-U-0491 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9049 | 35.9259 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R02 | Fiber ring
RO-02 | AMM-U-0492 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9049 | 35.9306 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R02 | Fiber ring
RO-02 | AMM-U-0506 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9092 | 35.8857 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R01 | Fiber ring
RO-02 | AMM-U-0507 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9084 | 35.8895 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R01 | Fiber ring
RO-02 | AMM-U-0508 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9084 | 35.8952 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R02 | Fiber ring
RO-02 | AMM-U-0509 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9084 | 35.8999 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R03 | Fiber ring
RO-02 | AMM-U-0510 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9076 | 35.9046 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R04 | Fiber ring
RO-02 | AMM-U-0511 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.908 | 35.9089 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R04 | Fiber ring
RO-02 | AMM-U-0512 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9076 | 35.9141 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R01 | Fiber ring
RO-02 | AMM-U-0513 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9084 | 35.9188 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R01 | Fiber ring
RO-02 | AMM-U-0514 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9084 | 35.9235 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R02 | Fiber ring
RO-02 | AMM-U-0515 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9084 | 35.9292 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R03 | Fiber ring
RO-02 | AMM-U-0516 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9084 | 35.933 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R03 | Fiber ring
RO-02 | AMM-U-0531 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9111 | 35.8834 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R01 | Fiber ring
RO-02 | AMM-U-0532 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9111 | 35.8881 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R01 | Fiber ring
RO-02 | AMM-U-0533 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9127 | 35.8928 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R01 | Fiber ring
RO-02 | AMM-U-0534 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9127 | 35.8975 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R03 | Fiber ring
RO-02 | AMM-U-0535 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9119 | 35.9032 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R04 | Fiber ring
RO-02 | AMM-U-0536 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9119 | 35.9061 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R04 | Fiber ring
RO-02 | AMM-U-0537 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9115 | 35.9122 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R01 | Fiber ring
RO-02 | AMM-U-0538 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9111 | 35.9164 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R01 | Fiber ring
RO-02 | AMM-U-0539 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9119 | 35.9212 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R01 | Fiber ring
RO-02 | AMM-U-0540 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9115 | 35.9264 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R02 | Fiber ring
RO-02 | AMM-U-0541 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9111 | 35.9306 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R03 | Fiber ring
RO-02 | AMM-U-0542 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9119 | 35.9353 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R03 | Fiber ring
RO-02 | AMM-U-0558 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9155 | 35.8819 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R08 | Fiber ring
RO-02 | AMM-U-0559 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9163 | 35.8857 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R07 | Fiber ring
RO-02 | AMM-U-0560 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9155 | 35.8905 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R07 | Fiber ring
RO-02 | AMM-U-0561 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9151 | 35.8947 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R01 | Fiber ring
RO-02 | AMM-U-0562 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9155 | 35.899 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R04 | Fiber ring
RO-02 | AMM-U-0563 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9155 | 35.9037 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R04 | Fiber ring
RO-02 | AMM-U-0564 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9147 | 35.9094 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R04 | Fiber ring
RO-02 | AMM-U-0565 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9155 | 35.9141 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R06 | Fiber ring
RO-02 | AMM-U-0566 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9163 | 35.9188 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R06 | Fiber ring
RO-02 | AMM-U-0567 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9155 | 35.9235 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R01 | Fiber ring
RO-02 | AMM-U-0568 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9163 | 35.9283 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R03 | Fiber ring
RO-02 | AMM-U-0569 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9155 | 35.933 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R03 | Fiber ring
RO-02 | AMM-U-0570 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9147 | 35.9377 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R03 | Fiber ring
RO-02 | AMM-U-0589 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9186 | 35.8838 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R07 | Fiber ring
RO-02 | AMM-U-0590 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9182 | 35.8881 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R07 | Fiber ring
RO-02 | AMM-U-0591 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.919 | 35.8938 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R06 | Fiber ring
RO-02 | AMM-U-0592 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.919 | 35.8966 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R06 | Fiber ring
RO-02 | AMM-U-0593 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.919 | 35.9023 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R05 | Fiber ring
RO-02 | AMM-U-0594 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.919 | 35.907 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R05 | Fiber ring
RO-02 | AMM-U-0595 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.919 | 35.9127 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R06 | Fiber ring
RO-02 | AMM-U-0596 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.919 | 35.9164 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R06 | Fiber ring
RO-02 | AMM-U-0597 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9182 | 35.9212 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R06 | Fiber ring
RO-02 | AMM-U-0598 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.919 | 35.9259 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R04 | Fiber ring
RO-02 | AMM-U-0599 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9186 | 35.9301 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R04 | Fiber ring
RO-02 | AMM-U-0600 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.919 | 35.9353 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R04 | Fiber ring
RO-02 | AMM-U-0601 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.919 | 35.9401 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R04 | Fiber ring
RO-02 | AMM-U-0621 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9229 | 35.8815 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R07 | Fiber ring
RO-02 | AMM-U-0622 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9217 | 35.8857 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R07 | Fiber ring
RO-02 | AMM-U-0623 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9225 | 35.8914 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R06 | Fiber ring
RO-02 | AMM-U-0624 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9225 | 35.8952 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R06 | Fiber ring
RO-02 | AMM-U-0625 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9225 | 35.8999 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R05 | Fiber ring
RO-02 | AMM-U-0626 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9233 | 35.9046 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R05 | Fiber ring
RO-02 | AMM-U-0627 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9221 | 35.9089 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R05 | Fiber ring
RO-02 | AMM-U-0628 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9229 | 35.9145 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R06 | Fiber ring
RO-02 | AMM-U-0629 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9217 | 35.9188 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R05 | Fiber ring
RO-02 | AMM-U-0630 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9225 | 35.9235 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R05 | Fiber ring
RO-02 | AMM-U-0631 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9225 | 35.9273 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R05 | Fiber ring
RO-02 | AMM-U-0632 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9225 | 35.933 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R04 | Fiber ring
RO-02 | AMM-U-0633 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9225 | 35.9377 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R04 | Fiber ring
RO-02 | AMM-U-0634 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9225 | 35.9424 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R04 | Fiber ring
RO-02 | AMM-U-0635 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9225 | 35.9481 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R02 | Fiber ring
RO-02 | AMM-U-0636 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9225 | 35.9528 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R02 | Fiber ring
RO-02 | AMM-U-0637 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9217 | 35.9566 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R02 | Fiber ring
RO-02 | AMM-U-0652 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.926 | 35.8645 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R01 | Fiber ring
RO-02 | AMM-U-0653 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9269 | 35.8692 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R01 | Fiber ring
RO-02 | AMM-U-0654 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9269 | 35.8739 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R01 | Fiber ring
RO-02 | AMM-U-0655 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9252 | 35.8786 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R02 | Fiber ring
RO-02 | AMM-U-0656 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9252 | 35.8834 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R07 | Fiber ring
RO-02 | AMM-U-0657 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.926 | 35.8881 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R06 | Fiber ring
RO-02 | AMM-U-0658 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.926 | 35.8919 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R06 | Fiber ring
RO-02 | AMM-U-0659 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.926 | 35.8975 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R06 | Fiber ring
RO-02 | AMM-U-0660 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.926 | 35.9023 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R05 | Fiber ring
RO-02 | AMM-U-0661 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.926 | 35.9061 | 30 | 3 | HUB-AMM-57 | HUB-AMM-57-R05 | Fiber ring
RO-02 | AMM-U-0662 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9269 | 35.9117 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R06 | Fiber ring
RO-02 | AMM-U-0663 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9252 | 35.9164 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R05 | Fiber ring
RO-02 | AMM-U-0664 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.926 | 35.9221 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R05 | Fiber ring
RO-02 | AMM-U-0665 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9252 | 35.9259 | 30 | 3 | HUB-AMM-35 | HUB-AMM-35-R05 | Fiber ring
RO-02 | AMM-U-0666 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9256 | 35.9301 | 32 | 3 | HUB-AMM-35 | HUB-AMM-35-R05 | Fiber ring
RO-02 | AMM-U-0669 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.926 | 35.9438 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R01 | Fiber ring
RO-02 | AMM-U-0670 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.926 | 35.9495 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R01 | Fiber ring
RO-02 | AMM-U-0671 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.926 | 35.9552 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R02 | Fiber ring
RO-02 | AMM-U-0672 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.926 | 35.9599 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R02 | Fiber ring
RO-02 | AMM-U-0673 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.926 | 35.9646 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R03 | Fiber ring
RO-02 | AMM-U-0687 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9296 | 35.863 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R01 | Fiber ring
RO-02 | AMM-U-0688 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9288 | 35.8763 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R02 | Fiber ring
RO-02 | AMM-U-0689 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9304 | 35.881 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R02 | Fiber ring
RO-02 | AMM-U-0690 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9288 | 35.8857 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R02 | Fiber ring
RO-02 | AMM-U-0691 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9288 | 35.8905 | 30 | 3 | HUB-AMM-41 | HUB-AMM-41-R01 | Fiber ring
RO-02 | AMM-U-0692 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9296 | 35.8961 | 30 | 3 | HUB-AMM-41 | HUB-AMM-41-R02 | Fiber ring
RO-02 | AMM-U-0693 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9288 | 35.8999 | 30 | 3 | HUB-AMM-41 | HUB-AMM-41-R02 | Fiber ring
RO-02 | AMM-U-0694 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9288 | 35.9046 | 30 | 3 | HUB-AMM-41 | HUB-AMM-41-R02 | Fiber ring
RO-02 | AMM-U-0695 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9296 | 35.9094 | 30 | 3 | HUB-AMM-41 | HUB-AMM-41-R03 | Fiber ring
RO-02 | AMM-U-0701 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9296 | 35.9528 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R02 | Fiber ring
RO-02 | AMM-U-0702 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9296 | 35.9557 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R02 | Fiber ring
RO-02 | AMM-U-0703 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9296 | 35.9623 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R03 | Fiber ring
RO-02 | AMM-U-0704 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9296 | 35.9651 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R03 | Fiber ring
RO-02 | AMM-U-0705 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9296 | 35.9699 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R03 | Fiber ring
RO-02 | AMM-U-0720 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9339 | 35.8597 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R01 | Fiber ring
RO-02 | AMM-U-0721 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9323 | 35.8645 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R01 | Fiber ring
RO-02 | AMM-U-0722 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9323 | 35.8692 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R01 | Fiber ring
RO-02 | AMM-U-0723 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9327 | 35.8734 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R02 | Fiber ring
RO-02 | AMM-U-0724 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9339 | 35.8786 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R02 | Fiber ring
RO-02 | AMM-U-0725 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9339 | 35.8834 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R02 | Fiber ring
RO-02 | AMM-U-0726 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9339 | 35.8881 | 30 | 3 | HUB-AMM-41 | HUB-AMM-41-R01 | Fiber ring
RO-02 | AMM-U-0727 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9331 | 35.8919 | 30 | 3 | HUB-AMM-41 | HUB-AMM-41-R01 | Fiber ring
RO-02 | AMM-U-0728 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9323 | 35.8975 | 30 | 3 | HUB-AMM-41 | HUB-AMM-41-R02 | Fiber ring
RO-02 | AMM-U-0729 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9327 | 35.9027 | 30 | 3 | HUB-AMM-41 | HUB-AMM-41-R02 | Fiber ring
RO-02 | AMM-U-0730 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9331 | 35.9061 | 30 | 3 | HUB-AMM-41 | HUB-AMM-41-R03 | Fiber ring
RO-02 | AMM-U-0731 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9323 | 35.9117 | 30 | 3 | HUB-AMM-41 | HUB-AMM-41-R03 | Fiber ring
RO-02 | AMM-U-0732 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9323 | 35.9543 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R01 | Fiber ring
RO-02 | AMM-U-0733 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9331 | 35.9599 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R03 | Fiber ring
RO-02 | AMM-U-0734 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9323 | 35.9637 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R03 | Fiber ring
RO-02 | AMM-U-0735 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9335 | 35.9689 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R03 | Fiber ring
RO-02 | AMM-U-0752 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.937 | 35.8578 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R07 | Fiber ring
RO-02 | AMM-U-0753 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9374 | 35.8621 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R07 | Fiber ring
RO-02 | AMM-U-0754 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9366 | 35.8668 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R07 | Fiber ring
RO-02 | AMM-U-0755 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9366 | 35.8706 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R01 | Fiber ring
RO-02 | AMM-U-0756 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9366 | 35.8772 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R03 | Fiber ring
RO-02 | AMM-U-0757 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9366 | 35.88 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R03 | Fiber ring
RO-02 | AMM-U-0758 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9366 | 35.8848 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R03 | Fiber ring
RO-02 | AMM-U-0759 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9362 | 35.89 | 30 | 3 | HUB-AMM-41 | HUB-AMM-41-R01 | Fiber ring
RO-02 | AMM-U-0760 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9366 | 35.8942 | 30 | 3 | HUB-AMM-41 | HUB-AMM-41-R01 | Fiber ring
RO-02 | AMM-U-0761 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9366 | 35.9008 | 30 | 3 | HUB-AMM-41 | HUB-AMM-41-R02 | Fiber ring
RO-02 | AMM-U-0762 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9366 | 35.9576 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R01 | Fiber ring
RO-02 | AMM-U-0763 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9374 | 35.9613 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R04 | Fiber ring
RO-02 | AMM-U-0764 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9366 | 35.967 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R04 | Fiber ring
RO-02 | AMM-U-0777 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.941 | 35.8361 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R01 | Fiber ring
RO-02 | AMM-U-0778 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9405 | 35.8404 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R01 | Fiber ring
RO-02 | AMM-U-0779 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.8456 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R02 | Fiber ring
RO-02 | AMM-U-0780 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.8503 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R02 | Fiber ring
RO-02 | AMM-U-0781 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9405 | 35.8555 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R06 | Fiber ring
RO-02 | AMM-U-0782 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.8607 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R06 | Fiber ring
RO-02 | AMM-U-0783 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.8635 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R06 | Fiber ring
RO-02 | AMM-U-0784 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9397 | 35.8687 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R06 | Fiber ring
RO-02 | AMM-U-0785 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.8749 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R04 | Fiber ring
RO-02 | AMM-U-0786 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.8786 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R03 | Fiber ring
RO-02 | AMM-U-0787 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.8824 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R03 | Fiber ring
RO-02 | AMM-U-0788 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.941 | 35.8881 | 30 | 3 | HUB-AMM-41 | HUB-AMM-41-R07 | Fiber ring
RO-02 | AMM-U-0789 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.941 | 35.959 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R05 | Fiber ring
RO-02 | AMM-U-0790 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.9628 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R04 | Fiber ring
RO-02 | AMM-U-0804 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9437 | 35.8337 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R01 | Fiber ring
RO-02 | AMM-U-0805 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9437 | 35.8385 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R01 | Fiber ring
RO-02 | AMM-U-0806 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9437 | 35.8432 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R02 | Fiber ring
RO-02 | AMM-U-0807 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9445 | 35.8479 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R02 | Fiber ring
RO-02 | AMM-U-0808 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9445 | 35.8526 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R02 | Fiber ring
RO-02 | AMM-U-0809 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9437 | 35.8574 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R06 | Fiber ring
RO-02 | AMM-U-0810 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9437 | 35.8621 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R06 | Fiber ring
RO-02 | AMM-U-0811 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9437 | 35.8668 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R05 | Fiber ring
RO-02 | AMM-U-0812 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9445 | 35.8715 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R05 | Fiber ring
RO-02 | AMM-U-0813 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9445 | 35.8763 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R04 | Fiber ring
RO-02 | AMM-U-0814 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9445 | 35.9613 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R04 | Fiber ring
RO-02 | AMM-U-0815 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9432 | 35.9656 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R04 | Fiber ring
RO-02 | AMM-U-0829 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9472 | 35.8314 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R01 | Fiber ring
RO-02 | AMM-U-0830 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9472 | 35.8361 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R01 | Fiber ring
RO-02 | AMM-U-0831 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9472 | 35.8408 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R01 | Fiber ring
RO-02 | AMM-U-0832 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.948 | 35.8456 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R02 | Fiber ring
RO-02 | AMM-U-0833 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9472 | 35.8503 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R02 | Fiber ring
RO-02 | AMM-U-0834 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9472 | 35.8541 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R03 | Fiber ring
RO-02 | AMM-U-0835 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9472 | 35.8607 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R06 | Fiber ring
RO-02 | AMM-U-0836 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9472 | 35.8645 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R05 | Fiber ring
RO-02 | AMM-U-0837 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9472 | 35.8692 | 30 | 3 | HUB-AMM-45 | HUB-AMM-45-R05 | Fiber ring
RO-02 | AMM-U-0838 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9464 | 35.9637 | 30 | 3 | HUB-AMM-52 | HUB-AMM-52-R04 | Fiber ring
RO-02 | AMM-U-0853 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9507 | 35.829 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R06 | Fiber ring
RO-02 | AMM-U-0854 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9507 | 35.8328 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R06 | Fiber ring
RO-02 | AMM-U-0855 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9507 | 35.8385 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R06 | Fiber ring
RO-02 | AMM-U-0856 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9507 | 35.8432 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R01 | Fiber ring
RO-02 | AMM-U-0857 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9507 | 35.8479 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R03 | Fiber ring
RO-02 | AMM-U-0858 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9511 | 35.8522 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R03 | Fiber ring
RO-02 | AMM-U-0859 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9507 | 35.8574 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R03 | Fiber ring
RO-02 | AMM-U-0875 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9542 | 35.8276 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R06 | Fiber ring
RO-02 | AMM-U-0876 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9534 | 35.8314 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R06 | Fiber ring
RO-02 | AMM-U-0877 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.955 | 35.8361 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R06 | Fiber ring
RO-02 | AMM-U-0878 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9546 | 35.8404 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R05 | Fiber ring
RO-02 | AMM-U-0879 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9538 | 35.846 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R04 | Fiber ring
RO-02 | AMM-U-0896 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9586 | 35.829 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R06 | Fiber ring
RO-02 | AMM-U-0897 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9578 | 35.8347 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R05 | Fiber ring
RO-02 | AMM-U-0898 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9578 | 35.8385 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R05 | Fiber ring
RO-02 | AMM-U-0899 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9578 | 35.8422 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R05 | Fiber ring
RO-02 | AMM-U-0900 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9586 | 35.8479 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R04 | Fiber ring
RO-02 | AMM-U-0918 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9613 | 35.8304 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R05 | Fiber ring
RO-02 | AMM-U-0919 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9613 | 35.837 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R05 | Fiber ring
RO-02 | AMM-U-0920 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9613 | 35.8408 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R05 | Fiber ring
RO-02 | AMM-U-0921 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9613 | 35.8446 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R04 | Fiber ring
RO-02 | AMM-U-0942 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.964 | 35.8432 | 31 | 3 | HUB-AMM-64 | HUB-AMM-64-R04 | Fiber ring
RO-02 | AMM-U-0943 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9648 | 35.8489 | 30 | 3 | HUB-AMM-64 | HUB-AMM-64-R04 | Fiber ring
RO-02 | AMM-U-0967 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9683 | 35.8503 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R01 | Fiber ring
RO-02 | AMM-U-0992 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9718 | 35.8489 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R01 | Fiber ring
RO-02 | AMM-U-0993 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9727 | 35.8526 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R01 | Fiber ring
RO-02 | AMM-U-1019 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9762 | 35.8503 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R01 | Fiber ring
RO-02 | AMM-U-1043 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9789 | 35.8479 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R07 | Fiber ring
RO-02 | AMM-U-1044 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9789 | 35.8526 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R07 | Fiber ring
RO-02 | AMM-U-1045 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9789 | 35.8564 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R06 | Fiber ring
RO-02 | AMM-U-1046 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9785 | 35.8616 | 36 | 3 | HUB-AMM-59 | HUB-AMM-59-R01 | Fiber ring
RO-02 | AMM-U-1071 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9824 | 35.8503 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R06 | Fiber ring
RO-02 | AMM-U-1072 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9824 | 35.8541 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R06 | Fiber ring
RO-02 | AMM-U-1073 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9832 | 35.8597 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R06 | Fiber ring
RO-02 | AMM-U-1074 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9832 | 35.8645 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R05 | Fiber ring
RO-02 | AMM-U-1075 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.982 | 35.8697 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R04 | Fiber ring
RO-02 | AMM-U-1076 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9824 | 35.8739 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R04 | Fiber ring
RO-02 | AMM-U-1102 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9859 | 35.8489 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R06 | Fiber ring
RO-02 | AMM-U-1103 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9855 | 35.8522 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R06 | Fiber ring
RO-02 | AMM-U-1104 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9868 | 35.8574 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R06 | Fiber ring
RO-02 | AMM-U-1105 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9859 | 35.8612 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R05 | Fiber ring
RO-02 | AMM-U-1106 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9859 | 35.8668 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R05 | Fiber ring
RO-02 | AMM-U-1107 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9859 | 35.8725 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R05 | Fiber ring
RO-02 | AMM-U-1108 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9851 | 35.8763 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R04 | Fiber ring
RO-02 | AMM-U-1109 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9864 | 35.8805 | 31 | 3 | HUB-AMM-23 | HUB-AMM-23-R06 | Fiber ring
RO-02 | AMM-U-1110 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9859 | 35.8857 | 30 | 3 | HUB-AMM-23 | HUB-AMM-23-R06 | Fiber ring
RO-02 | AMM-U-1139 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9887 | 35.8597 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R05 | Fiber ring
RO-02 | AMM-U-1141 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.8692 | 31 | 3 | HUB-AMM-59 | HUB-AMM-59-R05 | Fiber ring
RO-02 | AMM-U-1142 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.8749 | 30 | 3 | HUB-AMM-59 | HUB-AMM-59-R05 | Fiber ring
RO-02 | AMM-U-1143 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.8777 | 30 | 3 | HUB-AMM-23 | HUB-AMM-23-R06 | Fiber ring
RO-02 | AMM-U-1144 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.8843 | 30 | 3 | HUB-AMM-23 | HUB-AMM-23-R06 | Fiber ring
RO-02 | AMM-U-1145 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9903 | 35.8881 | 36 | 3 | HUB-AMM-23 | HUB-AMM-23-R06 | Fiber ring
RO-02 | AMM-U-1146 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.8919 | 34 | 3 | HUB-AMM-23 | HUB-AMM-23-R05 | Fiber ring
RO-02 | AMM-U-1147 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9903 | 35.8975 | 30 | 3 | HUB-AMM-23 | HUB-AMM-23-R04 | Fiber ring
RO-02 | AMM-U-1148 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.9023 | 30 | 3 | HUB-AMM-23 | HUB-AMM-23-R04 | Fiber ring
RO-02 | AMM-U-1149 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.907 | 30 | 3 | HUB-AMM-23 | HUB-AMM-23-R04 | Fiber ring
RO-02 | AMM-U-1186 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.993 | 35.8819 | 30 | 3 | HUB-AMM-23 | HUB-AMM-23-R06 | Fiber ring
RO-02 | AMM-U-1187 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.993 | 35.8848 | 30 | 3 | HUB-AMM-23 | HUB-AMM-23-R05 | Fiber ring
RO-02 | AMM-U-1188 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9934 | 35.89 | 36 | 3 | HUB-AMM-23 | HUB-AMM-23-R05 | Fiber ring
RO-02 | AMM-U-1189 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.993 | 35.8952 | 35 | 3 | HUB-AMM-23 | HUB-AMM-23-R05 | Fiber ring
RO-02 | AMM-U-1190 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9922 | 35.8999 | 30 | 3 | HUB-AMM-23 | HUB-AMM-23-R04 | Fiber ring
RO-02 | AMM-U-1191 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.993 | 35.9056 | 30 | 3 | HUB-AMM-23 | HUB-AMM-23-R04 | Fiber ring
RO-02 | AMM-U-1233 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9973 | 35.8928 | 30 | 3 | HUB-AMM-23 | HUB-AMM-23-R05 | Fiber ring
RO-02 | AMM-U-1234 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9973 | 35.8975 | 30 | 3 | HUB-AMM-23 | HUB-AMM-23-R05 | Fiber ring
RO-02 | AMM-U-1235 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9973 | 35.9023 | 30 | 3 | HUB-AMM-23 | HUB-AMM-23-R04 | Fiber ring
RO-02 | AMM-U-1277 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9992 | 35.8952 | 30 | 3 | HUB-AMM-23 | HUB-AMM-23-R05 | Fiber ring
RO-02 | AMM-U-1278 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9992 | 35.8999 | 30 | 3 | HUB-AMM-23 | HUB-AMM-23-R04 | Fiber ring
RO-02 | IRB-DU-0003 | DU | Rooftop | Irbid | Irbid | 32.5452 | 35.8495 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R01 | Fiber ring
RO-02 | IRB-DU-0004 | DU | Rooftop | Irbid | Irbid | 32.5452 | 35.8534 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R01 | Fiber ring
RO-02 | IRB-DU-0005 | DU | Rooftop | Irbid | Irbid | 32.5452 | 35.8574 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R01 | Fiber ring
RO-02 | IRB-DU-0009 | DU | Rooftop | Irbid | Irbid | 32.5474 | 35.8475 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R01 | Fiber ring
RO-02 | IRB-DU-0010 | DU | Rooftop | Irbid | Irbid | 32.5481 | 35.8515 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R01 | Fiber ring
RO-02 | IRB-DU-0011 | DU | Rooftop | Irbid | Irbid | 32.5481 | 35.8554 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R01 | Fiber ring
RO-02 | IRB-DU-0012 | DU | Rooftop | Irbid | Irbid | 32.5481 | 35.8593 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R02 | Fiber ring
RO-02 | IRB-DU-0013 | DU | Rooftop | Irbid | Irbid | 32.5481 | 35.8633 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R03 | Fiber ring
RO-02 | IRB-DU-0016 | DU | Rooftop | Irbid | Irbid | 32.551 | 35.8416 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R02 | Fiber ring
RO-02 | IRB-DU-0017 | DU | Rooftop | Irbid | Irbid | 32.551 | 35.8456 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R02 | Fiber ring
RO-02 | IRB-DU-0018 | DU | Rooftop | Irbid | Irbid | 32.551 | 35.8495 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R07 | Fiber ring
RO-02 | IRB-DU-0019 | DU | Rooftop | Irbid | Irbid | 32.551 | 35.8534 | 26 | 3 | HUB-IRB-15 | HUB-IRB-15-R08 | Fiber ring
RO-02 | IRB-DU-0020 | DU | Rooftop | Irbid | Irbid | 32.551 | 35.8574 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R08 | Fiber ring
RO-02 | IRB-DU-0021 | DU | Rooftop | Irbid | Irbid | 32.551 | 35.8613 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R01 | Fiber ring
RO-02 | IRB-DU-0022 | DU | Rooftop | Irbid | Irbid | 32.551 | 35.8653 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R04 | Fiber ring
RO-02 | IRB-DU-0023 | DU | Rooftop | Irbid | Irbid | 32.554 | 35.8357 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R02 | Fiber ring
RO-02 | IRB-DU-0024 | DU | Rooftop | Irbid | Irbid | 32.554 | 35.8396 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R02 | Fiber ring
RO-02 | IRB-DU-0025 | DU | Rooftop | Irbid | Irbid | 32.554 | 35.8436 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R02 | Fiber ring
RO-02 | IRB-DU-0026 | DU | Rooftop | Irbid | Irbid | 32.554 | 35.8475 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R03 | Fiber ring
RO-02 | IRB-DU-0027 | DU | Rooftop | Irbid | Irbid | 32.554 | 35.8515 | 27 | 3 | HUB-IRB-15 | HUB-IRB-15-R07 | Fiber ring
RO-02 | IRB-DU-0028 | DU | Rooftop | Irbid | Irbid | 32.554 | 35.8554 | 27 | 3 | HUB-IRB-15 | HUB-IRB-15-R07 | Fiber ring
RO-02 | IRB-DU-0029 | DU | Rooftop | Irbid | Irbid | 32.554 | 35.8593 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R07 | Fiber ring
RO-02 | IRB-DU-0030 | DU | Rooftop | Irbid | Irbid | 32.554 | 35.8633 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R05 | Fiber ring
RO-02 | IRB-DU-0031 | DU | Rooftop | Irbid | Irbid | 32.554 | 35.8672 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R05 | Fiber ring
RO-02 | IRB-DU-0032 | DU | Rooftop | Irbid | Irbid | 32.5562 | 35.8337 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R01 | Fiber ring
RO-02 | IRB-DU-0033 | DU | Rooftop | Irbid | Irbid | 32.5562 | 35.8377 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R02 | Fiber ring
RO-02 | IRB-DU-0034 | DU | Rooftop | Irbid | Irbid | 32.5576 | 35.8416 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R02 | Fiber ring
RO-02 | IRB-DU-0035 | DU | Rooftop | Irbid | Irbid | 32.5569 | 35.8463 | 26 | 3 | HUB-IRB-01 | HUB-IRB-01-R03 | Fiber ring
RO-02 | IRB-DU-0036 | DU | Rooftop | Irbid | Irbid | 32.5573 | 35.8491 | 26 | 3 | HUB-IRB-01 | HUB-IRB-01-R03 | Fiber ring
RO-02 | IRB-DU-0037 | DU | Rooftop | Irbid | Irbid | 32.5569 | 35.8534 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R07 | Fiber ring
RO-02 | IRB-DU-0038 | DU | Rooftop | Irbid | Irbid | 32.5569 | 35.8574 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R07 | Fiber ring
RO-02 | IRB-DU-0039 | DU | Rooftop | Irbid | Irbid | 32.5569 | 35.8613 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R06 | Fiber ring
RO-02 | IRB-DU-0040 | DU | Rooftop | Irbid | Irbid | 32.5569 | 35.8653 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R05 | Fiber ring
RO-02 | IRB-DU-0041 | DU | Rooftop | Irbid | Irbid | 32.5598 | 35.8365 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R01 | Fiber ring
RO-02 | IRB-DU-0042 | DU | Rooftop | Irbid | Irbid | 32.5598 | 35.8396 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R01 | Fiber ring
RO-02 | IRB-DU-0043 | DU | Rooftop | Irbid | Irbid | 32.5598 | 35.8436 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R03 | Fiber ring
RO-02 | IRB-DU-0044 | DU | Rooftop | Irbid | Irbid | 32.5592 | 35.8475 | 26 | 3 | HUB-IRB-01 | HUB-IRB-01-R03 | Fiber ring
RO-02 | IRB-DU-0045 | DU | Rooftop | Irbid | Irbid | 32.5592 | 35.8515 | 26 | 3 | HUB-IRB-01 | HUB-IRB-01-R03 | Fiber ring
RO-02 | IRB-DU-0046 | DU | Rooftop | Irbid | Irbid | 32.5598 | 35.8554 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R07 | Fiber ring
RO-02 | IRB-DU-0047 | DU | Rooftop | Irbid | Irbid | 32.5598 | 35.8593 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R06 | Fiber ring
RO-02 | IRB-DU-0048 | DU | Rooftop | Irbid | Irbid | 32.5598 | 35.8633 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R06 | Fiber ring
RO-02 | IRB-DU-0049 | DU | Rooftop | Irbid | Irbid | 32.5621 | 35.8377 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R06 | Fiber ring
RO-02 | IRB-DU-0050 | DU | Rooftop | Irbid | Irbid | 32.5621 | 35.8416 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R01 | Fiber ring
RO-02 | IRB-DU-0051 | DU | Rooftop | Irbid | Irbid | 32.5621 | 35.8456 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R03 | Fiber ring
RO-02 | IRB-DU-0052 | DU | Rooftop | Irbid | Irbid | 32.5621 | 35.8495 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R04 | Fiber ring
RO-02 | IRB-DU-0053 | DU | Rooftop | Irbid | Irbid | 32.5628 | 35.8534 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R04 | Fiber ring
RO-02 | IRB-DU-0054 | DU | Rooftop | Irbid | Irbid | 32.5628 | 35.8574 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R06 | Fiber ring
RO-02 | IRB-DU-0055 | DU | Rooftop | Irbid | Irbid | 32.5628 | 35.8613 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R06 | Fiber ring
RO-02 | IRB-DU-0056 | DU | Rooftop | Irbid | Irbid | 32.565 | 35.8436 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R04 | Fiber ring
RO-02 | IRB-DU-0057 | DU | Rooftop | Irbid | Irbid | 32.5657 | 35.8475 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R04 | Fiber ring
RO-02 | IRB-DU-0058 | DU | Rooftop | Irbid | Irbid | 32.565 | 35.8515 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R04 | Fiber ring
RO-02 | IRB-DU-0059 | DU | Rooftop | Irbid | Irbid | 32.5657 | 35.8562 | 25 | 3 | HUB-IRB-01 | HUB-IRB-01-R04 | Fiber ring
RO-02 | IRB-DU-0060 | DU | Rooftop | Irbid | Irbid | 32.5657 | 35.8593 | 25 | 3 | HUB-IRB-15 | HUB-IRB-15-R06 | Fiber ring
RO-02 | IRB-U-0195 | U | Rooftop | Irbid | Irbid | 32.5358 | 35.8526 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R02 | Fiber ring
RO-02 | IRB-U-0196 | U | Rooftop | Irbid | Irbid | 32.5358 | 35.8574 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R02 | Fiber ring
RO-02 | IRB-U-0197 | U | Rooftop | Irbid | Irbid | 32.5358 | 35.8612 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R02 | Fiber ring
RO-02 | IRB-U-0198 | U | Rooftop | Irbid | Irbid | 32.5358 | 35.8668 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R03 | Fiber ring
RO-02 | IRB-U-0217 | U | Rooftop | Irbid | Irbid | 32.5393 | 35.8512 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R01 | Fiber ring
RO-02 | IRB-U-0218 | U | Rooftop | Irbid | Irbid | 32.5393 | 35.8541 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R02 | Fiber ring
RO-02 | IRB-U-0219 | U | Rooftop | Irbid | Irbid | 32.5393 | 35.8597 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R02 | Fiber ring
RO-02 | IRB-U-0220 | U | Rooftop | Irbid | Irbid | 32.5393 | 35.8645 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R03 | Fiber ring
RO-02 | IRB-U-0221 | U | Rooftop | Irbid | Irbid | 32.5393 | 35.8692 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R03 | Fiber ring
RO-02 | IRB-U-0240 | U | Rooftop | Irbid | Irbid | 32.5428 | 35.8574 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R02 | Fiber ring
RO-02 | IRB-U-0241 | U | Rooftop | Irbid | Irbid | 32.5428 | 35.8621 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R03 | Fiber ring
RO-02 | IRB-U-0242 | U | Rooftop | Irbid | Irbid | 32.5428 | 35.8668 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R03 | Fiber ring
RO-02 | IRB-U-0243 | U | Rooftop | Irbid | Irbid | 32.542 | 35.8715 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R03 | Fiber ring
RO-02 | IRB-U-0244 | U | Rooftop | Irbid | Irbid | 32.5428 | 35.8763 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R04 | Fiber ring
RO-02 | IRB-U-0264 | U | Rooftop | Irbid | Irbid | 32.5463 | 35.8692 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R04 | Fiber ring
RO-02 | IRB-U-0265 | U | Rooftop | Irbid | Irbid | 32.5463 | 35.8739 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R04 | Fiber ring
RO-02 | IRB-U-0266 | U | Rooftop | Irbid | Irbid | 32.5463 | 35.8786 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R04 | Fiber ring
RO-02 | IRB-U-0286 | U | Rooftop | Irbid | Irbid | 32.5499 | 35.8715 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R04 | Fiber ring
RO-02 | IRB-U-0287 | U | Rooftop | Irbid | Irbid | 32.5499 | 35.8763 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R04 | Fiber ring
RO-02 | IRB-U-0309 | U | Rooftop | Irbid | Irbid | 32.5534 | 35.8739 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R05 | Fiber ring
RO-02 | IRB-U-0330 | U | Rooftop | Irbid | Irbid | 32.5569 | 35.8252 | 30 | 3 | HUB-IRB-01 | HUB-IRB-01-R01 | Fiber ring
RO-02 | IRB-U-0331 | U | Rooftop | Irbid | Irbid | 32.5569 | 35.829 | 30 | 3 | HUB-IRB-01 | HUB-IRB-01-R01 | Fiber ring
RO-02 | IRB-U-0332 | U | Rooftop | Irbid | Irbid | 32.5561 | 35.8715 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R05 | Fiber ring
RO-02 | IRB-U-0354 | U | Rooftop | Irbid | Irbid | 32.5596 | 35.8267 | 30 | 3 | HUB-IRB-01 | HUB-IRB-01-R01 | Fiber ring
RO-02 | IRB-U-0355 | U | Rooftop | Irbid | Irbid | 32.5596 | 35.8314 | 30 | 3 | HUB-IRB-01 | HUB-IRB-01-R01 | Fiber ring
RO-02 | IRB-U-0356 | U | Rooftop | Irbid | Irbid | 32.5604 | 35.8692 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R05 | Fiber ring
RO-02 | IRB-U-0378 | U | Rooftop | Irbid | Irbid | 32.5631 | 35.829 | 30 | 3 | HUB-IRB-01 | HUB-IRB-01-R06 | Fiber ring
RO-02 | IRB-U-0379 | U | Rooftop | Irbid | Irbid | 32.5631 | 35.8337 | 30 | 3 | HUB-IRB-01 | HUB-IRB-01-R05 | Fiber ring
RO-02 | IRB-U-0380 | U | Rooftop | Irbid | Irbid | 32.564 | 35.8668 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R05 | Fiber ring
RO-02 | IRB-U-0402 | U | Rooftop | Irbid | Irbid | 32.5667 | 35.8314 | 30 | 3 | HUB-IRB-01 | HUB-IRB-01-R05 | Fiber ring
RO-02 | IRB-U-0403 | U | Rooftop | Irbid | Irbid | 32.5675 | 35.8361 | 30 | 3 | HUB-IRB-01 | HUB-IRB-01-R05 | Fiber ring
RO-02 | IRB-U-0404 | U | Rooftop | Irbid | Irbid | 32.5675 | 35.8408 | 30 | 3 | HUB-IRB-01 | HUB-IRB-01-R05 | Fiber ring
RO-02 | IRB-U-0405 | U | Rooftop | Irbid | Irbid | 32.5675 | 35.8456 | 30 | 3 | HUB-IRB-01 | HUB-IRB-01-R04 | Fiber ring
RO-02 | IRB-U-0406 | U | Rooftop | Irbid | Irbid | 32.5675 | 35.8645 | 30 | 3 | HUB-IRB-15 | HUB-IRB-15-R06 | Fiber ring
RO-02 | IRB-U-0426 | U | Rooftop | Irbid | Irbid | 32.571 | 35.8337 | 30 | 3 | HUB-IRB-01 | HUB-IRB-01-R05 | Fiber ring
RO-02 | IRB-U-0427 | U | Rooftop | Irbid | Irbid | 32.571 | 35.8385 | 30 | 3 | HUB-IRB-01 | HUB-IRB-01-R05 | Fiber ring
RO-02 | IRB-U-0428 | U | Rooftop | Irbid | Irbid | 32.571 | 35.8432 | 30 | 3 | HUB-IRB-01 | HUB-IRB-01-R05 | Fiber ring
RO-03 | AMM-DU-0136 | DU | Rooftop | Amman-Zarqa Metro | Amman | 31.9519 | 35.9645 | 27 | 3 | HUB-AMM-83 | HUB-AMM-83-R07 | Fiber ring
RO-03 | AMM-U-0736 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9339 | 35.9731 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R01 | Fiber ring
RO-03 | AMM-U-0737 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9339 | 35.9779 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R02 | Fiber ring
RO-03 | AMM-U-0738 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9331 | 35.9836 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R02 | Fiber ring
RO-03 | AMM-U-0765 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9366 | 35.9717 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R01 | Fiber ring
RO-03 | AMM-U-0766 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9358 | 35.9755 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R02 | Fiber ring
RO-03 | AMM-U-0767 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9374 | 35.9802 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R02 | Fiber ring
RO-03 | AMM-U-0768 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9366 | 35.984 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R02 | Fiber ring
RO-03 | AMM-U-0791 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9397 | 35.9689 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R01 | Fiber ring
RO-03 | AMM-U-0792 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.9722 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R01 | Fiber ring
RO-03 | AMM-U-0793 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9393 | 35.9779 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R02 | Fiber ring
RO-03 | AMM-U-0794 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9393 | 35.9826 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R02 | Fiber ring
RO-03 | AMM-U-0795 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9393 | 35.9873 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R03 | Fiber ring
RO-03 | AMM-U-0796 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.941 | 35.9921 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R03 | Fiber ring
RO-03 | AMM-U-0816 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9437 | 35.9699 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R01 | Fiber ring
RO-03 | AMM-U-0817 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9437 | 35.9755 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R01 | Fiber ring
RO-03 | AMM-U-0818 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9428 | 35.9802 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R03 | Fiber ring
RO-03 | AMM-U-0819 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9437 | 35.9859 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R03 | Fiber ring
RO-03 | AMM-U-0820 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9437 | 35.9897 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R03 | Fiber ring
RO-03 | AMM-U-0821 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9437 | 35.9954 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R03 | Fiber ring
RO-03 | AMM-U-0839 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9464 | 35.9684 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R01 | Fiber ring
RO-03 | AMM-U-0840 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9472 | 35.9741 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R07 | Fiber ring
RO-03 | AMM-U-0841 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9472 | 35.9769 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R01 | Fiber ring
RO-03 | AMM-U-0842 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9472 | 35.9836 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R04 | Fiber ring
RO-03 | AMM-U-0843 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.948 | 35.9873 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R04 | Fiber ring
RO-03 | AMM-U-0844 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9472 | 35.993 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R04 | Fiber ring
RO-03 | AMM-U-0845 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9468 | 35.9963 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R03 | Fiber ring
RO-03 | AMM-U-0860 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9503 | 35.9656 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R07 | Fiber ring
RO-03 | AMM-U-0861 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9499 | 35.9708 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R07 | Fiber ring
RO-03 | AMM-U-0862 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9507 | 35.9746 | 32 | 3 | HUB-AMM-83 | HUB-AMM-83-R06 | Fiber ring
RO-03 | AMM-U-0863 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9507 | 35.9812 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R05 | Fiber ring
RO-03 | AMM-U-0864 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9503 | 35.9845 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R04 | Fiber ring
RO-03 | AMM-U-0865 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9499 | 35.9897 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R04 | Fiber ring
RO-03 | AMM-U-0866 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9499 | 35.9944 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R04 | Fiber ring
RO-03 | AMM-U-0880 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9538 | 35.9689 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R07 | Fiber ring
RO-03 | AMM-U-0881 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9542 | 35.9722 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R06 | Fiber ring
RO-03 | AMM-U-0882 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9538 | 35.9783 | 33 | 3 | HUB-AMM-83 | HUB-AMM-83-R06 | Fiber ring
RO-03 | AMM-U-0883 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9542 | 35.9836 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R05 | Fiber ring
RO-03 | AMM-U-0884 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9542 | 35.9864 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R05 | Fiber ring
RO-03 | AMM-U-0885 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9542 | 35.993 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R04 | Fiber ring
RO-03 | AMM-U-0901 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9578 | 35.9661 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R06 | Fiber ring
RO-03 | AMM-U-0902 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9569 | 35.9708 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R06 | Fiber ring
RO-03 | AMM-U-0903 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9582 | 35.976 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R06 | Fiber ring
RO-03 | AMM-U-0904 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9569 | 35.9802 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R06 | Fiber ring
RO-03 | AMM-U-0905 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9569 | 35.985 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R05 | Fiber ring
RO-03 | AMM-U-0906 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9574 | 35.9902 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R05 | Fiber ring
RO-03 | AMM-U-0917 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9613 | 35.8276 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R01 | Fiber ring
RO-03 | AMM-U-0922 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9613 | 35.9675 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R01 | Fiber ring
RO-03 | AMM-U-0923 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9613 | 35.9722 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R02 | Fiber ring
RO-03 | AMM-U-0924 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9613 | 35.9779 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R02 | Fiber ring
RO-03 | AMM-U-0925 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9605 | 35.9826 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R05 | Fiber ring
RO-03 | AMM-U-0926 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9609 | 35.9878 | 30 | 3 | HUB-AMM-83 | HUB-AMM-83-R05 | Fiber ring
RO-03 | AMM-U-0938 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9652 | 35.8248 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R01 | Fiber ring
RO-03 | AMM-U-0939 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9656 | 35.829 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R02 | Fiber ring
RO-03 | AMM-U-0940 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9652 | 35.8342 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R02 | Fiber ring
RO-03 | AMM-U-0941 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9648 | 35.8385 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R02 | Fiber ring
RO-03 | AMM-U-0944 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9648 | 35.9651 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R01 | Fiber ring
RO-03 | AMM-U-0945 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9656 | 35.9708 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R02 | Fiber ring
RO-03 | AMM-U-0946 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.964 | 35.9755 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R02 | Fiber ring
RO-03 | AMM-U-0947 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.964 | 35.9802 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R03 | Fiber ring
RO-03 | AMM-U-0948 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9648 | 35.985 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R03 | Fiber ring
RO-03 | AMM-U-0949 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9648 | 35.9897 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R03 | Fiber ring
RO-03 | AMM-U-0961 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9687 | 35.8224 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R01 | Fiber ring
RO-03 | AMM-U-0962 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9683 | 35.8267 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R01 | Fiber ring
RO-03 | AMM-U-0963 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9691 | 35.8314 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R02 | Fiber ring
RO-03 | AMM-U-0964 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9683 | 35.8361 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R02 | Fiber ring
RO-03 | AMM-U-0965 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9683 | 35.8408 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R02 | Fiber ring
RO-03 | AMM-U-0966 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9683 | 35.8465 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R03 | Fiber ring
RO-03 | AMM-U-0968 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9691 | 35.9637 | 31 | 3 | HUB-AMM-47 | HUB-AMM-47-R01 | Fiber ring
RO-03 | AMM-U-0969 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9675 | 35.9684 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R01 | Fiber ring
RO-03 | AMM-U-0970 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9683 | 35.9741 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R02 | Fiber ring
RO-03 | AMM-U-0971 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9687 | 35.9774 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R02 | Fiber ring
RO-03 | AMM-U-0972 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9675 | 35.9826 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R03 | Fiber ring
RO-03 | AMM-U-0973 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9675 | 35.9873 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R03 | Fiber ring
RO-03 | AMM-U-0974 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9683 | 35.9921 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R04 | Fiber ring
RO-03 | AMM-U-0987 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9718 | 35.8243 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R01 | Fiber ring
RO-03 | AMM-U-0988 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9727 | 35.829 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R01 | Fiber ring
RO-03 | AMM-U-0989 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9723 | 35.8342 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R02 | Fiber ring
RO-03 | AMM-U-0990 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.971 | 35.8385 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R03 | Fiber ring
RO-03 | AMM-U-0991 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9723 | 35.8437 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R03 | Fiber ring
RO-03 | AMM-U-0995 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9727 | 35.9661 | 33 | 3 | HUB-AMM-47 | HUB-AMM-47-R01 | Fiber ring
RO-03 | AMM-U-0996 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9718 | 35.9699 | 31 | 3 | HUB-AMM-47 | HUB-AMM-47-R01 | Fiber ring
RO-03 | AMM-U-0997 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9718 | 35.9755 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R02 | Fiber ring
RO-03 | AMM-U-0998 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9718 | 35.9802 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R03 | Fiber ring
RO-03 | AMM-U-0999 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9718 | 35.985 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R03 | Fiber ring
RO-03 | AMM-U-1000 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.971 | 35.9897 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R04 | Fiber ring
RO-03 | AMM-U-1001 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.971 | 35.9944 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R04 | Fiber ring
RO-03 | AMM-U-1013 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.8229 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R01 | Fiber ring
RO-03 | AMM-U-1014 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9762 | 35.8267 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R06 | Fiber ring
RO-03 | AMM-U-1015 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9762 | 35.8314 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R01 | Fiber ring
RO-03 | AMM-U-1016 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.8352 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R03 | Fiber ring
RO-03 | AMM-U-1017 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.8418 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R03 | Fiber ring
RO-03 | AMM-U-1018 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9762 | 35.8456 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R03 | Fiber ring
RO-03 | AMM-U-1020 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.9628 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R07 | Fiber ring
RO-03 | AMM-U-1021 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9746 | 35.9684 | 33 | 3 | HUB-AMM-47 | HUB-AMM-47-R01 | Fiber ring
RO-03 | AMM-U-1022 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.9741 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R07 | Fiber ring
RO-03 | AMM-U-1023 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.9779 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R01 | Fiber ring
RO-03 | AMM-U-1024 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.9826 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R04 | Fiber ring
RO-03 | AMM-U-1025 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9762 | 35.9873 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R04 | Fiber ring
RO-03 | AMM-U-1026 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.9911 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R04 | Fiber ring
RO-03 | AMM-U-1027 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9754 | 35.9968 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R04 | Fiber ring
RO-03 | AMM-U-1037 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9789 | 35.8205 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R06 | Fiber ring
RO-03 | AMM-U-1038 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9797 | 35.8243 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R06 | Fiber ring
RO-03 | AMM-U-1039 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9789 | 35.829 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R05 | Fiber ring
RO-03 | AMM-U-1040 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9789 | 35.8328 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R04 | Fiber ring
RO-03 | AMM-U-1041 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9793 | 35.838 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R04 | Fiber ring
RO-03 | AMM-U-1042 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9789 | 35.8432 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R03 | Fiber ring
RO-03 | AMM-U-1048 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9789 | 35.9613 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R07 | Fiber ring
RO-03 | AMM-U-1049 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9789 | 35.9661 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R07 | Fiber ring
RO-03 | AMM-U-1050 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9789 | 35.9699 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R07 | Fiber ring
RO-03 | AMM-U-1051 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9781 | 35.9755 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R06 | Fiber ring
RO-03 | AMM-U-1052 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9789 | 35.9812 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R05 | Fiber ring
RO-03 | AMM-U-1053 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9789 | 35.984 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R05 | Fiber ring
RO-03 | AMM-U-1054 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9797 | 35.9897 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R05 | Fiber ring
RO-03 | AMM-U-1055 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9789 | 35.9935 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R05 | Fiber ring
RO-03 | AMM-U-1065 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9824 | 35.8229 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R05 | Fiber ring
RO-03 | AMM-U-1066 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9824 | 35.8267 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R05 | Fiber ring
RO-03 | AMM-U-1067 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9816 | 35.8314 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R05 | Fiber ring
RO-03 | AMM-U-1068 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9824 | 35.8361 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R04 | Fiber ring
RO-03 | AMM-U-1069 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.982 | 35.8413 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R04 | Fiber ring
RO-03 | AMM-U-1070 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9824 | 35.8456 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R04 | Fiber ring
RO-03 | AMM-U-1077 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9824 | 35.9495 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R02 | Fiber ring
RO-03 | AMM-U-1078 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9828 | 35.9547 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R02 | Fiber ring
RO-03 | AMM-U-1079 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9832 | 35.959 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R03 | Fiber ring
RO-03 | AMM-U-1080 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9832 | 35.9637 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R06 | Fiber ring
RO-03 | AMM-U-1081 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9832 | 35.9684 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R06 | Fiber ring
RO-03 | AMM-U-1082 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9832 | 35.9731 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R06 | Fiber ring
RO-03 | AMM-U-1083 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9824 | 35.9788 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R06 | Fiber ring
RO-03 | AMM-U-1084 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.982 | 35.9821 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R05 | Fiber ring
RO-03 | AMM-U-1085 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9824 | 35.9873 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R05 | Fiber ring
RO-03 | AMM-U-1086 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9824 | 35.9911 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R05 | Fiber ring
RO-03 | AMM-U-1097 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9855 | 35.8238 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R05 | Fiber ring
RO-03 | AMM-U-1098 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9859 | 35.8281 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R05 | Fiber ring
RO-03 | AMM-U-1099 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9859 | 35.8337 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R05 | Fiber ring
RO-03 | AMM-U-1100 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9859 | 35.8394 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R04 | Fiber ring
RO-03 | AMM-U-1101 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9859 | 35.8441 | 30 | 3 | HUB-AMM-02 | HUB-AMM-02-R04 | Fiber ring
RO-03 | AMM-U-1111 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9859 | 35.9415 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R01 | Fiber ring
RO-03 | AMM-U-1112 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9859 | 35.9472 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R02 | Fiber ring
RO-03 | AMM-U-1113 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9859 | 35.9509 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R02 | Fiber ring
RO-03 | AMM-U-1114 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9864 | 35.9571 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R02 | Fiber ring
RO-03 | AMM-U-1115 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9855 | 35.9609 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R03 | Fiber ring
RO-03 | AMM-U-1116 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9859 | 35.9651 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R03 | Fiber ring
RO-03 | AMM-U-1117 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9851 | 35.9708 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R06 | Fiber ring
RO-03 | AMM-U-1118 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9859 | 35.9746 | 30 | 3 | HUB-AMM-47 | HUB-AMM-47-R06 | Fiber ring
RO-03 | AMM-U-1132 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9891 | 35.8262 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R01 | Fiber ring
RO-03 | AMM-U-1133 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9903 | 35.8314 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R02 | Fiber ring
RO-03 | AMM-U-1134 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9903 | 35.8361 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R02 | Fiber ring
RO-03 | AMM-U-1135 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.8408 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R02 | Fiber ring
RO-03 | AMM-U-1136 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.8465 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R03 | Fiber ring
RO-03 | AMM-U-1137 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.8503 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R01 | Fiber ring
RO-03 | AMM-U-1138 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.8541 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R01 | Fiber ring
RO-03 | AMM-U-1140 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9903 | 35.8645 | 31 | 3 | HUB-AMM-27 | HUB-AMM-27-R02 | Fiber ring
RO-03 | AMM-U-1154 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.9391 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R01 | Fiber ring
RO-03 | AMM-U-1155 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.9448 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R01 | Fiber ring
RO-03 | AMM-U-1156 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9887 | 35.9495 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R02 | Fiber ring
RO-03 | AMM-U-1157 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9887 | 35.9543 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R02 | Fiber ring
RO-03 | AMM-U-1158 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.959 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R03 | Fiber ring
RO-03 | AMM-U-1159 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.9637 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R03 | Fiber ring
RO-03 | AMM-U-1174 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9922 | 35.8243 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R01 | Fiber ring
RO-03 | AMM-U-1175 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.993 | 35.829 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R02 | Fiber ring
RO-03 | AMM-U-1176 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9938 | 35.8337 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R02 | Fiber ring
RO-03 | AMM-U-1177 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.993 | 35.8375 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R02 | Fiber ring
RO-03 | AMM-U-1178 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9922 | 35.8432 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R03 | Fiber ring
RO-03 | AMM-U-1179 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9926 | 35.8484 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R01 | Fiber ring
RO-03 | AMM-U-1180 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9934 | 35.8531 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R01 | Fiber ring
RO-03 | AMM-U-1181 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.993 | 35.8574 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R01 | Fiber ring
RO-03 | AMM-U-1182 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9934 | 35.8626 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R02 | Fiber ring
RO-03 | AMM-U-1183 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.993 | 35.8678 | 31 | 3 | HUB-AMM-27 | HUB-AMM-27-R02 | Fiber ring
RO-03 | AMM-U-1184 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.993 | 35.8715 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R02 | Fiber ring
RO-03 | AMM-U-1185 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.993 | 35.8763 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R01 | Fiber ring
RO-03 | AMM-U-1192 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.993 | 35.9103 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R01 | Fiber ring
RO-03 | AMM-U-1193 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.993 | 35.9131 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R02 | Fiber ring
RO-03 | AMM-U-1194 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.993 | 35.9188 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R02 | Fiber ring
RO-03 | AMM-U-1195 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9922 | 35.9235 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R02 | Fiber ring
RO-03 | AMM-U-1196 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9938 | 35.9283 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R03 | Fiber ring
RO-03 | AMM-U-1197 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9934 | 35.9325 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R03 | Fiber ring
RO-03 | AMM-U-1198 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.993 | 35.9377 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R01 | Fiber ring
RO-03 | AMM-U-1199 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.993 | 35.9415 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R01 | Fiber ring
RO-03 | AMM-U-1200 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9938 | 35.9472 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R01 | Fiber ring
RO-03 | AMM-U-1201 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.993 | 35.9509 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R01 | Fiber ring
RO-03 | AMM-U-1202 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9938 | 35.9566 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R03 | Fiber ring
RO-03 | AMM-U-1203 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9922 | 35.9613 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R03 | Fiber ring
RO-03 | AMM-U-1204 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9922 | 35.9661 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R04 | Fiber ring
RO-03 | AMM-U-1218 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9965 | 35.8219 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R01 | Fiber ring
RO-03 | AMM-U-1219 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9973 | 35.8267 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R01 | Fiber ring
RO-03 | AMM-U-1220 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9965 | 35.8304 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R01 | Fiber ring
RO-03 | AMM-U-1221 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9969 | 35.8356 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R02 | Fiber ring
RO-03 | AMM-U-1222 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9973 | 35.8408 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R03 | Fiber ring
RO-03 | AMM-U-1223 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9965 | 35.8456 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R03 | Fiber ring
RO-03 | AMM-U-1224 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9965 | 35.8503 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R01 | Fiber ring
RO-03 | AMM-U-1225 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9965 | 35.8541 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R01 | Fiber ring
RO-03 | AMM-U-1226 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9965 | 35.8588 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R02 | Fiber ring
RO-03 | AMM-U-1227 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9965 | 35.8635 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R02 | Fiber ring
RO-03 | AMM-U-1228 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9969 | 35.8687 | 31 | 3 | HUB-AMM-27 | HUB-AMM-27-R02 | Fiber ring
RO-03 | AMM-U-1229 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9965 | 35.8739 | 31 | 3 | HUB-AMM-11 | HUB-AMM-11-R01 | Fiber ring
RO-03 | AMM-U-1230 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9965 | 35.8786 | 33 | 3 | HUB-AMM-11 | HUB-AMM-11-R01 | Fiber ring
RO-03 | AMM-U-1231 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9961 | 35.8829 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R02 | Fiber ring
RO-03 | AMM-U-1232 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9973 | 35.8881 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R02 | Fiber ring
RO-03 | AMM-U-1236 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9969 | 35.9065 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R01 | Fiber ring
RO-03 | AMM-U-1237 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9965 | 35.9108 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R01 | Fiber ring
RO-03 | AMM-U-1238 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9973 | 35.9164 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R01 | Fiber ring
RO-03 | AMM-U-1239 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9965 | 35.9212 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R02 | Fiber ring
RO-03 | AMM-U-1240 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9969 | 35.9254 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R02 | Fiber ring
RO-03 | AMM-U-1241 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9973 | 35.9306 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R03 | Fiber ring
RO-03 | AMM-U-1242 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9973 | 35.9353 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R03 | Fiber ring
RO-03 | AMM-U-1243 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9973 | 35.9401 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R07 | Fiber ring
RO-03 | AMM-U-1244 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9973 | 35.9448 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R07 | Fiber ring
RO-03 | AMM-U-1245 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9965 | 35.9486 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R07 | Fiber ring
RO-03 | AMM-U-1246 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9957 | 35.9543 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R01 | Fiber ring
RO-03 | AMM-U-1247 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9965 | 35.959 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R04 | Fiber ring
RO-03 | AMM-U-1248 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9965 | 35.9628 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R04 | Fiber ring
RO-03 | AMM-U-1261 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9996 | 35.82 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R01 | Fiber ring
RO-03 | AMM-U-1262 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9996 | 35.8238 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R01 | Fiber ring
RO-03 | AMM-U-1263 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0009 | 35.829 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R05 | Fiber ring
RO-03 | AMM-U-1264 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0009 | 35.8337 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R01 | Fiber ring
RO-03 | AMM-U-1265 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0001 | 35.8385 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R03 | Fiber ring
RO-03 | AMM-U-1266 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0009 | 35.8432 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R03 | Fiber ring
RO-03 | AMM-U-1267 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0001 | 35.8489 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R05 | Fiber ring
RO-03 | AMM-U-1268 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0001 | 35.8536 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R05 | Fiber ring
RO-03 | AMM-U-1269 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9996 | 35.8569 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R01 | Fiber ring
RO-03 | AMM-U-1270 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0009 | 35.8621 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R03 | Fiber ring
RO-03 | AMM-U-1271 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0001 | 35.8678 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R03 | Fiber ring
RO-03 | AMM-U-1272 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0001 | 35.8706 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R03 | Fiber ring
RO-03 | AMM-U-1273 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0001 | 35.8772 | 33 | 3 | HUB-AMM-11 | HUB-AMM-11-R01 | Fiber ring
RO-03 | AMM-U-1274 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0001 | 35.8819 | 33 | 3 | HUB-AMM-11 | HUB-AMM-11-R02 | Fiber ring
RO-03 | AMM-U-1275 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0005 | 35.8862 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R02 | Fiber ring
RO-03 | AMM-U-1276 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9996 | 35.8905 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R02 | Fiber ring
RO-03 | AMM-U-1279 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9992 | 35.9046 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R01 | Fiber ring
RO-03 | AMM-U-1280 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9992 | 35.9094 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R01 | Fiber ring
RO-03 | AMM-U-1281 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0001 | 35.915 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R01 | Fiber ring
RO-03 | AMM-U-1282 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0005 | 35.9193 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R02 | Fiber ring
RO-03 | AMM-U-1283 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9992 | 35.9235 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R02 | Fiber ring
RO-03 | AMM-U-1284 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9992 | 35.9283 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R03 | Fiber ring
RO-03 | AMM-U-1285 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9996 | 35.9335 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R03 | Fiber ring
RO-03 | AMM-U-1286 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0005 | 35.9382 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R07 | Fiber ring
RO-03 | AMM-U-1287 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0001 | 35.9424 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R07 | Fiber ring
RO-03 | AMM-U-1288 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9992 | 35.9472 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R07 | Fiber ring
RO-03 | AMM-U-1289 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0009 | 35.9519 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R06 | Fiber ring
RO-03 | AMM-U-1290 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0001 | 35.9557 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R05 | Fiber ring
RO-03 | AMM-U-1291 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9996 | 35.9609 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R04 | Fiber ring
RO-03 | AMM-U-1292 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0001 | 35.9651 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R04 | Fiber ring
RO-03 | AMM-U-1308 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0028 | 35.8219 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R05 | Fiber ring
RO-03 | AMM-U-1309 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0036 | 35.8267 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R05 | Fiber ring
RO-03 | AMM-U-1310 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0036 | 35.8323 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R05 | Fiber ring
RO-03 | AMM-U-1311 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0036 | 35.8361 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R04 | Fiber ring
RO-03 | AMM-U-1312 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0044 | 35.8408 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R04 | Fiber ring
RO-03 | AMM-U-1313 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0036 | 35.8446 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R03 | Fiber ring
RO-03 | AMM-U-1314 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0044 | 35.8503 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R05 | Fiber ring
RO-03 | AMM-U-1315 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.004 | 35.8555 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R05 | Fiber ring
RO-03 | AMM-U-1316 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0036 | 35.8597 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R04 | Fiber ring
RO-03 | AMM-U-1317 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0036 | 35.8635 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R03 | Fiber ring
RO-03 | AMM-U-1318 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0036 | 35.8682 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R03 | Fiber ring
RO-03 | AMM-U-1319 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0036 | 35.873 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R01 | Fiber ring
RO-03 | AMM-U-1320 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0036 | 35.8796 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R01 | Fiber ring
RO-03 | AMM-U-1321 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0036 | 35.8843 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R02 | Fiber ring
RO-03 | AMM-U-1322 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0044 | 35.8881 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R03 | Fiber ring
RO-03 | AMM-U-1323 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.004 | 35.8923 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R03 | Fiber ring
RO-03 | AMM-U-1324 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0036 | 35.8966 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R03 | Fiber ring
RO-03 | AMM-U-1325 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0036 | 35.9023 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R02 | Fiber ring
RO-03 | AMM-U-1326 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0036 | 35.907 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R06 | Fiber ring
RO-03 | AMM-U-1327 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0036 | 35.9127 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R06 | Fiber ring
RO-03 | AMM-U-1328 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0028 | 35.9164 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R07 | Fiber ring
RO-03 | AMM-U-1329 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0028 | 35.9212 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R01 | Fiber ring
RO-03 | AMM-U-1330 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0036 | 35.925 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R04 | Fiber ring
RO-03 | AMM-U-1331 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0036 | 35.9297 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R04 | Fiber ring
RO-03 | AMM-U-1332 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0028 | 35.9353 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R03 | Fiber ring
RO-03 | AMM-U-1333 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0036 | 35.941 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R06 | Fiber ring
RO-03 | AMM-U-1334 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0044 | 35.9448 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R06 | Fiber ring
RO-03 | AMM-U-1335 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.004 | 35.949 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R06 | Fiber ring
RO-03 | AMM-U-1336 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0036 | 35.9533 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R05 | Fiber ring
RO-03 | AMM-U-1337 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0028 | 35.959 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R04 | Fiber ring
RO-03 | AMM-U-1338 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0036 | 35.9628 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R04 | Fiber ring
RO-03 | AMM-U-1357 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0071 | 35.8252 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R05 | Fiber ring
RO-03 | AMM-U-1358 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0079 | 35.829 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R05 | Fiber ring
RO-03 | AMM-U-1359 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0079 | 35.8337 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R04 | Fiber ring
RO-03 | AMM-U-1360 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0063 | 35.8385 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R04 | Fiber ring
RO-03 | AMM-U-1361 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0063 | 35.8432 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R04 | Fiber ring
RO-03 | AMM-U-1362 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0071 | 35.8479 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R05 | Fiber ring
RO-03 | AMM-U-1363 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0079 | 35.8526 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R05 | Fiber ring
RO-03 | AMM-U-1364 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0071 | 35.8574 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R04 | Fiber ring
RO-03 | AMM-U-1365 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0071 | 35.8612 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R04 | Fiber ring
RO-03 | AMM-U-1366 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0071 | 35.8668 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R03 | Fiber ring
RO-03 | AMM-U-1367 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0071 | 35.8706 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R06 | Fiber ring
RO-03 | AMM-U-1368 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0071 | 35.8753 | 33 | 3 | HUB-AMM-11 | HUB-AMM-11-R06 | Fiber ring
RO-03 | AMM-U-1369 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0071 | 35.8819 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R01 | Fiber ring
RO-03 | AMM-U-1370 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0067 | 35.8862 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R03 | Fiber ring
RO-03 | AMM-U-1371 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0071 | 35.8895 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R03 | Fiber ring
RO-03 | AMM-U-1372 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0071 | 35.8942 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R03 | Fiber ring
RO-03 | AMM-U-1373 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0079 | 35.8999 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R02 | Fiber ring
RO-03 | AMM-U-1374 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0079 | 35.9046 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R02 | Fiber ring
RO-03 | AMM-U-1375 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0079 | 35.9094 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R06 | Fiber ring
RO-03 | AMM-U-1376 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0063 | 35.9141 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R06 | Fiber ring
RO-03 | AMM-U-1377 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0067 | 35.9193 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R06 | Fiber ring
RO-03 | AMM-U-1378 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0071 | 35.9235 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R05 | Fiber ring
RO-03 | AMM-U-1379 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0071 | 35.9292 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R04 | Fiber ring
RO-03 | AMM-U-1380 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0071 | 35.932 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R04 | Fiber ring
RO-03 | AMM-U-1381 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0075 | 35.9372 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R04 | Fiber ring
RO-03 | AMM-U-1382 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0063 | 35.9424 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R06 | Fiber ring
RO-03 | AMM-U-1383 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0063 | 35.9472 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R06 | Fiber ring
RO-03 | AMM-U-1384 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0071 | 35.9509 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R05 | Fiber ring
RO-03 | AMM-U-1385 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0071 | 35.9566 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R05 | Fiber ring
RO-03 | AMM-U-1386 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0071 | 35.9613 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R05 | Fiber ring
RO-03 | AMM-U-1406 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0114 | 35.8314 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R05 | Fiber ring
RO-03 | AMM-U-1407 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0106 | 35.837 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R04 | Fiber ring
RO-03 | AMM-U-1408 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0106 | 35.8418 | 30 | 3 | HUB-AMM-04 | HUB-AMM-04-R04 | Fiber ring
RO-03 | AMM-U-1409 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0106 | 35.8465 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R02 | Fiber ring
RO-03 | AMM-U-1410 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0102 | 35.8507 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R05 | Fiber ring
RO-03 | AMM-U-1411 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0106 | 35.855 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R04 | Fiber ring
RO-03 | AMM-U-1412 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0106 | 35.8588 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R04 | Fiber ring
RO-03 | AMM-U-1413 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0106 | 35.8635 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R04 | Fiber ring
RO-03 | AMM-U-1414 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.011 | 35.8687 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R06 | Fiber ring
RO-03 | AMM-U-1415 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0106 | 35.8749 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R06 | Fiber ring
RO-03 | AMM-U-1416 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0102 | 35.8791 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R05 | Fiber ring
RO-03 | AMM-U-1417 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0106 | 35.8824 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R05 | Fiber ring
RO-03 | AMM-U-1418 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0114 | 35.8881 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R04 | Fiber ring
RO-03 | AMM-U-1419 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0106 | 35.8919 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R04 | Fiber ring
RO-03 | AMM-U-1420 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.011 | 35.8971 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R01 | Fiber ring
RO-03 | AMM-U-1421 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0106 | 35.9013 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R02 | Fiber ring
RO-03 | AMM-U-1422 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0114 | 35.907 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R02 | Fiber ring
RO-03 | AMM-U-1423 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0106 | 35.9174 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R06 | Fiber ring
RO-03 | AMM-U-1424 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0106 | 35.9221 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R05 | Fiber ring
RO-03 | AMM-U-1425 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0106 | 35.925 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R05 | Fiber ring
RO-03 | AMM-U-1426 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0106 | 35.9297 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R05 | Fiber ring
RO-03 | AMM-U-1427 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0098 | 35.9353 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R04 | Fiber ring
RO-03 | AMM-U-1428 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0106 | 35.9391 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R04 | Fiber ring
RO-03 | AMM-U-1429 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0114 | 35.9448 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R06 | Fiber ring
RO-03 | AMM-U-1430 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0098 | 35.9495 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R05 | Fiber ring
RO-03 | AMM-U-1431 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0098 | 35.9543 | 30 | 3 | HUB-AMM-56 | HUB-AMM-56-R05 | Fiber ring
RO-03 | AMM-U-1453 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0142 | 35.8375 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R01 | Fiber ring
RO-03 | AMM-U-1454 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0142 | 35.8422 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R01 | Fiber ring
RO-03 | AMM-U-1455 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0133 | 35.8479 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R02 | Fiber ring
RO-03 | AMM-U-1456 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0133 | 35.8526 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R02 | Fiber ring
RO-03 | AMM-U-1457 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0133 | 35.8574 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R02 | Fiber ring
RO-03 | AMM-U-1458 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0133 | 35.8621 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R04 | Fiber ring
RO-03 | AMM-U-1459 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0133 | 35.8668 | 30 | 3 | HUB-AMM-27 | HUB-AMM-27-R03 | Fiber ring
RO-03 | AMM-U-1460 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0142 | 35.8725 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R06 | Fiber ring
RO-03 | AMM-U-1461 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.015 | 35.8763 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R05 | Fiber ring
RO-03 | AMM-U-1462 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0137 | 35.8815 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R05 | Fiber ring
RO-03 | AMM-U-1463 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0145 | 35.8862 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R04 | Fiber ring
RO-03 | AMM-U-1464 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0142 | 35.8895 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R04 | Fiber ring
RO-03 | AMM-U-1465 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0142 | 35.8952 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R01 | Fiber ring
RO-03 | AMM-U-1466 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0133 | 35.8999 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R01 | Fiber ring
RO-03 | AMM-U-1467 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0133 | 35.9046 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R02 | Fiber ring
RO-03 | AMM-U-1468 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0133 | 35.9094 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R02 | Fiber ring
RO-03 | AMM-U-1469 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0133 | 35.9141 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R03 | Fiber ring
RO-03 | AMM-U-1470 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0133 | 35.9188 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R06 | Fiber ring
RO-03 | AMM-U-1471 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0133 | 35.9235 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R05 | Fiber ring
RO-03 | AMM-U-1472 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0133 | 35.9283 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R05 | Fiber ring
RO-03 | AMM-U-1473 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0142 | 35.932 | 30 | 3 | HUB-AMM-44 | HUB-AMM-44-R05 | Fiber ring
RO-03 | AMM-U-1498 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0177 | 35.837 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R01 | Fiber ring
RO-03 | AMM-U-1499 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0177 | 35.8399 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R01 | Fiber ring
RO-03 | AMM-U-1500 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0177 | 35.8456 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R01 | Fiber ring
RO-03 | AMM-U-1501 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0181 | 35.8498 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R02 | Fiber ring
RO-03 | AMM-U-1502 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0185 | 35.855 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R02 | Fiber ring
RO-03 | AMM-U-1503 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0177 | 35.8588 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R03 | Fiber ring
RO-03 | AMM-U-1504 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0173 | 35.864 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R03 | Fiber ring
RO-03 | AMM-U-1505 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0181 | 35.8687 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R06 | Fiber ring
RO-03 | AMM-U-1506 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0177 | 35.8749 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R05 | Fiber ring
RO-03 | AMM-U-1507 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0185 | 35.8786 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R05 | Fiber ring
RO-03 | AMM-U-1508 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0177 | 35.8843 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R04 | Fiber ring
RO-03 | AMM-U-1509 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0169 | 35.8881 | 30 | 3 | HUB-AMM-11 | HUB-AMM-11-R04 | Fiber ring
RO-03 | AMM-U-1510 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0173 | 35.8923 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R01 | Fiber ring
RO-03 | AMM-U-1511 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0177 | 35.8966 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R01 | Fiber ring
RO-03 | AMM-U-1512 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0185 | 35.9023 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R01 | Fiber ring
RO-03 | AMM-U-1513 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0185 | 35.907 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R03 | Fiber ring
RO-03 | AMM-U-1514 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0177 | 35.9108 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R03 | Fiber ring
RO-03 | AMM-U-1515 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0169 | 35.9164 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R03 | Fiber ring
RO-03 | AMM-U-1516 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0177 | 35.9202 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R03 | Fiber ring
RO-03 | AMM-U-1541 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0208 | 35.838 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R01 | Fiber ring
RO-03 | AMM-U-1542 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0212 | 35.8422 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R01 | Fiber ring
RO-03 | AMM-U-1543 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0212 | 35.8489 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R02 | Fiber ring
RO-03 | AMM-U-1544 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0212 | 35.8536 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R03 | Fiber ring
RO-03 | AMM-U-1545 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0212 | 35.8564 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R03 | Fiber ring
RO-03 | AMM-U-1546 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0212 | 35.863 | 31 | 3 | HUB-AMM-79 | HUB-AMM-79-R03 | Fiber ring
RO-03 | AMM-U-1547 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.022 | 35.8668 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R03 | Fiber ring
RO-03 | AMM-U-1548 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0212 | 35.8706 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R01 | Fiber ring
RO-03 | AMM-U-1549 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.022 | 35.8763 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R02 | Fiber ring
RO-03 | AMM-U-1550 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0212 | 35.88 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R02 | Fiber ring
RO-03 | AMM-U-1551 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0216 | 35.8852 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R02 | Fiber ring
RO-03 | AMM-U-1552 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0204 | 35.8905 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R01 | Fiber ring
RO-03 | AMM-U-1553 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0212 | 35.8942 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R06 | Fiber ring
RO-03 | AMM-U-1554 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0212 | 35.8999 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R06 | Fiber ring
RO-03 | AMM-U-1555 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0212 | 35.9037 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R01 | Fiber ring
RO-03 | AMM-U-1556 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0208 | 35.9089 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R03 | Fiber ring
RO-03 | AMM-U-1557 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.022 | 35.9141 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R04 | Fiber ring
RO-03 | AMM-U-1558 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0212 | 35.9179 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R03 | Fiber ring
RO-03 | AMM-U-1583 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0247 | 35.8361 | 31 | 3 | HUB-AMM-79 | HUB-AMM-79-R06 | Fiber ring
RO-03 | AMM-U-1584 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0247 | 35.8399 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R06 | Fiber ring
RO-03 | AMM-U-1585 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0247 | 35.8465 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R06 | Fiber ring
RO-03 | AMM-U-1586 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0247 | 35.8503 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R01 | Fiber ring
RO-03 | AMM-U-1587 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0255 | 35.855 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R04 | Fiber ring
RO-03 | AMM-U-1588 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0247 | 35.8607 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R03 | Fiber ring
RO-03 | AMM-U-1589 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0255 | 35.8645 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R04 | Fiber ring
RO-03 | AMM-U-1590 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0247 | 35.8682 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R01 | Fiber ring
RO-03 | AMM-U-1591 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0247 | 35.8749 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R02 | Fiber ring
RO-03 | AMM-U-1592 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0247 | 35.8786 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R02 | Fiber ring
RO-03 | AMM-U-1593 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0255 | 35.8834 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R02 | Fiber ring
RO-03 | AMM-U-1594 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0255 | 35.8881 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R03 | Fiber ring
RO-03 | AMM-U-1595 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0247 | 35.8938 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R06 | Fiber ring
RO-03 | AMM-U-1596 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0243 | 35.898 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R06 | Fiber ring
RO-03 | AMM-U-1597 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0243 | 35.9018 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R05 | Fiber ring
RO-03 | AMM-U-1598 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0247 | 35.9061 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R04 | Fiber ring
RO-03 | AMM-U-1599 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0247 | 35.9117 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R04 | Fiber ring
RO-03 | AMM-U-1600 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0243 | 35.916 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R04 | Fiber ring
RO-03 | AMM-U-1623 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0274 | 35.8337 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R06 | Fiber ring
RO-03 | AMM-U-1624 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0274 | 35.8385 | 31 | 3 | HUB-AMM-79 | HUB-AMM-79-R06 | Fiber ring
RO-03 | AMM-U-1625 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0282 | 35.8441 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R05 | Fiber ring
RO-03 | AMM-U-1626 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0282 | 35.8489 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R05 | Fiber ring
RO-03 | AMM-U-1627 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0291 | 35.8526 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R04 | Fiber ring
RO-03 | AMM-U-1628 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0278 | 35.8569 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R04 | Fiber ring
RO-03 | AMM-U-1629 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0282 | 35.8621 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R04 | Fiber ring
RO-03 | AMM-U-1630 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0282 | 35.8659 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R01 | Fiber ring
RO-03 | AMM-U-1631 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0282 | 35.8715 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R01 | Fiber ring
RO-03 | AMM-U-1632 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0282 | 35.8772 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R01 | Fiber ring
RO-03 | AMM-U-1633 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0274 | 35.881 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R02 | Fiber ring
RO-03 | AMM-U-1634 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0274 | 35.8857 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R03 | Fiber ring
RO-03 | AMM-U-1635 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0282 | 35.8895 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R03 | Fiber ring
RO-03 | AMM-U-1636 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0274 | 35.8952 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R05 | Fiber ring
RO-03 | AMM-U-1637 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0282 | 35.899 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R05 | Fiber ring
RO-03 | AMM-U-1638 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0291 | 35.9046 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R05 | Fiber ring
RO-03 | AMM-U-1639 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0291 | 35.9094 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R04 | Fiber ring
RO-03 | AMM-U-1640 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0286 | 35.9136 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R04 | Fiber ring
RO-03 | AMM-U-1667 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0309 | 35.8361 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R05 | Fiber ring
RO-03 | AMM-U-1668 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0318 | 35.8418 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R05 | Fiber ring
RO-03 | AMM-U-1669 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0318 | 35.8465 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R05 | Fiber ring
RO-03 | AMM-U-1670 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0309 | 35.8503 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R04 | Fiber ring
RO-03 | AMM-U-1671 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0309 | 35.855 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R04 | Fiber ring
RO-03 | AMM-U-1674 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0309 | 35.8692 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R01 | Fiber ring
RO-03 | AMM-U-1675 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0318 | 35.8739 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R06 | Fiber ring
RO-03 | AMM-U-1676 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0309 | 35.8786 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R01 | Fiber ring
RO-03 | AMM-U-1677 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0318 | 35.8824 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R01 | Fiber ring
RO-03 | AMM-U-1678 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0318 | 35.8871 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R03 | Fiber ring
RO-03 | AMM-U-1679 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0318 | 35.8919 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R03 | Fiber ring
RO-03 | AMM-U-1680 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0314 | 35.898 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R05 | Fiber ring
RO-03 | AMM-U-1681 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0309 | 35.9023 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R05 | Fiber ring
RO-03 | AMM-U-1682 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0309 | 35.907 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R05 | Fiber ring
RO-03 | AMM-U-1683 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0309 | 35.9117 | 30 | 3 | HUB-AMM-05 | HUB-AMM-05-R04 | Fiber ring
RO-03 | AMM-U-1710 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0353 | 35.8441 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R05 | Fiber ring
RO-03 | AMM-U-1711 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0345 | 35.8479 | 30 | 3 | HUB-AMM-79 | HUB-AMM-79-R05 | Fiber ring
RO-03 | AMM-U-1716 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0353 | 35.8706 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R06 | Fiber ring
RO-03 | AMM-U-1717 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0345 | 35.8763 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R05 | Fiber ring
RO-03 | AMM-U-1718 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0345 | 35.881 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R05 | Fiber ring
RO-03 | AMM-U-1719 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0353 | 35.8848 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R04 | Fiber ring
RO-03 | AMM-U-1720 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0357 | 35.89 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R03 | Fiber ring
RO-03 | AMM-U-1721 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0353 | 35.8942 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R03 | Fiber ring
RO-03 | AMM-U-1757 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0388 | 35.873 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R05 | Fiber ring
RO-03 | AMM-U-1758 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0396 | 35.8786 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R05 | Fiber ring
RO-03 | AMM-U-1759 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.038 | 35.8834 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R04 | Fiber ring
RO-03 | AMM-U-1760 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.038 | 35.8881 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R04 | Fiber ring
RO-03 | AMM-U-1761 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.038 | 35.8928 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R04 | Fiber ring
RO-03 | AMM-U-1795 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0423 | 35.8753 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R05 | Fiber ring
RO-03 | AMM-U-1796 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0432 | 35.881 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R05 | Fiber ring
RO-03 | AMM-U-1797 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0427 | 35.8862 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R04 | Fiber ring
RO-03 | AMM-U-1798 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0423 | 35.8895 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R04 | Fiber ring
RO-03 | AMM-U-1823 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0459 | 35.8777 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R05 | Fiber ring
RO-03 | AMM-U-1824 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0463 | 35.8829 | 30 | 3 | HUB-AMM-49 | HUB-AMM-49-R04 | Fiber ring
RO-03 | AQB-SU-0202 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5138 | 35.0429 | 32 | 3 | HUB-AQB-05 | HUB-AQB-05-R04 | Fiber ring
RO-03 | AQB-SU-0203 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5302 | 35.0477 | 32 | 3 | HUB-AQB-05 | HUB-AQB-05-R04 | Fiber ring
RO-03 | AQB-SU-0204 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5353 | 35.0443 | 32 | 3 | HUB-AQB-05 | HUB-AQB-05-R04 | Fiber ring
RO-03 | AQB-SU-0205 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5506 | 35.0477 | 32 | 3 | HUB-AQB-05 | HUB-AQB-05-R05 | Fiber ring
RO-03 | AQB-SU-0209 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5709 | 34.9931 | 32 | 3 | HUB-AQB-06 | HUB-AQB-06-R06 | Fiber ring
RO-03 | AQB-SU-0210 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.576 | 34.9952 | 32 | 3 | HUB-AQB-06 | HUB-AQB-06-R06 | Fiber ring
RO-03 | AQB-SU-0238 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.6117 | 35.019 | 32 | 3 | HUB-AQB-07 | HUB-AQB-07-R01 | Fiber ring
RO-03 | AQB-SU-0239 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.6117 | 35.0259 | 32 | 3 | HUB-AQB-07 | HUB-AQB-07-R01 | Fiber ring
RO-03 | AQB-SU-0240 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.6167 | 35.0156 | 32 | 3 | HUB-AQB-07 | HUB-AQB-07-R01 | Fiber ring
RO-03 | AQB-SU-0241 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.6167 | 35.0224 | 32 | 3 | HUB-AQB-07 | HUB-AQB-07-R01 | Fiber ring
RO-03 | AQB-SU-0242 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.6167 | 35.0375 | 32 | 3 | HUB-AQB-07 | HUB-AQB-07-R01 | Fiber ring
RO-03 | AQB-SU-0243 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.6218 | 35.019 | 32 | 3 | HUB-AQB-07 | HUB-AQB-07-R02 | Fiber ring
RO-03 | AQB-SU-0244 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.6218 | 35.0272 | 32 | 3 | HUB-AQB-07 | HUB-AQB-07-R01 | Fiber ring
RO-03 | AQB-SU-0245 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.6218 | 35.0327 | 32 | 3 | HUB-AQB-07 | HUB-AQB-07-R01 | Fiber ring
RO-03 | AQB-SU-0246 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.6218 | 35.0409 | 32 | 3 | HUB-AQB-07 | HUB-AQB-07-R01 | Fiber ring
RO-03 | AQB-SU-0247 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.6269 | 35.0156 | 32 | 3 | HUB-AQB-07 | HUB-AQB-07-R02 | Fiber ring
RO-03 | AQB-SU-0248 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.6269 | 35.0224 | 32 | 3 | HUB-AQB-07 | HUB-AQB-07-R02 | Fiber ring
RO-03 | AQB-SU-0249 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.6269 | 35.0293 | 32 | 3 | HUB-AQB-07 | HUB-AQB-07-R02 | Fiber ring
RO-03 | AQB-SU-0250 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.632 | 35.019 | 32 | 3 | HUB-AQB-07 | HUB-AQB-07-R02 | Fiber ring
RO-03 | AQB-SU-0251 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.6371 | 35.0224 | 32 | 3 | HUB-AQB-07 | HUB-AQB-07-R02 | Fiber ring
RO-03 | AQB-U-0001 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5039 | 35.0067 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R02 | Fiber ring
RO-03 | AQB-U-0002 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5153 | 35.0147 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R02 | Fiber ring
RO-03 | AQB-U-0003 | U | Monopole / greenfield | Aqaba | Aqaba | 29.518 | 35.0114 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R02 | Fiber ring
RO-03 | AQB-U-0004 | U | Monopole / greenfield | Aqaba | Aqaba | 29.518 | 35.0162 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R02 | Fiber ring
RO-03 | AQB-U-0005 | U | Rooftop | Aqaba | Aqaba | 29.522 | 35.0143 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R02 | Fiber ring
RO-03 | AQB-U-0006 | U | Rooftop | Aqaba | Aqaba | 29.522 | 35.019 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R03 | Fiber ring
RO-03 | AQB-U-0007 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5232 | 35.0232 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R03 | Fiber ring
RO-03 | AQB-U-0008 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5232 | 35.028 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R03 | Fiber ring
RO-03 | AQB-U-0009 | U | Rooftop | Aqaba | Aqaba | 29.5255 | 35.0119 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R01 | Fiber ring
RO-03 | AQB-U-0010 | U | Rooftop | Aqaba | Aqaba | 29.5255 | 35.0166 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R02 | Fiber ring
RO-03 | AQB-U-0011 | U | Rooftop | Aqaba | Aqaba | 29.5259 | 35.0218 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R03 | Fiber ring
RO-03 | AQB-U-0012 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5259 | 35.0266 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R03 | Fiber ring
RO-03 | AQB-U-0013 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5263 | 35.0308 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R03 | Fiber ring
RO-03 | AQB-U-0014 | U | Rooftop | Aqaba | Aqaba | 29.529 | 35.0095 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R01 | Fiber ring
RO-03 | AQB-U-0015 | U | Rooftop | Aqaba | Aqaba | 29.5286 | 35.0138 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R01 | Fiber ring
RO-03 | AQB-U-0016 | U | Rooftop | Aqaba | Aqaba | 29.529 | 35.019 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R01 | Fiber ring
RO-03 | AQB-U-0017 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5294 | 35.0242 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R03 | Fiber ring
RO-03 | AQB-U-0018 | U | Rooftop | Aqaba | Aqaba | 29.5329 | 35.0067 | 31 | 3 | HUB-AQB-05 | HUB-AQB-05-R01 | Fiber ring
RO-03 | AQB-U-0019 | U | Rooftop | Aqaba | Aqaba | 29.5329 | 35.0124 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R01 | Fiber ring
RO-03 | AQB-U-0020 | U | Rooftop | Aqaba | Aqaba | 29.5329 | 35.0171 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R01 | Fiber ring
RO-03 | AQB-U-0021 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5329 | 35.0218 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R02 | Fiber ring
RO-03 | AQB-U-0022 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5329 | 35.0266 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R04 | Fiber ring
RO-03 | AQB-U-0023 | U | Rooftop | Aqaba | Aqaba | 29.5365 | 34.9996 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R02 | Fiber ring
RO-03 | AQB-U-0024 | U | Rooftop | Aqaba | Aqaba | 29.5365 | 35.0043 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R03 | Fiber ring
RO-03 | AQB-U-0025 | U | Rooftop | Aqaba | Aqaba | 29.5369 | 35.0095 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R08 | Fiber ring
RO-03 | AQB-U-0026 | U | Rooftop | Aqaba | Aqaba | 29.5365 | 35.0147 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R08 | Fiber ring
RO-03 | AQB-U-0027 | U | Rooftop | Aqaba | Aqaba | 29.5365 | 35.0185 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R08 | Fiber ring
RO-03 | AQB-U-0028 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5365 | 35.0242 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R01 | Fiber ring
RO-03 | AQB-U-0029 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5357 | 35.0374 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R04 | Fiber ring
RO-03 | AQB-U-0030 | U | Rooftop | Aqaba | Aqaba | 29.54 | 34.9925 | 31 | 3 | HUB-AQB-06 | HUB-AQB-06-R02 | Fiber ring
RO-03 | AQB-U-0031 | U | Rooftop | Aqaba | Aqaba | 29.54 | 34.9973 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R02 | Fiber ring
RO-03 | AQB-U-0032 | U | Rooftop | Aqaba | Aqaba | 29.54 | 35.002 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R03 | Fiber ring
RO-03 | AQB-U-0033 | U | Rooftop | Aqaba | Aqaba | 29.54 | 35.0067 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R03 | Fiber ring
RO-03 | AQB-U-0034 | U | Rooftop | Aqaba | Aqaba | 29.54 | 35.0114 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R08 | Fiber ring
RO-03 | AQB-U-0035 | U | Rooftop | Aqaba | Aqaba | 29.54 | 35.0171 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R08 | Fiber ring
RO-03 | AQB-U-0036 | U | Rooftop | Aqaba | Aqaba | 29.54 | 35.0218 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R07 | Fiber ring
RO-03 | AQB-U-0037 | U | Monopole / greenfield | Aqaba | Aqaba | 29.54 | 35.0266 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R06 | Fiber ring
RO-03 | AQB-U-0038 | U | Monopole / greenfield | Aqaba | Aqaba | 29.54 | 35.0313 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R05 | Fiber ring
RO-03 | AQB-U-0039 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5396 | 35.0346 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R04 | Fiber ring
RO-03 | AQB-U-0040 | U | Monopole / greenfield | Aqaba | Aqaba | 29.54 | 35.0407 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R04 | Fiber ring
RO-03 | AQB-U-0041 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5435 | 34.9854 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R01 | Fiber ring
RO-03 | AQB-U-0042 | U | Rooftop | Aqaba | Aqaba | 29.5435 | 34.9902 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R01 | Fiber ring
RO-03 | AQB-U-0043 | U | Rooftop | Aqaba | Aqaba | 29.5435 | 34.9949 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R02 | Fiber ring
RO-03 | AQB-U-0044 | U | Rooftop | Aqaba | Aqaba | 29.5435 | 34.9996 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R02 | Fiber ring
RO-03 | AQB-U-0045 | U | Rooftop | Aqaba | Aqaba | 29.5435 | 35.0043 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R03 | Fiber ring
RO-03 | AQB-U-0046 | U | Rooftop | Aqaba | Aqaba | 29.5435 | 35.0091 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R03 | Fiber ring
RO-03 | AQB-U-0047 | U | Rooftop | Aqaba | Aqaba | 29.5435 | 35.0147 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R08 | Fiber ring
RO-03 | AQB-U-0048 | U | Rooftop | Aqaba | Aqaba | 29.5435 | 35.0195 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R08 | Fiber ring
RO-03 | AQB-U-0049 | U | Rooftop | Aqaba | Aqaba | 29.5435 | 35.0242 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R07 | Fiber ring
RO-03 | AQB-U-0050 | U | Rooftop | Aqaba | Aqaba | 29.5435 | 35.0289 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R06 | Fiber ring
RO-03 | AQB-U-0051 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5435 | 35.0336 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R05 | Fiber ring
RO-03 | AQB-U-0052 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5435 | 35.0384 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R05 | Fiber ring
RO-03 | AQB-U-0053 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5427 | 35.0421 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R05 | Fiber ring
RO-03 | AQB-U-0054 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5474 | 34.9835 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R01 | Fiber ring
RO-03 | AQB-U-0055 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5479 | 34.9878 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R01 | Fiber ring
RO-03 | AQB-U-0056 | U | Monopole / greenfield | Aqaba | Aqaba | 29.547 | 34.9935 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R02 | Fiber ring
RO-03 | AQB-U-0057 | U | Rooftop | Aqaba | Aqaba | 29.547 | 34.9973 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R02 | Fiber ring
RO-03 | AQB-U-0058 | U | Rooftop | Aqaba | Aqaba | 29.547 | 35.002 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R03 | Fiber ring
RO-03 | AQB-U-0059 | U | Rooftop | Aqaba | Aqaba | 29.547 | 35.0067 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R04 | Fiber ring
RO-03 | AQB-U-0060 | U | Rooftop | Aqaba | Aqaba | 29.547 | 35.0114 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R04 | Fiber ring
RO-03 | AQB-U-0061 | U | Rooftop | Aqaba | Aqaba | 29.547 | 35.0171 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R07 | Fiber ring
RO-03 | AQB-U-0062 | U | Rooftop | Aqaba | Aqaba | 29.5474 | 35.0213 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R07 | Fiber ring
RO-03 | AQB-U-0063 | U | Rooftop | Aqaba | Aqaba | 29.547 | 35.0266 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R07 | Fiber ring
RO-03 | AQB-U-0064 | U | Monopole / greenfield | Aqaba | Aqaba | 29.547 | 35.0313 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R06 | Fiber ring
RO-03 | AQB-U-0065 | U | Rooftop | Aqaba | Aqaba | 29.547 | 35.036 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R06 | Fiber ring
RO-03 | AQB-U-0066 | U | Rooftop | Aqaba | Aqaba | 29.547 | 35.0407 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R05 | Fiber ring
RO-03 | AQB-U-0067 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5506 | 34.9854 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R01 | Fiber ring
RO-03 | AQB-U-0068 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5506 | 34.9911 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R01 | Fiber ring
RO-03 | AQB-U-0069 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5506 | 34.9949 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R01 | Fiber ring
RO-03 | AQB-U-0070 | U | Rooftop | Aqaba | Aqaba | 29.5506 | 34.9996 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R03 | Fiber ring
RO-03 | AQB-U-0071 | U | Rooftop | Aqaba | Aqaba | 29.5506 | 35.0043 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R04 | Fiber ring
RO-03 | AQB-U-0072 | U | Rooftop | Aqaba | Aqaba | 29.5506 | 35.0091 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R04 | Fiber ring
RO-03 | AQB-U-0073 | U | Rooftop | Aqaba | Aqaba | 29.5506 | 35.0138 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R04 | Fiber ring
RO-03 | AQB-U-0074 | U | Rooftop | Aqaba | Aqaba | 29.5506 | 35.0185 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R07 | Fiber ring
RO-03 | AQB-U-0075 | U | Rooftop | Aqaba | Aqaba | 29.5506 | 35.0232 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R07 | Fiber ring
RO-03 | AQB-U-0076 | U | Rooftop | Aqaba | Aqaba | 29.5506 | 35.028 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R06 | Fiber ring
RO-03 | AQB-U-0077 | U | Rooftop | Aqaba | Aqaba | 29.5506 | 35.0336 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R06 | Fiber ring
RO-03 | AQB-U-0078 | U | Rooftop | Aqaba | Aqaba | 29.5497 | 35.0374 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R06 | Fiber ring
RO-03 | AQB-U-0079 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5506 | 35.0431 | 30 | 3 | HUB-AQB-05 | HUB-AQB-05-R05 | Fiber ring
RO-03 | AQB-U-0080 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5541 | 34.9831 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R08 | Fiber ring
RO-03 | AQB-U-0081 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5541 | 34.9878 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R08 | Fiber ring
RO-03 | AQB-U-0082 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5549 | 34.9925 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R07 | Fiber ring
RO-03 | AQB-U-0083 | U | Rooftop | Aqaba | Aqaba | 29.5541 | 34.9973 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R01 | Fiber ring
RO-03 | AQB-U-0084 | U | Rooftop | Aqaba | Aqaba | 29.5541 | 35.002 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R04 | Fiber ring
RO-03 | AQB-U-0085 | U | Rooftop | Aqaba | Aqaba | 29.5541 | 35.0067 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R04 | Fiber ring
RO-03 | AQB-U-0086 | U | Rooftop | Aqaba | Aqaba | 29.5541 | 35.0114 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R05 | Fiber ring
RO-03 | AQB-U-0093 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5576 | 34.9854 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R07 | Fiber ring
RO-03 | AQB-U-0094 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5576 | 34.9902 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R07 | Fiber ring
RO-03 | AQB-U-0095 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5576 | 34.9939 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R07 | Fiber ring
RO-03 | AQB-U-0096 | U | Rooftop | Aqaba | Aqaba | 29.5576 | 34.9996 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R05 | Fiber ring
RO-03 | AQB-U-0097 | U | Rooftop | Aqaba | Aqaba | 29.5576 | 35.0043 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R05 | Fiber ring
RO-03 | AQB-U-0098 | U | Rooftop | Aqaba | Aqaba | 29.5576 | 35.01 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R05 | Fiber ring
RO-03 | AQB-U-0105 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5611 | 34.9878 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R07 | Fiber ring
RO-03 | AQB-U-0106 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5611 | 34.9925 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R07 | Fiber ring
RO-03 | AQB-U-0107 | U | Rooftop | Aqaba | Aqaba | 29.5611 | 34.9982 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R06 | Fiber ring
RO-03 | AQB-U-0108 | U | Rooftop | Aqaba | Aqaba | 29.5611 | 35.002 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R05 | Fiber ring
RO-03 | AQB-U-0109 | U | Rooftop | Aqaba | Aqaba | 29.5611 | 35.0067 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R05 | Fiber ring
RO-03 | AQB-U-0116 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5647 | 34.9902 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R07 | Fiber ring
RO-03 | AQB-U-0117 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5647 | 34.9949 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R06 | Fiber ring
RO-03 | AQB-U-0118 | U | Rooftop | Aqaba | Aqaba | 29.5647 | 35.0006 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R06 | Fiber ring
RO-03 | AQB-U-0119 | U | Rooftop | Aqaba | Aqaba | 29.5647 | 35.0043 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R05 | Fiber ring
RO-03 | AQB-U-0127 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5682 | 34.9973 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R06 | Fiber ring
RO-03 | AQB-U-0128 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5682 | 35.002 | 30 | 3 | HUB-AQB-06 | HUB-AQB-06-R06 | Fiber ring
RO-03 | IRB-DU-0001 | DU | Rooftop | Irbid | Irbid | 32.5452 | 35.8416 | 25 | 3 | HUB-IRB-05 | HUB-IRB-05-R04 | Fiber ring
RO-03 | IRB-DU-0002 | DU | Rooftop | Irbid | Irbid | 32.5452 | 35.8456 | 25 | 3 | HUB-IRB-05 | HUB-IRB-05-R04 | Fiber ring
RO-03 | IRB-DU-0006 | DU | Rooftop | Irbid | Irbid | 32.5474 | 35.8357 | 25 | 3 | HUB-IRB-05 | HUB-IRB-05-R04 | Fiber ring
RO-03 | IRB-DU-0007 | DU | Rooftop | Irbid | Irbid | 32.5474 | 35.8396 | 25 | 3 | HUB-IRB-05 | HUB-IRB-05-R04 | Fiber ring
RO-03 | IRB-DU-0008 | DU | Rooftop | Irbid | Irbid | 32.5481 | 35.8436 | 25 | 3 | HUB-IRB-05 | HUB-IRB-05-R04 | Fiber ring
RO-03 | IRB-DU-0014 | DU | Rooftop | Irbid | Irbid | 32.5517 | 35.8337 | 25 | 3 | HUB-IRB-05 | HUB-IRB-05-R04 | Fiber ring
RO-03 | IRB-DU-0015 | DU | Rooftop | Irbid | Irbid | 32.551 | 35.8377 | 25 | 3 | HUB-IRB-05 | HUB-IRB-05-R04 | Fiber ring
RO-03 | IRB-U-0188 | U | Monopole / greenfield | Irbid | Irbid | 32.5358 | 35.8205 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R01 | Fiber ring
RO-03 | IRB-U-0189 | U | Monopole / greenfield | Irbid | Irbid | 32.5354 | 35.8248 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R02 | Fiber ring
RO-03 | IRB-U-0190 | U | Monopole / greenfield | Irbid | Irbid | 32.5358 | 35.8281 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R02 | Fiber ring
RO-03 | IRB-U-0191 | U | Rooftop | Irbid | Irbid | 32.5358 | 35.8337 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R02 | Fiber ring
RO-03 | IRB-U-0192 | U | Rooftop | Irbid | Irbid | 32.535 | 35.8385 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R02 | Fiber ring
RO-03 | IRB-U-0193 | U | Rooftop | Irbid | Irbid | 32.535 | 35.8432 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R03 | Fiber ring
RO-03 | IRB-U-0194 | U | Rooftop | Irbid | Irbid | 32.535 | 35.8479 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R03 | Fiber ring
RO-03 | IRB-U-0210 | U | Monopole / greenfield | Irbid | Irbid | 32.5393 | 35.8162 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R01 | Fiber ring
RO-03 | IRB-U-0211 | U | Monopole / greenfield | Irbid | Irbid | 32.5385 | 35.8219 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R01 | Fiber ring
RO-03 | IRB-U-0212 | U | Monopole / greenfield | Irbid | Irbid | 32.5385 | 35.8267 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R02 | Fiber ring
RO-03 | IRB-U-0213 | U | Rooftop | Irbid | Irbid | 32.5385 | 35.8314 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R02 | Fiber ring
RO-03 | IRB-U-0214 | U | Rooftop | Irbid | Irbid | 32.5385 | 35.8361 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R02 | Fiber ring
RO-03 | IRB-U-0215 | U | Rooftop | Irbid | Irbid | 32.5385 | 35.8408 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R03 | Fiber ring
RO-03 | IRB-U-0216 | U | Rooftop | Irbid | Irbid | 32.5393 | 35.8456 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R03 | Fiber ring
RO-03 | IRB-U-0234 | U | Monopole / greenfield | Irbid | Irbid | 32.5428 | 35.8186 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R01 | Fiber ring
RO-03 | IRB-U-0235 | U | Monopole / greenfield | Irbid | Irbid | 32.5428 | 35.8233 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R01 | Fiber ring
RO-03 | IRB-U-0236 | U | Monopole / greenfield | Irbid | Irbid | 32.5428 | 35.8281 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R01 | Fiber ring
RO-03 | IRB-U-0237 | U | Rooftop | Irbid | Irbid | 32.542 | 35.8337 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R03 | Fiber ring
RO-03 | IRB-U-0238 | U | Rooftop | Irbid | Irbid | 32.5432 | 35.8389 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R03 | Fiber ring
RO-03 | IRB-U-0239 | U | Rooftop | Irbid | Irbid | 32.5432 | 35.8437 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R03 | Fiber ring
RO-03 | IRB-U-0260 | U | Monopole / greenfield | Irbid | Irbid | 32.5459 | 35.8177 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R01 | Fiber ring
RO-03 | IRB-U-0261 | U | Monopole / greenfield | Irbid | Irbid | 32.5463 | 35.821 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R06 | Fiber ring
RO-03 | IRB-U-0262 | U | Monopole / greenfield | Irbid | Irbid | 32.5463 | 35.8276 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R06 | Fiber ring
RO-03 | IRB-U-0263 | U | Monopole / greenfield | Irbid | Irbid | 32.5463 | 35.8304 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R01 | Fiber ring
RO-03 | IRB-U-0283 | U | Monopole / greenfield | Irbid | Irbid | 32.5499 | 35.8196 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R05 | Fiber ring
RO-03 | IRB-U-0284 | U | Monopole / greenfield | Irbid | Irbid | 32.5499 | 35.8233 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R05 | Fiber ring
RO-03 | IRB-U-0285 | U | Monopole / greenfield | Irbid | Irbid | 32.5491 | 35.829 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R05 | Fiber ring
RO-03 | IRB-U-0305 | U | Monopole / greenfield | Irbid | Irbid | 32.5526 | 35.8172 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R05 | Fiber ring
RO-03 | IRB-U-0306 | U | Monopole / greenfield | Irbid | Irbid | 32.5534 | 35.821 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R05 | Fiber ring
RO-03 | IRB-U-0307 | U | Rooftop | Irbid | Irbid | 32.5542 | 35.8267 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R05 | Fiber ring
RO-03 | IRB-U-0308 | U | Rooftop | Irbid | Irbid | 32.5538 | 35.8319 | 30 | 3 | HUB-IRB-05 | HUB-IRB-05-R05 | Fiber ring
RO-04 | AMM-SU-2495 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8834 | 35.9406 | 32 | 3 | HUB-AMM-40 | HUB-AMM-40-R02 | Fiber ring
RO-04 | AMM-SU-2496 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8822 | 35.9461 | 32 | 3 | HUB-AMM-40 | HUB-AMM-40-R02 | Fiber ring
RO-04 | AMM-SU-2526 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8873 | 35.9385 | 32 | 3 | HUB-AMM-40 | HUB-AMM-40-R01 | Fiber ring
RO-04 | AMM-SU-2527 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8879 | 35.9447 | 32 | 3 | HUB-AMM-40 | HUB-AMM-40-R02 | Fiber ring
RO-04 | AMM-SU-2528 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8873 | 35.9495 | 32 | 3 | HUB-AMM-40 | HUB-AMM-40-R02 | Fiber ring
RO-04 | AMM-SU-2529 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8884 | 35.9577 | 32 | 3 | HUB-AMM-40 | HUB-AMM-40-R03 | Fiber ring
RO-04 | AMM-SU-2554 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8924 | 35.9597 | 32 | 3 | HUB-AMM-40 | HUB-AMM-40-R03 | Fiber ring
RO-04 | AMM-SU-2555 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8935 | 35.9679 | 32 | 3 | HUB-AMM-40 | HUB-AMM-40-R03 | Fiber ring
RO-04 | AMM-SU-2575 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8963 | 35.8553 | 32 | 3 | HUB-AMM-51 | HUB-AMM-51-R01 | Fiber ring
RO-04 | AMM-SU-2576 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8986 | 35.8621 | 32 | 3 | HUB-AMM-51 | HUB-AMM-51-R02 | Fiber ring
RO-04 | AMM-SU-2577 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8974 | 35.8689 | 32 | 3 | HUB-AMM-51 | HUB-AMM-51-R02 | Fiber ring
RO-04 | AMM-SU-2599 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9037 | 35.8382 | 32 | 3 | HUB-AMM-29 | HUB-AMM-29-R02 | Fiber ring
RO-04 | AMM-SU-2600 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9025 | 35.845 | 32 | 3 | HUB-AMM-51 | HUB-AMM-51-R01 | Fiber ring
RO-04 | AMM-SU-2601 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9025 | 35.8519 | 32 | 3 | HUB-AMM-51 | HUB-AMM-51-R01 | Fiber ring
RO-04 | AMM-SU-2602 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9014 | 35.8587 | 32 | 3 | HUB-AMM-51 | HUB-AMM-51-R01 | Fiber ring
RO-04 | AMM-SU-2603 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9031 | 35.8662 | 32 | 3 | HUB-AMM-51 | HUB-AMM-51-R02 | Fiber ring
RO-04 | AMM-SU-2623 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9064 | 35.828 | 32 | 3 | HUB-AMM-29 | HUB-AMM-29-R01 | Fiber ring
RO-04 | AMM-SU-2624 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9064 | 35.8348 | 32 | 3 | HUB-AMM-29 | HUB-AMM-29-R02 | Fiber ring
RO-04 | AMM-SU-2625 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9064 | 35.8416 | 32 | 3 | HUB-AMM-29 | HUB-AMM-29-R02 | Fiber ring
RO-04 | AMM-SU-2626 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9064 | 35.8484 | 32 | 3 | HUB-AMM-51 | HUB-AMM-51-R01 | Fiber ring
RO-04 | AMM-SU-2627 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9064 | 35.8553 | 32 | 3 | HUB-AMM-51 | HUB-AMM-51-R01 | Fiber ring
RO-04 | AMM-SU-2628 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9064 | 35.8621 | 32 | 3 | HUB-AMM-51 | HUB-AMM-51-R02 | Fiber ring
RO-04 | AMM-SU-2647 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9121 | 35.8252 | 32 | 3 | HUB-AMM-29 | HUB-AMM-29-R01 | Fiber ring
RO-04 | AMM-SU-2648 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9127 | 35.8327 | 32 | 3 | HUB-AMM-29 | HUB-AMM-29-R01 | Fiber ring
RO-04 | AMM-SU-2649 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9127 | 35.8396 | 32 | 3 | HUB-AMM-29 | HUB-AMM-29-R02 | Fiber ring
RO-04 | AMM-SU-2650 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9121 | 35.8457 | 32 | 3 | HUB-AMM-29 | HUB-AMM-29-R02 | Fiber ring
RO-04 | AMM-SU-2669 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9178 | 35.8293 | 32 | 3 | HUB-AMM-29 | HUB-AMM-29-R01 | Fiber ring
RO-04 | AMM-SU-2670 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9166 | 35.8348 | 32 | 3 | HUB-AMM-29 | HUB-AMM-29-R01 | Fiber ring
RO-04 | AMM-SU-2671 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9178 | 35.8402 | 32 | 3 | HUB-AMM-29 | HUB-AMM-29-R01 | Fiber ring
RO-04 | AMM-SU-2759 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9495 | 36.0191 | 32 | 3 | HUB-AMM-03 | HUB-AMM-03-R03 | Fiber ring
RO-04 | AMM-SU-2772 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9535 | 36.0239 | 32 | 3 | HUB-AMM-03 | HUB-AMM-03-R03 | Fiber ring
RO-04 | AMM-SU-2773 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9535 | 36.028 | 32 | 3 | HUB-AMM-03 | HUB-AMM-03-R03 | Fiber ring
RO-04 | AMM-SU-2785 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9597 | 36.0259 | 32 | 3 | HUB-AMM-03 | HUB-AMM-03-R04 | Fiber ring
RO-04 | AMM-SU-2854 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 31.9885 | 36.0252 | 32 | 3 | HUB-AMM-39 | HUB-AMM-39-R03 | Fiber ring
RO-04 | AMM-SU-2867 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 31.9942 | 36.0239 | 32 | 3 | HUB-AMM-39 | HUB-AMM-39-R03 | Fiber ring
RO-04 | AMM-SU-2880 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 31.9987 | 36.0184 | 32 | 3 | HUB-AMM-39 | HUB-AMM-39-R04 | Fiber ring
RO-04 | AMM-SU-2896 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0032 | 36.002 | 32 | 3 | HUB-AMM-39 | HUB-AMM-39-R05 | Fiber ring
RO-04 | AMM-SU-2897 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0038 | 36.0095 | 32 | 3 | HUB-AMM-39 | HUB-AMM-39-R04 | Fiber ring
RO-04 | AMM-SU-2898 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0055 | 36.0157 | 32 | 3 | HUB-AMM-39 | HUB-AMM-39-R04 | Fiber ring
RO-04 | AMM-SU-2911 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0095 | 35.9836 | 32 | 3 | HUB-AMM-54 | HUB-AMM-54-R04 | Fiber ring
RO-04 | AMM-SU-2912 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0106 | 35.9918 | 32 | 3 | HUB-AMM-54 | HUB-AMM-54-R04 | Fiber ring
RO-04 | AMM-SU-2913 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0095 | 35.9973 | 32 | 3 | HUB-AMM-54 | HUB-AMM-54-R03 | Fiber ring
RO-04 | AMM-SU-2914 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0089 | 36.0061 | 32 | 3 | HUB-AMM-39 | HUB-AMM-39-R05 | Fiber ring
RO-04 | AMM-SU-3066 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0412 | 36.0259 | 32 | 3 | HUB-AMM-15 | HUB-AMM-15-R06 | Fiber ring
RO-04 | AMM-SU-3096 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0439 | 36.0293 | 32 | 3 | HUB-AMM-15 | HUB-AMM-15-R06 | Fiber ring
RO-04 | AMM-SU-3097 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0457 | 36.0355 | 32 | 3 | HUB-AMM-15 | HUB-AMM-15-R05 | Fiber ring
RO-04 | AMM-SU-3098 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0439 | 36.043 | 32 | 3 | HUB-AMM-15 | HUB-AMM-15-R05 | Fiber ring
RO-04 | AMM-SU-3113 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.049 | 35.8484 | 32 | 3 | HUB-AMM-36 | HUB-AMM-36-R04 | Fiber ring
RO-04 | AMM-SU-3114 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0502 | 35.8566 | 32 | 3 | HUB-AMM-36 | HUB-AMM-36-R03 | Fiber ring
RO-04 | AMM-SU-3115 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0502 | 35.8635 | 32 | 3 | HUB-AMM-36 | HUB-AMM-36-R03 | Fiber ring
RO-04 | AMM-SU-3152 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0553 | 35.8532 | 32 | 3 | HUB-AMM-36 | HUB-AMM-36-R04 | Fiber ring
RO-04 | AMM-U-0427 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8908 | 35.9363 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R01 | Fiber ring
RO-04 | AMM-U-0428 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8904 | 35.9396 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R01 | Fiber ring
RO-04 | AMM-U-0429 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.89 | 35.9448 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R02 | Fiber ring
RO-04 | AMM-U-0439 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8943 | 35.9368 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R01 | Fiber ring
RO-04 | AMM-U-0440 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8947 | 35.9429 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R01 | Fiber ring
RO-04 | AMM-U-0441 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8947 | 35.9476 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R02 | Fiber ring
RO-04 | AMM-U-0442 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8943 | 35.9528 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R03 | Fiber ring
RO-04 | AMM-U-0453 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.897 | 35.9353 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R01 | Fiber ring
RO-04 | AMM-U-0454 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8978 | 35.9401 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R01 | Fiber ring
RO-04 | AMM-U-0455 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8978 | 35.9457 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R02 | Fiber ring
RO-04 | AMM-U-0456 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8986 | 35.9495 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R03 | Fiber ring
RO-04 | AMM-U-0457 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8986 | 35.9543 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R03 | Fiber ring
RO-04 | AMM-U-0458 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8983 | 35.9585 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R03 | Fiber ring
RO-04 | AMM-U-0459 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8986 | 35.9637 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R04 | Fiber ring
RO-04 | AMM-U-0460 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9014 | 35.881 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R03 | Fiber ring
RO-04 | AMM-U-0471 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9014 | 35.933 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R08 | Fiber ring
RO-04 | AMM-U-0472 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9014 | 35.9368 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R08 | Fiber ring
RO-04 | AMM-U-0473 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9014 | 35.9434 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R08 | Fiber ring
RO-04 | AMM-U-0474 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9005 | 35.9472 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R01 | Fiber ring
RO-04 | AMM-U-0475 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9014 | 35.9519 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R04 | Fiber ring
RO-04 | AMM-U-0476 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9018 | 35.9571 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R04 | Fiber ring
RO-04 | AMM-U-0477 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9018 | 35.9618 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R04 | Fiber ring
RO-04 | AMM-U-0480 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9049 | 35.8739 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R02 | Fiber ring
RO-04 | AMM-U-0481 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9049 | 35.8786 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R03 | Fiber ring
RO-04 | AMM-U-0493 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9049 | 35.9353 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R08 | Fiber ring
RO-04 | AMM-U-0494 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9049 | 35.9401 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R07 | Fiber ring
RO-04 | AMM-U-0495 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9057 | 35.9448 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R07 | Fiber ring
RO-04 | AMM-U-0496 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9057 | 35.9495 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R05 | Fiber ring
RO-04 | AMM-U-0497 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9049 | 35.9552 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R05 | Fiber ring
RO-04 | AMM-U-0498 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9049 | 35.958 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R04 | Fiber ring
RO-04 | AMM-U-0499 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9049 | 35.9628 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R04 | Fiber ring
RO-04 | AMM-U-0502 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9076 | 35.8668 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R02 | Fiber ring
RO-04 | AMM-U-0503 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9076 | 35.8715 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R02 | Fiber ring
RO-04 | AMM-U-0504 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9084 | 35.8763 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R03 | Fiber ring
RO-04 | AMM-U-0505 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9084 | 35.881 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R03 | Fiber ring
RO-04 | AMM-U-0517 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9084 | 35.9377 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R07 | Fiber ring
RO-04 | AMM-U-0518 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.908 | 35.9429 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R07 | Fiber ring
RO-04 | AMM-U-0519 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9088 | 35.9476 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R06 | Fiber ring
RO-04 | AMM-U-0520 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9084 | 35.9509 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R05 | Fiber ring
RO-04 | AMM-U-0521 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9084 | 35.9566 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R05 | Fiber ring
RO-04 | AMM-U-0522 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9076 | 35.9613 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R04 | Fiber ring
RO-04 | AMM-U-0526 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9119 | 35.8588 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R01 | Fiber ring
RO-04 | AMM-U-0527 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9127 | 35.8645 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R01 | Fiber ring
RO-04 | AMM-U-0528 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9127 | 35.8692 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R03 | Fiber ring
RO-04 | AMM-U-0529 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9119 | 35.8739 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R03 | Fiber ring
RO-04 | AMM-U-0530 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9119 | 35.8777 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R03 | Fiber ring
RO-04 | AMM-U-0543 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9119 | 35.9401 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R07 | Fiber ring
RO-04 | AMM-U-0544 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9115 | 35.9453 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R07 | Fiber ring
RO-04 | AMM-U-0545 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9111 | 35.9495 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R06 | Fiber ring
RO-04 | AMM-U-0546 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9115 | 35.9538 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R05 | Fiber ring
RO-04 | AMM-U-0547 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9119 | 35.959 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R05 | Fiber ring
RO-04 | AMM-U-0552 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9163 | 35.8526 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R02 | Fiber ring
RO-04 | AMM-U-0553 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9163 | 35.8574 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R05 | Fiber ring
RO-04 | AMM-U-0554 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9147 | 35.8621 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R05 | Fiber ring
RO-04 | AMM-U-0555 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9147 | 35.8668 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R04 | Fiber ring
RO-04 | AMM-U-0556 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9147 | 35.8715 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R04 | Fiber ring
RO-04 | AMM-U-0557 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9147 | 35.8763 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R04 | Fiber ring
RO-04 | AMM-U-0571 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9147 | 35.9424 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R07 | Fiber ring
RO-04 | AMM-U-0572 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9155 | 35.9481 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R06 | Fiber ring
RO-04 | AMM-U-0573 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9155 | 35.9528 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R06 | Fiber ring
RO-04 | AMM-U-0574 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9155 | 35.9557 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R05 | Fiber ring
RO-04 | AMM-U-0581 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.919 | 35.8465 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R02 | Fiber ring
RO-04 | AMM-U-0582 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.919 | 35.8512 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R03 | Fiber ring
RO-04 | AMM-U-0583 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.919 | 35.8541 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R03 | Fiber ring
RO-04 | AMM-U-0584 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.919 | 35.8588 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R05 | Fiber ring
RO-04 | AMM-U-0585 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.919 | 35.8654 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R05 | Fiber ring
RO-04 | AMM-U-0586 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9186 | 35.8687 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R05 | Fiber ring
RO-04 | AMM-U-0587 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9182 | 35.8739 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R04 | Fiber ring
RO-04 | AMM-U-0588 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9186 | 35.8782 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R04 | Fiber ring
RO-04 | AMM-U-0602 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.919 | 35.9448 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R06 | Fiber ring
RO-04 | AMM-U-0603 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9182 | 35.9495 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R06 | Fiber ring
RO-04 | AMM-U-0604 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9194 | 35.9547 | 30 | 3 | HUB-AMM-40 | HUB-AMM-40-R06 | Fiber ring
RO-04 | AMM-U-0612 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9217 | 35.8385 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R01 | Fiber ring
RO-04 | AMM-U-0613 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9229 | 35.8437 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R01 | Fiber ring
RO-04 | AMM-U-0614 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9229 | 35.8484 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R03 | Fiber ring
RO-04 | AMM-U-0615 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9217 | 35.8526 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R03 | Fiber ring
RO-04 | AMM-U-0616 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9225 | 35.8564 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R03 | Fiber ring
RO-04 | AMM-U-0617 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9225 | 35.863 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R05 | Fiber ring
RO-04 | AMM-U-0618 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9225 | 35.8659 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R05 | Fiber ring
RO-04 | AMM-U-0619 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9217 | 35.8715 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R04 | Fiber ring
RO-04 | AMM-U-0620 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9217 | 35.8763 | 30 | 3 | HUB-AMM-51 | HUB-AMM-51-R04 | Fiber ring
RO-04 | AMM-U-0645 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9252 | 35.8314 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R06 | Fiber ring
RO-04 | AMM-U-0646 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9252 | 35.8361 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R06 | Fiber ring
RO-04 | AMM-U-0647 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9252 | 35.8408 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R06 | Fiber ring
RO-04 | AMM-U-0648 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9252 | 35.8456 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R04 | Fiber ring
RO-04 | AMM-U-0649 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9252 | 35.8503 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R04 | Fiber ring
RO-04 | AMM-U-0650 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.926 | 35.8541 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R03 | Fiber ring
RO-04 | AMM-U-0651 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.926 | 35.8597 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R03 | Fiber ring
RO-04 | AMM-U-0681 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9304 | 35.8337 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R06 | Fiber ring
RO-04 | AMM-U-0682 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9296 | 35.8394 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R06 | Fiber ring
RO-04 | AMM-U-0683 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9304 | 35.8432 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R05 | Fiber ring
RO-04 | AMM-U-0684 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9296 | 35.8489 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R04 | Fiber ring
RO-04 | AMM-U-0685 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9291 | 35.8531 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R04 | Fiber ring
RO-04 | AMM-U-0686 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9296 | 35.8564 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R04 | Fiber ring
RO-04 | AMM-U-0715 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9335 | 35.8366 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R06 | Fiber ring
RO-04 | AMM-U-0716 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9327 | 35.8413 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R05 | Fiber ring
RO-04 | AMM-U-0717 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9327 | 35.8451 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R05 | Fiber ring
RO-04 | AMM-U-0718 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9331 | 35.8512 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R04 | Fiber ring
RO-04 | AMM-U-0719 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9331 | 35.8541 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R04 | Fiber ring
RO-04 | AMM-U-0748 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9366 | 35.8394 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R05 | Fiber ring
RO-04 | AMM-U-0749 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9374 | 35.8432 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R05 | Fiber ring
RO-04 | AMM-U-0750 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9366 | 35.847 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R05 | Fiber ring
RO-04 | AMM-U-0751 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.937 | 35.8531 | 30 | 3 | HUB-AMM-29 | HUB-AMM-29-R05 | Fiber ring
RO-04 | AMM-U-0846 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9464 | 36.0015 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R02 | Fiber ring
RO-04 | AMM-U-0847 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.948 | 36.0062 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R02 | Fiber ring
RO-04 | AMM-U-0848 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.948 | 36.011 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R02 | Fiber ring
RO-04 | AMM-U-0867 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9515 | 35.9992 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R01 | Fiber ring
RO-04 | AMM-U-0868 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9507 | 36.0029 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R01 | Fiber ring
RO-04 | AMM-U-0869 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9507 | 36.0076 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R02 | Fiber ring
RO-04 | AMM-U-0870 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9499 | 36.0133 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R03 | Fiber ring
RO-04 | AMM-U-0886 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9538 | 35.9963 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R01 | Fiber ring
RO-04 | AMM-U-0887 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9534 | 36.0015 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R01 | Fiber ring
RO-04 | AMM-U-0888 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9542 | 36.0062 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R02 | Fiber ring
RO-04 | AMM-U-0889 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.955 | 36.011 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R02 | Fiber ring
RO-04 | AMM-U-0890 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9538 | 36.0152 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R03 | Fiber ring
RO-04 | AMM-U-0907 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9582 | 35.9949 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R01 | Fiber ring
RO-04 | AMM-U-0908 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9578 | 35.9992 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R01 | Fiber ring
RO-04 | AMM-U-0909 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9578 | 36.0039 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R01 | Fiber ring
RO-04 | AMM-U-0910 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9569 | 36.0086 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R02 | Fiber ring
RO-04 | AMM-U-0911 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9578 | 36.0133 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R03 | Fiber ring
RO-04 | AMM-U-0912 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9586 | 36.0181 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R03 | Fiber ring
RO-04 | AMM-U-0927 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9613 | 35.9911 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R08 | Fiber ring
RO-04 | AMM-U-0928 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9613 | 35.9977 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R08 | Fiber ring
RO-04 | AMM-U-0929 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9613 | 36.0025 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R08 | Fiber ring
RO-04 | AMM-U-0930 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9613 | 36.0053 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R07 | Fiber ring
RO-04 | AMM-U-0931 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9605 | 36.011 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R01 | Fiber ring
RO-04 | AMM-U-0932 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9613 | 36.0147 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R04 | Fiber ring
RO-04 | AMM-U-0933 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9613 | 36.0204 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R04 | Fiber ring
RO-04 | AMM-U-0950 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9644 | 35.9949 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R07 | Fiber ring
RO-04 | AMM-U-0951 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.964 | 35.9992 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R07 | Fiber ring
RO-04 | AMM-U-0952 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.964 | 36.0039 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R07 | Fiber ring
RO-04 | AMM-U-0953 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.964 | 36.0086 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R06 | Fiber ring
RO-04 | AMM-U-0954 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.964 | 36.0133 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R05 | Fiber ring
RO-04 | AMM-U-0955 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.964 | 36.0181 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R04 | Fiber ring
RO-04 | AMM-U-0956 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9648 | 36.0218 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R04 | Fiber ring
RO-04 | AMM-U-0975 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9675 | 35.9968 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R07 | Fiber ring
RO-04 | AMM-U-0976 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9675 | 36.0015 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R07 | Fiber ring
RO-04 | AMM-U-0977 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9683 | 36.0062 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R06 | Fiber ring
RO-04 | AMM-U-0978 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9683 | 36.0119 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R05 | Fiber ring
RO-04 | AMM-U-0979 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9683 | 36.0166 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R05 | Fiber ring
RO-04 | AMM-U-0980 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9679 | 36.0204 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R04 | Fiber ring
RO-04 | AMM-U-1002 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9718 | 35.9992 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R07 | Fiber ring
RO-04 | AMM-U-1003 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.971 | 36.0039 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R06 | Fiber ring
RO-04 | AMM-U-1004 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9715 | 36.0081 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R06 | Fiber ring
RO-04 | AMM-U-1005 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9723 | 36.0138 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R05 | Fiber ring
RO-04 | AMM-U-1006 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9715 | 36.0185 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R05 | Fiber ring
RO-04 | AMM-U-1007 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9715 | 36.0223 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R04 | Fiber ring
RO-04 | AMM-U-1028 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9754 | 36.0015 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R06 | Fiber ring
RO-04 | AMM-U-1029 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9754 | 36.0062 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R06 | Fiber ring
RO-04 | AMM-U-1030 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9754 | 36.011 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R06 | Fiber ring
RO-04 | AMM-U-1031 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.975 | 36.0162 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R05 | Fiber ring
RO-04 | AMM-U-1032 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9754 | 36.0204 | 30 | 3 | HUB-AMM-03 | HUB-AMM-03-R05 | Fiber ring
RO-04 | AMM-U-1056 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9797 | 35.9992 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R01 | Fiber ring
RO-04 | AMM-U-1057 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9789 | 36.0029 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R01 | Fiber ring
RO-04 | AMM-U-1058 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9789 | 36.0086 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R02 | Fiber ring
RO-04 | AMM-U-1059 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9785 | 36.0138 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R02 | Fiber ring
RO-04 | AMM-U-1060 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9789 | 36.0181 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R02 | Fiber ring
RO-04 | AMM-U-1087 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9828 | 35.9963 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R01 | Fiber ring
RO-04 | AMM-U-1088 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9824 | 36.0006 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R01 | Fiber ring
RO-04 | AMM-U-1089 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9824 | 36.0072 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R02 | Fiber ring
RO-04 | AMM-U-1090 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9816 | 36.011 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R02 | Fiber ring
RO-04 | AMM-U-1091 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9824 | 36.0157 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R02 | Fiber ring
RO-04 | AMM-U-1092 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9828 | 36.0209 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R03 | Fiber ring
RO-04 | AMM-U-1119 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9859 | 35.9812 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R01 | Fiber ring
RO-04 | AMM-U-1120 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9859 | 35.9859 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R02 | Fiber ring
RO-04 | AMM-U-1121 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9859 | 35.9897 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R02 | Fiber ring
RO-04 | AMM-U-1122 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9851 | 35.9944 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R01 | Fiber ring
RO-04 | AMM-U-1123 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9859 | 35.9992 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R01 | Fiber ring
RO-04 | AMM-U-1124 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9859 | 36.0039 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R01 | Fiber ring
RO-04 | AMM-U-1125 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9851 | 36.0086 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R02 | Fiber ring
RO-04 | AMM-U-1126 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 31.9859 | 36.0143 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R03 | Fiber ring
RO-04 | AMM-U-1127 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 31.9859 | 36.019 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R03 | Fiber ring
RO-04 | AMM-U-1160 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9891 | 35.968 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R01 | Fiber ring
RO-04 | AMM-U-1161 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.9722 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R01 | Fiber ring
RO-04 | AMM-U-1162 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.9769 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R01 | Fiber ring
RO-04 | AMM-U-1163 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9891 | 35.9821 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R02 | Fiber ring
RO-04 | AMM-U-1164 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.9883 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R02 | Fiber ring
RO-04 | AMM-U-1165 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.9911 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R02 | Fiber ring
RO-04 | AMM-U-1166 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.9968 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R06 | Fiber ring
RO-04 | AMM-U-1167 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 36.0006 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R06 | Fiber ring
RO-04 | AMM-U-1168 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 31.9895 | 36.0053 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R01 | Fiber ring
RO-04 | AMM-U-1169 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 31.9899 | 36.0105 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R03 | Fiber ring
RO-04 | AMM-U-1170 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 31.9887 | 36.0157 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R03 | Fiber ring
RO-04 | AMM-U-1205 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.993 | 35.9699 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R01 | Fiber ring
RO-04 | AMM-U-1206 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.993 | 35.9755 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R01 | Fiber ring
RO-04 | AMM-U-1207 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9934 | 35.9798 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R01 | Fiber ring
RO-04 | AMM-U-1208 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9922 | 35.985 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R02 | Fiber ring
RO-04 | AMM-U-1209 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9922 | 35.9897 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R02 | Fiber ring
RO-04 | AMM-U-1210 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9922 | 35.9944 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R06 | Fiber ring
RO-04 | AMM-U-1211 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 31.9934 | 35.9987 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R06 | Fiber ring
RO-04 | AMM-U-1212 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 31.993 | 36.0039 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R05 | Fiber ring
RO-04 | AMM-U-1213 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 31.993 | 36.0076 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R04 | Fiber ring
RO-04 | AMM-U-1214 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 31.993 | 36.0133 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R04 | Fiber ring
RO-04 | AMM-U-1249 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9973 | 35.9684 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R06 | Fiber ring
RO-04 | AMM-U-1250 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9969 | 35.9736 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R06 | Fiber ring
RO-04 | AMM-U-1251 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9973 | 35.9779 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R05 | Fiber ring
RO-04 | AMM-U-1252 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9965 | 35.9817 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R01 | Fiber ring
RO-04 | AMM-U-1253 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9965 | 35.9883 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R03 | Fiber ring
RO-04 | AMM-U-1254 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9957 | 35.9921 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R03 | Fiber ring
RO-04 | AMM-U-1255 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 31.9965 | 35.9977 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R06 | Fiber ring
RO-04 | AMM-U-1256 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 31.9961 | 36.002 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R05 | Fiber ring
RO-04 | AMM-U-1257 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 31.9965 | 36.0053 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R05 | Fiber ring
RO-04 | AMM-U-1258 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 31.9965 | 36.011 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R04 | Fiber ring
RO-04 | AMM-U-1293 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0001 | 35.9708 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R05 | Fiber ring
RO-04 | AMM-U-1294 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9996 | 35.9751 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R05 | Fiber ring
RO-04 | AMM-U-1295 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9992 | 35.9802 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R04 | Fiber ring
RO-04 | AMM-U-1296 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0001 | 35.984 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R04 | Fiber ring
RO-04 | AMM-U-1297 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 31.9992 | 35.9897 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R03 | Fiber ring
RO-04 | AMM-U-1298 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0001 | 35.9954 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R03 | Fiber ring
RO-04 | AMM-U-1299 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0001 | 35.9992 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R05 | Fiber ring
RO-04 | AMM-U-1300 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 31.9996 | 36.0039 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R05 | Fiber ring
RO-04 | AMM-U-1301 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0009 | 36.0086 | 30 | 3 | HUB-AMM-39 | HUB-AMM-39-R04 | Fiber ring
RO-04 | AMM-U-1339 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0028 | 35.9684 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R05 | Fiber ring
RO-04 | AMM-U-1340 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0036 | 35.9722 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R05 | Fiber ring
RO-04 | AMM-U-1341 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0044 | 35.9779 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R04 | Fiber ring
RO-04 | AMM-U-1342 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.004 | 35.9821 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R04 | Fiber ring
RO-04 | AMM-U-1343 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0036 | 35.9873 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R03 | Fiber ring
RO-04 | AMM-U-1344 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0036 | 35.9911 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R03 | Fiber ring
RO-04 | AMM-U-1352 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0028 | 36.0582 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R01 | Fiber ring
RO-04 | AMM-U-1353 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0036 | 36.062 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R02 | Fiber ring
RO-04 | AMM-U-1388 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0079 | 35.9708 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R05 | Fiber ring
RO-04 | AMM-U-1389 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0071 | 35.9755 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R05 | Fiber ring
RO-04 | AMM-U-1390 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0063 | 35.9802 | 30 | 3 | HUB-AMM-54 | HUB-AMM-54-R04 | Fiber ring
RO-04 | AMM-U-1398 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0075 | 36.0554 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R01 | Fiber ring
RO-04 | AMM-U-1399 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0071 | 36.0615 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R02 | Fiber ring
RO-04 | AMM-U-1400 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0063 | 36.0653 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R02 | Fiber ring
RO-04 | AMM-U-1401 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0079 | 36.07 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R02 | Fiber ring
RO-04 | AMM-U-1443 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0098 | 36.0535 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R01 | Fiber ring
RO-04 | AMM-U-1444 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0106 | 36.0592 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R01 | Fiber ring
RO-04 | AMM-U-1445 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0106 | 36.063 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R02 | Fiber ring
RO-04 | AMM-U-1446 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0106 | 36.0677 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R02 | Fiber ring
RO-04 | AMM-U-1447 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0106 | 36.0714 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R03 | Fiber ring
RO-04 | AMM-U-1488 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.015 | 36.0511 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R01 | Fiber ring
RO-04 | AMM-U-1489 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0145 | 36.0554 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R01 | Fiber ring
RO-04 | AMM-U-1490 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0142 | 36.0596 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R01 | Fiber ring
RO-04 | AMM-U-1491 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0142 | 36.0653 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R02 | Fiber ring
RO-04 | AMM-U-1492 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0142 | 36.07 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R03 | Fiber ring
RO-04 | AMM-U-1493 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0142 | 36.0748 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R03 | Fiber ring
RO-04 | AMM-U-1530 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0185 | 36.0488 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R07 | Fiber ring
RO-04 | AMM-U-1531 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0169 | 36.0535 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R07 | Fiber ring
RO-04 | AMM-U-1532 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0177 | 36.0573 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R07 | Fiber ring
RO-04 | AMM-U-1533 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0169 | 36.063 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R01 | Fiber ring
RO-04 | AMM-U-1534 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0177 | 36.0677 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R03 | Fiber ring
RO-04 | AMM-U-1535 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0177 | 36.0714 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R03 | Fiber ring
RO-04 | AMM-U-1536 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0177 | 36.0771 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R03 | Fiber ring
RO-04 | AMM-U-1568 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.022 | 36.0228 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R02 | Fiber ring
RO-04 | AMM-U-1569 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0212 | 36.0275 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R02 | Fiber ring
RO-04 | AMM-U-1570 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0212 | 36.0322 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R02 | Fiber ring
RO-04 | AMM-U-1571 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0216 | 36.0374 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R03 | Fiber ring
RO-04 | AMM-U-1572 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0212 | 36.0417 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R03 | Fiber ring
RO-04 | AMM-U-1573 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.022 | 36.0464 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R03 | Fiber ring
RO-04 | AMM-U-1574 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0212 | 36.0511 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R07 | Fiber ring
RO-04 | AMM-U-1575 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.022 | 36.0559 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R06 | Fiber ring
RO-04 | AMM-U-1576 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.022 | 36.0606 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R06 | Fiber ring
RO-04 | AMM-U-1577 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.022 | 36.0653 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R05 | Fiber ring
RO-04 | AMM-U-1578 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0212 | 36.07 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R04 | Fiber ring
RO-04 | AMM-U-1579 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0208 | 36.0743 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R03 | Fiber ring
RO-04 | AMM-U-1608 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0247 | 36.0204 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R01 | Fiber ring
RO-04 | AMM-U-1609 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0255 | 36.0251 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R02 | Fiber ring
RO-04 | AMM-U-1610 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0255 | 36.0299 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R02 | Fiber ring
RO-04 | AMM-U-1611 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0255 | 36.0346 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R02 | Fiber ring
RO-04 | AMM-U-1612 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0247 | 36.0393 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R03 | Fiber ring
RO-04 | AMM-U-1613 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0255 | 36.044 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R03 | Fiber ring
RO-04 | AMM-U-1614 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0247 | 36.0497 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R07 | Fiber ring
RO-04 | AMM-U-1615 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0251 | 36.053 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R06 | Fiber ring
RO-04 | AMM-U-1616 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0247 | 36.0582 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R06 | Fiber ring
RO-04 | AMM-U-1617 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0247 | 36.062 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R05 | Fiber ring
RO-04 | AMM-U-1618 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0247 | 36.0677 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R04 | Fiber ring
RO-04 | AMM-U-1619 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0247 | 36.0714 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R04 | Fiber ring
RO-04 | AMM-U-1620 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0247 | 36.0771 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R04 | Fiber ring
RO-04 | AMM-U-1646 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0291 | 36.0181 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R01 | Fiber ring
RO-04 | AMM-U-1647 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0291 | 36.0228 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R01 | Fiber ring
RO-04 | AMM-U-1648 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0291 | 36.0275 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R01 | Fiber ring
RO-04 | AMM-U-1649 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0282 | 36.0332 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R02 | Fiber ring
RO-04 | AMM-U-1650 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0291 | 36.037 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R03 | Fiber ring
RO-04 | AMM-U-1651 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0282 | 36.0417 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R03 | Fiber ring
RO-04 | AMM-U-1652 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0282 | 36.0455 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R04 | Fiber ring
RO-04 | AMM-U-1653 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0282 | 36.0511 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R06 | Fiber ring
RO-04 | AMM-U-1654 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0282 | 36.0549 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R06 | Fiber ring
RO-04 | AMM-U-1655 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0291 | 36.0606 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R05 | Fiber ring
RO-04 | AMM-U-1656 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0282 | 36.0644 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R05 | Fiber ring
RO-04 | AMM-U-1657 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0282 | 36.0691 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R04 | Fiber ring
RO-04 | AMM-U-1658 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0282 | 36.0748 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R04 | Fiber ring
RO-04 | AMM-U-1672 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0326 | 35.8597 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R01 | Fiber ring
RO-04 | AMM-U-1673 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0309 | 35.8645 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R02 | Fiber ring
RO-04 | AMM-U-1688 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0314 | 36.0204 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R01 | Fiber ring
RO-04 | AMM-U-1689 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0318 | 36.0251 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R01 | Fiber ring
RO-04 | AMM-U-1690 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0309 | 36.0299 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R01 | Fiber ring
RO-04 | AMM-U-1691 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0326 | 36.0346 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R01 | Fiber ring
RO-04 | AMM-U-1692 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0309 | 36.0393 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R04 | Fiber ring
RO-04 | AMM-U-1693 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0326 | 36.044 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R04 | Fiber ring
RO-04 | AMM-U-1694 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0322 | 36.0483 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R04 | Fiber ring
RO-04 | AMM-U-1695 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0309 | 36.0535 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R06 | Fiber ring
RO-04 | AMM-U-1696 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0318 | 36.0573 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R05 | Fiber ring
RO-04 | AMM-U-1697 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0309 | 36.063 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R05 | Fiber ring
RO-04 | AMM-U-1698 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0314 | 36.0672 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R05 | Fiber ring
RO-04 | AMM-U-1699 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0326 | 36.0724 | 30 | 3 | HUB-AMM-07 | HUB-AMM-07-R04 | Fiber ring
RO-04 | AMM-U-1712 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0345 | 35.8526 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R01 | Fiber ring
RO-04 | AMM-U-1713 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0345 | 35.8574 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R01 | Fiber ring
RO-04 | AMM-U-1714 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0353 | 35.8612 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R01 | Fiber ring
RO-04 | AMM-U-1715 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0357 | 35.8663 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R02 | Fiber ring
RO-04 | AMM-U-1729 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0361 | 36.0228 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R06 | Fiber ring
RO-04 | AMM-U-1730 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0353 | 36.0275 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R06 | Fiber ring
RO-04 | AMM-U-1731 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0353 | 36.0332 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R06 | Fiber ring
RO-04 | AMM-U-1732 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0361 | 36.037 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R05 | Fiber ring
RO-04 | AMM-U-1733 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0353 | 36.0417 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R04 | Fiber ring
RO-04 | AMM-U-1734 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0353 | 36.0455 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R04 | Fiber ring
RO-04 | AMM-U-1735 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0353 | 36.0502 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R04 | Fiber ring
RO-04 | AMM-U-1751 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.038 | 35.8456 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R01 | Fiber ring
RO-04 | AMM-U-1752 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.038 | 35.8503 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R01 | Fiber ring
RO-04 | AMM-U-1753 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0388 | 35.8559 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R01 | Fiber ring
RO-04 | AMM-U-1754 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.038 | 35.8597 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R02 | Fiber ring
RO-04 | AMM-U-1755 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.038 | 35.8645 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R02 | Fiber ring
RO-04 | AMM-U-1756 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0396 | 35.8692 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R02 | Fiber ring
RO-04 | AMM-U-1767 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0388 | 36.0337 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R05 | Fiber ring
RO-04 | AMM-U-1768 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0388 | 36.0384 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R05 | Fiber ring
RO-04 | AMM-U-1769 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0388 | 36.0431 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R05 | Fiber ring
RO-04 | AMM-U-1770 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0396 | 36.0488 | 30 | 3 | HUB-AMM-15 | HUB-AMM-15-R05 | Fiber ring
RO-04 | AMM-U-1789 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0415 | 35.8479 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R04 | Fiber ring
RO-04 | AMM-U-1790 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0415 | 35.8526 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R04 | Fiber ring
RO-04 | AMM-U-1791 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0415 | 35.8574 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R01 | Fiber ring
RO-04 | AMM-U-1792 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0415 | 35.8621 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R02 | Fiber ring
RO-04 | AMM-U-1793 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0415 | 35.8668 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R02 | Fiber ring
RO-04 | AMM-U-1794 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0419 | 35.8711 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R03 | Fiber ring
RO-04 | AMM-U-1812 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0427 | 36.1083 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R02 | Fiber ring
RO-04 | AMM-U-1813 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0423 | 36.1126 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R02 | Fiber ring
RO-04 | AMM-U-1816 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0451 | 35.8456 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R04 | Fiber ring
RO-04 | AMM-U-1817 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0455 | 35.8498 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R04 | Fiber ring
RO-04 | AMM-U-1818 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0451 | 35.855 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R04 | Fiber ring
RO-04 | AMM-U-1819 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0451 | 35.8597 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R03 | Fiber ring
RO-04 | AMM-U-1820 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0451 | 35.8645 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R03 | Fiber ring
RO-04 | AMM-U-1821 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0459 | 35.8701 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R03 | Fiber ring
RO-04 | AMM-U-1822 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0467 | 35.8739 | 30 | 3 | HUB-AMM-36 | HUB-AMM-36-R03 | Fiber ring
RO-04 | AMM-U-1834 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0463 | 36.0918 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R01 | Fiber ring
RO-04 | AMM-U-1835 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0455 | 36.0965 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R01 | Fiber ring
RO-04 | AMM-U-1836 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0467 | 36.1008 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R01 | Fiber ring
RO-04 | AMM-U-1837 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0451 | 36.1055 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R01 | Fiber ring
RO-04 | AMM-U-1838 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0459 | 36.1093 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R02 | Fiber ring
RO-04 | AMM-U-1839 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0459 | 36.1149 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R02 | Fiber ring
RO-04 | AMM-U-1851 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0494 | 36.0889 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R01 | Fiber ring
RO-04 | AMM-U-1852 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0486 | 36.0937 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R01 | Fiber ring
RO-04 | AMM-U-1853 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0494 | 36.0984 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R01 | Fiber ring
RO-04 | AMM-U-1854 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0494 | 36.1041 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R02 | Fiber ring
RO-04 | AMM-U-1855 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0494 | 36.1069 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R02 | Fiber ring
RO-04 | AMM-U-1856 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0502 | 36.1126 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R02 | Fiber ring
RO-04 | AMM-U-1867 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0529 | 36.0875 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R06 | Fiber ring
RO-04 | AMM-U-1868 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0529 | 36.0922 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R06 | Fiber ring
RO-04 | AMM-U-1869 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0537 | 36.096 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R06 | Fiber ring
RO-04 | AMM-U-1870 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0529 | 36.1008 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R01 | Fiber ring
RO-04 | AMM-U-1871 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0521 | 36.1055 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R03 | Fiber ring
RO-04 | AMM-U-1872 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0529 | 36.1112 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R03 | Fiber ring
RO-04 | AMM-U-1873 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0529 | 36.1149 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R03 | Fiber ring
RO-04 | AMM-U-1883 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0573 | 36.0842 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R06 | Fiber ring
RO-04 | AMM-U-1884 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0564 | 36.0889 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R06 | Fiber ring
RO-04 | AMM-U-1885 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0564 | 36.0937 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R06 | Fiber ring
RO-04 | AMM-U-1886 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0564 | 36.0984 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R05 | Fiber ring
RO-04 | AMM-U-1887 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0564 | 36.1031 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R04 | Fiber ring
RO-04 | AMM-U-1888 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0564 | 36.1078 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R03 | Fiber ring
RO-04 | AMM-U-1889 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0564 | 36.1126 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R03 | Fiber ring
RO-04 | AMM-U-1894 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0608 | 36.0582 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R01 | Fiber ring
RO-04 | AMM-U-1896 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.06 | 36.0667 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R02 | Fiber ring
RO-04 | AMM-U-1897 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.06 | 36.0714 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R02 | Fiber ring
RO-04 | AMM-U-1898 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0592 | 36.0771 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R02 | Fiber ring
RO-04 | AMM-U-1899 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0608 | 36.0819 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R03 | Fiber ring
RO-04 | AMM-U-1900 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0608 | 36.0866 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R05 | Fiber ring
RO-04 | AMM-U-1901 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.06 | 36.0913 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R05 | Fiber ring
RO-04 | AMM-U-1902 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.06 | 36.096 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R05 | Fiber ring
RO-04 | AMM-U-1903 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.06 | 36.1008 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R04 | Fiber ring
RO-04 | AMM-U-1904 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.06 | 36.1055 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R03 | Fiber ring
RO-04 | AMM-U-1905 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.06 | 36.1102 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R03 | Fiber ring
RO-04 | AMM-U-1911 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0635 | 36.0568 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R01 | Fiber ring
RO-04 | AMM-U-1912 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0635 | 36.0606 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R01 | Fiber ring
RO-04 | AMM-U-1913 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0635 | 36.0653 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R02 | Fiber ring
RO-04 | AMM-U-1914 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0639 | 36.0696 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R02 | Fiber ring
RO-04 | AMM-U-1915 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0635 | 36.0738 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R02 | Fiber ring
RO-04 | AMM-U-1916 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0635 | 36.0804 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R03 | Fiber ring
RO-04 | AMM-U-1917 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0635 | 36.0842 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R03 | Fiber ring
RO-04 | AMM-U-1918 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0635 | 36.0889 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R05 | Fiber ring
RO-04 | AMM-U-1919 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0635 | 36.0937 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R05 | Fiber ring
RO-04 | AMM-U-1920 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0635 | 36.0984 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R04 | Fiber ring
RO-04 | AMM-U-1921 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0635 | 36.1031 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R04 | Fiber ring
RO-04 | AMM-U-1922 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0635 | 36.1078 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R04 | Fiber ring
RO-04 | AMM-U-1934 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.067 | 36.0573 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R01 | Fiber ring
RO-04 | AMM-U-1935 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0662 | 36.063 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R01 | Fiber ring
RO-04 | AMM-U-1936 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0666 | 36.0672 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R01 | Fiber ring
RO-04 | AMM-U-1937 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.067 | 36.0714 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R02 | Fiber ring
RO-04 | AMM-U-1938 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.067 | 36.0781 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R03 | Fiber ring
RO-04 | AMM-U-1939 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.067 | 36.0819 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R03 | Fiber ring
RO-04 | AMM-U-1940 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0662 | 36.0866 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R03 | Fiber ring
RO-04 | AMM-U-1942 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.067 | 36.096 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R05 | Fiber ring
RO-04 | AMM-U-1943 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0666 | 36.1012 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R04 | Fiber ring
RO-04 | AMM-U-1944 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.067 | 36.1045 | 30 | 3 | HUB-AMM-24 | HUB-AMM-24-R04 | Fiber ring
RO-04 | AMM-U-1956 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0705 | 36.0554 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R06 | Fiber ring
RO-04 | AMM-U-1957 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0697 | 36.0606 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R01 | Fiber ring
RO-04 | AMM-U-1958 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0705 | 36.0653 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R06 | Fiber ring
RO-04 | AMM-U-1959 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0705 | 36.07 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R01 | Fiber ring
RO-04 | AMM-U-1960 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0705 | 36.0757 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R03 | Fiber ring
RO-04 | AMM-U-1961 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0705 | 36.0795 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R04 | Fiber ring
RO-04 | AMM-U-1962 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0705 | 36.0842 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R04 | Fiber ring
RO-04 | AMM-U-1981 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0741 | 36.0573 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R06 | Fiber ring
RO-04 | AMM-U-1982 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0749 | 36.063 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R06 | Fiber ring
RO-04 | AMM-U-1983 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0737 | 36.0672 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R05 | Fiber ring
RO-04 | AMM-U-1984 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0741 | 36.0733 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R04 | Fiber ring
RO-04 | AMM-U-1985 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0741 | 36.0762 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R04 | Fiber ring
RO-04 | AMM-U-1986 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0741 | 36.0828 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R04 | Fiber ring
RO-04 | AMM-U-2006 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0772 | 36.0606 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R06 | Fiber ring
RO-04 | AMM-U-2007 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0768 | 36.0653 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R05 | Fiber ring
RO-04 | AMM-U-2008 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0776 | 36.071 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R05 | Fiber ring
RO-04 | AMM-U-2009 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0776 | 36.0748 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R04 | Fiber ring
RO-04 | AMM-U-2010 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0776 | 36.0795 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R04 | Fiber ring
RO-04 | AMM-U-2028 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0819 | 36.0582 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R06 | Fiber ring
RO-04 | AMM-U-2029 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0803 | 36.063 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R05 | Fiber ring
RO-04 | AMM-U-2030 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0811 | 36.0686 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R05 | Fiber ring
RO-04 | AMM-U-2031 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0811 | 36.0724 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R05 | Fiber ring
RO-04 | AMM-U-2032 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0819 | 36.0771 | 30 | 3 | HUB-AMM-01 | HUB-AMM-01-R05 | Fiber ring
RO-04 | AQB-SU-0206 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5556 | 35.0511 | 32 | 3 | HUB-AQB-03 | HUB-AQB-03-R03 | Fiber ring
RO-04 | AQB-SU-0207 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5607 | 35.0477 | 32 | 3 | HUB-AQB-03 | HUB-AQB-03-R03 | Fiber ring
RO-04 | AQB-SU-0208 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5658 | 35.0429 | 32 | 3 | HUB-AQB-03 | HUB-AQB-03-R04 | Fiber ring
RO-04 | AQB-SU-0211 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5811 | 34.9986 | 32 | 3 | HUB-AQB-03 | HUB-AQB-03-R07 | Fiber ring
RO-04 | AQB-SU-0212 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5805 | 35.0061 | 32 | 3 | HUB-AQB-03 | HUB-AQB-03-R06 | Fiber ring
RO-04 | AQB-SU-0213 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5811 | 35.0136 | 32 | 3 | HUB-AQB-03 | HUB-AQB-03-R06 | Fiber ring
RO-04 | AQB-U-0087 | U | Rooftop | Aqaba | Aqaba | 29.5541 | 35.0162 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R01 | Fiber ring
RO-04 | AQB-U-0088 | U | Rooftop | Aqaba | Aqaba | 29.5541 | 35.0209 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R01 | Fiber ring
RO-04 | AQB-U-0089 | U | Rooftop | Aqaba | Aqaba | 29.5537 | 35.0261 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R02 | Fiber ring
RO-04 | AQB-U-0090 | U | Rooftop | Aqaba | Aqaba | 29.5541 | 35.0313 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R02 | Fiber ring
RO-04 | AQB-U-0091 | U | Rooftop | Aqaba | Aqaba | 29.5533 | 35.0351 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R02 | Fiber ring
RO-04 | AQB-U-0092 | U | Rooftop | Aqaba | Aqaba | 29.5541 | 35.0407 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R03 | Fiber ring
RO-04 | AQB-U-0099 | U | Rooftop | Aqaba | Aqaba | 29.5576 | 35.0138 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R01 | Fiber ring
RO-04 | AQB-U-0100 | U | Rooftop | Aqaba | Aqaba | 29.5576 | 35.0185 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R01 | Fiber ring
RO-04 | AQB-U-0101 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5576 | 35.0232 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R02 | Fiber ring
RO-04 | AQB-U-0102 | U | Rooftop | Aqaba | Aqaba | 29.5576 | 35.028 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R02 | Fiber ring
RO-04 | AQB-U-0103 | U | Rooftop | Aqaba | Aqaba | 29.5576 | 35.0327 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R02 | Fiber ring
RO-04 | AQB-U-0104 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5576 | 35.0384 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R03 | Fiber ring
RO-04 | AQB-U-0110 | U | Rooftop | Aqaba | Aqaba | 29.5611 | 35.0114 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R01 | Fiber ring
RO-04 | AQB-U-0111 | U | Rooftop | Aqaba | Aqaba | 29.5611 | 35.0162 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R01 | Fiber ring
RO-04 | AQB-U-0112 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5611 | 35.0209 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R01 | Fiber ring
RO-04 | AQB-U-0113 | U | Rooftop | Aqaba | Aqaba | 29.5611 | 35.0256 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R02 | Fiber ring
RO-04 | AQB-U-0114 | U | Rooftop | Aqaba | Aqaba | 29.5611 | 35.0303 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R03 | Fiber ring
RO-04 | AQB-U-0115 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5611 | 35.0351 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R03 | Fiber ring
RO-04 | AQB-U-0120 | U | Rooftop | Aqaba | Aqaba | 29.5647 | 35.0091 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R07 | Fiber ring
RO-04 | AQB-U-0121 | U | Rooftop | Aqaba | Aqaba | 29.5647 | 35.0138 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R08 | Fiber ring
RO-04 | AQB-U-0122 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5647 | 35.0195 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R08 | Fiber ring
RO-04 | AQB-U-0123 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5647 | 35.0232 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R01 | Fiber ring
RO-04 | AQB-U-0124 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5647 | 35.028 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R03 | Fiber ring
RO-04 | AQB-U-0125 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5647 | 35.0327 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R04 | Fiber ring
RO-04 | AQB-U-0126 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5647 | 35.0374 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R04 | Fiber ring
RO-04 | AQB-U-0129 | U | Rooftop | Aqaba | Aqaba | 29.5674 | 35.0067 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R07 | Fiber ring
RO-04 | AQB-U-0130 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5682 | 35.0114 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R07 | Fiber ring
RO-04 | AQB-U-0131 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5682 | 35.0162 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R07 | Fiber ring
RO-04 | AQB-U-0132 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5682 | 35.0218 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R06 | Fiber ring
RO-04 | AQB-U-0133 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5682 | 35.0256 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R04 | Fiber ring
RO-04 | AQB-U-0134 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5682 | 35.0303 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R04 | Fiber ring
RO-04 | AQB-U-0135 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5682 | 35.0351 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R04 | Fiber ring
RO-04 | AQB-U-0136 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5717 | 35.0091 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R07 | Fiber ring
RO-04 | AQB-U-0137 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5717 | 35.0138 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R06 | Fiber ring
RO-04 | AQB-U-0138 | U | Rooftop | Aqaba | Aqaba | 29.5713 | 35.019 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R06 | Fiber ring
RO-04 | AQB-U-0139 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5717 | 35.0232 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R05 | Fiber ring
RO-04 | AQB-U-0140 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5717 | 35.028 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R05 | Fiber ring
RO-04 | AQB-U-0141 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5717 | 35.0327 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R04 | Fiber ring
RO-04 | AQB-U-0142 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5752 | 35.002 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R07 | Fiber ring
RO-04 | AQB-U-0143 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5752 | 35.0114 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R06 | Fiber ring
RO-04 | AQB-U-0144 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5752 | 35.0162 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R06 | Fiber ring
RO-04 | AQB-U-0145 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5752 | 35.0209 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R05 | Fiber ring
RO-04 | AQB-U-0146 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5752 | 35.0256 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R05 | Fiber ring
RO-04 | AQB-U-0147 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5752 | 35.0303 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R05 | Fiber ring
RO-04 | AQB-U-0148 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5788 | 35.0242 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R05 | Fiber ring
RO-04 | AQB-U-0149 | U | Monopole / greenfield | Aqaba | Aqaba | 29.5788 | 35.028 | 30 | 3 | HUB-AQB-03 | HUB-AQB-03-R05 | Fiber ring
RO-04 | HWY-HW-0001 | HW | Lattice tower | Highway | Amman | 31.4902 | 36.0088 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0002 | HW | Lattice tower | Highway | Amman | 31.426 | 36.0177 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0003 | HW | Lattice tower | Highway | Amman | 31.3649 | 36.0303 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0004 | HW | Lattice tower | Highway | Amman | 31.3039 | 36.0429 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0005 | HW | Lattice tower | Highway | Karak | 31.2397 | 36.0479 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0006 | HW | Lattice tower | Highway | Karak | 31.1757 | 36.0373 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0007 | HW | Lattice tower | Highway | Karak | 31.1181 | 36.023 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0008 | HW | Lattice tower | Highway | Karak | 31.0525 | 36.0068 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0009 | HW | Lattice tower | Highway | Karak | 30.9901 | 35.998 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0010 | HW | Lattice tower | Highway | Karak | 30.9262 | 35.9856 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0011 | HW | Lattice tower | Highway | Karak | 30.8638 | 35.9712 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0012 | HW | Lattice tower | Highway | Tafilah | 30.8058 | 35.9418 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0013 | HW | Lattice tower | Highway | Tafilah | 30.7545 | 35.9043 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0014 | HW | Lattice tower | Highway | Tafilah | 30.7 | 35.8632 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0015 | HW | Lattice tower | Highway | Ma'an | 30.6394 | 35.8441 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0016 | HW | Lattice tower | Highway | Ma'an | 30.5742 | 35.8328 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0017 | HW | Lattice tower | Highway | Ma'an | 30.5154 | 35.8179 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0018 | HW | Lattice tower | Highway | Ma'an | 30.4534 | 35.8029 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0019 | HW | Lattice tower | Highway | Ma'an | 30.3913 | 35.7859 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0020 | HW | Lattice tower | Highway | Ma'an | 30.328 | 35.7864 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0021 | HW | Lattice tower | Highway | Ma'an | 30.2648 | 35.7832 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0022 | HW | Lattice tower | Highway | Ma'an | 30.1179 | 35.6668 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0023 | HW | Lattice tower | Highway | Ma'an | 30.0763 | 35.6187 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0024 | HW | Lattice tower | Highway | Ma'an | 30.0347 | 35.5633 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0025 | HW | Lattice tower | Highway | Ma'an | 29.9931 | 35.5078 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0026 | HW | Lattice tower | Highway | Aqaba | 29.9441 | 35.4575 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0027 | HW | Lattice tower | Highway | Aqaba | 29.9008 | 35.4077 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0028 | HW | Lattice tower | Highway | Aqaba | 29.8481 | 35.3597 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0029 | HW | Lattice tower | Highway | Aqaba | 29.8017 | 35.3081 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0030 | HW | Lattice tower | Highway | Aqaba | 29.7565 | 35.2566 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0031 | HW | Lattice tower | Highway | Aqaba | 29.7114 | 35.2124 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0032 | HW | Lattice tower | Highway | Aqaba | 29.6663 | 35.1535 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | HWY-HW-0033 | HW | Lattice tower | Highway | Aqaba | 29.6266 | 35.1036 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-04 | IRB-SU-0578 | SU | Monopole / greenfield | Irbid | Irbid | 32.514 | 35.8184 | 32 | 3 | HUB-IRB-07 | HUB-IRB-07-R01 | Fiber ring
RO-04 | IRB-SU-0701 | SU | Monopole / greenfield | Irbid | Irbid | 32.5688 | 35.9024 | 32 | 3 | HUB-IRB-08 | HUB-IRB-08-R03 | Fiber ring
RO-04 | IRB-SU-0712 | SU | Monopole / greenfield | Irbid | Irbid | 32.5734 | 35.8928 | 32 | 3 | HUB-IRB-08 | HUB-IRB-08-R04 | Fiber ring
RO-04 | IRB-SU-0713 | SU | Monopole / greenfield | Irbid | Irbid | 32.5745 | 35.8996 | 32 | 3 | HUB-IRB-08 | HUB-IRB-08-R04 | Fiber ring
RO-04 | IRB-U-0061 | U | Monopole / greenfield | Irbid | Irbid | 32.5072 | 35.8474 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R02 | Fiber ring
RO-04 | IRB-U-0062 | U | Rooftop | Irbid | Irbid | 32.5076 | 35.8536 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R02 | Fiber ring
RO-04 | IRB-U-0063 | U | Rooftop | Irbid | Irbid | 32.5076 | 35.8574 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R02 | Fiber ring
RO-04 | IRB-U-0064 | U | Monopole / greenfield | Irbid | Irbid | 32.5067 | 35.8621 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R03 | Fiber ring
RO-04 | IRB-U-0065 | U | Monopole / greenfield | Irbid | Irbid | 32.5103 | 35.8314 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R01 | Fiber ring
RO-04 | IRB-U-0066 | U | Monopole / greenfield | Irbid | Irbid | 32.5111 | 35.8352 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R02 | Fiber ring
RO-04 | IRB-U-0067 | U | Monopole / greenfield | Irbid | Irbid | 32.5111 | 35.8418 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R02 | Fiber ring
RO-04 | IRB-U-0068 | U | Monopole / greenfield | Irbid | Irbid | 32.5119 | 35.8456 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R01 | Fiber ring
RO-04 | IRB-U-0069 | U | Monopole / greenfield | Irbid | Irbid | 32.5115 | 35.8498 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R02 | Fiber ring
RO-04 | IRB-U-0070 | U | Rooftop | Irbid | Irbid | 32.5111 | 35.8559 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R02 | Fiber ring
RO-04 | IRB-U-0071 | U | Rooftop | Irbid | Irbid | 32.5103 | 35.8597 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R02 | Fiber ring
RO-04 | IRB-U-0072 | U | Monopole / greenfield | Irbid | Irbid | 32.5103 | 35.8645 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R03 | Fiber ring
RO-04 | IRB-U-0073 | U | Monopole / greenfield | Irbid | Irbid | 32.5111 | 35.8682 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R03 | Fiber ring
RO-04 | IRB-U-0074 | U | Monopole / greenfield | Irbid | Irbid | 32.5111 | 35.8739 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R03 | Fiber ring
RO-04 | IRB-U-0076 | U | Monopole / greenfield | Irbid | Irbid | 32.5138 | 35.8243 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R01 | Fiber ring
RO-04 | IRB-U-0077 | U | Monopole / greenfield | Irbid | Irbid | 32.5142 | 35.8295 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R01 | Fiber ring
RO-04 | IRB-U-0078 | U | Monopole / greenfield | Irbid | Irbid | 32.5146 | 35.8328 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R02 | Fiber ring
RO-04 | IRB-U-0079 | U | Monopole / greenfield | Irbid | Irbid | 32.5146 | 35.8394 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R02 | Fiber ring
RO-04 | IRB-U-0080 | U | Monopole / greenfield | Irbid | Irbid | 32.5146 | 35.8432 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R01 | Fiber ring
RO-04 | IRB-U-0081 | U | Rooftop | Irbid | Irbid | 32.5138 | 35.8479 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R01 | Fiber ring
RO-04 | IRB-U-0082 | U | Rooftop | Irbid | Irbid | 32.5138 | 35.8526 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R01 | Fiber ring
RO-04 | IRB-U-0083 | U | Rooftop | Irbid | Irbid | 32.5146 | 35.8564 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R02 | Fiber ring
RO-04 | IRB-U-0084 | U | Monopole / greenfield | Irbid | Irbid | 32.5146 | 35.8621 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R03 | Fiber ring
RO-04 | IRB-U-0085 | U | Monopole / greenfield | Irbid | Irbid | 32.5146 | 35.8668 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R03 | Fiber ring
RO-04 | IRB-U-0086 | U | Monopole / greenfield | Irbid | Irbid | 32.5146 | 35.8715 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R03 | Fiber ring
RO-04 | IRB-U-0087 | U | Monopole / greenfield | Irbid | Irbid | 32.5146 | 35.8763 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R01 | Fiber ring
RO-04 | IRB-U-0088 | U | Monopole / greenfield | Irbid | Irbid | 32.5146 | 35.881 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R02 | Fiber ring
RO-04 | IRB-U-0089 | U | Monopole / greenfield | Irbid | Irbid | 32.5146 | 35.8857 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R02 | Fiber ring
RO-04 | IRB-U-0090 | U | Monopole / greenfield | Irbid | Irbid | 32.5181 | 35.8181 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R01 | Fiber ring
RO-04 | IRB-U-0091 | U | Monopole / greenfield | Irbid | Irbid | 32.5181 | 35.8219 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R01 | Fiber ring
RO-04 | IRB-U-0092 | U | Monopole / greenfield | Irbid | Irbid | 32.5173 | 35.8267 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R01 | Fiber ring
RO-04 | IRB-U-0093 | U | Monopole / greenfield | Irbid | Irbid | 32.5173 | 35.8314 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R02 | Fiber ring
RO-04 | IRB-U-0094 | U | Monopole / greenfield | Irbid | Irbid | 32.5181 | 35.837 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R02 | Fiber ring
RO-04 | IRB-U-0095 | U | Monopole / greenfield | Irbid | Irbid | 32.5181 | 35.8408 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R02 | Fiber ring
RO-04 | IRB-U-0096 | U | Rooftop | Irbid | Irbid | 32.5181 | 35.8456 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R01 | Fiber ring
RO-04 | IRB-U-0097 | U | Rooftop | Irbid | Irbid | 32.5181 | 35.8503 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R01 | Fiber ring
RO-04 | IRB-U-0098 | U | Rooftop | Irbid | Irbid | 32.5181 | 35.8541 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R01 | Fiber ring
RO-04 | IRB-U-0099 | U | Rooftop | Irbid | Irbid | 32.5185 | 35.8593 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R01 | Fiber ring
RO-04 | IRB-U-0100 | U | Monopole / greenfield | Irbid | Irbid | 32.5181 | 35.8645 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R04 | Fiber ring
RO-04 | IRB-U-0101 | U | Monopole / greenfield | Irbid | Irbid | 32.5181 | 35.8692 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R04 | Fiber ring
RO-04 | IRB-U-0102 | U | Monopole / greenfield | Irbid | Irbid | 32.5181 | 35.8739 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R01 | Fiber ring
RO-04 | IRB-U-0103 | U | Monopole / greenfield | Irbid | Irbid | 32.5181 | 35.8786 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R01 | Fiber ring
RO-04 | IRB-U-0104 | U | Monopole / greenfield | Irbid | Irbid | 32.5181 | 35.8834 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R02 | Fiber ring
RO-04 | IRB-U-0105 | U | Monopole / greenfield | Irbid | Irbid | 32.5181 | 35.8881 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R02 | Fiber ring
RO-04 | IRB-U-0106 | U | Monopole / greenfield | Irbid | Irbid | 32.5181 | 35.8928 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R03 | Fiber ring
RO-04 | IRB-U-0107 | U | Monopole / greenfield | Irbid | Irbid | 32.5221 | 35.8153 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R06 | Fiber ring
RO-04 | IRB-U-0108 | U | Monopole / greenfield | Irbid | Irbid | 32.5217 | 35.8196 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R06 | Fiber ring
RO-04 | IRB-U-0109 | U | Monopole / greenfield | Irbid | Irbid | 32.5217 | 35.8233 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R06 | Fiber ring
RO-04 | IRB-U-0110 | U | Monopole / greenfield | Irbid | Irbid | 32.5213 | 35.8295 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R01 | Fiber ring
RO-04 | IRB-U-0111 | U | Monopole / greenfield | Irbid | Irbid | 32.5217 | 35.8347 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R03 | Fiber ring
RO-04 | IRB-U-0112 | U | Monopole / greenfield | Irbid | Irbid | 32.5209 | 35.8385 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R03 | Fiber ring
RO-04 | IRB-U-0113 | U | Rooftop | Irbid | Irbid | 32.5217 | 35.8432 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R03 | Fiber ring
RO-04 | IRB-U-0114 | U | Rooftop | Irbid | Irbid | 32.5217 | 35.8479 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R07 | Fiber ring
RO-04 | IRB-U-0115 | U | Rooftop | Irbid | Irbid | 32.5217 | 35.8517 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R06 | Fiber ring
RO-04 | IRB-U-0116 | U | Rooftop | Irbid | Irbid | 32.5217 | 35.8574 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R05 | Fiber ring
RO-04 | IRB-U-0117 | U | Rooftop | Irbid | Irbid | 32.5217 | 35.8612 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R04 | Fiber ring
RO-04 | IRB-U-0118 | U | Monopole / greenfield | Irbid | Irbid | 32.5217 | 35.8668 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R04 | Fiber ring
RO-04 | IRB-U-0119 | U | Monopole / greenfield | Irbid | Irbid | 32.5217 | 35.8715 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R01 | Fiber ring
RO-04 | IRB-U-0120 | U | Monopole / greenfield | Irbid | Irbid | 32.5217 | 35.8753 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R01 | Fiber ring
RO-04 | IRB-U-0121 | U | Monopole / greenfield | Irbid | Irbid | 32.5217 | 35.881 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R02 | Fiber ring
RO-04 | IRB-U-0122 | U | Monopole / greenfield | Irbid | Irbid | 32.5217 | 35.8857 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R02 | Fiber ring
RO-04 | IRB-U-0123 | U | Monopole / greenfield | Irbid | Irbid | 32.5209 | 35.8905 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R03 | Fiber ring
RO-04 | IRB-U-0124 | U | Monopole / greenfield | Irbid | Irbid | 32.5217 | 35.8952 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R03 | Fiber ring
RO-04 | IRB-U-0126 | U | Monopole / greenfield | Irbid | Irbid | 32.5244 | 35.8172 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R06 | Fiber ring
RO-04 | IRB-U-0127 | U | Monopole / greenfield | Irbid | Irbid | 32.5244 | 35.8219 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R06 | Fiber ring
RO-04 | IRB-U-0128 | U | Monopole / greenfield | Irbid | Irbid | 32.5248 | 35.8262 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R05 | Fiber ring
RO-04 | IRB-U-0129 | U | Monopole / greenfield | Irbid | Irbid | 32.5244 | 35.8314 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R04 | Fiber ring
RO-04 | IRB-U-0130 | U | Rooftop | Irbid | Irbid | 32.526 | 35.8361 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R03 | Fiber ring
RO-04 | IRB-U-0131 | U | Rooftop | Irbid | Irbid | 32.526 | 35.8408 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R03 | Fiber ring
RO-04 | IRB-U-0132 | U | Rooftop | Irbid | Irbid | 32.5252 | 35.8456 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R06 | Fiber ring
RO-04 | IRB-U-0133 | U | Rooftop | Irbid | Irbid | 32.5252 | 35.8503 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R06 | Fiber ring
RO-04 | IRB-U-0134 | U | Rooftop | Irbid | Irbid | 32.5252 | 35.8541 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R06 | Fiber ring
RO-04 | IRB-U-0135 | U | Rooftop | Irbid | Irbid | 32.526 | 35.8597 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R05 | Fiber ring
RO-04 | IRB-U-0136 | U | Rooftop | Irbid | Irbid | 32.5252 | 35.8635 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R04 | Fiber ring
RO-04 | IRB-U-0137 | U | Monopole / greenfield | Irbid | Irbid | 32.5252 | 35.8682 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R04 | Fiber ring
RO-04 | IRB-U-0138 | U | Monopole / greenfield | Irbid | Irbid | 32.5252 | 35.8739 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R01 | Fiber ring
RO-04 | IRB-U-0139 | U | Monopole / greenfield | Irbid | Irbid | 32.5252 | 35.8786 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R01 | Fiber ring
RO-04 | IRB-U-0140 | U | Monopole / greenfield | Irbid | Irbid | 32.5252 | 35.8834 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R02 | Fiber ring
RO-04 | IRB-U-0141 | U | Monopole / greenfield | Irbid | Irbid | 32.5244 | 35.8881 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R03 | Fiber ring
RO-04 | IRB-U-0142 | U | Monopole / greenfield | Irbid | Irbid | 32.5244 | 35.8928 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R03 | Fiber ring
RO-04 | IRB-U-0143 | U | Monopole / greenfield | Irbid | Irbid | 32.5252 | 35.8975 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R03 | Fiber ring
RO-04 | IRB-U-0145 | U | Monopole / greenfield | Irbid | Irbid | 32.5287 | 35.8139 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R05 | Fiber ring
RO-04 | IRB-U-0146 | U | Monopole / greenfield | Irbid | Irbid | 32.5287 | 35.8205 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R05 | Fiber ring
RO-04 | IRB-U-0147 | U | Monopole / greenfield | Irbid | Irbid | 32.5287 | 35.8233 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R05 | Fiber ring
RO-04 | IRB-U-0148 | U | Monopole / greenfield | Irbid | Irbid | 32.5287 | 35.83 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R04 | Fiber ring
RO-04 | IRB-U-0149 | U | Rooftop | Irbid | Irbid | 32.5287 | 35.8347 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R04 | Fiber ring
RO-04 | IRB-U-0150 | U | Rooftop | Irbid | Irbid | 32.5279 | 35.8385 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R04 | Fiber ring
RO-04 | IRB-U-0151 | U | Rooftop | Irbid | Irbid | 32.5279 | 35.8432 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R03 | Fiber ring
RO-04 | IRB-U-0152 | U | Rooftop | Irbid | Irbid | 32.5279 | 35.8479 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R06 | Fiber ring
RO-04 | IRB-U-0153 | U | Rooftop | Irbid | Irbid | 32.5287 | 35.8526 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R06 | Fiber ring
RO-04 | IRB-U-0154 | U | Rooftop | Irbid | Irbid | 32.5279 | 35.8574 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R05 | Fiber ring
RO-04 | IRB-U-0155 | U | Rooftop | Irbid | Irbid | 32.5287 | 35.8621 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R05 | Fiber ring
RO-04 | IRB-U-0156 | U | Rooftop | Irbid | Irbid | 32.5287 | 35.8659 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R04 | Fiber ring
RO-04 | IRB-U-0157 | U | Monopole / greenfield | Irbid | Irbid | 32.5287 | 35.8715 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R06 | Fiber ring
RO-04 | IRB-U-0158 | U | Monopole / greenfield | Irbid | Irbid | 32.5287 | 35.8763 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R06 | Fiber ring
RO-04 | IRB-U-0159 | U | Monopole / greenfield | Irbid | Irbid | 32.5287 | 35.881 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R01 | Fiber ring
RO-04 | IRB-U-0160 | U | Monopole / greenfield | Irbid | Irbid | 32.5287 | 35.8857 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R03 | Fiber ring
RO-04 | IRB-U-0161 | U | Monopole / greenfield | Irbid | Irbid | 32.5287 | 35.8905 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R04 | Fiber ring
RO-04 | IRB-U-0162 | U | Monopole / greenfield | Irbid | Irbid | 32.5287 | 35.8952 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R04 | Fiber ring
RO-04 | IRB-U-0166 | U | Monopole / greenfield | Irbid | Irbid | 32.5322 | 35.8162 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R05 | Fiber ring
RO-04 | IRB-U-0167 | U | Monopole / greenfield | Irbid | Irbid | 32.5314 | 35.8219 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R05 | Fiber ring
RO-04 | IRB-U-0168 | U | Monopole / greenfield | Irbid | Irbid | 32.5322 | 35.8267 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R05 | Fiber ring
RO-04 | IRB-U-0169 | U | Rooftop | Irbid | Irbid | 32.5322 | 35.8323 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R04 | Fiber ring
RO-04 | IRB-U-0170 | U | Rooftop | Irbid | Irbid | 32.5322 | 35.8352 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R04 | Fiber ring
RO-04 | IRB-U-0171 | U | Rooftop | Irbid | Irbid | 32.5314 | 35.8408 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R04 | Fiber ring
RO-04 | IRB-U-0172 | U | Rooftop | Irbid | Irbid | 32.5318 | 35.8451 | 30 | 3 | HUB-IRB-07 | HUB-IRB-07-R03 | Fiber ring
RO-04 | IRB-U-0173 | U | Rooftop | Irbid | Irbid | 32.5314 | 35.8503 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R06 | Fiber ring
RO-04 | IRB-U-0174 | U | Rooftop | Irbid | Irbid | 32.5322 | 35.855 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R05 | Fiber ring
RO-04 | IRB-U-0175 | U | Rooftop | Irbid | Irbid | 32.5322 | 35.8597 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R05 | Fiber ring
RO-04 | IRB-U-0176 | U | Rooftop | Irbid | Irbid | 32.5322 | 35.8645 | 30 | 3 | HUB-IRB-11 | HUB-IRB-11-R05 | Fiber ring
RO-04 | IRB-U-0177 | U | Rooftop | Irbid | Irbid | 32.5322 | 35.8692 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R06 | Fiber ring
RO-04 | IRB-U-0178 | U | Monopole / greenfield | Irbid | Irbid | 32.5322 | 35.8739 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R06 | Fiber ring
RO-04 | IRB-U-0179 | U | Monopole / greenfield | Irbid | Irbid | 32.5322 | 35.8786 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R06 | Fiber ring
RO-04 | IRB-U-0180 | U | Monopole / greenfield | Irbid | Irbid | 32.5322 | 35.8834 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R04 | Fiber ring
RO-04 | IRB-U-0181 | U | Monopole / greenfield | Irbid | Irbid | 32.5322 | 35.8881 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R04 | Fiber ring
RO-04 | IRB-U-0182 | U | Monopole / greenfield | Irbid | Irbid | 32.5322 | 35.8928 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R04 | Fiber ring
RO-04 | IRB-U-0199 | U | Rooftop | Irbid | Irbid | 32.5358 | 35.8715 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R06 | Fiber ring
RO-04 | IRB-U-0200 | U | Monopole / greenfield | Irbid | Irbid | 32.5358 | 35.8763 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R05 | Fiber ring
RO-04 | IRB-U-0201 | U | Monopole / greenfield | Irbid | Irbid | 32.5358 | 35.881 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R05 | Fiber ring
RO-04 | IRB-U-0202 | U | Monopole / greenfield | Irbid | Irbid | 32.5358 | 35.8857 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R04 | Fiber ring
RO-04 | IRB-U-0203 | U | Monopole / greenfield | Irbid | Irbid | 32.5358 | 35.8905 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R04 | Fiber ring
RO-04 | IRB-U-0222 | U | Rooftop | Irbid | Irbid | 32.5393 | 35.8739 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R05 | Fiber ring
RO-04 | IRB-U-0223 | U | Rooftop | Irbid | Irbid | 32.5393 | 35.8786 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R05 | Fiber ring
RO-04 | IRB-U-0224 | U | Monopole / greenfield | Irbid | Irbid | 32.5393 | 35.8834 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R05 | Fiber ring
RO-04 | IRB-U-0225 | U | Monopole / greenfield | Irbid | Irbid | 32.5393 | 35.8881 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R05 | Fiber ring
RO-04 | IRB-U-0245 | U | Rooftop | Irbid | Irbid | 32.5428 | 35.881 | 30 | 3 | HUB-IRB-17 | HUB-IRB-17-R05 | Fiber ring
RO-04 | IRB-U-0267 | U | Monopole / greenfield | Irbid | Irbid | 32.5463 | 35.8834 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R01 | Fiber ring
RO-04 | IRB-U-0288 | U | Rooftop | Irbid | Irbid | 32.5499 | 35.881 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R01 | Fiber ring
RO-04 | IRB-U-0289 | U | Monopole / greenfield | Irbid | Irbid | 32.5499 | 35.8857 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R02 | Fiber ring
RO-04 | IRB-U-0290 | U | Monopole / greenfield | Irbid | Irbid | 32.5499 | 35.8905 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R02 | Fiber ring
RO-04 | IRB-U-0310 | U | Rooftop | Irbid | Irbid | 32.5534 | 35.8786 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R01 | Fiber ring
RO-04 | IRB-U-0311 | U | Rooftop | Irbid | Irbid | 32.5534 | 35.8834 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R01 | Fiber ring
RO-04 | IRB-U-0312 | U | Monopole / greenfield | Irbid | Irbid | 32.5534 | 35.8881 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R02 | Fiber ring
RO-04 | IRB-U-0313 | U | Monopole / greenfield | Irbid | Irbid | 32.5534 | 35.8919 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R02 | Fiber ring
RO-04 | IRB-U-0333 | U | Rooftop | Irbid | Irbid | 32.5569 | 35.8763 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R01 | Fiber ring
RO-04 | IRB-U-0334 | U | Rooftop | Irbid | Irbid | 32.5569 | 35.881 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R01 | Fiber ring
RO-04 | IRB-U-0335 | U | Monopole / greenfield | Irbid | Irbid | 32.5577 | 35.8857 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R01 | Fiber ring
RO-04 | IRB-U-0336 | U | Rooftop | Irbid | Irbid | 32.5569 | 35.8905 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R02 | Fiber ring
RO-04 | IRB-U-0337 | U | Rooftop | Irbid | Irbid | 32.5569 | 35.8942 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R02 | Fiber ring
RO-04 | IRB-U-0338 | U | Rooftop | Irbid | Irbid | 32.5569 | 35.899 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R02 | Fiber ring
RO-04 | IRB-U-0357 | U | Rooftop | Irbid | Irbid | 32.5604 | 35.8739 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R06 | Fiber ring
RO-04 | IRB-U-0358 | U | Rooftop | Irbid | Irbid | 32.5604 | 35.8786 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R06 | Fiber ring
RO-04 | IRB-U-0359 | U | Monopole / greenfield | Irbid | Irbid | 32.5604 | 35.8834 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R06 | Fiber ring
RO-04 | IRB-U-0360 | U | Monopole / greenfield | Irbid | Irbid | 32.5596 | 35.8881 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R01 | Fiber ring
RO-04 | IRB-U-0361 | U | Rooftop | Irbid | Irbid | 32.5604 | 35.8928 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R03 | Fiber ring
RO-04 | IRB-U-0362 | U | Rooftop | Irbid | Irbid | 32.5604 | 35.8966 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R03 | Fiber ring
RO-04 | IRB-U-0363 | U | Monopole / greenfield | Irbid | Irbid | 32.5608 | 35.9018 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R03 | Fiber ring
RO-04 | IRB-U-0381 | U | Rooftop | Irbid | Irbid | 32.564 | 35.8715 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R06 | Fiber ring
RO-04 | IRB-U-0382 | U | Rooftop | Irbid | Irbid | 32.564 | 35.8763 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R06 | Fiber ring
RO-04 | IRB-U-0383 | U | Rooftop | Irbid | Irbid | 32.564 | 35.881 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R05 | Fiber ring
RO-04 | IRB-U-0384 | U | Monopole / greenfield | Irbid | Irbid | 32.564 | 35.8857 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R05 | Fiber ring
RO-04 | IRB-U-0385 | U | Monopole / greenfield | Irbid | Irbid | 32.564 | 35.8905 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R04 | Fiber ring
RO-04 | IRB-U-0386 | U | Monopole / greenfield | Irbid | Irbid | 32.564 | 35.8952 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R03 | Fiber ring
RO-04 | IRB-U-0387 | U | Monopole / greenfield | Irbid | Irbid | 32.564 | 35.8999 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R03 | Fiber ring
RO-04 | IRB-U-0407 | U | Rooftop | Irbid | Irbid | 32.5675 | 35.8692 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R05 | Fiber ring
RO-04 | IRB-U-0408 | U | Rooftop | Irbid | Irbid | 32.5675 | 35.8739 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R05 | Fiber ring
RO-04 | IRB-U-0409 | U | Rooftop | Irbid | Irbid | 32.5675 | 35.8786 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R05 | Fiber ring
RO-04 | IRB-U-0410 | U | Rooftop | Irbid | Irbid | 32.5667 | 35.8834 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R05 | Fiber ring
RO-04 | IRB-U-0411 | U | Monopole / greenfield | Irbid | Irbid | 32.5675 | 35.8881 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R04 | Fiber ring
RO-04 | IRB-U-0412 | U | Monopole / greenfield | Irbid | Irbid | 32.5675 | 35.8928 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R04 | Fiber ring
RO-04 | IRB-U-0413 | U | Monopole / greenfield | Irbid | Irbid | 32.5667 | 35.8975 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R03 | Fiber ring
RO-04 | IRB-U-0436 | U | Rooftop | Irbid | Irbid | 32.5702 | 35.881 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R05 | Fiber ring
RO-04 | IRB-U-0437 | U | Monopole / greenfield | Irbid | Irbid | 32.571 | 35.8857 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R04 | Fiber ring
RO-04 | IRB-U-0438 | U | Monopole / greenfield | Irbid | Irbid | 32.571 | 35.8914 | 30 | 3 | HUB-IRB-08 | HUB-IRB-08-R04 | Fiber ring
RO-05 | AMM-SU-2423 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.872 | 35.8996 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R01 | Fiber ring
RO-05 | AMM-SU-2424 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8732 | 35.9065 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R01 | Fiber ring
RO-05 | AMM-SU-2425 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8708 | 35.9133 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R02 | Fiber ring
RO-05 | AMM-SU-2426 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8714 | 35.9208 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R02 | Fiber ring
RO-05 | AMM-SU-2427 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8732 | 35.9269 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R02 | Fiber ring
RO-05 | AMM-SU-2428 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.872 | 35.9338 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R03 | Fiber ring
RO-05 | AMM-SU-2456 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8771 | 35.9017 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R01 | Fiber ring
RO-05 | AMM-SU-2457 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8771 | 35.9099 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R02 | Fiber ring
RO-05 | AMM-SU-2458 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8783 | 35.9167 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R02 | Fiber ring
RO-05 | AMM-SU-2459 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8759 | 35.9235 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R02 | Fiber ring
RO-05 | AMM-SU-2460 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8783 | 35.9304 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R03 | Fiber ring
RO-05 | AMM-SU-2461 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8765 | 35.9379 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R03 | Fiber ring
RO-05 | AMM-SU-2489 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8816 | 35.899 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R01 | Fiber ring
RO-05 | AMM-SU-2490 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8828 | 35.9058 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R01 | Fiber ring
RO-05 | AMM-SU-2491 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8834 | 35.9133 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R01 | Fiber ring
RO-05 | AMM-SU-2492 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8822 | 35.9188 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R02 | Fiber ring
RO-05 | AMM-SU-2493 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8828 | 35.9263 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R03 | Fiber ring
RO-05 | AMM-SU-2494 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8828 | 35.9331 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R03 | Fiber ring
RO-05 | AMM-SU-2523 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8873 | 35.9044 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R01 | Fiber ring
RO-05 | AMM-SU-2524 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8884 | 35.9099 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R07 | Fiber ring
RO-05 | AMM-SU-2525 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8884 | 35.9167 | 32 | 3 | HUB-AMM-46 | HUB-AMM-46-R01 | Fiber ring
RO-05 | AMM-SU-2557 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8935 | 35.9816 | 32 | 3 | HUB-AMM-33 | HUB-AMM-33-R02 | Fiber ring
RO-05 | AMM-SU-2558 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8935 | 35.9884 | 32 | 3 | HUB-AMM-33 | HUB-AMM-33-R02 | Fiber ring
RO-05 | AMM-SU-2580 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8986 | 35.9713 | 32 | 3 | HUB-AMM-33 | HUB-AMM-33-R01 | Fiber ring
RO-05 | AMM-SU-2581 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8986 | 35.9781 | 32 | 3 | HUB-AMM-33 | HUB-AMM-33-R02 | Fiber ring
RO-05 | AMM-SU-2582 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8974 | 35.985 | 32 | 3 | HUB-AMM-33 | HUB-AMM-33-R02 | Fiber ring
RO-05 | AMM-SU-2583 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8963 | 35.9918 | 32 | 3 | HUB-AMM-33 | HUB-AMM-33-R02 | Fiber ring
RO-05 | AMM-SU-2604 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9019 | 35.9822 | 32 | 3 | HUB-AMM-33 | HUB-AMM-33-R02 | Fiber ring
RO-05 | AMM-SU-2605 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9025 | 35.9884 | 32 | 3 | HUB-AMM-33 | HUB-AMM-33-R03 | Fiber ring
RO-05 | AMM-SU-2606 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9014 | 35.9952 | 32 | 3 | HUB-AMM-33 | HUB-AMM-33-R03 | Fiber ring
RO-05 | AMM-SU-2629 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9064 | 35.985 | 32 | 3 | HUB-AMM-33 | HUB-AMM-33-R03 | Fiber ring
RO-05 | AMM-SU-2630 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.907 | 35.9911 | 32 | 3 | HUB-AMM-33 | HUB-AMM-33-R03 | Fiber ring
RO-05 | AMM-SU-2631 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9064 | 35.9986 | 32 | 3 | HUB-AMM-33 | HUB-AMM-33-R03 | Fiber ring
RO-05 | AMM-SU-2651 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9139 | 35.9884 | 32 | 3 | HUB-AMM-33 | HUB-AMM-33-R03 | Fiber ring
RO-05 | AMM-SU-2652 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9127 | 35.9938 | 32 | 3 | HUB-AMM-33 | HUB-AMM-33-R03 | Fiber ring
RO-05 | AMM-SU-2668 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9172 | 35.8205 | 32 | 3 | HUB-AMM-22 | HUB-AMM-22-R02 | Fiber ring
RO-05 | AMM-SU-2672 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9178 | 35.9918 | 32 | 3 | HUB-AMM-33 | HUB-AMM-33-R04 | Fiber ring
RO-05 | AMM-SU-2689 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9223 | 35.8184 | 32 | 3 | HUB-AMM-22 | HUB-AMM-22-R02 | Fiber ring
RO-05 | AMM-SU-2690 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9229 | 35.8246 | 32 | 3 | HUB-AMM-22 | HUB-AMM-22-R02 | Fiber ring
RO-05 | AMM-SU-2705 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9292 | 35.8075 | 32 | 3 | HUB-AMM-22 | HUB-AMM-22-R01 | Fiber ring
RO-05 | AMM-SU-2706 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9292 | 35.8143 | 32 | 3 | HUB-AMM-22 | HUB-AMM-22-R01 | Fiber ring
RO-05 | AMM-SU-2707 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9292 | 35.8211 | 32 | 3 | HUB-AMM-22 | HUB-AMM-22-R02 | Fiber ring
RO-05 | AMM-SU-2721 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9319 | 35.8041 | 32 | 3 | HUB-AMM-22 | HUB-AMM-22-R01 | Fiber ring
RO-05 | AMM-SU-2722 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9325 | 35.8116 | 32 | 3 | HUB-AMM-22 | HUB-AMM-22-R01 | Fiber ring
RO-05 | AMM-SU-2723 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9343 | 35.8177 | 32 | 3 | HUB-AMM-22 | HUB-AMM-22-R02 | Fiber ring
RO-05 | AMM-SU-2733 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9394 | 35.8007 | 32 | 3 | HUB-AMM-22 | HUB-AMM-22-R06 | Fiber ring
RO-05 | AMM-SU-2734 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.937 | 35.8075 | 32 | 3 | HUB-AMM-22 | HUB-AMM-22-R01 | Fiber ring
RO-05 | AMM-SU-2745 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9444 | 35.8041 | 32 | 3 | HUB-AMM-22 | HUB-AMM-22-R06 | Fiber ring
RO-05 | AMM-SU-2746 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9421 | 35.8109 | 32 | 3 | HUB-AMM-22 | HUB-AMM-22-R06 | Fiber ring
RO-05 | AMM-SU-2757 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9489 | 35.8 | 32 | 3 | HUB-AMM-19 | HUB-AMM-19-R02 | Fiber ring
RO-05 | AMM-SU-2758 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9484 | 35.8061 | 32 | 3 | HUB-AMM-19 | HUB-AMM-19-R02 | Fiber ring
RO-05 | AMM-SU-2770 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9535 | 35.7986 | 32 | 3 | HUB-AMM-19 | HUB-AMM-19-R01 | Fiber ring
RO-05 | AMM-SU-2771 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9535 | 35.8027 | 32 | 3 | HUB-AMM-19 | HUB-AMM-19-R02 | Fiber ring
RO-05 | AMM-SU-2783 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9585 | 35.7931 | 32 | 3 | HUB-AMM-19 | HUB-AMM-19-R01 | Fiber ring
RO-05 | AMM-SU-2784 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9597 | 35.8007 | 32 | 3 | HUB-AMM-19 | HUB-AMM-19-R01 | Fiber ring
RO-05 | AMM-SU-2795 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9648 | 35.7904 | 32 | 3 | HUB-AMM-19 | HUB-AMM-19-R01 | Fiber ring
RO-05 | AMM-SU-2796 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9636 | 35.7986 | 32 | 3 | HUB-AMM-19 | HUB-AMM-19-R01 | Fiber ring
RO-05 | AMM-SU-2806 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9675 | 35.7938 | 32 | 3 | HUB-AMM-19 | HUB-AMM-19-R06 | Fiber ring
RO-05 | AMM-SU-2818 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.975 | 35.7972 | 32 | 3 | HUB-AMM-19 | HUB-AMM-19-R06 | Fiber ring
RO-05 | AMM-SU-2829 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9789 | 35.7952 | 32 | 3 | HUB-AMM-72 | HUB-AMM-72-R01 | Fiber ring
RO-05 | AMM-SU-2830 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9795 | 35.8013 | 32 | 3 | HUB-AMM-72 | HUB-AMM-72-R02 | Fiber ring
RO-05 | AMM-SU-2840 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.984 | 35.7904 | 32 | 3 | HUB-AMM-72 | HUB-AMM-72-R01 | Fiber ring
RO-05 | AMM-SU-2841 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9846 | 35.7966 | 32 | 3 | HUB-AMM-72 | HUB-AMM-72-R01 | Fiber ring
RO-05 | AMM-SU-2851 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 31.9891 | 35.7884 | 32 | 3 | HUB-AMM-72 | HUB-AMM-72-R01 | Fiber ring
RO-05 | AMM-SU-2852 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9891 | 35.7925 | 32 | 3 | HUB-AMM-72 | HUB-AMM-72-R01 | Fiber ring
RO-05 | AMM-SU-2853 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9891 | 35.802 | 32 | 3 | HUB-AMM-72 | HUB-AMM-72-R01 | Fiber ring
RO-05 | AMM-SU-2864 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 31.9953 | 35.7904 | 32 | 3 | HUB-AMM-72 | HUB-AMM-72-R06 | Fiber ring
RO-05 | AMM-SU-2865 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9942 | 35.7959 | 32 | 3 | HUB-AMM-72 | HUB-AMM-72-R06 | Fiber ring
RO-05 | AMM-SU-2866 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9936 | 35.8047 | 32 | 3 | HUB-AMM-72 | HUB-AMM-72-R05 | Fiber ring
RO-05 | AMM-SU-2868 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 31.9936 | 36.03 | 32 | 3 | HUB-AMM-62 | HUB-AMM-62-R01 | Fiber ring
RO-05 | AMM-SU-2869 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 31.9936 | 36.0355 | 32 | 3 | HUB-AMM-62 | HUB-AMM-62-R01 | Fiber ring
RO-05 | AMM-SU-2870 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.993 | 36.043 | 32 | 3 | HUB-AMM-62 | HUB-AMM-62-R02 | Fiber ring
RO-05 | AMM-SU-2871 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.993 | 36.0498 | 32 | 3 | HUB-AMM-62 | HUB-AMM-62-R02 | Fiber ring
RO-05 | AMM-SU-2872 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9942 | 36.0553 | 32 | 3 | HUB-AMM-62 | HUB-AMM-62-R02 | Fiber ring
RO-05 | AMM-SU-2878 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9993 | 35.7938 | 32 | 3 | HUB-AMM-72 | HUB-AMM-72-R06 | Fiber ring
RO-05 | AMM-SU-2879 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9987 | 35.8 | 32 | 3 | HUB-AMM-72 | HUB-AMM-72-R05 | Fiber ring
RO-05 | AMM-SU-2881 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 31.9993 | 36.0246 | 32 | 3 | HUB-AMM-62 | HUB-AMM-62-R01 | Fiber ring
RO-05 | AMM-SU-2882 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 31.9993 | 36.0314 | 32 | 3 | HUB-AMM-62 | HUB-AMM-62-R01 | Fiber ring
RO-05 | AMM-SU-2894 | SU | Rooftop | Amman-Zarqa Metro | Amman | 32.0038 | 35.7972 | 32 | 3 | HUB-AMM-72 | HUB-AMM-72-R05 | Fiber ring
RO-05 | AMM-SU-2895 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0044 | 35.8054 | 32 | 3 | HUB-AMM-72 | HUB-AMM-72-R05 | Fiber ring
RO-05 | AMM-SU-2909 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0083 | 35.8007 | 32 | 3 | HUB-AMM-72 | HUB-AMM-72-R05 | Fiber ring
RO-05 | AMM-SU-2910 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0083 | 35.8075 | 32 | 3 | HUB-AMM-61 | HUB-AMM-61-R01 | Fiber ring
RO-05 | AMM-SU-2926 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0145 | 35.7986 | 32 | 3 | HUB-AMM-61 | HUB-AMM-61-R01 | Fiber ring
RO-05 | AMM-SU-2927 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0134 | 35.8041 | 32 | 3 | HUB-AMM-61 | HUB-AMM-61-R01 | Fiber ring
RO-05 | AMM-SU-2928 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0145 | 35.8123 | 32 | 3 | HUB-AMM-61 | HUB-AMM-61-R01 | Fiber ring
RO-05 | AMM-SU-2949 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0196 | 35.802 | 32 | 3 | HUB-AMM-61 | HUB-AMM-61-R01 | Fiber ring
RO-05 | AMM-SU-2950 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0208 | 35.8075 | 32 | 3 | HUB-AMM-61 | HUB-AMM-61-R06 | Fiber ring
RO-05 | AMM-SU-2974 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0253 | 35.8047 | 32 | 3 | HUB-AMM-61 | HUB-AMM-61-R06 | Fiber ring
RO-05 | AMM-SU-2975 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0259 | 35.8109 | 32 | 3 | HUB-AMM-61 | HUB-AMM-61-R06 | Fiber ring
RO-05 | AMM-SU-2976 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0259 | 35.8177 | 32 | 3 | HUB-AMM-61 | HUB-AMM-61-R05 | Fiber ring
RO-05 | AMM-SU-2986 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0247 | 36.084 | 32 | 3 | HUB-AMM-65 | HUB-AMM-65-R02 | Fiber ring
RO-05 | AMM-SU-2987 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0247 | 36.0921 | 32 | 3 | HUB-AMM-65 | HUB-AMM-65-R02 | Fiber ring
RO-05 | AMM-SU-2988 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0247 | 36.099 | 32 | 3 | HUB-AMM-65 | HUB-AMM-65-R02 | Fiber ring
RO-05 | AMM-SU-2989 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0247 | 36.1031 | 32 | 3 | HUB-AMM-65 | HUB-AMM-65-R03 | Fiber ring
RO-05 | AMM-SU-3001 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0298 | 35.8088 | 32 | 3 | HUB-AMM-61 | HUB-AMM-61-R05 | Fiber ring
RO-05 | AMM-SU-3002 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0304 | 35.815 | 32 | 3 | HUB-AMM-61 | HUB-AMM-61-R05 | Fiber ring
RO-05 | AMM-SU-3003 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0298 | 35.9427 | 32 | 3 | HUB-AMM-66 | HUB-AMM-66-R03 | Fiber ring
RO-05 | AMM-SU-3004 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0304 | 35.9502 | 32 | 3 | HUB-AMM-66 | HUB-AMM-66-R04 | Fiber ring
RO-05 | AMM-SU-3023 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0349 | 35.8123 | 32 | 3 | HUB-AMM-61 | HUB-AMM-61-R05 | Fiber ring
RO-05 | AMM-SU-3024 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0337 | 35.8177 | 32 | 3 | HUB-AMM-61 | HUB-AMM-61-R05 | Fiber ring
RO-05 | AMM-SU-3026 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0337 | 35.9338 | 32 | 3 | HUB-AMM-66 | HUB-AMM-66-R04 | Fiber ring
RO-05 | AMM-SU-3027 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0349 | 35.942 | 32 | 3 | HUB-AMM-66 | HUB-AMM-66-R04 | Fiber ring
RO-05 | AMM-SU-3028 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0355 | 35.9481 | 32 | 3 | HUB-AMM-66 | HUB-AMM-66-R04 | Fiber ring
RO-05 | AMM-SU-3051 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.04 | 35.9222 | 32 | 3 | HUB-AMM-66 | HUB-AMM-66-R05 | Fiber ring
RO-05 | AMM-SU-3052 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.04 | 35.929 | 32 | 3 | HUB-AMM-66 | HUB-AMM-66-R05 | Fiber ring
RO-05 | AMM-SU-3053 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0406 | 35.9365 | 32 | 3 | HUB-AMM-66 | HUB-AMM-66-R04 | Fiber ring
RO-05 | AMM-SU-3054 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0388 | 35.944 | 32 | 3 | HUB-AMM-66 | HUB-AMM-66-R04 | Fiber ring
RO-05 | AMM-SU-3081 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0439 | 35.9269 | 32 | 3 | HUB-AMM-66 | HUB-AMM-66-R05 | Fiber ring
RO-05 | AMM-SU-3082 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0451 | 35.9324 | 32 | 3 | HUB-AMM-66 | HUB-AMM-66-R05 | Fiber ring
RO-05 | AMM-SU-3083 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0463 | 35.9406 | 32 | 3 | HUB-AMM-66 | HUB-AMM-66-R04 | Fiber ring
RO-05 | AMM-SU-3099 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0445 | 36.0491 | 32 | 3 | HUB-AMM-70 | HUB-AMM-70-R01 | Fiber ring
RO-05 | AMM-SU-3138 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0502 | 36.045 | 32 | 3 | HUB-AMM-70 | HUB-AMM-70-R07 | Fiber ring
RO-05 | AMM-SU-3177 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0553 | 36.0444 | 32 | 3 | HUB-AMM-70 | HUB-AMM-70-R07 | Fiber ring
RO-05 | AMM-SU-3190 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0603 | 35.843 | 32 | 3 | HUB-AMM-86 | HUB-AMM-86-R02 | Fiber ring
RO-05 | AMM-SU-3191 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0603 | 35.8498 | 32 | 3 | HUB-AMM-86 | HUB-AMM-86-R02 | Fiber ring
RO-05 | AMM-SU-3226 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0654 | 35.8327 | 32 | 3 | HUB-AMM-86 | HUB-AMM-86-R01 | Fiber ring
RO-05 | AMM-SU-3255 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0705 | 35.828 | 32 | 3 | HUB-AMM-86 | HUB-AMM-86-R01 | Fiber ring
RO-05 | AMM-SU-3313 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0807 | 35.8635 | 32 | 3 | HUB-AMM-86 | HUB-AMM-86-R04 | Fiber ring
RO-05 | AMM-SU-3339 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.087 | 35.8246 | 32 | 3 | HUB-AMM-86 | HUB-AMM-86-R06 | Fiber ring
RO-05 | AMM-SU-3340 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0858 | 35.8587 | 32 | 3 | HUB-AMM-86 | HUB-AMM-86-R04 | Fiber ring
RO-05 | AMM-SU-3360 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0921 | 35.828 | 32 | 3 | HUB-AMM-86 | HUB-AMM-86-R06 | Fiber ring
RO-05 | AMM-SU-3361 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0897 | 35.8553 | 32 | 3 | HUB-AMM-86 | HUB-AMM-86-R05 | Fiber ring
RO-05 | AMM-SU-3362 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0909 | 35.8621 | 32 | 3 | HUB-AMM-86 | HUB-AMM-86-R04 | Fiber ring
RO-05 | AMM-U-0418 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8873 | 35.9226 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R03 | Fiber ring
RO-05 | AMM-U-0419 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8873 | 35.9283 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R04 | Fiber ring
RO-05 | AMM-U-0420 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8864 | 35.933 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R03 | Fiber ring
RO-05 | AMM-U-0421 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8908 | 35.907 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R07 | Fiber ring
RO-05 | AMM-U-0422 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8912 | 35.9122 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R07 | Fiber ring
RO-05 | AMM-U-0423 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8908 | 35.9174 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R05 | Fiber ring
RO-05 | AMM-U-0424 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8908 | 35.9212 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R04 | Fiber ring
RO-05 | AMM-U-0425 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8916 | 35.9259 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R04 | Fiber ring
RO-05 | AMM-U-0426 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.89 | 35.9306 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R04 | Fiber ring
RO-05 | AMM-U-0431 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8935 | 35.8999 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R07 | Fiber ring
RO-05 | AMM-U-0432 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8943 | 35.9046 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R07 | Fiber ring
RO-05 | AMM-U-0433 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8943 | 35.9103 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R06 | Fiber ring
RO-05 | AMM-U-0434 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8939 | 35.9136 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R06 | Fiber ring
RO-05 | AMM-U-0435 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8943 | 35.9188 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R05 | Fiber ring
RO-05 | AMM-U-0436 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8943 | 35.9245 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R05 | Fiber ring
RO-05 | AMM-U-0437 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8947 | 35.9278 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R04 | Fiber ring
RO-05 | AMM-U-0438 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8943 | 35.932 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R04 | Fiber ring
RO-05 | AMM-U-0446 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8978 | 35.9023 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R06 | Fiber ring
RO-05 | AMM-U-0447 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8978 | 35.9079 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R06 | Fiber ring
RO-05 | AMM-U-0448 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8986 | 35.9117 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R06 | Fiber ring
RO-05 | AMM-U-0449 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8986 | 35.9164 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R05 | Fiber ring
RO-05 | AMM-U-0450 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8978 | 35.9212 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R05 | Fiber ring
RO-05 | AMM-U-0451 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.897 | 35.9259 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R05 | Fiber ring
RO-05 | AMM-U-0452 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8978 | 35.9297 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R04 | Fiber ring
RO-05 | AMM-U-0466 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9014 | 35.9094 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R06 | Fiber ring
RO-05 | AMM-U-0467 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9005 | 35.9141 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R06 | Fiber ring
RO-05 | AMM-U-0468 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9014 | 35.9188 | 30 | 3 | HUB-AMM-46 | HUB-AMM-46-R05 | Fiber ring
RO-05 | AMM-U-0478 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9022 | 35.9661 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R01 | Fiber ring
RO-05 | AMM-U-0479 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9014 | 35.9699 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R01 | Fiber ring
RO-05 | AMM-U-0500 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9049 | 35.9694 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R01 | Fiber ring
RO-05 | AMM-U-0501 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9057 | 35.9731 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R01 | Fiber ring
RO-05 | AMM-U-0523 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9084 | 35.9651 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R01 | Fiber ring
RO-05 | AMM-U-0524 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.908 | 35.9703 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R01 | Fiber ring
RO-05 | AMM-U-0525 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9076 | 35.9755 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R02 | Fiber ring
RO-05 | AMM-U-0548 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9119 | 35.9637 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R07 | Fiber ring
RO-05 | AMM-U-0549 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9119 | 35.9694 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R08 | Fiber ring
RO-05 | AMM-U-0550 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9119 | 35.9722 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R08 | Fiber ring
RO-05 | AMM-U-0551 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9119 | 35.9769 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R01 | Fiber ring
RO-05 | AMM-U-0575 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9151 | 35.9618 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R07 | Fiber ring
RO-05 | AMM-U-0576 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9155 | 35.967 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R07 | Fiber ring
RO-05 | AMM-U-0577 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9147 | 35.9708 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R07 | Fiber ring
RO-05 | AMM-U-0578 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9155 | 35.9746 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R06 | Fiber ring
RO-05 | AMM-U-0579 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9159 | 35.9798 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R04 | Fiber ring
RO-05 | AMM-U-0580 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9159 | 35.9854 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R04 | Fiber ring
RO-05 | AMM-U-0605 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.919 | 35.958 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R07 | Fiber ring
RO-05 | AMM-U-0606 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9194 | 35.9632 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R07 | Fiber ring
RO-05 | AMM-U-0607 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.919 | 35.9694 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R06 | Fiber ring
RO-05 | AMM-U-0608 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.919 | 35.9731 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R06 | Fiber ring
RO-05 | AMM-U-0609 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9194 | 35.9774 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R05 | Fiber ring
RO-05 | AMM-U-0610 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.919 | 35.9817 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R04 | Fiber ring
RO-05 | AMM-U-0611 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9182 | 35.9873 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R04 | Fiber ring
RO-05 | AMM-U-0638 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9217 | 35.9613 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R07 | Fiber ring
RO-05 | AMM-U-0639 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9233 | 35.9661 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R06 | Fiber ring
RO-05 | AMM-U-0640 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9225 | 35.9717 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R06 | Fiber ring
RO-05 | AMM-U-0641 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9217 | 35.9755 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R05 | Fiber ring
RO-05 | AMM-U-0642 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9217 | 35.9802 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R05 | Fiber ring
RO-05 | AMM-U-0643 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9229 | 35.9854 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R04 | Fiber ring
RO-05 | AMM-U-0644 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9221 | 35.9892 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R04 | Fiber ring
RO-05 | AMM-U-0674 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.926 | 35.9675 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R06 | Fiber ring
RO-05 | AMM-U-0675 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9252 | 35.9731 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R06 | Fiber ring
RO-05 | AMM-U-0676 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9256 | 35.9783 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R05 | Fiber ring
RO-05 | AMM-U-0677 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.926 | 35.9836 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R05 | Fiber ring
RO-05 | AMM-U-0680 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9304 | 35.829 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R03 | Fiber ring
RO-05 | AMM-U-0706 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9296 | 35.9755 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R05 | Fiber ring
RO-05 | AMM-U-0707 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9296 | 35.9793 | 30 | 3 | HUB-AMM-33 | HUB-AMM-33-R05 | Fiber ring
RO-05 | AMM-U-0712 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9339 | 35.8219 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R02 | Fiber ring
RO-05 | AMM-U-0713 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9339 | 35.8267 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R03 | Fiber ring
RO-05 | AMM-U-0714 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9331 | 35.8304 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R03 | Fiber ring
RO-05 | AMM-U-0743 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9366 | 35.8158 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R01 | Fiber ring
RO-05 | AMM-U-0744 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9374 | 35.8196 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R01 | Fiber ring
RO-05 | AMM-U-0745 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9366 | 35.8252 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R03 | Fiber ring
RO-05 | AMM-U-0746 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.937 | 35.8285 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R03 | Fiber ring
RO-05 | AMM-U-0747 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9374 | 35.8337 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R03 | Fiber ring
RO-05 | AMM-U-0773 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.8181 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R06 | Fiber ring
RO-05 | AMM-U-0774 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.821 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R04 | Fiber ring
RO-05 | AMM-U-0775 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9401 | 35.8276 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R04 | Fiber ring
RO-05 | AMM-U-0776 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9405 | 35.8319 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R04 | Fiber ring
RO-05 | AMM-U-0800 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9437 | 35.8158 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R06 | Fiber ring
RO-05 | AMM-U-0801 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9437 | 35.8205 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R05 | Fiber ring
RO-05 | AMM-U-0802 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9437 | 35.8233 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R04 | Fiber ring
RO-05 | AMM-U-0803 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9437 | 35.83 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R04 | Fiber ring
RO-05 | AMM-U-0825 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9472 | 35.8115 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R06 | Fiber ring
RO-05 | AMM-U-0826 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9472 | 35.8181 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R05 | Fiber ring
RO-05 | AMM-U-0827 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9472 | 35.8229 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R05 | Fiber ring
RO-05 | AMM-U-0828 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.948 | 35.8267 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R04 | Fiber ring
RO-05 | AMM-U-0849 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9507 | 35.8092 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R02 | Fiber ring
RO-05 | AMM-U-0850 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9507 | 35.8158 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R05 | Fiber ring
RO-05 | AMM-U-0851 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9507 | 35.8205 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R05 | Fiber ring
RO-05 | AMM-U-0852 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9499 | 35.8243 | 30 | 3 | HUB-AMM-22 | HUB-AMM-22-R05 | Fiber ring
RO-05 | AMM-U-0871 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9542 | 35.8068 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R02 | Fiber ring
RO-05 | AMM-U-0872 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9542 | 35.8115 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R03 | Fiber ring
RO-05 | AMM-U-0873 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9542 | 35.8181 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R03 | Fiber ring
RO-05 | AMM-U-0874 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9534 | 35.8219 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R03 | Fiber ring
RO-05 | AMM-U-0891 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9569 | 35.8054 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R02 | Fiber ring
RO-05 | AMM-U-0892 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9578 | 35.8092 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R02 | Fiber ring
RO-05 | AMM-U-0893 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9569 | 35.8148 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R03 | Fiber ring
RO-05 | AMM-U-0894 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9582 | 35.82 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R03 | Fiber ring
RO-05 | AMM-U-0895 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9586 | 35.8243 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R04 | Fiber ring
RO-05 | AMM-U-0913 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9613 | 35.8068 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R01 | Fiber ring
RO-05 | AMM-U-0914 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9621 | 35.8125 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R03 | Fiber ring
RO-05 | AMM-U-0915 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9613 | 35.8181 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R03 | Fiber ring
RO-05 | AMM-U-0916 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9621 | 35.8219 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R04 | Fiber ring
RO-05 | AMM-U-0934 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9648 | 35.8044 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R01 | Fiber ring
RO-05 | AMM-U-0935 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9652 | 35.8106 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R01 | Fiber ring
RO-05 | AMM-U-0936 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9656 | 35.8148 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R04 | Fiber ring
RO-05 | AMM-U-0937 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9648 | 35.8205 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R04 | Fiber ring
RO-05 | AMM-U-0957 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9691 | 35.803 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R06 | Fiber ring
RO-05 | AMM-U-0958 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9687 | 35.8082 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R05 | Fiber ring
RO-05 | AMM-U-0959 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9691 | 35.8125 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R05 | Fiber ring
RO-05 | AMM-U-0960 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9691 | 35.8172 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R04 | Fiber ring
RO-05 | AMM-U-0982 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9723 | 35.8011 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R06 | Fiber ring
RO-05 | AMM-U-0983 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9723 | 35.8054 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R05 | Fiber ring
RO-05 | AMM-U-0984 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9727 | 35.8101 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R05 | Fiber ring
RO-05 | AMM-U-0985 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9718 | 35.8148 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R04 | Fiber ring
RO-05 | AMM-U-0986 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9718 | 35.8186 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R04 | Fiber ring
RO-05 | AMM-U-1009 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9746 | 35.803 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R06 | Fiber ring
RO-05 | AMM-U-1010 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9754 | 35.8068 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R05 | Fiber ring
RO-05 | AMM-U-1011 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9762 | 35.8125 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R05 | Fiber ring
RO-05 | AMM-U-1012 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9754 | 35.8162 | 30 | 3 | HUB-AMM-19 | HUB-AMM-19-R05 | Fiber ring
RO-05 | AMM-U-1034 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9781 | 35.8054 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R02 | Fiber ring
RO-05 | AMM-U-1035 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9793 | 35.8096 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R02 | Fiber ring
RO-05 | AMM-U-1036 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9789 | 35.8139 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R02 | Fiber ring
RO-05 | AMM-U-1062 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9824 | 35.8068 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R02 | Fiber ring
RO-05 | AMM-U-1063 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9824 | 35.8125 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R02 | Fiber ring
RO-05 | AMM-U-1064 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9832 | 35.8172 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R03 | Fiber ring
RO-05 | AMM-U-1093 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9868 | 35.8054 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R01 | Fiber ring
RO-05 | AMM-U-1094 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9868 | 35.8101 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R02 | Fiber ring
RO-05 | AMM-U-1095 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9859 | 35.8139 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R03 | Fiber ring
RO-05 | AMM-U-1096 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9859 | 35.8205 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R03 | Fiber ring
RO-05 | AMM-U-1128 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9903 | 35.8077 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R01 | Fiber ring
RO-05 | AMM-U-1129 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9903 | 35.8125 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R03 | Fiber ring
RO-05 | AMM-U-1130 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9903 | 35.8172 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R03 | Fiber ring
RO-05 | AMM-U-1131 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9895 | 35.8219 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R03 | Fiber ring
RO-05 | AMM-U-1171 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.993 | 35.8092 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R04 | Fiber ring
RO-05 | AMM-U-1172 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9922 | 35.8148 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R04 | Fiber ring
RO-05 | AMM-U-1173 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9926 | 35.8191 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R03 | Fiber ring
RO-05 | AMM-U-1215 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9965 | 35.8087 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R05 | Fiber ring
RO-05 | AMM-U-1216 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9973 | 35.8125 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R04 | Fiber ring
RO-05 | AMM-U-1217 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9965 | 35.8172 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R04 | Fiber ring
RO-05 | AMM-U-1259 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0005 | 35.8096 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R05 | Fiber ring
RO-05 | AMM-U-1260 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0001 | 35.8139 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R04 | Fiber ring
RO-05 | AMM-U-1302 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0001 | 36.0379 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R02 | Fiber ring
RO-05 | AMM-U-1303 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0001 | 36.0417 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R02 | Fiber ring
RO-05 | AMM-U-1304 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0001 | 36.0464 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R02 | Fiber ring
RO-05 | AMM-U-1305 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0001 | 36.0511 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R03 | Fiber ring
RO-05 | AMM-U-1306 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0044 | 35.8125 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R04 | Fiber ring
RO-05 | AMM-U-1307 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0036 | 35.8162 | 30 | 3 | HUB-AMM-72 | HUB-AMM-72-R04 | Fiber ring
RO-05 | AMM-U-1345 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0036 | 36.0242 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R01 | Fiber ring
RO-05 | AMM-U-1346 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0036 | 36.0299 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R01 | Fiber ring
RO-05 | AMM-U-1347 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0036 | 36.0337 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R01 | Fiber ring
RO-05 | AMM-U-1348 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0036 | 36.0393 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R02 | Fiber ring
RO-05 | AMM-U-1349 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0036 | 36.0431 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R03 | Fiber ring
RO-05 | AMM-U-1350 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0028 | 36.0488 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R03 | Fiber ring
RO-05 | AMM-U-1351 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0036 | 36.0535 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R03 | Fiber ring
RO-05 | AMM-U-1354 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0071 | 35.8101 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R01 | Fiber ring
RO-05 | AMM-U-1355 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0071 | 35.8148 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R02 | Fiber ring
RO-05 | AMM-U-1356 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0063 | 35.8196 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R02 | Fiber ring
RO-05 | AMM-U-1391 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0079 | 36.0228 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R07 | Fiber ring
RO-05 | AMM-U-1392 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0079 | 36.0275 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R07 | Fiber ring
RO-05 | AMM-U-1393 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0071 | 36.0322 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R07 | Fiber ring
RO-05 | AMM-U-1394 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0063 | 36.037 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R01 | Fiber ring
RO-05 | AMM-U-1395 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0071 | 36.0407 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R03 | Fiber ring
RO-05 | AMM-U-1396 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0071 | 36.0464 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R03 | Fiber ring
RO-05 | AMM-U-1397 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0071 | 36.0511 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R03 | Fiber ring
RO-05 | AMM-U-1402 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0098 | 35.8125 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R02 | Fiber ring
RO-05 | AMM-U-1403 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0106 | 35.8172 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R02 | Fiber ring
RO-05 | AMM-U-1404 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0098 | 35.8219 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R02 | Fiber ring
RO-05 | AMM-U-1405 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0114 | 35.8267 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R03 | Fiber ring
RO-05 | AMM-U-1435 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0106 | 36.0147 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R06 | Fiber ring
RO-05 | AMM-U-1436 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0106 | 36.0195 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R06 | Fiber ring
RO-05 | AMM-U-1437 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0106 | 36.0251 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R06 | Fiber ring
RO-05 | AMM-U-1438 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0106 | 36.0289 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R06 | Fiber ring
RO-05 | AMM-U-1439 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0106 | 36.0346 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R05 | Fiber ring
RO-05 | AMM-U-1440 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0106 | 36.0393 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R04 | Fiber ring
RO-05 | AMM-U-1441 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0106 | 36.045 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R04 | Fiber ring
RO-05 | AMM-U-1442 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0106 | 36.0478 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R04 | Fiber ring
RO-05 | AMM-U-1448 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0145 | 35.8153 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R01 | Fiber ring
RO-05 | AMM-U-1449 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.015 | 35.8196 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R02 | Fiber ring
RO-05 | AMM-U-1450 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.015 | 35.8243 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R03 | Fiber ring
RO-05 | AMM-U-1451 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0142 | 35.829 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R03 | Fiber ring
RO-05 | AMM-U-1452 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0142 | 35.8328 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R03 | Fiber ring
RO-05 | AMM-U-1474 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0137 | 35.9382 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R02 | Fiber ring
RO-05 | AMM-U-1475 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0133 | 35.9424 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R02 | Fiber ring
RO-05 | AMM-U-1481 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0133 | 36.0181 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R06 | Fiber ring
RO-05 | AMM-U-1482 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0145 | 36.0223 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R06 | Fiber ring
RO-05 | AMM-U-1483 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0137 | 36.028 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R05 | Fiber ring
RO-05 | AMM-U-1484 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0137 | 36.0318 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R05 | Fiber ring
RO-05 | AMM-U-1485 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0133 | 36.037 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R05 | Fiber ring
RO-05 | AMM-U-1486 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0145 | 36.0421 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R04 | Fiber ring
RO-05 | AMM-U-1487 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0145 | 36.0459 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R04 | Fiber ring
RO-05 | AMM-U-1494 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0169 | 35.8172 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R02 | Fiber ring
RO-05 | AMM-U-1495 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0169 | 35.8219 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R03 | Fiber ring
RO-05 | AMM-U-1496 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0173 | 35.8262 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R03 | Fiber ring
RO-05 | AMM-U-1497 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0181 | 35.8309 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R03 | Fiber ring
RO-05 | AMM-U-1517 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0169 | 35.9306 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R01 | Fiber ring
RO-05 | AMM-U-1518 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0177 | 35.9363 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R02 | Fiber ring
RO-05 | AMM-U-1519 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0169 | 35.9401 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R02 | Fiber ring
RO-05 | AMM-U-1520 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0169 | 35.9448 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R03 | Fiber ring
RO-05 | AMM-U-1524 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0169 | 36.0204 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R06 | Fiber ring
RO-05 | AMM-U-1525 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0169 | 36.0251 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R05 | Fiber ring
RO-05 | AMM-U-1526 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0169 | 36.0299 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R05 | Fiber ring
RO-05 | AMM-U-1527 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0169 | 36.0346 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R05 | Fiber ring
RO-05 | AMM-U-1528 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0169 | 36.0393 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R04 | Fiber ring
RO-05 | AMM-U-1529 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0169 | 36.044 | 30 | 3 | HUB-AMM-62 | HUB-AMM-62-R04 | Fiber ring
RO-05 | AMM-U-1537 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0204 | 35.8196 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R01 | Fiber ring
RO-05 | AMM-U-1538 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0212 | 35.8252 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R04 | Fiber ring
RO-05 | AMM-U-1539 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0204 | 35.829 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R04 | Fiber ring
RO-05 | AMM-U-1540 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0212 | 35.8337 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R04 | Fiber ring
RO-05 | AMM-U-1559 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.022 | 35.9235 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R01 | Fiber ring
RO-05 | AMM-U-1560 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.022 | 35.9283 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R01 | Fiber ring
RO-05 | AMM-U-1561 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0212 | 35.933 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R02 | Fiber ring
RO-05 | AMM-U-1562 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0212 | 35.9368 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R02 | Fiber ring
RO-05 | AMM-U-1563 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.022 | 35.9424 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R03 | Fiber ring
RO-05 | AMM-U-1564 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.022 | 35.9472 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R03 | Fiber ring
RO-05 | AMM-U-1580 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0247 | 35.8229 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R04 | Fiber ring
RO-05 | AMM-U-1581 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0243 | 35.8271 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R04 | Fiber ring
RO-05 | AMM-U-1582 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0239 | 35.8314 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R04 | Fiber ring
RO-05 | AMM-U-1601 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0239 | 35.9212 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R01 | Fiber ring
RO-05 | AMM-U-1602 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0243 | 35.9264 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R01 | Fiber ring
RO-05 | AMM-U-1603 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0243 | 35.9301 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R01 | Fiber ring
RO-05 | AMM-U-1604 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0255 | 35.9353 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R02 | Fiber ring
RO-05 | AMM-U-1605 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0255 | 35.9401 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R03 | Fiber ring
RO-05 | AMM-U-1606 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0255 | 35.9448 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R03 | Fiber ring
RO-05 | AMM-U-1621 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0282 | 35.8252 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R05 | Fiber ring
RO-05 | AMM-U-1622 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0282 | 35.83 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R04 | Fiber ring
RO-05 | AMM-U-1641 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0291 | 35.9188 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R06 | Fiber ring
RO-05 | AMM-U-1642 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0282 | 35.9226 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R01 | Fiber ring
RO-05 | AMM-U-1643 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0291 | 35.9283 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R06 | Fiber ring
RO-05 | AMM-U-1644 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0291 | 35.933 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R01 | Fiber ring
RO-05 | AMM-U-1645 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0291 | 35.9377 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R03 | Fiber ring
RO-05 | AMM-U-1659 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0282 | 36.0795 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R01 | Fiber ring
RO-05 | AMM-U-1660 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0282 | 36.0842 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R01 | Fiber ring
RO-05 | AMM-U-1661 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0282 | 36.0889 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R02 | Fiber ring
RO-05 | AMM-U-1662 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0282 | 36.0946 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R02 | Fiber ring
RO-05 | AMM-U-1663 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0278 | 36.0989 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R03 | Fiber ring
RO-05 | AMM-U-1664 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0286 | 36.1036 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R03 | Fiber ring
RO-05 | AMM-U-1665 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0314 | 35.8262 | 30 | 3 | HUB-AMM-61 | HUB-AMM-61-R05 | Fiber ring
RO-05 | AMM-U-1684 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0309 | 35.9164 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R06 | Fiber ring
RO-05 | AMM-U-1685 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0318 | 35.9202 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R06 | Fiber ring
RO-05 | AMM-U-1686 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0326 | 35.9259 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R06 | Fiber ring
RO-05 | AMM-U-1687 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0318 | 35.9316 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R05 | Fiber ring
RO-05 | AMM-U-1700 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0326 | 36.0771 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R01 | Fiber ring
RO-05 | AMM-U-1701 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0314 | 36.0823 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R01 | Fiber ring
RO-05 | AMM-U-1702 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0318 | 36.0856 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R01 | Fiber ring
RO-05 | AMM-U-1703 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0318 | 36.0913 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R02 | Fiber ring
RO-05 | AMM-U-1704 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0322 | 36.0965 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R03 | Fiber ring
RO-05 | AMM-U-1705 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0326 | 36.1008 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R03 | Fiber ring
RO-05 | AMM-U-1706 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0318 | 36.1055 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R03 | Fiber ring
RO-05 | AMM-U-1726 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0353 | 35.9198 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R06 | Fiber ring
RO-05 | AMM-U-1727 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0361 | 35.9235 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R05 | Fiber ring
RO-05 | AMM-U-1728 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0357 | 35.9278 | 30 | 3 | HUB-AMM-66 | HUB-AMM-66-R05 | Fiber ring
RO-05 | AMM-U-1736 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0357 | 36.0554 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R01 | Fiber ring
RO-05 | AMM-U-1737 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0353 | 36.0615 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R02 | Fiber ring
RO-05 | AMM-U-1738 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0357 | 36.0648 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R02 | Fiber ring
RO-05 | AMM-U-1739 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0353 | 36.071 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R02 | Fiber ring
RO-05 | AMM-U-1740 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0361 | 36.0748 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R03 | Fiber ring
RO-05 | AMM-U-1741 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0361 | 36.0795 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R06 | Fiber ring
RO-05 | AMM-U-1742 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0345 | 36.0842 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R01 | Fiber ring
RO-05 | AMM-U-1743 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0353 | 36.0899 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R06 | Fiber ring
RO-05 | AMM-U-1744 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0353 | 36.0946 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R01 | Fiber ring
RO-05 | AMM-U-1745 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0345 | 36.0984 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R04 | Fiber ring
RO-05 | AMM-U-1746 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0353 | 36.1031 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R04 | Fiber ring
RO-05 | AMM-U-1747 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0345 | 36.1078 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R04 | Fiber ring
RO-05 | AMM-U-1771 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0396 | 36.0535 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R01 | Fiber ring
RO-05 | AMM-U-1772 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0388 | 36.0592 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R01 | Fiber ring
RO-05 | AMM-U-1773 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0396 | 36.063 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R02 | Fiber ring
RO-05 | AMM-U-1774 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0392 | 36.0672 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R02 | Fiber ring
RO-05 | AMM-U-1775 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0388 | 36.0714 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R02 | Fiber ring
RO-05 | AMM-U-1776 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0388 | 36.0771 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R03 | Fiber ring
RO-05 | AMM-U-1777 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0388 | 36.0809 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R06 | Fiber ring
RO-05 | AMM-U-1778 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0388 | 36.0875 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R06 | Fiber ring
RO-05 | AMM-U-1779 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0388 | 36.0913 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R06 | Fiber ring
RO-05 | AMM-U-1780 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0388 | 36.097 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R05 | Fiber ring
RO-05 | AMM-U-1781 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0384 | 36.1003 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R04 | Fiber ring
RO-05 | AMM-U-1782 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0396 | 36.1055 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R04 | Fiber ring
RO-05 | AMM-U-1783 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0388 | 36.1102 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R04 | Fiber ring
RO-05 | AMM-U-1802 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0423 | 36.0615 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R01 | Fiber ring
RO-05 | AMM-U-1803 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0423 | 36.0644 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R02 | Fiber ring
RO-05 | AMM-U-1804 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0415 | 36.07 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R03 | Fiber ring
RO-05 | AMM-U-1805 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0419 | 36.0752 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R03 | Fiber ring
RO-05 | AMM-U-1806 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0423 | 36.0785 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R03 | Fiber ring
RO-05 | AMM-U-1807 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0423 | 36.0833 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R06 | Fiber ring
RO-05 | AMM-U-1808 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0419 | 36.0894 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R05 | Fiber ring
RO-05 | AMM-U-1809 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0423 | 36.0946 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R05 | Fiber ring
RO-05 | AMM-U-1810 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0419 | 36.0979 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R05 | Fiber ring
RO-05 | AMM-U-1811 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0423 | 36.1041 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R05 | Fiber ring
RO-05 | AMM-U-1827 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0459 | 36.0592 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R01 | Fiber ring
RO-05 | AMM-U-1828 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0455 | 36.0625 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R01 | Fiber ring
RO-05 | AMM-U-1829 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0455 | 36.0682 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R03 | Fiber ring
RO-05 | AMM-U-1830 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0455 | 36.0729 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R03 | Fiber ring
RO-05 | AMM-U-1831 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0459 | 36.0762 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R04 | Fiber ring
RO-05 | AMM-U-1832 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0459 | 36.0809 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R04 | Fiber ring
RO-05 | AMM-U-1833 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0459 | 36.0875 | 30 | 3 | HUB-AMM-65 | HUB-AMM-65-R05 | Fiber ring
RO-05 | AMM-U-1844 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0494 | 36.0549 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R07 | Fiber ring
RO-05 | AMM-U-1845 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0486 | 36.0606 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R07 | Fiber ring
RO-05 | AMM-U-1846 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0486 | 36.0653 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R01 | Fiber ring
RO-05 | AMM-U-1847 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0494 | 36.07 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R04 | Fiber ring
RO-05 | AMM-U-1848 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0498 | 36.0743 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R04 | Fiber ring
RO-05 | AMM-U-1849 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0494 | 36.0795 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R04 | Fiber ring
RO-05 | AMM-U-1850 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0494 | 36.0833 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R04 | Fiber ring
RO-05 | AMM-U-1860 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0521 | 36.0535 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R07 | Fiber ring
RO-05 | AMM-U-1861 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0529 | 36.0573 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R06 | Fiber ring
RO-05 | AMM-U-1862 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0529 | 36.063 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R06 | Fiber ring
RO-05 | AMM-U-1863 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0529 | 36.0667 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R05 | Fiber ring
RO-05 | AMM-U-1864 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0525 | 36.0729 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R05 | Fiber ring
RO-05 | AMM-U-1865 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0529 | 36.0762 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R05 | Fiber ring
RO-05 | AMM-U-1866 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0529 | 36.0809 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R04 | Fiber ring
RO-05 | AMM-U-1876 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0568 | 36.0507 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R06 | Fiber ring
RO-05 | AMM-U-1877 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.056 | 36.0563 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R06 | Fiber ring
RO-05 | AMM-U-1878 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0564 | 36.0596 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R06 | Fiber ring
RO-05 | AMM-U-1879 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0556 | 36.0653 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R05 | Fiber ring
RO-05 | AMM-U-1880 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0564 | 36.071 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R05 | Fiber ring
RO-05 | AMM-U-1881 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0556 | 36.0748 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R05 | Fiber ring
RO-05 | AMM-U-1882 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.056 | 36.079 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R05 | Fiber ring
RO-05 | AMM-U-1890 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0564 | 36.1182 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R01 | Fiber ring
RO-05 | AMM-U-1893 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0596 | 36.053 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R06 | Fiber ring
RO-05 | AMM-U-1895 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0592 | 36.063 | 30 | 3 | HUB-AMM-70 | HUB-AMM-70-R06 | Fiber ring
RO-05 | AMM-U-1906 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.06 | 36.1149 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R01 | Fiber ring
RO-05 | AMM-U-1907 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.06 | 36.1197 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R01 | Fiber ring
RO-05 | AMM-U-1908 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.06 | 36.1244 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R02 | Fiber ring
RO-05 | AMM-U-1923 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0635 | 36.1126 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R01 | Fiber ring
RO-05 | AMM-U-1924 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0631 | 36.1168 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R01 | Fiber ring
RO-05 | AMM-U-1925 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0635 | 36.122 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R02 | Fiber ring
RO-05 | AMM-U-1926 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0635 | 36.1268 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R02 | Fiber ring
RO-05 | AMM-U-1927 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0635 | 36.1315 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R02 | Fiber ring
RO-05 | AMM-U-1928 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0662 | 35.8361 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R01 | Fiber ring
RO-05 | AMM-U-1929 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.067 | 35.8408 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R02 | Fiber ring
RO-05 | AMM-U-1930 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0678 | 35.8456 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R02 | Fiber ring
RO-05 | AMM-U-1931 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.067 | 35.8512 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R03 | Fiber ring
RO-05 | AMM-U-1941 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.067 | 36.0904 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R01 | Fiber ring
RO-05 | AMM-U-1945 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.067 | 36.1102 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R01 | Fiber ring
RO-05 | AMM-U-1946 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.067 | 36.1149 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R01 | Fiber ring
RO-05 | AMM-U-1947 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.067 | 36.1197 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R02 | Fiber ring
RO-05 | AMM-U-1948 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0674 | 36.1249 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R02 | Fiber ring
RO-05 | AMM-U-1949 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0678 | 36.1291 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R02 | Fiber ring
RO-05 | AMM-U-1950 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0705 | 35.8337 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R01 | Fiber ring
RO-05 | AMM-U-1951 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0705 | 35.8394 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R02 | Fiber ring
RO-05 | AMM-U-1952 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0705 | 35.8432 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R02 | Fiber ring
RO-05 | AMM-U-1953 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0705 | 35.8479 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R03 | Fiber ring
RO-05 | AMM-U-1954 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0697 | 35.8526 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R03 | Fiber ring
RO-05 | AMM-U-1963 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0705 | 36.0889 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R01 | Fiber ring
RO-05 | AMM-U-1964 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0705 | 36.0937 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R02 | Fiber ring
RO-05 | AMM-U-1965 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0705 | 36.0975 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R02 | Fiber ring
RO-05 | AMM-U-1966 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0697 | 36.1031 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R02 | Fiber ring
RO-05 | AMM-U-1967 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0705 | 36.1088 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R05 | Fiber ring
RO-05 | AMM-U-1968 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0714 | 36.1126 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R05 | Fiber ring
RO-05 | AMM-U-1969 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0705 | 36.1163 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R01 | Fiber ring
RO-05 | AMM-U-1970 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0705 | 36.123 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R03 | Fiber ring
RO-05 | AMM-U-1971 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0705 | 36.1268 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R03 | Fiber ring
RO-05 | AMM-U-1972 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0705 | 36.1305 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R03 | Fiber ring
RO-05 | AMM-U-1973 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0741 | 35.8323 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R01 | Fiber ring
RO-05 | AMM-U-1974 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0741 | 35.8361 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R01 | Fiber ring
RO-05 | AMM-U-1975 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0733 | 35.8408 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R01 | Fiber ring
RO-05 | AMM-U-1976 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0733 | 35.8456 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R02 | Fiber ring
RO-05 | AMM-U-1977 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0741 | 35.8503 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R03 | Fiber ring
RO-05 | AMM-U-1978 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0741 | 35.855 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R03 | Fiber ring
RO-05 | AMM-U-1987 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0741 | 36.0875 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R01 | Fiber ring
RO-05 | AMM-U-1988 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0749 | 36.0913 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R01 | Fiber ring
RO-05 | AMM-U-1989 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0741 | 36.0951 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R02 | Fiber ring
RO-05 | AMM-U-1990 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0745 | 36.1003 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R02 | Fiber ring
RO-05 | AMM-U-1991 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0741 | 36.1055 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R02 | Fiber ring
RO-05 | AMM-U-1992 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0733 | 36.1102 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R05 | Fiber ring
RO-05 | AMM-U-1993 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0741 | 36.114 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R04 | Fiber ring
RO-05 | AMM-U-1994 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0741 | 36.1197 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R03 | Fiber ring
RO-05 | AMM-U-1995 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0749 | 36.1244 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R03 | Fiber ring
RO-05 | AMM-U-1996 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0733 | 36.1291 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R03 | Fiber ring
RO-05 | AMM-U-1997 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0776 | 35.829 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R07 | Fiber ring
RO-05 | AMM-U-1998 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0776 | 35.8347 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R07 | Fiber ring
RO-05 | AMM-U-1999 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0776 | 35.8385 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R07 | Fiber ring
RO-05 | AMM-U-2000 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0776 | 35.8432 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R01 | Fiber ring
RO-05 | AMM-U-2001 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0776 | 35.8479 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R03 | Fiber ring
RO-05 | AMM-U-2002 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0768 | 35.8526 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R03 | Fiber ring
RO-05 | AMM-U-2003 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0776 | 35.8574 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R04 | Fiber ring
RO-05 | AMM-U-2011 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0776 | 36.0852 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R01 | Fiber ring
RO-05 | AMM-U-2012 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0776 | 36.0889 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R01 | Fiber ring
RO-05 | AMM-U-2013 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0776 | 36.0937 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R01 | Fiber ring
RO-05 | AMM-U-2014 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0784 | 36.0984 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R02 | Fiber ring
RO-05 | AMM-U-2015 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.078 | 36.1026 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R03 | Fiber ring
RO-05 | AMM-U-2016 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0772 | 36.1083 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R05 | Fiber ring
RO-05 | AMM-U-2017 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0776 | 36.1126 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R04 | Fiber ring
RO-05 | AMM-U-2018 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0776 | 36.1173 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R04 | Fiber ring
RO-05 | AMM-U-2019 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0776 | 36.122 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R04 | Fiber ring
RO-05 | AMM-U-2020 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0768 | 36.1268 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R03 | Fiber ring
RO-05 | AMM-U-2021 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0803 | 35.8314 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R07 | Fiber ring
RO-05 | AMM-U-2022 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0811 | 35.8361 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R06 | Fiber ring
RO-05 | AMM-U-2023 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0811 | 35.8408 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R06 | Fiber ring
RO-05 | AMM-U-2024 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0803 | 35.8456 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R05 | Fiber ring
RO-05 | AMM-U-2025 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0803 | 35.8503 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R04 | Fiber ring
RO-05 | AMM-U-2026 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0811 | 35.855 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R04 | Fiber ring
RO-05 | AMM-U-2033 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0815 | 36.0823 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R05 | Fiber ring
RO-05 | AMM-U-2034 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0819 | 36.0866 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R05 | Fiber ring
RO-05 | AMM-U-2035 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0811 | 36.0904 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R05 | Fiber ring
RO-05 | AMM-U-2036 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0811 | 36.0951 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R01 | Fiber ring
RO-05 | AMM-U-2037 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0811 | 36.1017 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R03 | Fiber ring
RO-05 | AMM-U-2038 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0811 | 36.1045 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R03 | Fiber ring
RO-05 | AMM-U-2039 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0811 | 36.1112 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R01 | Fiber ring
RO-05 | AMM-U-2040 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0811 | 36.114 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R04 | Fiber ring
RO-05 | AMM-U-2041 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0811 | 36.1206 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R04 | Fiber ring
RO-05 | AMM-U-2042 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0811 | 36.1253 | 30 | 3 | HUB-AMM-63 | HUB-AMM-63-R04 | Fiber ring
RO-05 | AMM-U-2044 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0846 | 35.8337 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R06 | Fiber ring
RO-05 | AMM-U-2045 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0846 | 35.8385 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R06 | Fiber ring
RO-05 | AMM-U-2046 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0846 | 35.8432 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R05 | Fiber ring
RO-05 | AMM-U-2047 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0846 | 35.8479 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R05 | Fiber ring
RO-05 | AMM-U-2048 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0838 | 35.8526 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R04 | Fiber ring
RO-05 | AMM-U-2051 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0838 | 36.0606 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R01 | Fiber ring
RO-05 | AMM-U-2052 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0846 | 36.0644 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R01 | Fiber ring
RO-05 | AMM-U-2053 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0846 | 36.071 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R02 | Fiber ring
RO-05 | AMM-U-2054 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0846 | 36.0738 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R02 | Fiber ring
RO-05 | AMM-U-2055 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0855 | 36.0795 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R02 | Fiber ring
RO-05 | AMM-U-2056 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0846 | 36.0842 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R05 | Fiber ring
RO-05 | AMM-U-2057 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0846 | 36.0889 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R05 | Fiber ring
RO-05 | AMM-U-2058 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0846 | 36.0937 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R04 | Fiber ring
RO-05 | AMM-U-2059 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0846 | 36.0975 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R03 | Fiber ring
RO-05 | AMM-U-2060 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0846 | 36.1031 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R03 | Fiber ring
RO-05 | AMM-U-2061 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0846 | 36.1069 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R01 | Fiber ring
RO-05 | AMM-U-2062 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0846 | 36.1126 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R01 | Fiber ring
RO-05 | AMM-U-2063 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0846 | 36.1173 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R02 | Fiber ring
RO-05 | AMM-U-2064 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.085 | 36.1225 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R02 | Fiber ring
RO-05 | AMM-U-2066 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.089 | 35.8361 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R06 | Fiber ring
RO-05 | AMM-U-2067 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0882 | 35.8408 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R05 | Fiber ring
RO-05 | AMM-U-2068 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0882 | 35.8456 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R05 | Fiber ring
RO-05 | AMM-U-2069 | U | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0882 | 35.8503 | 30 | 3 | HUB-AMM-86 | HUB-AMM-86-R05 | Fiber ring
RO-05 | AMM-U-2071 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0877 | 36.0577 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R01 | Fiber ring
RO-05 | AMM-U-2072 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0873 | 36.063 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R01 | Fiber ring
RO-05 | AMM-U-2073 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0882 | 36.0686 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R02 | Fiber ring
RO-05 | AMM-U-2074 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0882 | 36.0733 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R02 | Fiber ring
RO-05 | AMM-U-2075 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0886 | 36.0776 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R03 | Fiber ring
RO-05 | AMM-U-2076 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.089 | 36.0819 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R03 | Fiber ring
RO-05 | AMM-U-2077 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0882 | 36.0856 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R05 | Fiber ring
RO-05 | AMM-U-2078 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.089 | 36.0913 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R04 | Fiber ring
RO-05 | AMM-U-2079 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.089 | 36.096 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R04 | Fiber ring
RO-05 | AMM-U-2080 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0882 | 36.1008 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R03 | Fiber ring
RO-05 | AMM-U-2081 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0882 | 36.1055 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R01 | Fiber ring
RO-05 | AMM-U-2082 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0882 | 36.1093 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R01 | Fiber ring
RO-05 | AMM-U-2083 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0882 | 36.1149 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R01 | Fiber ring
RO-05 | AMM-U-2084 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0882 | 36.1206 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R02 | Fiber ring
RO-05 | AMM-U-2085 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0873 | 36.1244 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R02 | Fiber ring
RO-05 | AMM-U-2086 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0909 | 36.0559 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R01 | Fiber ring
RO-05 | AMM-U-2087 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0917 | 36.0596 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R01 | Fiber ring
RO-05 | AMM-U-2088 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0917 | 36.0663 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R01 | Fiber ring
RO-05 | AMM-U-2089 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0913 | 36.0705 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R02 | Fiber ring
RO-05 | AMM-U-2090 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0921 | 36.0752 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R02 | Fiber ring
RO-05 | AMM-U-2091 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0913 | 36.079 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R03 | Fiber ring
RO-05 | AMM-U-2092 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0913 | 36.0837 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R03 | Fiber ring
RO-05 | AMM-U-2093 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0917 | 36.088 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R04 | Fiber ring
RO-05 | AMM-U-2094 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0917 | 36.0937 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R04 | Fiber ring
RO-05 | AMM-U-2095 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0917 | 36.0984 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R03 | Fiber ring
RO-05 | AMM-U-2096 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0913 | 36.1026 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R01 | Fiber ring
RO-05 | AMM-U-2097 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0917 | 36.1069 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R05 | Fiber ring
RO-05 | AMM-U-2098 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0917 | 36.1135 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R01 | Fiber ring
RO-05 | AMM-U-2099 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0909 | 36.1173 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R02 | Fiber ring
RO-05 | AMM-U-2100 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0913 | 36.1225 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R02 | Fiber ring
RO-05 | AMM-U-2101 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0909 | 36.1268 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R02 | Fiber ring
RO-05 | AMM-U-2102 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0952 | 36.0573 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R06 | Fiber ring
RO-05 | AMM-U-2103 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0952 | 36.062 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R06 | Fiber ring
RO-05 | AMM-U-2104 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0952 | 36.0686 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R06 | Fiber ring
RO-05 | AMM-U-2105 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0952 | 36.0733 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R01 | Fiber ring
RO-05 | AMM-U-2106 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0944 | 36.0771 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R03 | Fiber ring
RO-05 | AMM-U-2107 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0948 | 36.0814 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R03 | Fiber ring
RO-05 | AMM-U-2108 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0944 | 36.0866 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R03 | Fiber ring
RO-05 | AMM-U-2109 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0952 | 36.0904 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R04 | Fiber ring
RO-05 | AMM-U-2110 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0944 | 36.096 | 30 | 3 | HUB-AMM-85 | HUB-AMM-85-R04 | Fiber ring
RO-05 | AMM-U-2111 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0944 | 36.1008 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R05 | Fiber ring
RO-05 | AMM-U-2112 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0944 | 36.1055 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R05 | Fiber ring
RO-05 | AMM-U-2113 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0952 | 36.1093 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R04 | Fiber ring
RO-05 | AMM-U-2114 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0952 | 36.1149 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R03 | Fiber ring
RO-05 | AMM-U-2115 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0952 | 36.1197 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R03 | Fiber ring
RO-05 | AMM-U-2116 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0952 | 36.1244 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R03 | Fiber ring
RO-05 | AMM-U-2117 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0987 | 36.0596 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R06 | Fiber ring
RO-05 | AMM-U-2118 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0987 | 36.0663 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R06 | Fiber ring
RO-05 | AMM-U-2119 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0987 | 36.0705 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R05 | Fiber ring
RO-05 | AMM-U-2120 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0979 | 36.0748 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R04 | Fiber ring
RO-05 | AMM-U-2121 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0979 | 36.0795 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R04 | Fiber ring
RO-05 | AMM-U-2122 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0979 | 36.0842 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R04 | Fiber ring
RO-05 | AMM-U-2123 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0979 | 36.0889 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R04 | Fiber ring
RO-05 | AMM-U-2125 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0987 | 36.0984 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R05 | Fiber ring
RO-05 | AMM-U-2126 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0987 | 36.1031 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R04 | Fiber ring
RO-05 | AMM-U-2127 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0987 | 36.1078 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R04 | Fiber ring
RO-05 | AMM-U-2128 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0987 | 36.1126 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R03 | Fiber ring
RO-05 | AMM-U-2129 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0987 | 36.1173 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R03 | Fiber ring
RO-05 | AMM-U-2130 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0987 | 36.122 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R03 | Fiber ring
RO-05 | AMM-U-2131 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1023 | 36.063 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R05 | Fiber ring
RO-05 | AMM-U-2132 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1023 | 36.0686 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R05 | Fiber ring
RO-05 | AMM-U-2133 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1027 | 36.0729 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R05 | Fiber ring
RO-05 | AMM-U-2134 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1023 | 36.0762 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R04 | Fiber ring
RO-05 | AMM-U-2135 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1018 | 36.0814 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R04 | Fiber ring
RO-05 | AMM-U-2139 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1014 | 36.1008 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R04 | Fiber ring
RO-05 | AMM-U-2140 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1023 | 36.1055 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R04 | Fiber ring
RO-05 | AMM-U-2141 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1023 | 36.1102 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R04 | Fiber ring
RO-05 | AMM-U-2142 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1023 | 36.1149 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R03 | Fiber ring
RO-05 | AMM-U-2143 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1058 | 36.0663 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R05 | Fiber ring
RO-05 | AMM-U-2144 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1058 | 36.0691 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R05 | Fiber ring
RO-05 | AMM-U-2145 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.105 | 36.0748 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R04 | Fiber ring
RO-05 | AMM-U-2152 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1058 | 36.1069 | 30 | 3 | HUB-AMM-42 | HUB-AMM-42-R04 | Fiber ring
RO-05 | AMM-U-2154 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1093 | 36.0733 | 30 | 3 | HUB-AMM-77 | HUB-AMM-77-R05 | Fiber ring
RO-05 | DEA-SU-0001 | SU | Monopole / greenfield | Dead Sea | Madaba | 31.6887 | 35.5938 | 32 | 3 | HUB-DEA-01 | HUB-DEA-01-R01 | Fiber ring
RO-05 | DEA-SU-0002 | SU | Monopole / greenfield | Dead Sea | Madaba | 31.6938 | 35.5972 | 32 | 3 | HUB-DEA-01 | HUB-DEA-01-R01 | Fiber ring
RO-05 | DEA-SU-0003 | SU | Monopole / greenfield | Dead Sea | Madaba | 31.6983 | 35.5931 | 32 | 3 | HUB-DEA-01 | HUB-DEA-01-R01 | Fiber ring
RO-05 | DEA-SU-0004 | SU | Monopole / greenfield | Dead Sea | Madaba | 31.7034 | 35.5897 | 32 | 3 | HUB-DEA-01 | HUB-DEA-01-R01 | Fiber ring
RO-05 | DEA-SU-0005 | SU | Monopole / greenfield | Dead Sea | Madaba | 31.704 | 35.5972 | 32 | 3 | HUB-DEA-01 | HUB-DEA-01-R02 | Fiber ring
RO-05 | DEA-SU-0006 | SU | Monopole / greenfield | Dead Sea | Madaba | 31.7091 | 35.5938 | 32 | 3 | HUB-DEA-01 | HUB-DEA-01-R01 | Fiber ring
RO-05 | DEA-SU-0007 | SU | Monopole / greenfield | Dead Sea | Madaba | 31.7091 | 35.6007 | 32 | 3 | HUB-DEA-01 | HUB-DEA-01-R02 | Fiber ring
RO-05 | DEA-SU-0008 | SU | Monopole / greenfield | Dead Sea | Balqa | 31.7142 | 35.5904 | 32 | 3 | HUB-DEA-01 | HUB-DEA-01-R01 | Fiber ring
RO-05 | DEA-SU-0009 | SU | Monopole / greenfield | Dead Sea | Balqa | 31.7142 | 35.5972 | 32 | 3 | HUB-DEA-01 | HUB-DEA-01-R02 | Fiber ring
RO-05 | DEA-SU-0010 | SU | Monopole / greenfield | Dead Sea | Balqa | 31.7193 | 35.5938 | 32 | 3 | HUB-DEA-01 | HUB-DEA-01-R01 | Fiber ring
RO-05 | DEA-SU-0011 | SU | Monopole / greenfield | Dead Sea | Balqa | 31.7193 | 35.6007 | 32 | 3 | HUB-DEA-01 | HUB-DEA-01-R02 | Fiber ring
RO-05 | DEA-SU-0012 | SU | Monopole / greenfield | Dead Sea | Balqa | 31.7244 | 35.5972 | 32 | 3 | HUB-DEA-01 | HUB-DEA-01-R02 | Fiber ring
RO-05 | DEA-SU-0013 | SU | Monopole / greenfield | Dead Sea | Balqa | 31.7232 | 35.6027 | 32 | 3 | HUB-DEA-01 | HUB-DEA-01-R02 | Fiber ring
RO-05 | DEA-SU-0014 | SU | Monopole / greenfield | Dead Sea | Balqa | 31.7294 | 35.5938 | 32 | 3 | HUB-DEA-01 | HUB-DEA-01-R03 | Fiber ring
RO-05 | DEA-SU-0015 | SU | Monopole / greenfield | Dead Sea | Balqa | 31.7294 | 35.6007 | 32 | 3 | HUB-DEA-01 | HUB-DEA-01-R03 | Fiber ring
RO-05 | DEA-SU-0016 | SU | Monopole / greenfield | Dead Sea | Balqa | 31.7345 | 35.5972 | 32 | 3 | HUB-DEA-01 | HUB-DEA-01-R03 | Fiber ring
RO-05 | DEA-SU-0017 | SU | Monopole / greenfield | Dead Sea | Balqa | 31.7345 | 35.6041 | 32 | 3 | HUB-DEA-01 | HUB-DEA-01-R03 | Fiber ring
RO-05 | DEA-SU-0018 | SU | Monopole / greenfield | Dead Sea | Balqa | 31.7396 | 35.6007 | 32 | 3 | HUB-DEA-01 | HUB-DEA-01-R03 | Fiber ring
RO-05 | DEA-SU-0019 | SU | Monopole / greenfield | Dead Sea | Balqa | 31.7447 | 35.5972 | 32 | 3 | HUB-DEA-01 | HUB-DEA-01-R03 | Fiber ring
RO-05 | HWY-HW-0034 | HW | Lattice tower | Highway | Madaba | 31.6575 | 35.5926 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0035 | HW | Lattice tower | Highway | Madaba | 31.5962 | 35.5818 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0036 | HW | Lattice tower | Highway | Madaba | 31.5298 | 35.5818 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0037 | HW | Lattice tower | Highway | Madaba | 31.4681 | 35.5832 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0038 | HW | Lattice tower | Highway | Karak | 31.4061 | 35.5684 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0039 | HW | Lattice tower | Highway | Karak | 31.344 | 35.5537 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0040 | HW | Lattice tower | Highway | Karak | 31.282 | 35.5389 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0041 | HW | Lattice tower | Highway | Karak | 31.2201 | 35.5237 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0042 | HW | Lattice tower | Highway | Karak | 31.1582 | 35.5046 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0043 | HW | Lattice tower | Highway | Karak | 31.0963 | 35.4891 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0044 | HW | Lattice tower | Highway | Karak | 30.9766 | 35.4433 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0045 | HW | Lattice tower | Highway | Karak | 30.9181 | 35.4153 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0046 | HW | Lattice tower | Highway | Tafilah | 30.8549 | 35.3919 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0047 | HW | Lattice tower | Highway | Tafilah | 30.7981 | 35.3721 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0048 | HW | Lattice tower | Highway | Tafilah | 30.7381 | 35.3449 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0049 | HW | Lattice tower | Highway | Aqaba | 30.6775 | 35.324 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0050 | HW | Lattice tower | Highway | Aqaba | 30.6158 | 35.3075 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0051 | HW | Lattice tower | Highway | Aqaba | 30.5541 | 35.2911 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0052 | HW | Lattice tower | Highway | Aqaba | 30.4924 | 35.2783 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0053 | HW | Lattice tower | Highway | Aqaba | 30.4307 | 35.2582 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0054 | HW | Lattice tower | Highway | Aqaba | 30.3685 | 35.2451 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0055 | HW | Lattice tower | Highway | Aqaba | 30.3026 | 35.2353 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0056 | HW | Lattice tower | Highway | Aqaba | 30.243 | 35.2291 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0057 | HW | Lattice tower | Highway | Aqaba | 30.1803 | 35.2157 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0058 | HW | Lattice tower | Highway | Aqaba | 30.116 | 35.2077 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0059 | HW | Lattice tower | Highway | Aqaba | 30.0559 | 35.1942 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0060 | HW | Lattice tower | Highway | Aqaba | 29.9959 | 35.1707 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0061 | HW | Lattice tower | Highway | Aqaba | 29.936 | 35.1471 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0062 | HW | Lattice tower | Highway | Aqaba | 29.876 | 35.1199 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0063 | HW | Lattice tower | Highway | Aqaba | 29.8129 | 35.0963 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0064 | HW | Lattice tower | Highway | Aqaba | 29.7566 | 35.0747 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | HWY-HW-0065 | HW | Lattice tower | Highway | Aqaba | 29.6974 | 35.0488 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-05 | IRB-SU-0618 | SU | Monopole / greenfield | Irbid | Irbid | 32.5338 | 35.9119 | 32 | 3 | HUB-IRB-03 | HUB-IRB-03-R02 | Fiber ring
RO-05 | IRB-SU-0619 | SU | Monopole / greenfield | Irbid | Irbid | 32.5338 | 35.9188 | 32 | 3 | HUB-IRB-03 | HUB-IRB-03-R02 | Fiber ring
RO-05 | IRB-SU-0631 | SU | Monopole / greenfield | Irbid | Irbid | 32.5395 | 35.916 | 32 | 3 | HUB-IRB-03 | HUB-IRB-03-R02 | Fiber ring
RO-05 | IRB-SU-0632 | SU | Monopole / greenfield | Irbid | Irbid | 32.5389 | 35.9235 | 32 | 3 | HUB-IRB-03 | HUB-IRB-03-R02 | Fiber ring
RO-05 | IRB-SU-0646 | SU | Monopole / greenfield | Irbid | Irbid | 32.544 | 35.9119 | 32 | 3 | HUB-IRB-03 | HUB-IRB-03-R03 | Fiber ring
RO-05 | IRB-SU-0647 | SU | Monopole / greenfield | Irbid | Irbid | 32.544 | 35.9201 | 32 | 3 | HUB-IRB-03 | HUB-IRB-03-R03 | Fiber ring
RO-05 | IRB-SU-0659 | SU | Monopole / greenfield | Irbid | Irbid | 32.5479 | 35.9099 | 32 | 3 | HUB-IRB-03 | HUB-IRB-03-R03 | Fiber ring
RO-05 | IRB-U-0163 | U | Monopole / greenfield | Irbid | Irbid | 32.5287 | 35.8999 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R01 | Fiber ring
RO-05 | IRB-U-0183 | U | Monopole / greenfield | Irbid | Irbid | 32.5322 | 35.8975 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R01 | Fiber ring
RO-05 | IRB-U-0184 | U | Monopole / greenfield | Irbid | Irbid | 32.5322 | 35.9023 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R02 | Fiber ring
RO-05 | IRB-U-0204 | U | Monopole / greenfield | Irbid | Irbid | 32.5358 | 35.8952 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R01 | Fiber ring
RO-05 | IRB-U-0205 | U | Monopole / greenfield | Irbid | Irbid | 32.5358 | 35.8999 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R01 | Fiber ring
RO-05 | IRB-U-0206 | U | Monopole / greenfield | Irbid | Irbid | 32.5358 | 35.9046 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R02 | Fiber ring
RO-05 | IRB-U-0226 | U | Monopole / greenfield | Irbid | Irbid | 32.5393 | 35.8928 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R01 | Fiber ring
RO-05 | IRB-U-0227 | U | Monopole / greenfield | Irbid | Irbid | 32.5385 | 35.8975 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R01 | Fiber ring
RO-05 | IRB-U-0228 | U | Monopole / greenfield | Irbid | Irbid | 32.5393 | 35.9023 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R01 | Fiber ring
RO-05 | IRB-U-0229 | U | Monopole / greenfield | Irbid | Irbid | 32.5393 | 35.9061 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R02 | Fiber ring
RO-05 | IRB-U-0246 | U | Monopole / greenfield | Irbid | Irbid | 32.5428 | 35.8857 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R05 | Fiber ring
RO-05 | IRB-U-0247 | U | Monopole / greenfield | Irbid | Irbid | 32.5428 | 35.8905 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R05 | Fiber ring
RO-05 | IRB-U-0248 | U | Monopole / greenfield | Irbid | Irbid | 32.5428 | 35.8942 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R05 | Fiber ring
RO-05 | IRB-U-0249 | U | Monopole / greenfield | Irbid | Irbid | 32.5428 | 35.899 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R05 | Fiber ring
RO-05 | IRB-U-0250 | U | Monopole / greenfield | Irbid | Irbid | 32.5428 | 35.9046 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R01 | Fiber ring
RO-05 | IRB-U-0251 | U | Monopole / greenfield | Irbid | Irbid | 32.5428 | 35.9084 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R03 | Fiber ring
RO-05 | IRB-U-0268 | U | Monopole / greenfield | Irbid | Irbid | 32.5463 | 35.8881 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R05 | Fiber ring
RO-05 | IRB-U-0269 | U | Monopole / greenfield | Irbid | Irbid | 32.5463 | 35.8928 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R05 | Fiber ring
RO-05 | IRB-U-0270 | U | Monopole / greenfield | Irbid | Irbid | 32.5463 | 35.8975 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R04 | Fiber ring
RO-05 | IRB-U-0271 | U | Monopole / greenfield | Irbid | Irbid | 32.5463 | 35.9013 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R04 | Fiber ring
RO-05 | IRB-U-0272 | U | Monopole / greenfield | Irbid | Irbid | 32.5463 | 35.907 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R03 | Fiber ring
RO-05 | IRB-U-0291 | U | Monopole / greenfield | Irbid | Irbid | 32.5491 | 35.8952 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R04 | Fiber ring
RO-05 | IRB-U-0292 | U | Monopole / greenfield | Irbid | Irbid | 32.5491 | 35.8999 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R04 | Fiber ring
RO-05 | IRB-U-0293 | U | Monopole / greenfield | Irbid | Irbid | 32.5499 | 35.9046 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R03 | Fiber ring
RO-05 | IRB-U-0314 | U | Monopole / greenfield | Irbid | Irbid | 32.5534 | 35.8975 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R04 | Fiber ring
RO-05 | IRB-U-0315 | U | Monopole / greenfield | Irbid | Irbid | 32.5526 | 35.9023 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R04 | Fiber ring
RO-05 | IRB-U-0316 | U | Monopole / greenfield | Irbid | Irbid | 32.5526 | 35.907 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R03 | Fiber ring
RO-05 | IRB-U-0339 | U | Monopole / greenfield | Irbid | Irbid | 32.5577 | 35.9046 | 30 | 3 | HUB-IRB-03 | HUB-IRB-03-R04 | Fiber ring
RO-05 | WAD-SU-0039 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.304 | 35.4641 | 32 | 3 | HUB-WAD-02 | HUB-WAD-02-R01 | Fiber ring
RO-05 | WAD-SU-0040 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3028 | 35.4696 | 32 | 3 | HUB-WAD-02 | HUB-WAD-02-R01 | Fiber ring
RO-05 | WAD-SU-0041 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.304 | 35.475 | 32 | 3 | HUB-WAD-02 | HUB-WAD-02-R02 | Fiber ring
RO-05 | WAD-SU-0042 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3028 | 35.4832 | 32 | 3 | HUB-WAD-02 | HUB-WAD-02-R02 | Fiber ring
RO-05 | WAD-SU-0043 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.304 | 35.4969 | 32 | 3 | HUB-WAD-01 | HUB-WAD-01-R02 | Fiber ring
RO-05 | WAD-SU-0044 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3091 | 35.4607 | 32 | 3 | HUB-WAD-02 | HUB-WAD-02-R01 | Fiber ring
RO-05 | WAD-SU-0045 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3079 | 35.4662 | 32 | 3 | HUB-WAD-02 | HUB-WAD-02-R01 | Fiber ring
RO-05 | WAD-SU-0046 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3091 | 35.4948 | 32 | 3 | HUB-WAD-01 | HUB-WAD-01-R01 | Fiber ring
RO-05 | WAD-SU-0047 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3091 | 35.4989 | 32 | 3 | HUB-WAD-01 | HUB-WAD-01-R02 | Fiber ring
RO-05 | WAD-SU-0048 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.313 | 35.4627 | 32 | 3 | HUB-WAD-02 | HUB-WAD-02-R01 | Fiber ring
RO-05 | WAD-SU-0049 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3148 | 35.5044 | 32 | 3 | HUB-WAD-01 | HUB-WAD-01-R02 | Fiber ring
RO-05 | WAD-SU-0050 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3193 | 35.4511 | 32 | 3 | HUB-WAD-02 | HUB-WAD-02-R05 | Fiber ring
RO-05 | WAD-SU-0051 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3187 | 35.501 | 32 | 3 | HUB-WAD-01 | HUB-WAD-01-R02 | Fiber ring
RO-05 | WAD-SU-0052 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3205 | 35.5071 | 32 | 3 | HUB-WAD-01 | HUB-WAD-01-R02 | Fiber ring
RO-05 | WAD-SU-0053 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3232 | 35.4969 | 32 | 3 | HUB-WAD-01 | HUB-WAD-01-R02 | Fiber ring
RO-05 | WAD-SU-0054 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3255 | 35.5037 | 32 | 3 | HUB-WAD-01 | HUB-WAD-01-R03 | Fiber ring
RO-05 | WAD-SU-0055 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3306 | 35.4935 | 32 | 3 | HUB-WAD-01 | HUB-WAD-01-R03 | Fiber ring
RO-05 | WAD-SU-0056 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3295 | 35.5017 | 32 | 3 | HUB-WAD-01 | HUB-WAD-01-R03 | Fiber ring
RO-05 | WAD-SU-0057 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3295 | 35.5085 | 32 | 3 | HUB-WAD-01 | HUB-WAD-01-R03 | Fiber ring
RO-05 | WAD-SU-0058 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3346 | 35.4914 | 32 | 3 | HUB-WAD-01 | HUB-WAD-01-R03 | Fiber ring
RO-05 | WAD-SU-0059 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3357 | 35.4969 | 32 | 3 | HUB-WAD-01 | HUB-WAD-01-R03 | Fiber ring
RO-05 | WAD-SU-0060 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3357 | 35.5037 | 32 | 3 | HUB-WAD-01 | HUB-WAD-01-R03 | Fiber ring
RO-05 | WAD-SU-0061 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3408 | 35.4593 | 32 | 3 | HUB-WAD-02 | HUB-WAD-02-R05 | Fiber ring
RO-05 | WAD-SU-0062 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3396 | 35.4744 | 32 | 3 | HUB-WAD-01 | HUB-WAD-01-R04 | Fiber ring
RO-05 | WAD-SU-0063 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3408 | 35.4798 | 32 | 3 | HUB-WAD-01 | HUB-WAD-01-R04 | Fiber ring
RO-05 | WAD-SU-0064 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3391 | 35.4873 | 32 | 3 | HUB-WAD-01 | HUB-WAD-01-R04 | Fiber ring
RO-05 | WAD-SU-0065 | SU | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3436 | 35.4901 | 32 | 3 | HUB-WAD-01 | HUB-WAD-01-R04 | Fiber ring
RO-05 | WAD-U-0001 | U | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3118 | 35.4713 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R02 | Fiber ring
RO-05 | WAD-U-0002 | U | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.311 | 35.4769 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R02 | Fiber ring
RO-05 | WAD-U-0003 | U | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.311 | 35.4817 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R02 | Fiber ring
RO-05 | WAD-U-0004 | U | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3118 | 35.4873 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R03 | Fiber ring
RO-05 | WAD-U-0005 | U | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3146 | 35.4698 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R01 | Fiber ring
RO-05 | WAD-U-0006 | U | Rooftop | Wadi Musa / Petra | Ma'an | 30.3146 | 35.4746 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R02 | Fiber ring
RO-05 | WAD-U-0007 | U | Rooftop | Wadi Musa / Petra | Ma'an | 30.3154 | 35.4783 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R03 | Fiber ring
RO-05 | WAD-U-0008 | U | Rooftop | Wadi Musa / Petra | Ma'an | 30.3154 | 35.485 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R03 | Fiber ring
RO-05 | WAD-U-0009 | U | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3154 | 35.4897 | 30 | 3 | HUB-WAD-01 | HUB-WAD-01-R01 | Fiber ring
RO-05 | WAD-U-0010 | U | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3154 | 35.4935 | 30 | 3 | HUB-WAD-01 | HUB-WAD-01-R01 | Fiber ring
RO-05 | WAD-U-0011 | U | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3181 | 35.4675 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R05 | Fiber ring
RO-05 | WAD-U-0012 | U | Rooftop | Wadi Musa / Petra | Ma'an | 30.3181 | 35.4722 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R01 | Fiber ring
RO-05 | WAD-U-0013 | U | Rooftop | Wadi Musa / Petra | Ma'an | 30.3185 | 35.4765 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R03 | Fiber ring
RO-05 | WAD-U-0014 | U | Rooftop | Wadi Musa / Petra | Ma'an | 30.3189 | 35.4826 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R03 | Fiber ring
RO-05 | WAD-U-0015 | U | Rooftop | Wadi Musa / Petra | Ma'an | 30.3189 | 35.4873 | 30 | 3 | HUB-WAD-01 | HUB-WAD-01-R01 | Fiber ring
RO-05 | WAD-U-0016 | U | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3189 | 35.492 | 30 | 3 | HUB-WAD-01 | HUB-WAD-01-R01 | Fiber ring
RO-05 | WAD-U-0017 | U | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3228 | 35.4656 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R05 | Fiber ring
RO-05 | WAD-U-0018 | U | Rooftop | Wadi Musa / Petra | Ma'an | 30.3224 | 35.4708 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R05 | Fiber ring
RO-05 | WAD-U-0019 | U | Rooftop | Wadi Musa / Petra | Ma'an | 30.3216 | 35.4746 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R04 | Fiber ring
RO-05 | WAD-U-0020 | U | Rooftop | Wadi Musa / Petra | Ma'an | 30.3224 | 35.4802 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R03 | Fiber ring
RO-05 | WAD-U-0021 | U | Rooftop | Wadi Musa / Petra | Ma'an | 30.3216 | 35.484 | 30 | 3 | HUB-WAD-01 | HUB-WAD-01-R01 | Fiber ring
RO-05 | WAD-U-0022 | U | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3216 | 35.4888 | 30 | 3 | HUB-WAD-01 | HUB-WAD-01-R01 | Fiber ring
RO-05 | WAD-U-0023 | U | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.322 | 35.493 | 30 | 3 | HUB-WAD-01 | HUB-WAD-01-R02 | Fiber ring
RO-05 | WAD-U-0024 | U | Rooftop | Wadi Musa / Petra | Ma'an | 30.3259 | 35.4675 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R05 | Fiber ring
RO-05 | WAD-U-0025 | U | Rooftop | Wadi Musa / Petra | Ma'an | 30.3264 | 35.4727 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R04 | Fiber ring
RO-05 | WAD-U-0026 | U | Rooftop | Wadi Musa / Petra | Ma'an | 30.3251 | 35.4769 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R04 | Fiber ring
RO-05 | WAD-U-0027 | U | Rooftop | Wadi Musa / Petra | Ma'an | 30.3264 | 35.4821 | 30 | 3 | HUB-WAD-01 | HUB-WAD-01-R05 | Fiber ring
RO-05 | WAD-U-0028 | U | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3259 | 35.4873 | 30 | 3 | HUB-WAD-01 | HUB-WAD-01-R05 | Fiber ring
RO-05 | WAD-U-0029 | U | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3251 | 35.4911 | 30 | 3 | HUB-WAD-01 | HUB-WAD-01-R01 | Fiber ring
RO-05 | WAD-U-0030 | U | Rooftop | Wadi Musa / Petra | Ma'an | 30.3303 | 35.4698 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R04 | Fiber ring
RO-05 | WAD-U-0031 | U | Rooftop | Wadi Musa / Petra | Ma'an | 30.3303 | 35.4746 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R04 | Fiber ring
RO-05 | WAD-U-0032 | U | Rooftop | Wadi Musa / Petra | Ma'an | 30.3295 | 35.4802 | 30 | 3 | HUB-WAD-01 | HUB-WAD-01-R05 | Fiber ring
RO-05 | WAD-U-0033 | U | Rooftop | Wadi Musa / Petra | Ma'an | 30.3295 | 35.485 | 30 | 3 | HUB-WAD-01 | HUB-WAD-01-R05 | Fiber ring
RO-05 | WAD-U-0034 | U | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3295 | 35.4897 | 30 | 3 | HUB-WAD-01 | HUB-WAD-01-R04 | Fiber ring
RO-05 | WAD-U-0035 | U | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.333 | 35.4731 | 30 | 3 | HUB-WAD-02 | HUB-WAD-02-R04 | Fiber ring
RO-05 | WAD-U-0036 | U | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.3338 | 35.4769 | 30 | 3 | HUB-WAD-01 | HUB-WAD-01-R05 | Fiber ring
RO-05 | WAD-U-0037 | U | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.333 | 35.4826 | 30 | 3 | HUB-WAD-01 | HUB-WAD-01-R04 | Fiber ring
RO-05 | WAD-U-0038 | U | Monopole / greenfield | Wadi Musa / Petra | Ma'an | 30.333 | 35.4873 | 30 | 3 | HUB-WAD-01 | HUB-WAD-01-R04 | Fiber ring
RO-06 | AMM-SU-2653 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9127 | 36.002 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R01 | Fiber ring
RO-06 | AMM-SU-2654 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9121 | 36.0095 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R01 | Fiber ring
RO-06 | AMM-SU-2655 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9127 | 36.0143 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R02 | Fiber ring
RO-06 | AMM-SU-2673 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9172 | 35.9979 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R01 | Fiber ring
RO-06 | AMM-SU-2674 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9178 | 36.0041 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R01 | Fiber ring
RO-06 | AMM-SU-2675 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9166 | 36.0123 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R02 | Fiber ring
RO-06 | AMM-SU-2676 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9178 | 36.0177 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R02 | Fiber ring
RO-06 | AMM-SU-2677 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9178 | 36.0273 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R02 | Fiber ring
RO-06 | AMM-SU-2691 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9217 | 35.9952 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R01 | Fiber ring
RO-06 | AMM-SU-2692 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9241 | 36.002 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R01 | Fiber ring
RO-06 | AMM-SU-2693 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9217 | 36.0089 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R02 | Fiber ring
RO-06 | AMM-SU-2694 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9217 | 36.0157 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R02 | Fiber ring
RO-06 | AMM-SU-2695 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9229 | 36.0211 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R02 | Fiber ring
RO-06 | AMM-SU-2708 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9268 | 36.0055 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R01 | Fiber ring
RO-06 | AMM-SU-2709 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.928 | 36.0109 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R03 | Fiber ring
RO-06 | AMM-SU-2710 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9286 | 36.0184 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R03 | Fiber ring
RO-06 | AMM-SU-2711 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9286 | 36.0252 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R03 | Fiber ring
RO-06 | AMM-SU-2724 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9331 | 36.0075 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R03 | Fiber ring
RO-06 | AMM-SU-2725 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9331 | 36.0143 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R03 | Fiber ring
RO-06 | AMM-SU-2735 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.937 | 36.0123 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R03 | Fiber ring
RO-06 | AMM-SU-2736 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9388 | 36.0184 | 32 | 3 | HUB-AMM-81 | HUB-AMM-81-R03 | Fiber ring
RO-06 | AMM-SU-2929 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0157 | 35.9679 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R02 | Fiber ring
RO-06 | AMM-SU-2930 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0151 | 35.974 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R02 | Fiber ring
RO-06 | AMM-SU-2931 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0157 | 35.9816 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R02 | Fiber ring
RO-06 | AMM-SU-2951 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0196 | 35.9563 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R05 | Fiber ring
RO-06 | AMM-SU-2952 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0185 | 35.9645 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R01 | Fiber ring
RO-06 | AMM-SU-2953 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0185 | 35.9713 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R02 | Fiber ring
RO-06 | AMM-SU-2954 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0196 | 35.9768 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R03 | Fiber ring
RO-06 | AMM-SU-2955 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0196 | 35.9836 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R02 | Fiber ring
RO-06 | AMM-SU-2977 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0259 | 35.9543 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R05 | Fiber ring
RO-06 | AMM-SU-2978 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0259 | 35.9611 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R04 | Fiber ring
RO-06 | AMM-SU-2979 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0259 | 35.9679 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R03 | Fiber ring
RO-06 | AMM-SU-2980 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0253 | 35.974 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R03 | Fiber ring
RO-06 | AMM-SU-2981 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0235 | 35.9816 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R03 | Fiber ring
RO-06 | AMM-SU-3005 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0304 | 35.957 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R04 | Fiber ring
RO-06 | AMM-SU-3006 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0286 | 35.9645 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R04 | Fiber ring
RO-06 | AMM-SU-3007 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0292 | 35.9706 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R03 | Fiber ring
RO-06 | AMM-SU-3008 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0298 | 35.9795 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R03 | Fiber ring
RO-06 | AMM-SU-3029 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0355 | 35.9536 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R04 | Fiber ring
RO-06 | AMM-SU-3030 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0361 | 35.9611 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R04 | Fiber ring
RO-06 | AMM-SU-3031 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0355 | 35.9672 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R04 | Fiber ring
RO-06 | AMM-SU-3032 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0349 | 35.9734 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R03 | Fiber ring
RO-06 | AMM-SU-3058 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0388 | 35.9713 | 32 | 3 | HUB-AMM-06 | HUB-AMM-06-R04 | Fiber ring
RO-06 | AMM-SU-3079 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0463 | 35.9133 | 32 | 3 | HUB-AMM-76 | HUB-AMM-76-R03 | Fiber ring
RO-06 | AMM-SU-3080 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0463 | 35.9201 | 32 | 3 | HUB-AMM-76 | HUB-AMM-76-R03 | Fiber ring
RO-06 | AMM-SU-3117 | SU | Rooftop | Amman-Zarqa Metro | Amman | 32.0502 | 35.888 | 32 | 3 | HUB-AMM-76 | HUB-AMM-76-R05 | Fiber ring
RO-06 | AMM-SU-3118 | SU | Rooftop | Amman-Zarqa Metro | Amman | 32.049 | 35.8962 | 32 | 3 | HUB-AMM-76 | HUB-AMM-76-R01 | Fiber ring
RO-06 | AMM-SU-3119 | SU | Rooftop | Amman-Zarqa Metro | Amman | 32.0502 | 35.9017 | 32 | 3 | HUB-AMM-76 | HUB-AMM-76-R05 | Fiber ring
RO-06 | AMM-SU-3120 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0496 | 35.9092 | 32 | 3 | HUB-AMM-76 | HUB-AMM-76-R01 | Fiber ring
RO-06 | AMM-SU-3121 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.049 | 35.9167 | 32 | 3 | HUB-AMM-76 | HUB-AMM-76-R03 | Fiber ring
RO-06 | AMM-SU-3122 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.049 | 35.9235 | 32 | 3 | HUB-AMM-76 | HUB-AMM-76-R03 | Fiber ring
RO-06 | AMM-SU-3123 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0502 | 35.929 | 32 | 3 | HUB-AMM-76 | HUB-AMM-76-R03 | Fiber ring
RO-06 | AMM-SU-3158 | SU | Rooftop | Amman-Zarqa Metro | Amman | 32.0553 | 35.8928 | 32 | 3 | HUB-AMM-76 | HUB-AMM-76-R05 | Fiber ring
RO-06 | AMM-SU-3159 | SU | Rooftop | Amman-Zarqa Metro | Amman | 32.0564 | 35.8996 | 32 | 3 | HUB-AMM-76 | HUB-AMM-76-R05 | Fiber ring
RO-06 | AMM-SU-3160 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0558 | 35.9058 | 32 | 3 | HUB-AMM-76 | HUB-AMM-76-R04 | Fiber ring
RO-06 | AMM-SU-3161 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0564 | 35.9133 | 32 | 3 | HUB-AMM-76 | HUB-AMM-76-R04 | Fiber ring
RO-06 | AMM-SU-3162 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0564 | 35.9201 | 32 | 3 | HUB-AMM-76 | HUB-AMM-76-R03 | Fiber ring
RO-06 | AMM-SU-3198 | SU | Rooftop | Amman-Zarqa Metro | Amman | 32.0603 | 35.8962 | 32 | 3 | HUB-AMM-76 | HUB-AMM-76-R04 | Fiber ring
RO-06 | AMM-SU-3199 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0603 | 35.9017 | 32 | 3 | HUB-AMM-76 | HUB-AMM-76-R04 | Fiber ring
RO-06 | AMM-SU-3200 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0603 | 35.9085 | 32 | 3 | HUB-AMM-76 | HUB-AMM-76-R04 | Fiber ring
RO-06 | AMM-SU-3233 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0654 | 35.901 | 32 | 3 | HUB-AMM-76 | HUB-AMM-76-R04 | Fiber ring
RO-06 | AMM-SU-3234 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.066 | 35.9058 | 32 | 3 | HUB-AMM-76 | HUB-AMM-76-R04 | Fiber ring
RO-06 | AMM-SU-3413 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1163 | 36.0758 | 32 | 3 | HUB-AMM-60 | HUB-AMM-60-R06 | Fiber ring
RO-06 | AMM-SU-3414 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1163 | 36.084 | 32 | 3 | HUB-AMM-60 | HUB-AMM-60-R06 | Fiber ring
RO-06 | AMM-SU-3415 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1163 | 36.0894 | 32 | 3 | HUB-AMM-60 | HUB-AMM-60-R05 | Fiber ring
RO-06 | AMM-SU-3416 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1163 | 36.0962 | 32 | 3 | HUB-AMM-60 | HUB-AMM-60-R04 | Fiber ring
RO-06 | AMM-SU-3417 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1175 | 36.1044 | 32 | 3 | HUB-AMM-60 | HUB-AMM-60-R04 | Fiber ring
RO-06 | AMM-SU-3425 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1226 | 36.0805 | 32 | 3 | HUB-AMM-60 | HUB-AMM-60-R06 | Fiber ring
RO-06 | AMM-SU-3426 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1215 | 36.0928 | 32 | 3 | HUB-AMM-60 | HUB-AMM-60-R05 | Fiber ring
RO-06 | AMM-SU-3427 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1203 | 36.101 | 32 | 3 | HUB-AMM-60 | HUB-AMM-60-R05 | Fiber ring
RO-06 | AMM-SU-3428 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1215 | 36.1072 | 32 | 3 | HUB-AMM-60 | HUB-AMM-60-R04 | Fiber ring
RO-06 | AMM-SU-3434 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1265 | 36.0785 | 32 | 3 | HUB-AMM-60 | HUB-AMM-60-R06 | Fiber ring
RO-06 | AMM-SU-3435 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.126 | 36.0846 | 32 | 3 | HUB-AMM-60 | HUB-AMM-60-R05 | Fiber ring
RO-06 | AMM-SU-3436 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.126 | 36.1037 | 32 | 3 | HUB-AMM-60 | HUB-AMM-60-R05 | Fiber ring
RO-06 | AMM-SU-3439 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.131 | 36.0812 | 32 | 3 | HUB-AMM-60 | HUB-AMM-60-R06 | Fiber ring
RO-06 | AMM-SU-3440 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1305 | 36.0874 | 32 | 3 | HUB-AMM-60 | HUB-AMM-60-R05 | Fiber ring
RO-06 | AMM-U-0678 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.926 | 35.9873 | 30 | 3 | HUB-AMM-81 | HUB-AMM-81-R01 | Fiber ring
RO-06 | AMM-U-0679 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9269 | 35.9921 | 30 | 3 | HUB-AMM-81 | HUB-AMM-81-R06 | Fiber ring
RO-06 | AMM-U-0708 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9296 | 35.9859 | 30 | 3 | HUB-AMM-81 | HUB-AMM-81-R06 | Fiber ring
RO-06 | AMM-U-0709 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9296 | 35.9897 | 30 | 3 | HUB-AMM-81 | HUB-AMM-81-R06 | Fiber ring
RO-06 | AMM-U-0710 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9296 | 35.9944 | 30 | 3 | HUB-AMM-81 | HUB-AMM-81-R06 | Fiber ring
RO-06 | AMM-U-0711 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9288 | 35.9992 | 30 | 3 | HUB-AMM-81 | HUB-AMM-81-R05 | Fiber ring
RO-06 | AMM-U-0739 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9323 | 35.9873 | 30 | 3 | HUB-AMM-81 | HUB-AMM-81-R06 | Fiber ring
RO-06 | AMM-U-0740 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9331 | 35.993 | 30 | 3 | HUB-AMM-81 | HUB-AMM-81-R05 | Fiber ring
RO-06 | AMM-U-0741 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9331 | 35.9958 | 30 | 3 | HUB-AMM-81 | HUB-AMM-81-R05 | Fiber ring
RO-06 | AMM-U-0742 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9339 | 36.0015 | 30 | 3 | HUB-AMM-81 | HUB-AMM-81-R04 | Fiber ring
RO-06 | AMM-U-0769 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9362 | 35.9902 | 30 | 3 | HUB-AMM-81 | HUB-AMM-81-R05 | Fiber ring
RO-06 | AMM-U-0770 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9366 | 35.9954 | 30 | 3 | HUB-AMM-81 | HUB-AMM-81-R05 | Fiber ring
RO-06 | AMM-U-0771 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9374 | 35.9992 | 30 | 3 | HUB-AMM-81 | HUB-AMM-81-R05 | Fiber ring
RO-06 | AMM-U-0772 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9366 | 36.0039 | 30 | 3 | HUB-AMM-81 | HUB-AMM-81-R04 | Fiber ring
RO-06 | AMM-U-0797 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9405 | 35.9963 | 30 | 3 | HUB-AMM-81 | HUB-AMM-81-R05 | Fiber ring
RO-06 | AMM-U-0798 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9401 | 36.0025 | 30 | 3 | HUB-AMM-81 | HUB-AMM-81-R04 | Fiber ring
RO-06 | AMM-U-0799 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9401 | 36.0053 | 30 | 3 | HUB-AMM-81 | HUB-AMM-81-R04 | Fiber ring
RO-06 | AMM-U-0822 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.9437 | 35.9992 | 30 | 3 | HUB-AMM-81 | HUB-AMM-81-R04 | Fiber ring
RO-06 | AMM-U-0823 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9428 | 36.0039 | 30 | 3 | HUB-AMM-81 | HUB-AMM-81-R04 | Fiber ring
RO-06 | AMM-U-0824 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9437 | 36.0086 | 30 | 3 | HUB-AMM-81 | HUB-AMM-81-R04 | Fiber ring
RO-06 | AMM-U-1387 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0079 | 35.9661 | 30 | 3 | HUB-AMM-06 | HUB-AMM-06-R02 | Fiber ring
RO-06 | AMM-U-1432 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0114 | 35.959 | 30 | 3 | HUB-AMM-06 | HUB-AMM-06-R01 | Fiber ring
RO-06 | AMM-U-1433 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0114 | 35.9637 | 30 | 3 | HUB-AMM-06 | HUB-AMM-06-R01 | Fiber ring
RO-06 | AMM-U-1434 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0106 | 35.9684 | 30 | 3 | HUB-AMM-06 | HUB-AMM-06-R02 | Fiber ring
RO-06 | AMM-U-1476 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.015 | 35.9472 | 30 | 3 | HUB-AMM-06 | HUB-AMM-06-R01 | Fiber ring
RO-06 | AMM-U-1477 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0145 | 35.9514 | 30 | 3 | HUB-AMM-06 | HUB-AMM-06-R01 | Fiber ring
RO-06 | AMM-U-1478 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0145 | 35.9571 | 30 | 3 | HUB-AMM-06 | HUB-AMM-06-R01 | Fiber ring
RO-06 | AMM-U-1479 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0142 | 35.9613 | 30 | 3 | HUB-AMM-06 | HUB-AMM-06-R01 | Fiber ring
RO-06 | AMM-U-1521 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0173 | 35.95 | 30 | 3 | HUB-AMM-06 | HUB-AMM-06-R01 | Fiber ring
RO-06 | AMM-U-1522 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0185 | 35.9543 | 30 | 3 | HUB-AMM-06 | HUB-AMM-06-R05 | Fiber ring
RO-06 | AMM-U-1565 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0212 | 35.9528 | 30 | 3 | HUB-AMM-06 | HUB-AMM-06-R05 | Fiber ring
RO-06 | AMM-U-1722 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0345 | 35.8999 | 30 | 3 | HUB-AMM-76 | HUB-AMM-76-R02 | Fiber ring
RO-06 | AMM-U-1723 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0361 | 35.9046 | 30 | 3 | HUB-AMM-76 | HUB-AMM-76-R02 | Fiber ring
RO-06 | AMM-U-1724 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0353 | 35.9094 | 30 | 3 | HUB-AMM-76 | HUB-AMM-76-R02 | Fiber ring
RO-06 | AMM-U-1725 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0361 | 35.9141 | 30 | 3 | HUB-AMM-76 | HUB-AMM-76-R02 | Fiber ring
RO-06 | AMM-U-1762 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0396 | 35.8975 | 30 | 3 | HUB-AMM-76 | HUB-AMM-76-R01 | Fiber ring
RO-06 | AMM-U-1763 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0396 | 35.9023 | 30 | 3 | HUB-AMM-76 | HUB-AMM-76-R02 | Fiber ring
RO-06 | AMM-U-1764 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0396 | 35.907 | 30 | 3 | HUB-AMM-76 | HUB-AMM-76-R02 | Fiber ring
RO-06 | AMM-U-1765 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0388 | 35.9117 | 30 | 3 | HUB-AMM-76 | HUB-AMM-76-R02 | Fiber ring
RO-06 | AMM-U-1766 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0396 | 35.9164 | 30 | 3 | HUB-AMM-76 | HUB-AMM-76-R03 | Fiber ring
RO-06 | AMM-U-1799 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0432 | 35.8952 | 30 | 3 | HUB-AMM-76 | HUB-AMM-76-R01 | Fiber ring
RO-06 | AMM-U-1800 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0423 | 35.9008 | 30 | 3 | HUB-AMM-76 | HUB-AMM-76-R01 | Fiber ring
RO-06 | AMM-U-1801 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0423 | 35.9037 | 30 | 3 | HUB-AMM-76 | HUB-AMM-76-R01 | Fiber ring
RO-06 | AMM-U-1825 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0463 | 35.8886 | 30 | 3 | HUB-AMM-76 | HUB-AMM-76-R01 | Fiber ring
RO-06 | AMM-U-1826 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0467 | 35.8928 | 30 | 3 | HUB-AMM-76 | HUB-AMM-76-R01 | Fiber ring
RO-06 | AMM-U-2124 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0983 | 36.0932 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R02 | Fiber ring
RO-06 | AMM-U-2136 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1014 | 36.0866 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R02 | Fiber ring
RO-06 | AMM-U-2137 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1023 | 36.0904 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R02 | Fiber ring
RO-06 | AMM-U-2138 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1031 | 36.096 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R02 | Fiber ring
RO-06 | AMM-U-2146 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1062 | 36.0795 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R01 | Fiber ring
RO-06 | AMM-U-2147 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1054 | 36.0837 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R01 | Fiber ring
RO-06 | AMM-U-2148 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1058 | 36.0889 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R02 | Fiber ring
RO-06 | AMM-U-2149 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1054 | 36.0932 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R02 | Fiber ring
RO-06 | AMM-U-2150 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1058 | 36.0975 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R03 | Fiber ring
RO-06 | AMM-U-2151 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1058 | 36.1031 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R03 | Fiber ring
RO-06 | AMM-U-2155 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1093 | 36.0781 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R01 | Fiber ring
RO-06 | AMM-U-2156 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1097 | 36.0814 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R01 | Fiber ring
RO-06 | AMM-U-2157 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1093 | 36.0856 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R01 | Fiber ring
RO-06 | AMM-U-2158 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1101 | 36.0913 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R03 | Fiber ring
RO-06 | AMM-U-2159 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1093 | 36.096 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R03 | Fiber ring
RO-06 | AMM-U-2160 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1085 | 36.1008 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R03 | Fiber ring
RO-06 | AMM-U-2161 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1093 | 36.1045 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R03 | Fiber ring
RO-06 | AMM-U-2163 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1128 | 36.0804 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R01 | Fiber ring
RO-06 | AMM-U-2164 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1136 | 36.0842 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R06 | Fiber ring
RO-06 | AMM-U-2165 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1136 | 36.0889 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R01 | Fiber ring
RO-06 | AMM-U-2166 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1132 | 36.0932 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R04 | Fiber ring
RO-06 | AMM-U-2167 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1128 | 36.0975 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R04 | Fiber ring
RO-06 | AMM-U-2168 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1128 | 36.1031 | 30 | 3 | HUB-AMM-60 | HUB-AMM-60-R04 | Fiber ring
RO-06 | AQB-SU-0214 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5811 | 35.0204 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R01 | Fiber ring
RO-06 | AQB-SU-0215 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5811 | 35.0327 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R02 | Fiber ring
RO-06 | AQB-SU-0216 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5811 | 35.0395 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R02 | Fiber ring
RO-06 | AQB-SU-0217 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5862 | 35.0156 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R01 | Fiber ring
RO-06 | AQB-SU-0218 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5862 | 35.0224 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R01 | Fiber ring
RO-06 | AQB-SU-0219 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5862 | 35.0293 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R01 | Fiber ring
RO-06 | AQB-SU-0220 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5862 | 35.0361 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R02 | Fiber ring
RO-06 | AQB-SU-0221 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5862 | 35.0429 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R02 | Fiber ring
RO-06 | AQB-SU-0222 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5913 | 35.019 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R01 | Fiber ring
RO-06 | AQB-SU-0223 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5913 | 35.0259 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R01 | Fiber ring
RO-06 | AQB-SU-0224 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5913 | 35.0327 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R02 | Fiber ring
RO-06 | AQB-SU-0225 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5913 | 35.0395 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R02 | Fiber ring
RO-06 | AQB-SU-0226 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5964 | 35.0156 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R04 | Fiber ring
RO-06 | AQB-SU-0227 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5964 | 35.0224 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R04 | Fiber ring
RO-06 | AQB-SU-0228 | SU | Rooftop | Aqaba | Aqaba | 29.5958 | 35.03 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R01 | Fiber ring
RO-06 | AQB-SU-0229 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5964 | 35.0375 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R03 | Fiber ring
RO-06 | AQB-SU-0230 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.5964 | 35.0429 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R03 | Fiber ring
RO-06 | AQB-SU-0231 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.6015 | 35.0122 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R04 | Fiber ring
RO-06 | AQB-SU-0232 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.6015 | 35.019 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R04 | Fiber ring
RO-06 | AQB-SU-0233 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.6015 | 35.0272 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R03 | Fiber ring
RO-06 | AQB-SU-0234 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.6015 | 35.0341 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R03 | Fiber ring
RO-06 | AQB-SU-0235 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.6015 | 35.0409 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R03 | Fiber ring
RO-06 | AQB-SU-0236 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.6066 | 35.0156 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R04 | Fiber ring
RO-06 | AQB-SU-0237 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.6066 | 35.0224 | 32 | 3 | HUB-AQB-02 | HUB-AQB-02-R03 | Fiber ring
RO-06 | HWY-HW-0066 | HW | Lattice tower | Highway | Tafilah | 30.6528 | 35.5804 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-06 | HWY-HW-0067 | HW | Lattice tower | Highway | Ma'an | 30.5884 | 35.566 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-06 | HWY-HW-0068 | HW | Lattice tower | Highway | Ma'an | 30.5255 | 35.5571 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-06 | HWY-HW-0069 | HW | Lattice tower | Highway | Ma'an | 30.4655 | 35.5343 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-06 | HWY-HW-0070 | HW | Lattice tower | Highway | Ma'an | 30.4057 | 35.5101 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-06 | HWY-HW-0071 | HW | Lattice tower | Highway | Ma'an | 30.2657 | 35.5747 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-06 | HWY-HW-0072 | HW | Lattice tower | Highway | Ma'an | 30.2303 | 35.6406 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-06 | IRB-SU-0612 | SU | Monopole / greenfield | Irbid | Irbid | 32.5287 | 35.9986 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R02 | Fiber ring
RO-06 | IRB-SU-0613 | SU | Monopole / greenfield | Irbid | Irbid | 32.5287 | 36.0055 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R03 | Fiber ring
RO-06 | IRB-SU-0616 | SU | Monopole / greenfield | Irbid | Irbid | 32.535 | 35.7904 | 32 | 3 | HUB-IRB-18 | HUB-IRB-18-R01 | Fiber ring
RO-06 | IRB-SU-0617 | SU | Monopole / greenfield | Irbid | Irbid | 32.535 | 35.7972 | 32 | 3 | HUB-IRB-18 | HUB-IRB-18-R02 | Fiber ring
RO-06 | IRB-SU-0622 | SU | Monopole / greenfield | Irbid | Irbid | 32.5338 | 35.9816 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R01 | Fiber ring
RO-06 | IRB-SU-0623 | SU | Monopole / greenfield | Irbid | Irbid | 32.5338 | 35.9884 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R02 | Fiber ring
RO-06 | IRB-SU-0624 | SU | Monopole / greenfield | Irbid | Irbid | 32.5338 | 35.9952 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R02 | Fiber ring
RO-06 | IRB-SU-0625 | SU | Monopole / greenfield | Irbid | Irbid | 32.5338 | 36.002 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R02 | Fiber ring
RO-06 | IRB-SU-0626 | SU | Monopole / greenfield | Irbid | Irbid | 32.5338 | 36.0075 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R03 | Fiber ring
RO-06 | IRB-SU-0627 | SU | Monopole / greenfield | Irbid | Irbid | 32.5338 | 36.0157 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R03 | Fiber ring
RO-06 | IRB-SU-0628 | SU | Monopole / greenfield | Irbid | Irbid | 32.5401 | 35.7802 | 32 | 3 | HUB-IRB-18 | HUB-IRB-18-R01 | Fiber ring
RO-06 | IRB-SU-0629 | SU | Monopole / greenfield | Irbid | Irbid | 32.5389 | 35.7884 | 32 | 3 | HUB-IRB-18 | HUB-IRB-18-R01 | Fiber ring
RO-06 | IRB-SU-0630 | SU | Monopole / greenfield | Irbid | Irbid | 32.5377 | 35.7938 | 32 | 3 | HUB-IRB-18 | HUB-IRB-18-R01 | Fiber ring
RO-06 | IRB-SU-0635 | SU | Monopole / greenfield | Irbid | Irbid | 32.5389 | 35.9781 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R01 | Fiber ring
RO-06 | IRB-SU-0636 | SU | Monopole / greenfield | Irbid | Irbid | 32.5389 | 35.985 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R01 | Fiber ring
RO-06 | IRB-SU-0637 | SU | Monopole / greenfield | Irbid | Irbid | 32.5389 | 35.9918 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R02 | Fiber ring
RO-06 | IRB-SU-0638 | SU | Monopole / greenfield | Irbid | Irbid | 32.5389 | 36 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R02 | Fiber ring
RO-06 | IRB-SU-0639 | SU | Rooftop | Irbid | Irbid | 32.5401 | 36.0055 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R03 | Fiber ring
RO-06 | IRB-SU-0640 | SU | Monopole / greenfield | Irbid | Irbid | 32.5389 | 36.0109 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R03 | Fiber ring
RO-06 | IRB-SU-0641 | SU | Monopole / greenfield | Irbid | Irbid | 32.5389 | 36.0191 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R04 | Fiber ring
RO-06 | IRB-SU-0642 | SU | Monopole / greenfield | Irbid | Irbid | 32.5389 | 36.0259 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R04 | Fiber ring
RO-06 | IRB-SU-0643 | SU | Monopole / greenfield | Irbid | Irbid | 32.544 | 35.7768 | 32 | 3 | HUB-IRB-18 | HUB-IRB-18-R01 | Fiber ring
RO-06 | IRB-SU-0644 | SU | Monopole / greenfield | Irbid | Irbid | 32.5428 | 35.7836 | 32 | 3 | HUB-IRB-18 | HUB-IRB-18-R01 | Fiber ring
RO-06 | IRB-SU-0645 | SU | Monopole / greenfield | Irbid | Irbid | 32.544 | 35.7918 | 32 | 3 | HUB-IRB-18 | HUB-IRB-18-R01 | Fiber ring
RO-06 | IRB-SU-0651 | SU | Monopole / greenfield | Irbid | Irbid | 32.544 | 35.9747 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R01 | Fiber ring
RO-06 | IRB-SU-0652 | SU | Monopole / greenfield | Irbid | Irbid | 32.544 | 35.9816 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R01 | Fiber ring
RO-06 | IRB-SU-0653 | SU | Monopole / greenfield | Irbid | Irbid | 32.544 | 35.9884 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R01 | Fiber ring
RO-06 | IRB-SU-0654 | SU | Monopole / greenfield | Irbid | Irbid | 32.544 | 36.0293 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R04 | Fiber ring
RO-06 | IRB-SU-0655 | SU | Monopole / greenfield | Irbid | Irbid | 32.5491 | 35.7815 | 32 | 3 | HUB-IRB-18 | HUB-IRB-18-R06 | Fiber ring
RO-06 | IRB-SU-0656 | SU | Monopole / greenfield | Irbid | Irbid | 32.5491 | 35.7884 | 32 | 3 | HUB-IRB-18 | HUB-IRB-18-R06 | Fiber ring
RO-06 | IRB-SU-0657 | SU | Monopole / greenfield | Irbid | Irbid | 32.5491 | 35.7952 | 32 | 3 | HUB-IRB-18 | HUB-IRB-18-R06 | Fiber ring
RO-06 | IRB-SU-0658 | SU | Monopole / greenfield | Irbid | Irbid | 32.5485 | 35.8013 | 32 | 3 | HUB-IRB-18 | HUB-IRB-18-R06 | Fiber ring
RO-06 | IRB-SU-0662 | SU | Monopole / greenfield | Irbid | Irbid | 32.5491 | 35.9699 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R09 | Fiber ring
RO-06 | IRB-SU-0663 | SU | Monopole / greenfield | Irbid | Irbid | 32.5491 | 35.9781 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R08 | Fiber ring
RO-06 | IRB-SU-0664 | SU | Monopole / greenfield | Irbid | Irbid | 32.5491 | 35.985 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R08 | Fiber ring
RO-06 | IRB-SU-0665 | SU | Monopole / greenfield | Irbid | Irbid | 32.5491 | 36.0328 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R05 | Fiber ring
RO-06 | IRB-SU-0666 | SU | Monopole / greenfield | Irbid | Irbid | 32.5542 | 35.785 | 32 | 3 | HUB-IRB-18 | HUB-IRB-18-R06 | Fiber ring
RO-06 | IRB-SU-0667 | SU | Monopole / greenfield | Irbid | Irbid | 32.553 | 35.7904 | 32 | 3 | HUB-IRB-18 | HUB-IRB-18-R06 | Fiber ring
RO-06 | IRB-SU-0668 | SU | Monopole / greenfield | Irbid | Irbid | 32.553 | 35.7972 | 32 | 3 | HUB-IRB-18 | HUB-IRB-18-R05 | Fiber ring
RO-06 | IRB-SU-0674 | SU | Monopole / greenfield | Irbid | Irbid | 32.553 | 35.9679 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R08 | Fiber ring
RO-06 | IRB-SU-0675 | SU | Monopole / greenfield | Irbid | Irbid | 32.5542 | 35.9747 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R08 | Fiber ring
RO-06 | IRB-SU-0676 | SU | Monopole / greenfield | Irbid | Irbid | 32.5542 | 35.9802 | 32 | 3 | HUB-IRB-06 | HUB-IRB-06-R08 | Fiber ring
RO-06 | IRB-SU-0677 | SU | Monopole / greenfield | Irbid | Irbid | 32.5593 | 35.7884 | 32 | 3 | HUB-IRB-18 | HUB-IRB-18-R05 | Fiber ring
RO-06 | IRB-SU-0678 | SU | Monopole / greenfield | Irbid | Irbid | 32.5587 | 35.7945 | 32 | 3 | HUB-IRB-18 | HUB-IRB-18-R05 | Fiber ring
RO-06 | IRB-SU-0679 | SU | Monopole / greenfield | Irbid | Irbid | 32.5587 | 35.8013 | 32 | 3 | HUB-IRB-18 | HUB-IRB-18-R05 | Fiber ring
RO-06 | IRB-SU-0685 | SU | Monopole / greenfield | Irbid | Irbid | 32.5598 | 35.9706 | 32 | 3 | HUB-IRB-13 | HUB-IRB-13-R01 | Fiber ring
RO-06 | IRB-SU-0686 | SU | Monopole / greenfield | Irbid | Irbid | 32.5598 | 35.9788 | 32 | 3 | HUB-IRB-13 | HUB-IRB-13-R01 | Fiber ring
RO-06 | IRB-SU-0687 | SU | Monopole / greenfield | Irbid | Irbid | 32.5593 | 36.0328 | 32 | 3 | HUB-IRB-13 | HUB-IRB-13-R04 | Fiber ring
RO-06 | IRB-SU-0688 | SU | Monopole / greenfield | Irbid | Irbid | 32.5632 | 35.7904 | 32 | 3 | HUB-IRB-18 | HUB-IRB-18-R05 | Fiber ring
RO-06 | IRB-SU-0689 | SU | Monopole / greenfield | Irbid | Irbid | 32.5638 | 35.7979 | 32 | 3 | HUB-IRB-04 | HUB-IRB-04-R01 | Fiber ring
RO-06 | IRB-SU-0690 | SU | Monopole / greenfield | Irbid | Irbid | 32.5643 | 35.8041 | 32 | 3 | HUB-IRB-04 | HUB-IRB-04-R01 | Fiber ring
RO-06 | IRB-SU-0696 | SU | Monopole / greenfield | Irbid | Irbid | 32.5643 | 35.9679 | 32 | 3 | HUB-IRB-13 | HUB-IRB-13-R01 | Fiber ring
RO-06 | IRB-SU-0697 | SU | Monopole / greenfield | Irbid | Irbid | 32.5643 | 35.9747 | 32 | 3 | HUB-IRB-13 | HUB-IRB-13-R01 | Fiber ring
RO-06 | IRB-SU-0698 | SU | Monopole / greenfield | Irbid | Irbid | 32.5683 | 35.7938 | 32 | 3 | HUB-IRB-04 | HUB-IRB-04-R01 | Fiber ring
RO-06 | IRB-SU-0699 | SU | Monopole / greenfield | Irbid | Irbid | 32.5694 | 35.802 | 32 | 3 | HUB-IRB-04 | HUB-IRB-04-R01 | Fiber ring
RO-06 | IRB-SU-0700 | SU | Monopole / greenfield | Irbid | Irbid | 32.5694 | 35.8075 | 32 | 3 | HUB-IRB-04 | HUB-IRB-04-R01 | Fiber ring
RO-06 | IRB-SU-0706 | SU | Monopole / greenfield | Irbid | Irbid | 32.5694 | 35.9713 | 32 | 3 | HUB-IRB-13 | HUB-IRB-13-R10 | Fiber ring
RO-06 | IRB-SU-0707 | SU | Monopole / greenfield | Irbid | Irbid | 32.5694 | 35.9781 | 32 | 3 | HUB-IRB-13 | HUB-IRB-13-R10 | Fiber ring
RO-06 | IRB-SU-0708 | SU | Monopole / greenfield | Irbid | Irbid | 32.5745 | 35.7986 | 32 | 3 | HUB-IRB-04 | HUB-IRB-04-R06 | Fiber ring
RO-06 | IRB-SU-0709 | SU | Monopole / greenfield | Irbid | Irbid | 32.5745 | 35.8054 | 32 | 3 | HUB-IRB-04 | HUB-IRB-04-R06 | Fiber ring
RO-06 | IRB-SU-0710 | SU | Monopole / greenfield | Irbid | Irbid | 32.5745 | 35.8095 | 32 | 3 | HUB-IRB-04 | HUB-IRB-04-R05 | Fiber ring
RO-06 | IRB-SU-0711 | SU | Monopole / greenfield | Irbid | Irbid | 32.5757 | 35.8177 | 32 | 3 | HUB-IRB-04 | HUB-IRB-04-R05 | Fiber ring
RO-06 | IRB-SU-0718 | SU | Monopole / greenfield | Irbid | Irbid | 32.5734 | 35.9747 | 32 | 3 | HUB-IRB-13 | HUB-IRB-13-R10 | Fiber ring
RO-06 | IRB-SU-0719 | SU | Monopole / greenfield | Irbid | Irbid | 32.5757 | 35.9816 | 32 | 3 | HUB-IRB-13 | HUB-IRB-13-R09 | Fiber ring
RO-06 | IRB-SU-0720 | SU | Monopole / greenfield | Irbid | Irbid | 32.5784 | 35.8007 | 32 | 3 | HUB-IRB-04 | HUB-IRB-04-R05 | Fiber ring
RO-06 | IRB-SU-0721 | SU | Monopole / greenfield | Irbid | Irbid | 32.5784 | 35.8075 | 32 | 3 | HUB-IRB-04 | HUB-IRB-04-R05 | Fiber ring
RO-06 | IRB-SU-0722 | SU | Monopole / greenfield | Irbid | Irbid | 32.5796 | 35.8157 | 32 | 3 | HUB-IRB-04 | HUB-IRB-04-R05 | Fiber ring
RO-06 | IRB-SU-0723 | SU | Monopole / greenfield | Irbid | Irbid | 32.5784 | 35.8211 | 32 | 3 | HUB-IRB-04 | HUB-IRB-04-R04 | Fiber ring
RO-06 | IRB-SU-0724 | SU | Monopole / greenfield | Irbid | Irbid | 32.5796 | 35.8894 | 32 | 3 | HUB-IRB-19 | HUB-IRB-19-R03 | Fiber ring
RO-06 | IRB-SU-0725 | SU | Monopole / greenfield | Irbid | Irbid | 32.5784 | 35.8962 | 32 | 3 | HUB-IRB-19 | HUB-IRB-19-R03 | Fiber ring
RO-06 | IRB-SU-0726 | SU | Monopole / greenfield | Irbid | Irbid | 32.5796 | 35.9031 | 32 | 3 | HUB-IRB-19 | HUB-IRB-19-R03 | Fiber ring
RO-06 | IRB-SU-0729 | SU | Monopole / greenfield | Irbid | Irbid | 32.5796 | 35.9768 | 32 | 3 | HUB-IRB-13 | HUB-IRB-13-R09 | Fiber ring
RO-06 | IRB-SU-0730 | SU | Monopole / greenfield | Irbid | Irbid | 32.5796 | 35.985 | 32 | 3 | HUB-IRB-13 | HUB-IRB-13-R09 | Fiber ring
RO-06 | IRB-SU-0731 | SU | Monopole / greenfield | Irbid | Irbid | 32.5796 | 35.9918 | 32 | 3 | HUB-IRB-13 | HUB-IRB-13-R09 | Fiber ring
RO-06 | IRB-SU-0732 | SU | Monopole / greenfield | Irbid | Irbid | 32.5796 | 36.0205 | 32 | 3 | HUB-IRB-13 | HUB-IRB-13-R07 | Fiber ring
RO-06 | IRB-SU-0733 | SU | Monopole / greenfield | Irbid | Irbid | 32.5847 | 35.8123 | 32 | 3 | HUB-IRB-04 | HUB-IRB-04-R05 | Fiber ring
RO-06 | IRB-SU-0734 | SU | Monopole / greenfield | Irbid | Irbid | 32.5835 | 35.8177 | 32 | 3 | HUB-IRB-04 | HUB-IRB-04-R05 | Fiber ring
RO-06 | IRB-SU-0735 | SU | Monopole / greenfield | Irbid | Irbid | 32.5859 | 35.8246 | 32 | 3 | HUB-IRB-04 | HUB-IRB-04-R04 | Fiber ring
RO-06 | IRB-SU-0736 | SU | Monopole / greenfield | Irbid | Irbid | 32.5847 | 35.8314 | 32 | 3 | HUB-IRB-09 | HUB-IRB-09-R06 | Fiber ring
RO-06 | IRB-SU-0737 | SU | Monopole / greenfield | Irbid | Irbid | 32.5847 | 35.8382 | 32 | 3 | HUB-IRB-09 | HUB-IRB-09-R06 | Fiber ring
RO-06 | IRB-SU-0738 | SU | Monopole / greenfield | Irbid | Irbid | 32.5853 | 35.8525 | 32 | 3 | HUB-IRB-09 | HUB-IRB-09-R04 | Fiber ring
RO-06 | IRB-SU-0739 | SU | Monopole / greenfield | Irbid | Irbid | 32.5859 | 35.8587 | 32 | 3 | HUB-IRB-09 | HUB-IRB-09-R04 | Fiber ring
RO-06 | IRB-SU-0740 | SU | Rooftop | Irbid | Irbid | 32.5847 | 35.8655 | 32 | 3 | HUB-IRB-19 | HUB-IRB-19-R05 | Fiber ring
RO-06 | IRB-SU-0741 | SU | Rooftop | Irbid | Irbid | 32.5853 | 35.8717 | 32 | 3 | HUB-IRB-19 | HUB-IRB-19-R05 | Fiber ring
RO-06 | IRB-SU-0742 | SU | Monopole / greenfield | Irbid | Irbid | 32.5847 | 35.8792 | 32 | 3 | HUB-IRB-19 | HUB-IRB-19-R01 | Fiber ring
RO-06 | IRB-SU-0743 | SU | Monopole / greenfield | Irbid | Irbid | 32.5847 | 35.886 | 32 | 3 | HUB-IRB-19 | HUB-IRB-19-R03 | Fiber ring
RO-06 | IRB-SU-0744 | SU | Monopole / greenfield | Irbid | Irbid | 32.5847 | 35.8928 | 32 | 3 | HUB-IRB-19 | HUB-IRB-19-R03 | Fiber ring
RO-06 | IRB-SU-0745 | SU | Monopole / greenfield | Irbid | Irbid | 32.5859 | 35.8996 | 32 | 3 | HUB-IRB-19 | HUB-IRB-19-R04 | Fiber ring
RO-06 | IRB-SU-0746 | SU | Monopole / greenfield | Irbid | Irbid | 32.5847 | 35.9065 | 32 | 3 | HUB-IRB-19 | HUB-IRB-19-R03 | Fiber ring
RO-06 | IRB-SU-0748 | SU | Monopole / greenfield | Irbid | Irbid | 32.5847 | 35.9884 | 32 | 3 | HUB-IRB-13 | HUB-IRB-13-R09 | Fiber ring
RO-06 | IRB-SU-0749 | SU | Monopole / greenfield | Irbid | Irbid | 32.5847 | 35.9966 | 32 | 3 | HUB-IRB-13 | HUB-IRB-13-R08 | Fiber ring
RO-06 | IRB-SU-0750 | SU | Monopole / greenfield | Irbid | Irbid | 32.5847 | 36.0034 | 32 | 3 | HUB-IRB-13 | HUB-IRB-13-R08 | Fiber ring
RO-06 | IRB-SU-0751 | SU | Monopole / greenfield | Irbid | Irbid | 32.5847 | 36.0089 | 32 | 3 | HUB-IRB-13 | HUB-IRB-13-R07 | Fiber ring
RO-06 | IRB-SU-0752 | SU | Monopole / greenfield | Irbid | Irbid | 32.5886 | 35.8211 | 32 | 3 | HUB-IRB-04 | HUB-IRB-04-R04 | Fiber ring
RO-06 | IRB-SU-0753 | SU | Monopole / greenfield | Irbid | Irbid | 32.5886 | 35.828 | 32 | 3 | HUB-IRB-09 | HUB-IRB-09-R06 | Fiber ring
RO-06 | IRB-SU-0754 | SU | Monopole / greenfield | Irbid | Irbid | 32.5898 | 35.8362 | 32 | 3 | HUB-IRB-09 | HUB-IRB-09-R06 | Fiber ring
RO-06 | IRB-SU-0755 | SU | Monopole / greenfield | Irbid | Irbid | 32.5886 | 35.8416 | 32 | 3 | HUB-IRB-09 | HUB-IRB-09-R05 | Fiber ring
RO-06 | IRB-SU-0756 | SU | Rooftop | Irbid | Irbid | 32.5898 | 35.8498 | 32 | 3 | HUB-IRB-09 | HUB-IRB-09-R05 | Fiber ring
RO-06 | IRB-SU-0757 | SU | Rooftop | Irbid | Irbid | 32.5904 | 35.8559 | 32 | 3 | HUB-IRB-09 | HUB-IRB-09-R04 | Fiber ring
RO-06 | IRB-SU-0758 | SU | Monopole / greenfield | Irbid | Irbid | 32.591 | 35.8621 | 32 | 3 | HUB-IRB-09 | HUB-IRB-09-R04 | Fiber ring
RO-06 | IRB-SU-0759 | SU | Rooftop | Irbid | Irbid | 32.5892 | 35.8682 | 32 | 3 | HUB-IRB-19 | HUB-IRB-19-R05 | Fiber ring
RO-06 | IRB-SU-0760 | SU | Monopole / greenfield | Irbid | Irbid | 32.5904 | 35.8751 | 32 | 3 | HUB-IRB-19 | HUB-IRB-19-R05 | Fiber ring
RO-06 | IRB-SU-0761 | SU | Monopole / greenfield | Irbid | Irbid | 32.5904 | 35.8833 | 32 | 3 | HUB-IRB-19 | HUB-IRB-19-R04 | Fiber ring
RO-06 | IRB-SU-0762 | SU | Monopole / greenfield | Irbid | Irbid | 32.5904 | 35.8901 | 32 | 3 | HUB-IRB-19 | HUB-IRB-19-R04 | Fiber ring
RO-06 | IRB-SU-0763 | SU | Monopole / greenfield | Irbid | Irbid | 32.5904 | 35.8969 | 32 | 3 | HUB-IRB-19 | HUB-IRB-19-R04 | Fiber ring
RO-06 | IRB-SU-0764 | SU | Monopole / greenfield | Irbid | Irbid | 32.5898 | 35.9031 | 32 | 3 | HUB-IRB-19 | HUB-IRB-19-R04 | Fiber ring
RO-06 | IRB-SU-0765 | SU | Monopole / greenfield | Irbid | Irbid | 32.5949 | 35.8314 | 32 | 3 | HUB-IRB-09 | HUB-IRB-09-R05 | Fiber ring
RO-06 | IRB-SU-0766 | SU | Monopole / greenfield | Irbid | Irbid | 32.5949 | 35.8396 | 32 | 3 | HUB-IRB-09 | HUB-IRB-09-R05 | Fiber ring
RO-06 | IRB-SU-0767 | SU | Monopole / greenfield | Irbid | Irbid | 32.5949 | 35.8464 | 32 | 3 | HUB-IRB-09 | HUB-IRB-09-R05 | Fiber ring
RO-06 | IRB-SU-0768 | SU | Rooftop | Irbid | Irbid | 32.5961 | 35.8519 | 32 | 3 | HUB-IRB-09 | HUB-IRB-09-R05 | Fiber ring
RO-06 | IRB-SU-0769 | SU | Monopole / greenfield | Irbid | Irbid | 32.5949 | 35.8587 | 32 | 3 | HUB-IRB-09 | HUB-IRB-09-R04 | Fiber ring
RO-06 | IRB-SU-0770 | SU | Monopole / greenfield | Irbid | Irbid | 32.5961 | 35.8655 | 32 | 3 | HUB-IRB-19 | HUB-IRB-19-R05 | Fiber ring
RO-06 | IRB-SU-0771 | SU | Monopole / greenfield | Irbid | Irbid | 32.5961 | 35.8723 | 32 | 3 | HUB-IRB-19 | HUB-IRB-19-R05 | Fiber ring
RO-06 | IRB-SU-0772 | SU | Rooftop | Irbid | Irbid | 32.5943 | 35.8798 | 32 | 3 | HUB-IRB-19 | HUB-IRB-19-R04 | Fiber ring
RO-06 | IRB-SU-0773 | SU | Rooftop | Irbid | Irbid | 32.5937 | 35.886 | 32 | 3 | HUB-IRB-19 | HUB-IRB-19-R04 | Fiber ring
RO-06 | IRB-U-0164 | U | Monopole / greenfield | Irbid | Irbid | 32.5322 | 35.8087 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R02 | Fiber ring
RO-06 | IRB-U-0165 | U | Monopole / greenfield | Irbid | Irbid | 32.5322 | 35.8125 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R03 | Fiber ring
RO-06 | IRB-U-0185 | U | Monopole / greenfield | Irbid | Irbid | 32.5362 | 35.8059 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R02 | Fiber ring
RO-06 | IRB-U-0186 | U | Monopole / greenfield | Irbid | Irbid | 32.5358 | 35.8101 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R03 | Fiber ring
RO-06 | IRB-U-0187 | U | Monopole / greenfield | Irbid | Irbid | 32.5358 | 35.8139 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R03 | Fiber ring
RO-06 | IRB-U-0207 | U | Monopole / greenfield | Irbid | Irbid | 32.5385 | 35.803 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R02 | Fiber ring
RO-06 | IRB-U-0208 | U | Monopole / greenfield | Irbid | Irbid | 32.5393 | 35.8077 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R02 | Fiber ring
RO-06 | IRB-U-0209 | U | Monopole / greenfield | Irbid | Irbid | 32.5393 | 35.8125 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R03 | Fiber ring
RO-06 | IRB-U-0230 | U | Rooftop | Irbid | Irbid | 32.5428 | 35.8016 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R02 | Fiber ring
RO-06 | IRB-U-0231 | U | Rooftop | Irbid | Irbid | 32.542 | 35.8054 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R02 | Fiber ring
RO-06 | IRB-U-0232 | U | Monopole / greenfield | Irbid | Irbid | 32.542 | 35.8101 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R03 | Fiber ring
RO-06 | IRB-U-0233 | U | Monopole / greenfield | Irbid | Irbid | 32.542 | 35.8148 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R03 | Fiber ring
RO-06 | IRB-U-0252 | U | Monopole / greenfield | Irbid | Irbid | 32.5428 | 35.9944 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R01 | Fiber ring
RO-06 | IRB-U-0253 | U | Monopole / greenfield | Irbid | Irbid | 32.5428 | 36.0001 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R02 | Fiber ring
RO-06 | IRB-U-0254 | U | Rooftop | Irbid | Irbid | 32.5428 | 36.0048 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R03 | Fiber ring
RO-06 | IRB-U-0255 | U | Rooftop | Irbid | Irbid | 32.5428 | 36.0086 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R03 | Fiber ring
RO-06 | IRB-U-0256 | U | Monopole / greenfield | Irbid | Irbid | 32.5428 | 36.0124 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R04 | Fiber ring
RO-06 | IRB-U-0257 | U | Rooftop | Irbid | Irbid | 32.5472 | 35.803 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R01 | Fiber ring
RO-06 | IRB-U-0258 | U | Rooftop | Irbid | Irbid | 32.5463 | 35.8077 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R03 | Fiber ring
RO-06 | IRB-U-0259 | U | Monopole / greenfield | Irbid | Irbid | 32.5463 | 35.8115 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R04 | Fiber ring
RO-06 | IRB-U-0273 | U | Monopole / greenfield | Irbid | Irbid | 32.5463 | 35.9921 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R09 | Fiber ring
RO-06 | IRB-U-0274 | U | Monopole / greenfield | Irbid | Irbid | 32.5463 | 35.9968 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R09 | Fiber ring
RO-06 | IRB-U-0275 | U | Monopole / greenfield | Irbid | Irbid | 32.5463 | 36.0015 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R01 | Fiber ring
RO-06 | IRB-U-0276 | U | Rooftop | Irbid | Irbid | 32.5463 | 36.0062 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R04 | Fiber ring
RO-06 | IRB-U-0277 | U | Rooftop | Irbid | Irbid | 32.5463 | 36.01 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R04 | Fiber ring
RO-06 | IRB-U-0278 | U | Monopole / greenfield | Irbid | Irbid | 32.5463 | 36.0157 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R04 | Fiber ring
RO-06 | IRB-U-0279 | U | Monopole / greenfield | Irbid | Irbid | 32.5472 | 36.0204 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R05 | Fiber ring
RO-06 | IRB-U-0280 | U | Rooftop | Irbid | Irbid | 32.5491 | 35.8054 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R04 | Fiber ring
RO-06 | IRB-U-0281 | U | Rooftop | Irbid | Irbid | 32.5491 | 35.8101 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R04 | Fiber ring
RO-06 | IRB-U-0282 | U | Monopole / greenfield | Irbid | Irbid | 32.5499 | 35.8158 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R04 | Fiber ring
RO-06 | IRB-U-0294 | U | Monopole / greenfield | Irbid | Irbid | 32.5499 | 35.9897 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R08 | Fiber ring
RO-06 | IRB-U-0295 | U | Monopole / greenfield | Irbid | Irbid | 32.5499 | 35.9944 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R07 | Fiber ring
RO-06 | IRB-U-0296 | U | Monopole / greenfield | Irbid | Irbid | 32.5499 | 35.9992 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R07 | Fiber ring
RO-06 | IRB-U-0297 | U | Rooftop | Irbid | Irbid | 32.5499 | 36.0039 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R06 | Fiber ring
RO-06 | IRB-U-0298 | U | Rooftop | Irbid | Irbid | 32.5499 | 36.0076 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R06 | Fiber ring
RO-06 | IRB-U-0299 | U | Rooftop | Irbid | Irbid | 32.5499 | 36.0133 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R05 | Fiber ring
RO-06 | IRB-U-0300 | U | Rooftop | Irbid | Irbid | 32.5499 | 36.0181 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R05 | Fiber ring
RO-06 | IRB-U-0301 | U | Monopole / greenfield | Irbid | Irbid | 32.5507 | 36.0228 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R05 | Fiber ring
RO-06 | IRB-U-0302 | U | Monopole / greenfield | Irbid | Irbid | 32.5526 | 35.803 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R05 | Fiber ring
RO-06 | IRB-U-0303 | U | Monopole / greenfield | Irbid | Irbid | 32.5526 | 35.8077 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R04 | Fiber ring
RO-06 | IRB-U-0304 | U | Monopole / greenfield | Irbid | Irbid | 32.5534 | 35.8115 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R04 | Fiber ring
RO-06 | IRB-U-0317 | U | Monopole / greenfield | Irbid | Irbid | 32.5534 | 35.9873 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R08 | Fiber ring
RO-06 | IRB-U-0318 | U | Monopole / greenfield | Irbid | Irbid | 32.5534 | 35.9921 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R07 | Fiber ring
RO-06 | IRB-U-0319 | U | Monopole / greenfield | Irbid | Irbid | 32.5534 | 35.9968 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R07 | Fiber ring
RO-06 | IRB-U-0320 | U | Rooftop | Irbid | Irbid | 32.5534 | 36.0025 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R06 | Fiber ring
RO-06 | IRB-U-0321 | U | Rooftop | Irbid | Irbid | 32.5526 | 36.0062 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R06 | Fiber ring
RO-06 | IRB-U-0322 | U | Rooftop | Irbid | Irbid | 32.5534 | 36.011 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R06 | Fiber ring
RO-06 | IRB-U-0323 | U | Rooftop | Irbid | Irbid | 32.5534 | 36.0157 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R06 | Fiber ring
RO-06 | IRB-U-0324 | U | Rooftop | Irbid | Irbid | 32.5534 | 36.0204 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R05 | Fiber ring
RO-06 | IRB-U-0325 | U | Monopole / greenfield | Irbid | Irbid | 32.5534 | 36.0251 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R05 | Fiber ring
RO-06 | IRB-U-0326 | U | Monopole / greenfield | Irbid | Irbid | 32.5569 | 35.8054 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R05 | Fiber ring
RO-06 | IRB-U-0327 | U | Monopole / greenfield | Irbid | Irbid | 32.5569 | 35.8092 | 30 | 3 | HUB-IRB-18 | HUB-IRB-18-R04 | Fiber ring
RO-06 | IRB-U-0328 | U | Monopole / greenfield | Irbid | Irbid | 32.5565 | 35.8153 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R02 | Fiber ring
RO-06 | IRB-U-0329 | U | Monopole / greenfield | Irbid | Irbid | 32.5569 | 35.8186 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R02 | Fiber ring
RO-06 | IRB-U-0340 | U | Monopole / greenfield | Irbid | Irbid | 32.5569 | 35.985 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R07 | Fiber ring
RO-06 | IRB-U-0341 | U | Monopole / greenfield | Irbid | Irbid | 32.5569 | 35.9897 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R07 | Fiber ring
RO-06 | IRB-U-0342 | U | Monopole / greenfield | Irbid | Irbid | 32.5569 | 35.9944 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R07 | Fiber ring
RO-06 | IRB-U-0343 | U | Rooftop | Irbid | Irbid | 32.5569 | 35.9992 | 30 | 3 | HUB-IRB-06 | HUB-IRB-06-R06 | Fiber ring
RO-06 | IRB-U-0344 | U | Rooftop | Irbid | Irbid | 32.5569 | 36.0039 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R02 | Fiber ring
RO-06 | IRB-U-0345 | U | Rooftop | Irbid | Irbid | 32.5569 | 36.0086 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R03 | Fiber ring
RO-06 | IRB-U-0346 | U | Rooftop | Irbid | Irbid | 32.5569 | 36.0124 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R03 | Fiber ring
RO-06 | IRB-U-0347 | U | Rooftop | Irbid | Irbid | 32.5569 | 36.0181 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R03 | Fiber ring
RO-06 | IRB-U-0348 | U | Monopole / greenfield | Irbid | Irbid | 32.5569 | 36.0228 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R04 | Fiber ring
RO-06 | IRB-U-0349 | U | Monopole / greenfield | Irbid | Irbid | 32.5569 | 36.0275 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R04 | Fiber ring
RO-06 | IRB-U-0350 | U | Monopole / greenfield | Irbid | Irbid | 32.5596 | 35.8077 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R02 | Fiber ring
RO-06 | IRB-U-0351 | U | Monopole / greenfield | Irbid | Irbid | 32.5604 | 35.8125 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R02 | Fiber ring
RO-06 | IRB-U-0352 | U | Monopole / greenfield | Irbid | Irbid | 32.5596 | 35.8172 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R02 | Fiber ring
RO-06 | IRB-U-0353 | U | Rooftop | Irbid | Irbid | 32.5604 | 35.8229 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R03 | Fiber ring
RO-06 | IRB-U-0364 | U | Monopole / greenfield | Irbid | Irbid | 32.5604 | 35.9826 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R01 | Fiber ring
RO-06 | IRB-U-0365 | U | Monopole / greenfield | Irbid | Irbid | 32.5604 | 35.9864 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R02 | Fiber ring
RO-06 | IRB-U-0366 | U | Monopole / greenfield | Irbid | Irbid | 32.5604 | 35.9921 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R02 | Fiber ring
RO-06 | IRB-U-0367 | U | Rooftop | Irbid | Irbid | 32.5604 | 35.9968 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R02 | Fiber ring
RO-06 | IRB-U-0368 | U | Rooftop | Irbid | Irbid | 32.5604 | 36.0015 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R02 | Fiber ring
RO-06 | IRB-U-0369 | U | Rooftop | Irbid | Irbid | 32.5604 | 36.0062 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R03 | Fiber ring
RO-06 | IRB-U-0370 | U | Rooftop | Irbid | Irbid | 32.5604 | 36.0119 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R03 | Fiber ring
RO-06 | IRB-U-0371 | U | Rooftop | Irbid | Irbid | 32.5604 | 36.0147 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R03 | Fiber ring
RO-06 | IRB-U-0372 | U | Rooftop | Irbid | Irbid | 32.5604 | 36.0204 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R04 | Fiber ring
RO-06 | IRB-U-0373 | U | Monopole / greenfield | Irbid | Irbid | 32.5604 | 36.0251 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R04 | Fiber ring
RO-06 | IRB-U-0374 | U | Monopole / greenfield | Irbid | Irbid | 32.564 | 35.8101 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R01 | Fiber ring
RO-06 | IRB-U-0375 | U | Monopole / greenfield | Irbid | Irbid | 32.564 | 35.8139 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R02 | Fiber ring
RO-06 | IRB-U-0376 | U | Rooftop | Irbid | Irbid | 32.564 | 35.8205 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R03 | Fiber ring
RO-06 | IRB-U-0377 | U | Rooftop | Irbid | Irbid | 32.564 | 35.8243 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R03 | Fiber ring
RO-06 | IRB-U-0388 | U | Monopole / greenfield | Irbid | Irbid | 32.564 | 35.985 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R01 | Fiber ring
RO-06 | IRB-U-0389 | U | Monopole / greenfield | Irbid | Irbid | 32.564 | 35.9897 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R01 | Fiber ring
RO-06 | IRB-U-0390 | U | Monopole / greenfield | Irbid | Irbid | 32.564 | 35.9935 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R02 | Fiber ring
RO-06 | IRB-U-0391 | U | Rooftop | Irbid | Irbid | 32.564 | 35.9992 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R02 | Fiber ring
RO-06 | IRB-U-0392 | U | Rooftop | Irbid | Irbid | 32.564 | 36.0039 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R03 | Fiber ring
RO-06 | IRB-U-0393 | U | Rooftop | Irbid | Irbid | 32.564 | 36.0095 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R04 | Fiber ring
RO-06 | IRB-U-0394 | U | Rooftop | Irbid | Irbid | 32.5631 | 36.0133 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R04 | Fiber ring
RO-06 | IRB-U-0395 | U | Rooftop | Irbid | Irbid | 32.564 | 36.0181 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R05 | Fiber ring
RO-06 | IRB-U-0396 | U | Rooftop | Irbid | Irbid | 32.564 | 36.0228 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R05 | Fiber ring
RO-06 | IRB-U-0397 | U | Monopole / greenfield | Irbid | Irbid | 32.564 | 36.0275 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R05 | Fiber ring
RO-06 | IRB-U-0398 | U | Monopole / greenfield | Irbid | Irbid | 32.5667 | 35.8125 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R01 | Fiber ring
RO-06 | IRB-U-0399 | U | Rooftop | Irbid | Irbid | 32.5675 | 35.8181 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R02 | Fiber ring
RO-06 | IRB-U-0400 | U | Rooftop | Irbid | Irbid | 32.5675 | 35.8219 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R03 | Fiber ring
RO-06 | IRB-U-0401 | U | Rooftop | Irbid | Irbid | 32.5675 | 35.8257 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R03 | Fiber ring
RO-06 | IRB-U-0414 | U | Monopole / greenfield | Irbid | Irbid | 32.5675 | 35.9873 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R10 | Fiber ring
RO-06 | IRB-U-0415 | U | Monopole / greenfield | Irbid | Irbid | 32.5675 | 35.9921 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R10 | Fiber ring
RO-06 | IRB-U-0416 | U | Rooftop | Irbid | Irbid | 32.5675 | 35.9977 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R10 | Fiber ring
RO-06 | IRB-U-0417 | U | Rooftop | Irbid | Irbid | 32.5671 | 36.001 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R01 | Fiber ring
RO-06 | IRB-U-0418 | U | Rooftop | Irbid | Irbid | 32.5675 | 36.0062 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R06 | Fiber ring
RO-06 | IRB-U-0419 | U | Rooftop | Irbid | Irbid | 32.5675 | 36.011 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R05 | Fiber ring
RO-06 | IRB-U-0420 | U | Rooftop | Irbid | Irbid | 32.5675 | 36.0157 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R05 | Fiber ring
RO-06 | IRB-U-0421 | U | Rooftop | Irbid | Irbid | 32.5675 | 36.0204 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R05 | Fiber ring
RO-06 | IRB-U-0422 | U | Rooftop | Irbid | Irbid | 32.5667 | 36.0251 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R05 | Fiber ring
RO-06 | IRB-U-0423 | U | Rooftop | Irbid | Irbid | 32.5702 | 35.8196 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R01 | Fiber ring
RO-06 | IRB-U-0424 | U | Rooftop | Irbid | Irbid | 32.5702 | 35.8243 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R03 | Fiber ring
RO-06 | IRB-U-0425 | U | Rooftop | Irbid | Irbid | 32.5718 | 35.829 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R03 | Fiber ring
RO-06 | IRB-U-0429 | U | Rooftop | Irbid | Irbid | 32.571 | 35.8479 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R02 | Fiber ring
RO-06 | IRB-U-0430 | U | Rooftop | Irbid | Irbid | 32.571 | 35.8526 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R02 | Fiber ring
RO-06 | IRB-U-0431 | U | Rooftop | Irbid | Irbid | 32.5702 | 35.8574 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R02 | Fiber ring
RO-06 | IRB-U-0432 | U | Rooftop | Irbid | Irbid | 32.571 | 35.8621 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R03 | Fiber ring
RO-06 | IRB-U-0433 | U | Rooftop | Irbid | Irbid | 32.571 | 35.8668 | 30 | 3 | HUB-IRB-19 | HUB-IRB-19-R01 | Fiber ring
RO-06 | IRB-U-0434 | U | Rooftop | Irbid | Irbid | 32.571 | 35.8715 | 30 | 3 | HUB-IRB-19 | HUB-IRB-19-R02 | Fiber ring
RO-06 | IRB-U-0435 | U | Rooftop | Irbid | Irbid | 32.571 | 35.8763 | 30 | 3 | HUB-IRB-19 | HUB-IRB-19-R02 | Fiber ring
RO-06 | IRB-U-0439 | U | Monopole / greenfield | Irbid | Irbid | 32.5706 | 35.9892 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R10 | Fiber ring
RO-06 | IRB-U-0440 | U | Monopole / greenfield | Irbid | Irbid | 32.571 | 35.9944 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R09 | Fiber ring
RO-06 | IRB-U-0441 | U | Monopole / greenfield | Irbid | Irbid | 32.571 | 35.9992 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R08 | Fiber ring
RO-06 | IRB-U-0442 | U | Monopole / greenfield | Irbid | Irbid | 32.571 | 36.0039 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R07 | Fiber ring
RO-06 | IRB-U-0443 | U | Rooftop | Irbid | Irbid | 32.571 | 36.0086 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R06 | Fiber ring
RO-06 | IRB-U-0444 | U | Rooftop | Irbid | Irbid | 32.571 | 36.0133 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R06 | Fiber ring
RO-06 | IRB-U-0445 | U | Rooftop | Irbid | Irbid | 32.571 | 36.0181 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R06 | Fiber ring
RO-06 | IRB-U-0446 | U | Rooftop | Irbid | Irbid | 32.571 | 36.0228 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R06 | Fiber ring
RO-06 | IRB-U-0447 | U | Monopole / greenfield | Irbid | Irbid | 32.5745 | 35.8229 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R04 | Fiber ring
RO-06 | IRB-U-0448 | U | Rooftop | Irbid | Irbid | 32.5745 | 35.8267 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R04 | Fiber ring
RO-06 | IRB-U-0449 | U | Rooftop | Irbid | Irbid | 32.5737 | 35.8314 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R04 | Fiber ring
RO-06 | IRB-U-0450 | U | Rooftop | Irbid | Irbid | 32.5745 | 35.8361 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R01 | Fiber ring
RO-06 | IRB-U-0451 | U | Rooftop | Irbid | Irbid | 32.5745 | 35.8408 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R01 | Fiber ring
RO-06 | IRB-U-0452 | U | Rooftop | Irbid | Irbid | 32.5745 | 35.8456 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R01 | Fiber ring
RO-06 | IRB-U-0453 | U | Rooftop | Irbid | Irbid | 32.5745 | 35.8503 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R02 | Fiber ring
RO-06 | IRB-U-0454 | U | Rooftop | Irbid | Irbid | 32.5749 | 35.8555 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R02 | Fiber ring
RO-06 | IRB-U-0455 | U | Rooftop | Irbid | Irbid | 32.5754 | 35.8597 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R03 | Fiber ring
RO-06 | IRB-U-0456 | U | Rooftop | Irbid | Irbid | 32.5745 | 35.8645 | 30 | 3 | HUB-IRB-19 | HUB-IRB-19-R01 | Fiber ring
RO-06 | IRB-U-0457 | U | Rooftop | Irbid | Irbid | 32.5745 | 35.8692 | 30 | 3 | HUB-IRB-19 | HUB-IRB-19-R01 | Fiber ring
RO-06 | IRB-U-0458 | U | Rooftop | Irbid | Irbid | 32.5745 | 35.8739 | 30 | 3 | HUB-IRB-19 | HUB-IRB-19-R02 | Fiber ring
RO-06 | IRB-U-0459 | U | Rooftop | Irbid | Irbid | 32.5745 | 35.8786 | 30 | 3 | HUB-IRB-19 | HUB-IRB-19-R02 | Fiber ring
RO-06 | IRB-U-0460 | U | Monopole / greenfield | Irbid | Irbid | 32.5745 | 35.8834 | 30 | 3 | HUB-IRB-19 | HUB-IRB-19-R02 | Fiber ring
RO-06 | IRB-U-0461 | U | Monopole / greenfield | Irbid | Irbid | 32.5745 | 35.8881 | 30 | 3 | HUB-IRB-19 | HUB-IRB-19-R03 | Fiber ring
RO-06 | IRB-U-0462 | U | Monopole / greenfield | Irbid | Irbid | 32.5754 | 35.9921 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R09 | Fiber ring
RO-06 | IRB-U-0463 | U | Monopole / greenfield | Irbid | Irbid | 32.5737 | 35.9968 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R08 | Fiber ring
RO-06 | IRB-U-0464 | U | Monopole / greenfield | Irbid | Irbid | 32.5745 | 36.0015 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R08 | Fiber ring
RO-06 | IRB-U-0465 | U | Monopole / greenfield | Irbid | Irbid | 32.5745 | 36.0072 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R07 | Fiber ring
RO-06 | IRB-U-0466 | U | Monopole / greenfield | Irbid | Irbid | 32.5745 | 36.011 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R07 | Fiber ring
RO-06 | IRB-U-0467 | U | Rooftop | Irbid | Irbid | 32.5745 | 36.0157 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R06 | Fiber ring
RO-06 | IRB-U-0468 | U | Rooftop | Irbid | Irbid | 32.5745 | 36.0195 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R06 | Fiber ring
RO-06 | IRB-U-0469 | U | Monopole / greenfield | Irbid | Irbid | 32.5772 | 35.829 | 30 | 3 | HUB-IRB-04 | HUB-IRB-04-R04 | Fiber ring
RO-06 | IRB-U-0470 | U | Rooftop | Irbid | Irbid | 32.5772 | 35.8337 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R01 | Fiber ring
RO-06 | IRB-U-0471 | U | Monopole / greenfield | Irbid | Irbid | 32.5789 | 35.8385 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R01 | Fiber ring
RO-06 | IRB-U-0472 | U | Rooftop | Irbid | Irbid | 32.5781 | 35.8432 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R01 | Fiber ring
RO-06 | IRB-U-0473 | U | Rooftop | Irbid | Irbid | 32.5781 | 35.8489 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R02 | Fiber ring
RO-06 | IRB-U-0474 | U | Rooftop | Irbid | Irbid | 32.5781 | 35.8536 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R03 | Fiber ring
RO-06 | IRB-U-0475 | U | Rooftop | Irbid | Irbid | 32.5781 | 35.8583 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R03 | Fiber ring
RO-06 | IRB-U-0476 | U | Rooftop | Irbid | Irbid | 32.5781 | 35.8621 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R03 | Fiber ring
RO-06 | IRB-U-0477 | U | Rooftop | Irbid | Irbid | 32.5781 | 35.8668 | 30 | 3 | HUB-IRB-19 | HUB-IRB-19-R01 | Fiber ring
RO-06 | IRB-U-0478 | U | Rooftop | Irbid | Irbid | 32.5781 | 35.8706 | 30 | 3 | HUB-IRB-19 | HUB-IRB-19-R01 | Fiber ring
RO-06 | IRB-U-0479 | U | Monopole / greenfield | Irbid | Irbid | 32.5781 | 35.8763 | 30 | 3 | HUB-IRB-19 | HUB-IRB-19-R02 | Fiber ring
RO-06 | IRB-U-0480 | U | Monopole / greenfield | Irbid | Irbid | 32.5781 | 35.881 | 30 | 3 | HUB-IRB-19 | HUB-IRB-19-R02 | Fiber ring
RO-06 | IRB-U-0481 | U | Monopole / greenfield | Irbid | Irbid | 32.5781 | 35.9992 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R08 | Fiber ring
RO-06 | IRB-U-0482 | U | Monopole / greenfield | Irbid | Irbid | 32.5785 | 36.0044 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R08 | Fiber ring
RO-06 | IRB-U-0483 | U | Monopole / greenfield | Irbid | Irbid | 32.5781 | 36.0086 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R07 | Fiber ring
RO-06 | IRB-U-0484 | U | Monopole / greenfield | Irbid | Irbid | 32.5781 | 36.0133 | 30 | 3 | HUB-IRB-13 | HUB-IRB-13-R07 | Fiber ring
RO-06 | IRB-U-0485 | U | Monopole / greenfield | Irbid | Irbid | 32.5816 | 35.8408 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R06 | Fiber ring
RO-06 | IRB-U-0486 | U | Rooftop | Irbid | Irbid | 32.5808 | 35.8456 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R06 | Fiber ring
RO-06 | IRB-U-0487 | U | Rooftop | Irbid | Irbid | 32.5808 | 35.8503 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R01 | Fiber ring
RO-06 | IRB-U-0488 | U | Rooftop | Irbid | Irbid | 32.5812 | 35.8555 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R04 | Fiber ring
RO-06 | IRB-U-0489 | U | Rooftop | Irbid | Irbid | 32.5808 | 35.8597 | 30 | 3 | HUB-IRB-09 | HUB-IRB-09-R03 | Fiber ring
RO-06 | IRB-U-0490 | U | Rooftop | Irbid | Irbid | 32.5808 | 35.8645 | 30 | 3 | HUB-IRB-19 | HUB-IRB-19-R01 | Fiber ring
RO-06 | IRB-U-0491 | U | Rooftop | Irbid | Irbid | 32.5808 | 35.8692 | 30 | 3 | HUB-IRB-19 | HUB-IRB-19-R01 | Fiber ring
RO-06 | KAR-SU-0062 | SU | Monopole / greenfield | Karak | Karak | 31.1542 | 35.6914 | 32 | 3 | HUB-KAR-03 | HUB-KAR-03-R02 | Fiber ring
RO-06 | KAR-SU-0063 | SU | Monopole / greenfield | Karak | Karak | 31.1542 | 35.6996 | 32 | 3 | HUB-KAR-03 | HUB-KAR-03-R02 | Fiber ring
RO-06 | KAR-SU-0064 | SU | Monopole / greenfield | Karak | Karak | 31.1536 | 35.7044 | 32 | 3 | HUB-KAR-03 | HUB-KAR-03-R02 | Fiber ring
RO-06 | KAR-SU-0065 | SU | Monopole / greenfield | Karak | Karak | 31.1581 | 35.688 | 32 | 3 | HUB-KAR-03 | HUB-KAR-03-R01 | Fiber ring
RO-06 | KAR-SU-0066 | SU | Monopole / greenfield | Karak | Karak | 31.1593 | 35.6935 | 32 | 3 | HUB-KAR-03 | HUB-KAR-03-R01 | Fiber ring
RO-06 | KAR-SU-0067 | SU | Monopole / greenfield | Karak | Karak | 31.1593 | 35.703 | 32 | 3 | HUB-KAR-03 | HUB-KAR-03-R02 | Fiber ring
RO-06 | KAR-SU-0068 | SU | Monopole / greenfield | Karak | Karak | 31.1593 | 35.7071 | 32 | 3 | HUB-KAR-03 | HUB-KAR-03-R02 | Fiber ring
RO-06 | KAR-SU-0069 | SU | Monopole / greenfield | Karak | Karak | 31.1587 | 35.7228 | 32 | 3 | HUB-KAR-03 | HUB-KAR-03-R03 | Fiber ring
RO-06 | KAR-SU-0070 | SU | Monopole / greenfield | Karak | Karak | 31.1655 | 35.6778 | 32 | 3 | HUB-KAR-03 | HUB-KAR-03-R01 | Fiber ring
RO-06 | KAR-SU-0071 | SU | Monopole / greenfield | Karak | Karak | 31.165 | 35.6839 | 32 | 3 | HUB-KAR-03 | HUB-KAR-03-R01 | Fiber ring
RO-06 | KAR-SU-0072 | SU | Monopole / greenfield | Karak | Karak | 31.1644 | 35.6928 | 32 | 3 | HUB-KAR-03 | HUB-KAR-03-R01 | Fiber ring
RO-06 | KAR-SU-0073 | SU | Monopole / greenfield | Karak | Karak | 31.1644 | 35.7174 | 32 | 3 | HUB-KAR-03 | HUB-KAR-03-R03 | Fiber ring
RO-06 | KAR-SU-0076 | SU | Monopole / greenfield | Karak | Karak | 31.1683 | 35.6812 | 32 | 3 | HUB-KAR-03 | HUB-KAR-03-R01 | Fiber ring
RO-06 | KAR-U-0001 | U | Monopole / greenfield | Karak | Karak | 31.1656 | 35.699 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R02 | Fiber ring
RO-06 | KAR-U-0002 | U | Monopole / greenfield | Karak | Karak | 31.1648 | 35.7047 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R02 | Fiber ring
RO-06 | KAR-U-0003 | U | Monopole / greenfield | Karak | Karak | 31.1648 | 35.7094 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R03 | Fiber ring
RO-06 | KAR-U-0004 | U | Monopole / greenfield | Karak | Karak | 31.1652 | 35.7128 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R03 | Fiber ring
RO-06 | KAR-U-0005 | U | Monopole / greenfield | Karak | Karak | 31.1675 | 35.692 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R01 | Fiber ring
RO-06 | KAR-U-0006 | U | Monopole / greenfield | Karak | Karak | 31.1683 | 35.6976 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R06 | Fiber ring
RO-06 | KAR-U-0007 | U | Monopole / greenfield | Karak | Karak | 31.1683 | 35.7005 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R01 | Fiber ring
RO-06 | KAR-U-0008 | U | Rooftop | Karak | Karak | 31.1683 | 35.7071 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R03 | Fiber ring
RO-06 | KAR-U-0009 | U | Rooftop | Karak | Karak | 31.1691 | 35.7109 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R03 | Fiber ring
RO-06 | KAR-U-0010 | U | Monopole / greenfield | Karak | Karak | 31.1679 | 35.7151 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R03 | Fiber ring
RO-06 | KAR-U-0011 | U | Rooftop | Karak | Karak | 31.1718 | 35.6887 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R06 | Fiber ring
RO-06 | KAR-U-0012 | U | Monopole / greenfield | Karak | Karak | 31.1718 | 35.6953 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R05 | Fiber ring
RO-06 | KAR-U-0013 | U | Monopole / greenfield | Karak | Karak | 31.171 | 35.699 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R05 | Fiber ring
RO-06 | KAR-U-0014 | U | Monopole / greenfield | Karak | Karak | 31.1718 | 35.7028 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R04 | Fiber ring
RO-06 | KAR-U-0015 | U | Rooftop | Karak | Karak | 31.1718 | 35.7094 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R04 | Fiber ring
RO-06 | KAR-U-0016 | U | Rooftop | Karak | Karak | 31.1714 | 35.7128 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R04 | Fiber ring
RO-06 | KAR-U-0018 | U | Rooftop | Karak | Karak | 31.1753 | 35.6863 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R05 | Fiber ring
RO-06 | KAR-U-0019 | U | Rooftop | Karak | Karak | 31.1753 | 35.691 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R05 | Fiber ring
RO-06 | KAR-U-0020 | U | Monopole / greenfield | Karak | Karak | 31.1745 | 35.6967 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R05 | Fiber ring
RO-06 | KAR-U-0021 | U | Monopole / greenfield | Karak | Karak | 31.1749 | 35.7009 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R05 | Fiber ring
RO-06 | KAR-U-0022 | U | Rooftop | Karak | Karak | 31.1753 | 35.7071 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R04 | Fiber ring
RO-06 | KAR-U-0023 | U | Rooftop | Karak | Karak | 31.1753 | 35.7099 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R04 | Fiber ring
RO-06 | KAR-U-0028 | U | Rooftop | Karak | Karak | 31.1789 | 35.7 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R05 | Fiber ring
RO-06 | KAR-U-0029 | U | Rooftop | Karak | Karak | 31.1789 | 35.7028 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R04 | Fiber ring
RO-06 | KAR-U-0030 | U | Rooftop | Karak | Karak | 31.178 | 35.7085 | 30 | 3 | HUB-KAR-03 | HUB-KAR-03-R04 | Fiber ring
RO-06 | MA-SU-0102 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1773 | 35.759 | 32 | 3 | HUB-MA-02 | HUB-MA-02-R02 | Fiber ring
RO-06 | MA-SU-0106 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1818 | 35.7631 | 32 | 3 | HUB-MA-02 | HUB-MA-02-R02 | Fiber ring
RO-06 | MA-SU-0109 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1875 | 35.759 | 32 | 3 | HUB-MA-02 | HUB-MA-02-R02 | Fiber ring
RO-06 | MA-SU-0110 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1869 | 35.7665 | 32 | 3 | HUB-MA-02 | HUB-MA-02-R02 | Fiber ring
RO-06 | MA-SU-0113 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1926 | 35.7624 | 32 | 3 | HUB-MA-02 | HUB-MA-02-R02 | Fiber ring
RO-06 | MA-SU-0114 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.192 | 35.7686 | 32 | 3 | HUB-MA-02 | HUB-MA-02-R03 | Fiber ring
RO-06 | MA-SU-0117 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1971 | 35.7665 | 32 | 3 | HUB-MA-02 | HUB-MA-02-R03 | Fiber ring
RO-06 | MA-SU-0119 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.2034 | 35.7631 | 32 | 3 | HUB-MA-02 | HUB-MA-02-R03 | Fiber ring
RO-06 | MA-SU-0122 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.2061 | 35.7597 | 32 | 3 | HUB-MA-02 | HUB-MA-02-R03 | Fiber ring
RO-06 | MA-SU-0125 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.2124 | 35.7563 | 32 | 3 | HUB-MA-02 | HUB-MA-02-R04 | Fiber ring
RO-06 | MA-U-0019 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1854 | 35.7458 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R01 | Fiber ring
RO-06 | MA-U-0020 | U | Monopole / greenfield | Ma'an | Ma'an | 30.185 | 35.751 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R01 | Fiber ring
RO-06 | MA-U-0021 | U | Monopole / greenfield | Ma'an | Ma'an | 30.185 | 35.7558 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R02 | Fiber ring
RO-06 | MA-U-0028 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1885 | 35.7439 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R01 | Fiber ring
RO-06 | MA-U-0029 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1889 | 35.7482 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R01 | Fiber ring
RO-06 | MA-U-0030 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1889 | 35.7529 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R02 | Fiber ring
RO-06 | MA-U-0036 | U | Rooftop | Ma'an | Ma'an | 30.192 | 35.7369 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R01 | Fiber ring
RO-06 | MA-U-0037 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1928 | 35.7416 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R01 | Fiber ring
RO-06 | MA-U-0038 | U | Monopole / greenfield | Ma'an | Ma'an | 30.192 | 35.7473 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R01 | Fiber ring
RO-06 | MA-U-0043 | U | Rooftop | Ma'an | Ma'an | 30.1955 | 35.7345 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R05 | Fiber ring
RO-06 | MA-U-0044 | U | Rooftop | Ma'an | Ma'an | 30.1955 | 35.7392 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R05 | Fiber ring
RO-06 | MA-U-0045 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1955 | 35.743 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R05 | Fiber ring
RO-06 | MA-U-0046 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1947 | 35.7487 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R01 | Fiber ring
RO-06 | MA-U-0047 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1947 | 35.7581 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R03 | Fiber ring
RO-06 | MA-U-0053 | U | Rooftop | Ma'an | Ma'an | 30.1991 | 35.7378 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R05 | Fiber ring
RO-06 | MA-U-0054 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1991 | 35.7406 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R05 | Fiber ring
RO-06 | MA-U-0055 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1991 | 35.7463 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R05 | Fiber ring
RO-06 | MA-U-0056 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1991 | 35.751 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R03 | Fiber ring
RO-06 | MA-U-0057 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1991 | 35.7558 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R03 | Fiber ring
RO-06 | MA-U-0064 | U | Monopole / greenfield | Ma'an | Ma'an | 30.203 | 35.7444 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R04 | Fiber ring
RO-06 | MA-U-0065 | U | Monopole / greenfield | Ma'an | Ma'an | 30.203 | 35.7482 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R04 | Fiber ring
RO-06 | MA-U-0066 | U | Monopole / greenfield | Ma'an | Ma'an | 30.2026 | 35.7525 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R04 | Fiber ring
RO-06 | MA-U-0073 | U | Monopole / greenfield | Ma'an | Ma'an | 30.2053 | 35.7463 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R04 | Fiber ring
RO-06 | MA-U-0074 | U | Monopole / greenfield | Ma'an | Ma'an | 30.2061 | 35.751 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R04 | Fiber ring
RO-06 | MA-U-0081 | U | Monopole / greenfield | Ma'an | Ma'an | 30.2096 | 35.7487 | 30 | 3 | HUB-MA-02 | HUB-MA-02-R04 | Fiber ring
RO-06 | MAD-SU-0103 | SU | Monopole / greenfield | Madaba | Amman | 31.6836 | 35.7938 | 32 | 3 | HUB-MAD-02 | HUB-MAD-02-R02 | Fiber ring
RO-06 | MAD-SU-0104 | SU | Monopole / greenfield | Madaba | Madaba | 31.6899 | 35.7768 | 32 | 3 | HUB-MAD-02 | HUB-MAD-02-R01 | Fiber ring
RO-06 | MAD-SU-0105 | SU | Monopole / greenfield | Madaba | Madaba | 31.6887 | 35.7836 | 32 | 3 | HUB-MAD-02 | HUB-MAD-02-R01 | Fiber ring
RO-06 | MAD-SU-0106 | SU | Monopole / greenfield | Madaba | Madaba | 31.6887 | 35.7891 | 32 | 3 | HUB-MAD-02 | HUB-MAD-02-R02 | Fiber ring
RO-06 | MAD-SU-0107 | SU | Monopole / greenfield | Madaba | Amman | 31.6887 | 35.7972 | 32 | 3 | HUB-MAD-02 | HUB-MAD-02-R02 | Fiber ring
RO-06 | MAD-SU-0108 | SU | Monopole / greenfield | Madaba | Amman | 31.6887 | 35.8109 | 32 | 3 | HUB-MAD-03 | HUB-MAD-03-R01 | Fiber ring
RO-06 | MAD-SU-0109 | SU | Monopole / greenfield | Madaba | Madaba | 31.6938 | 35.7727 | 32 | 3 | HUB-MAD-02 | HUB-MAD-02-R01 | Fiber ring
RO-06 | MAD-SU-0110 | SU | Monopole / greenfield | Madaba | Madaba | 31.695 | 35.7802 | 32 | 3 | HUB-MAD-02 | HUB-MAD-02-R01 | Fiber ring
RO-06 | MAD-SU-0111 | SU | Monopole / greenfield | Madaba | Amman | 31.6938 | 35.7938 | 32 | 3 | HUB-MAD-02 | HUB-MAD-02-R02 | Fiber ring
RO-06 | MAD-SU-0112 | SU | Monopole / greenfield | Madaba | Amman | 31.6938 | 35.8075 | 32 | 3 | HUB-MAD-03 | HUB-MAD-03-R01 | Fiber ring
RO-06 | MAD-SU-0113 | SU | Monopole / greenfield | Madaba | Amman | 31.6926 | 35.8143 | 32 | 3 | HUB-MAD-03 | HUB-MAD-03-R02 | Fiber ring
RO-06 | MAD-SU-0114 | SU | Monopole / greenfield | Madaba | Amman | 31.6938 | 35.8225 | 32 | 3 | HUB-MAD-03 | HUB-MAD-03-R02 | Fiber ring
RO-06 | MAD-SU-0115 | SU | Monopole / greenfield | Madaba | Madaba | 31.7001 | 35.7631 | 32 | 3 | HUB-MAD-02 | HUB-MAD-02-R01 | Fiber ring
RO-06 | MAD-SU-0116 | SU | Monopole / greenfield | Madaba | Madaba | 31.6989 | 35.7713 | 32 | 3 | HUB-MAD-02 | HUB-MAD-02-R01 | Fiber ring
RO-06 | MAD-SU-0117 | SU | Monopole / greenfield | Madaba | Amman | 31.6989 | 35.8246 | 32 | 3 | HUB-MAD-03 | HUB-MAD-03-R02 | Fiber ring
RO-06 | MAD-SU-0118 | SU | Monopole / greenfield | Madaba | Madaba | 31.704 | 35.7583 | 32 | 3 | HUB-MAD-02 | HUB-MAD-02-R06 | Fiber ring
RO-06 | MAD-SU-0119 | SU | Monopole / greenfield | Madaba | Madaba | 31.7028 | 35.7665 | 32 | 3 | HUB-MAD-02 | HUB-MAD-02-R06 | Fiber ring
RO-06 | MAD-SU-0120 | SU | Monopole / greenfield | Madaba | Amman | 31.704 | 35.8211 | 32 | 3 | HUB-MAD-03 | HUB-MAD-03-R02 | Fiber ring
RO-06 | MAD-SU-0121 | SU | Monopole / greenfield | Madaba | Madaba | 31.7091 | 35.7631 | 32 | 3 | HUB-MAD-02 | HUB-MAD-02-R06 | Fiber ring
RO-06 | MAD-SU-0122 | SU | Monopole / greenfield | Madaba | Amman | 31.7091 | 35.8259 | 32 | 3 | HUB-MAD-03 | HUB-MAD-03-R02 | Fiber ring
RO-06 | MAD-SU-0123 | SU | Monopole / greenfield | Madaba | Amman | 31.7091 | 35.8314 | 32 | 3 | HUB-MAD-03 | HUB-MAD-03-R02 | Fiber ring
RO-06 | MAD-SU-0124 | SU | Monopole / greenfield | Madaba | Madaba | 31.7142 | 35.7583 | 32 | 3 | HUB-MAD-04 | HUB-MAD-04-R01 | Fiber ring
RO-06 | MAD-SU-0125 | SU | Monopole / greenfield | Madaba | Madaba | 31.713 | 35.7665 | 32 | 3 | HUB-MAD-04 | HUB-MAD-04-R01 | Fiber ring
RO-06 | MAD-SU-0126 | SU | Monopole / greenfield | Madaba | Amman | 31.7142 | 35.8198 | 32 | 3 | HUB-MAD-03 | HUB-MAD-03-R03 | Fiber ring
RO-06 | MAD-SU-0127 | SU | Monopole / greenfield | Madaba | Amman | 31.7142 | 35.828 | 32 | 3 | HUB-MAD-03 | HUB-MAD-03-R03 | Fiber ring
RO-06 | MAD-SU-0128 | SU | Monopole / greenfield | Madaba | Madaba | 31.7204 | 35.7631 | 32 | 3 | HUB-MAD-04 | HUB-MAD-04-R01 | Fiber ring
RO-06 | MAD-SU-0129 | SU | Monopole / greenfield | Madaba | Amman | 31.7181 | 35.8246 | 32 | 3 | HUB-MAD-03 | HUB-MAD-03-R03 | Fiber ring
RO-06 | MAD-SU-0130 | SU | Monopole / greenfield | Madaba | Amman | 31.7204 | 35.8314 | 32 | 3 | HUB-MAD-03 | HUB-MAD-03-R03 | Fiber ring
RO-06 | MAD-SU-0131 | SU | Monopole / greenfield | Madaba | Madaba | 31.7232 | 35.7597 | 32 | 3 | HUB-MAD-04 | HUB-MAD-04-R01 | Fiber ring
RO-06 | MAD-SU-0132 | SU | Monopole / greenfield | Madaba | Madaba | 31.7232 | 35.7665 | 32 | 3 | HUB-MAD-04 | HUB-MAD-04-R01 | Fiber ring
RO-06 | MAD-SU-0133 | SU | Monopole / greenfield | Madaba | Madaba | 31.7244 | 35.8211 | 32 | 3 | HUB-MAD-03 | HUB-MAD-03-R04 | Fiber ring
RO-06 | MAD-SU-0134 | SU | Monopole / greenfield | Madaba | Madaba | 31.7306 | 35.7631 | 32 | 3 | HUB-MAD-04 | HUB-MAD-04-R06 | Fiber ring
RO-06 | MAD-SU-0135 | SU | Monopole / greenfield | Madaba | Madaba | 31.7294 | 35.7699 | 32 | 3 | HUB-MAD-04 | HUB-MAD-04-R06 | Fiber ring
RO-06 | MAD-SU-0138 | SU | Monopole / greenfield | Madaba | Madaba | 31.7334 | 35.7665 | 32 | 3 | HUB-MAD-04 | HUB-MAD-04-R06 | Fiber ring
RO-06 | MAD-SU-0139 | SU | Monopole / greenfield | Madaba | Madaba | 31.7345 | 35.772 | 32 | 3 | HUB-MAD-04 | HUB-MAD-04-R06 | Fiber ring
RO-06 | MAD-SU-0143 | SU | Monopole / greenfield | Madaba | Madaba | 31.7396 | 35.7699 | 32 | 3 | HUB-MAD-04 | HUB-MAD-04-R05 | Fiber ring
RO-06 | MAD-SU-0144 | SU | Monopole / greenfield | Madaba | Madaba | 31.7396 | 35.7768 | 32 | 3 | HUB-MAD-04 | HUB-MAD-04-R05 | Fiber ring
RO-06 | MAD-SU-0145 | SU | Monopole / greenfield | Madaba | Madaba | 31.7396 | 35.7836 | 32 | 3 | HUB-MAD-04 | HUB-MAD-04-R05 | Fiber ring
RO-06 | MAD-SU-0151 | SU | Monopole / greenfield | Madaba | Madaba | 31.7447 | 35.7802 | 32 | 3 | HUB-MAD-04 | HUB-MAD-04-R05 | Fiber ring
RO-06 | MAD-SU-0152 | SU | Monopole / greenfield | Madaba | Madaba | 31.7435 | 35.787 | 32 | 3 | HUB-MAD-04 | HUB-MAD-04-R05 | Fiber ring
RO-06 | MAD-U-0001 | U | Monopole / greenfield | Madaba | Madaba | 31.697 | 35.7865 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R02 | Fiber ring
RO-06 | MAD-U-0002 | U | Monopole / greenfield | Madaba | Madaba | 31.6961 | 35.7912 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R02 | Fiber ring
RO-06 | MAD-U-0003 | U | Monopole / greenfield | Madaba | Amman | 31.697 | 35.7959 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R02 | Fiber ring
RO-06 | MAD-U-0004 | U | Monopole / greenfield | Madaba | Amman | 31.697 | 35.8007 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R03 | Fiber ring
RO-06 | MAD-U-0005 | U | Monopole / greenfield | Madaba | Madaba | 31.6997 | 35.7794 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R01 | Fiber ring
RO-06 | MAD-U-0006 | U | Rooftop | Madaba | Madaba | 31.7013 | 35.7841 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R01 | Fiber ring
RO-06 | MAD-U-0007 | U | Monopole / greenfield | Madaba | Madaba | 31.7005 | 35.7879 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R03 | Fiber ring
RO-06 | MAD-U-0008 | U | Monopole / greenfield | Madaba | Madaba | 31.7005 | 35.7936 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R03 | Fiber ring
RO-06 | MAD-U-0009 | U | Monopole / greenfield | Madaba | Amman | 31.7005 | 35.7983 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R03 | Fiber ring
RO-06 | MAD-U-0010 | U | Monopole / greenfield | Madaba | Amman | 31.7005 | 35.803 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R01 | Fiber ring
RO-06 | MAD-U-0011 | U | Monopole / greenfield | Madaba | Amman | 31.7005 | 35.8077 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R01 | Fiber ring
RO-06 | MAD-U-0012 | U | Monopole / greenfield | Madaba | Madaba | 31.704 | 35.7761 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R06 | Fiber ring
RO-06 | MAD-U-0013 | U | Rooftop | Madaba | Madaba | 31.704 | 35.7827 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R05 | Fiber ring
RO-06 | MAD-U-0014 | U | Rooftop | Madaba | Madaba | 31.704 | 35.7855 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R04 | Fiber ring
RO-06 | MAD-U-0015 | U | Rooftop | Madaba | Madaba | 31.7044 | 35.7907 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R03 | Fiber ring
RO-06 | MAD-U-0016 | U | Monopole / greenfield | Madaba | Madaba | 31.7048 | 35.7959 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R03 | Fiber ring
RO-06 | MAD-U-0017 | U | Monopole / greenfield | Madaba | Amman | 31.704 | 35.8007 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R01 | Fiber ring
RO-06 | MAD-U-0018 | U | Monopole / greenfield | Madaba | Amman | 31.7048 | 35.8054 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R01 | Fiber ring
RO-06 | MAD-U-0019 | U | Monopole / greenfield | Madaba | Amman | 31.704 | 35.8101 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R01 | Fiber ring
RO-06 | MAD-U-0020 | U | Monopole / greenfield | Madaba | Amman | 31.704 | 35.8148 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R02 | Fiber ring
RO-06 | MAD-U-0021 | U | Monopole / greenfield | Madaba | Madaba | 31.7075 | 35.7737 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R06 | Fiber ring
RO-06 | MAD-U-0022 | U | Monopole / greenfield | Madaba | Madaba | 31.7083 | 35.7794 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R05 | Fiber ring
RO-06 | MAD-U-0023 | U | Rooftop | Madaba | Madaba | 31.7075 | 35.7841 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R05 | Fiber ring
RO-06 | MAD-U-0024 | U | Rooftop | Madaba | Madaba | 31.7083 | 35.7888 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R04 | Fiber ring
RO-06 | MAD-U-0025 | U | Rooftop | Madaba | Madaba | 31.7075 | 35.7926 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R03 | Fiber ring
RO-06 | MAD-U-0026 | U | Rooftop | Madaba | Madaba | 31.7075 | 35.7983 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R06 | Fiber ring
RO-06 | MAD-U-0027 | U | Rooftop | Madaba | Amman | 31.7075 | 35.803 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R06 | Fiber ring
RO-06 | MAD-U-0028 | U | Monopole / greenfield | Madaba | Amman | 31.7075 | 35.8068 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R06 | Fiber ring
RO-06 | MAD-U-0029 | U | Monopole / greenfield | Madaba | Amman | 31.7075 | 35.8125 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R01 | Fiber ring
RO-06 | MAD-U-0030 | U | Monopole / greenfield | Madaba | Madaba | 31.711 | 35.7723 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R05 | Fiber ring
RO-06 | MAD-U-0031 | U | Rooftop | Madaba | Madaba | 31.7114 | 35.7775 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R05 | Fiber ring
RO-06 | MAD-U-0032 | U | Rooftop | Madaba | Madaba | 31.711 | 35.7808 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R05 | Fiber ring
RO-06 | MAD-U-0033 | U | Rooftop | Madaba | Madaba | 31.711 | 35.7865 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R04 | Fiber ring
RO-06 | MAD-U-0034 | U | Rooftop | Madaba | Madaba | 31.711 | 35.7903 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R04 | Fiber ring
RO-06 | MAD-U-0035 | U | Rooftop | Madaba | Madaba | 31.7119 | 35.7959 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R04 | Fiber ring
RO-06 | MAD-U-0036 | U | Rooftop | Madaba | Madaba | 31.711 | 35.8007 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R05 | Fiber ring
RO-06 | MAD-U-0037 | U | Rooftop | Madaba | Amman | 31.711 | 35.8044 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R05 | Fiber ring
RO-06 | MAD-U-0038 | U | Monopole / greenfield | Madaba | Amman | 31.711 | 35.8101 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R04 | Fiber ring
RO-06 | MAD-U-0039 | U | Monopole / greenfield | Madaba | Amman | 31.711 | 35.8148 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R03 | Fiber ring
RO-06 | MAD-U-0040 | U | Rooftop | Madaba | Madaba | 31.7142 | 35.7751 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R02 | Fiber ring
RO-06 | MAD-U-0041 | U | Rooftop | Madaba | Madaba | 31.7146 | 35.7784 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R02 | Fiber ring
RO-06 | MAD-U-0042 | U | Rooftop | Madaba | Madaba | 31.7146 | 35.7841 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R05 | Fiber ring
RO-06 | MAD-U-0043 | U | Rooftop | Madaba | Madaba | 31.7154 | 35.7888 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R04 | Fiber ring
RO-06 | MAD-U-0044 | U | Rooftop | Madaba | Madaba | 31.7146 | 35.7936 | 30 | 3 | HUB-MAD-02 | HUB-MAD-02-R04 | Fiber ring
RO-06 | MAD-U-0045 | U | Rooftop | Madaba | Madaba | 31.7146 | 35.7974 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R05 | Fiber ring
RO-06 | MAD-U-0046 | U | Rooftop | Madaba | Madaba | 31.7146 | 35.803 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R05 | Fiber ring
RO-06 | MAD-U-0047 | U | Monopole / greenfield | Madaba | Amman | 31.7146 | 35.8077 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R05 | Fiber ring
RO-06 | MAD-U-0048 | U | Monopole / greenfield | Madaba | Amman | 31.7146 | 35.8125 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R04 | Fiber ring
RO-06 | MAD-U-0049 | U | Monopole / greenfield | Madaba | Amman | 31.7146 | 35.8172 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R03 | Fiber ring
RO-06 | MAD-U-0050 | U | Monopole / greenfield | Madaba | Madaba | 31.7173 | 35.7723 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R01 | Fiber ring
RO-06 | MAD-U-0051 | U | Rooftop | Madaba | Madaba | 31.7181 | 35.777 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R02 | Fiber ring
RO-06 | MAD-U-0052 | U | Rooftop | Madaba | Madaba | 31.7189 | 35.7818 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R02 | Fiber ring
RO-06 | MAD-U-0053 | U | Rooftop | Madaba | Madaba | 31.7181 | 35.7874 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R02 | Fiber ring
RO-06 | MAD-U-0054 | U | Rooftop | Madaba | Madaba | 31.7181 | 35.7903 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R02 | Fiber ring
RO-06 | MAD-U-0055 | U | Rooftop | Madaba | Madaba | 31.7181 | 35.795 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R03 | Fiber ring
RO-06 | MAD-U-0056 | U | Rooftop | Madaba | Madaba | 31.7189 | 35.8007 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R05 | Fiber ring
RO-06 | MAD-U-0057 | U | Rooftop | Madaba | Madaba | 31.7181 | 35.8054 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R05 | Fiber ring
RO-06 | MAD-U-0058 | U | Monopole / greenfield | Madaba | Madaba | 31.7181 | 35.8101 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R04 | Fiber ring
RO-06 | MAD-U-0059 | U | Monopole / greenfield | Madaba | Amman | 31.7181 | 35.8148 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R04 | Fiber ring
RO-06 | MAD-U-0060 | U | Monopole / greenfield | Madaba | Amman | 31.7181 | 35.8196 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R03 | Fiber ring
RO-06 | MAD-U-0061 | U | Monopole / greenfield | Madaba | Madaba | 31.7216 | 35.7747 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R01 | Fiber ring
RO-06 | MAD-U-0062 | U | Rooftop | Madaba | Madaba | 31.7216 | 35.7803 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R02 | Fiber ring
RO-06 | MAD-U-0063 | U | Rooftop | Madaba | Madaba | 31.7224 | 35.7841 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R03 | Fiber ring
RO-06 | MAD-U-0064 | U | Rooftop | Madaba | Madaba | 31.7216 | 35.7879 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R03 | Fiber ring
RO-06 | MAD-U-0065 | U | Rooftop | Madaba | Madaba | 31.7216 | 35.7936 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R03 | Fiber ring
RO-06 | MAD-U-0069 | U | Monopole / greenfield | Madaba | Madaba | 31.7212 | 35.813 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R04 | Fiber ring
RO-06 | MAD-U-0070 | U | Monopole / greenfield | Madaba | Madaba | 31.7216 | 35.8172 | 30 | 3 | HUB-MAD-03 | HUB-MAD-03-R04 | Fiber ring
RO-06 | MAD-U-0071 | U | Monopole / greenfield | Madaba | Madaba | 31.726 | 35.7723 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R06 | Fiber ring
RO-06 | MAD-U-0072 | U | Monopole / greenfield | Madaba | Madaba | 31.7251 | 35.777 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R01 | Fiber ring
RO-06 | MAD-U-0073 | U | Monopole / greenfield | Madaba | Madaba | 31.7251 | 35.7827 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R03 | Fiber ring
RO-06 | MAD-U-0074 | U | Rooftop | Madaba | Madaba | 31.7247 | 35.786 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R03 | Fiber ring
RO-06 | MAD-U-0075 | U | Rooftop | Madaba | Madaba | 31.7243 | 35.7912 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R03 | Fiber ring
RO-06 | MAD-U-0081 | U | Monopole / greenfield | Madaba | Madaba | 31.7287 | 35.7747 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R06 | Fiber ring
RO-06 | MAD-U-0082 | U | Monopole / greenfield | Madaba | Madaba | 31.7287 | 35.7794 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R05 | Fiber ring
RO-06 | MAD-U-0083 | U | Rooftop | Madaba | Madaba | 31.7287 | 35.7841 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R04 | Fiber ring
RO-06 | MAD-U-0084 | U | Rooftop | Madaba | Madaba | 31.7287 | 35.7879 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R04 | Fiber ring
RO-06 | MAD-U-0090 | U | Monopole / greenfield | Madaba | Madaba | 31.7322 | 35.777 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R05 | Fiber ring
RO-06 | MAD-U-0091 | U | Monopole / greenfield | Madaba | Madaba | 31.7322 | 35.7818 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R04 | Fiber ring
RO-06 | MAD-U-0092 | U | Rooftop | Madaba | Madaba | 31.7322 | 35.7865 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R04 | Fiber ring
RO-06 | MAD-U-0093 | U | Rooftop | Madaba | Madaba | 31.7322 | 35.7903 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R04 | Fiber ring
RO-06 | MAD-U-0098 | U | Monopole / greenfield | Madaba | Madaba | 31.7357 | 35.7841 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R04 | Fiber ring
RO-06 | MAD-U-0099 | U | Monopole / greenfield | Madaba | Madaba | 31.7353 | 35.7884 | 30 | 3 | HUB-MAD-04 | HUB-MAD-04-R04 | Fiber ring
RO-06 | MAF-SU-0121 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3098 | 36.2068 | 32 | 3 | HUB-MAF-02 | HUB-MAF-02-R01 | Fiber ring
RO-06 | MAF-SU-0122 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3161 | 36.1898 | 32 | 3 | HUB-MAF-02 | HUB-MAF-02-R01 | Fiber ring
RO-06 | MAF-SU-0123 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3149 | 36.1952 | 32 | 3 | HUB-MAF-02 | HUB-MAF-02-R01 | Fiber ring
RO-06 | MAF-SU-0124 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3149 | 36.2034 | 32 | 3 | HUB-MAF-02 | HUB-MAF-02-R01 | Fiber ring
RO-06 | MAF-SU-0125 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3149 | 36.2102 | 32 | 3 | HUB-MAF-02 | HUB-MAF-02-R02 | Fiber ring
RO-06 | MAF-SU-0126 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3149 | 36.2171 | 32 | 3 | HUB-MAF-02 | HUB-MAF-02-R02 | Fiber ring
RO-06 | MAF-SU-0127 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3149 | 36.2239 | 32 | 3 | HUB-MAF-02 | HUB-MAF-02-R02 | Fiber ring
RO-06 | MAF-SU-0131 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.32 | 36.1932 | 32 | 3 | HUB-MAF-02 | HUB-MAF-02-R01 | Fiber ring
RO-06 | MAF-SU-0132 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.32 | 36.2 | 32 | 3 | HUB-MAF-02 | HUB-MAF-02-R01 | Fiber ring
RO-06 | MAF-SU-0133 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.32 | 36.2068 | 32 | 3 | HUB-MAF-02 | HUB-MAF-02-R01 | Fiber ring
RO-06 | MAF-SU-0134 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.32 | 36.2137 | 32 | 3 | HUB-MAF-02 | HUB-MAF-02-R02 | Fiber ring
RO-06 | MAF-SU-0135 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.32 | 36.2205 | 32 | 3 | HUB-MAF-02 | HUB-MAF-02-R02 | Fiber ring
RO-06 | MAF-SU-0161 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3556 | 36.2375 | 32 | 3 | HUB-MAF-05 | HUB-MAF-05-R03 | Fiber ring
RO-06 | MAF-SU-0169 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3658 | 36.2239 | 32 | 3 | HUB-MAF-05 | HUB-MAF-05-R04 | Fiber ring
RO-06 | MAF-SU-0174 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3709 | 36.2137 | 32 | 3 | HUB-MAF-05 | HUB-MAF-05-R05 | Fiber ring
RO-06 | MAF-SU-0175 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3709 | 36.2205 | 32 | 3 | HUB-MAF-05 | HUB-MAF-05-R04 | Fiber ring
RO-06 | MAF-U-0001 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3243 | 36.1976 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R05 | Fiber ring
RO-06 | MAF-U-0002 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3243 | 36.2024 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R05 | Fiber ring
RO-06 | MAF-U-0003 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3243 | 36.2071 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R01 | Fiber ring
RO-06 | MAF-U-0004 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3243 | 36.2118 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R02 | Fiber ring
RO-06 | MAF-U-0005 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3243 | 36.2165 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R02 | Fiber ring
RO-06 | MAF-U-0006 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3243 | 36.2213 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R03 | Fiber ring
RO-06 | MAF-U-0008 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3278 | 36.1953 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R05 | Fiber ring
RO-06 | MAF-U-0009 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3278 | 36.2 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R05 | Fiber ring
RO-06 | MAF-U-0010 | U | Rooftop | Mafraq | Mafraq | 32.3278 | 36.2047 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R04 | Fiber ring
RO-06 | MAF-U-0011 | U | Rooftop | Mafraq | Mafraq | 32.3278 | 36.2094 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R03 | Fiber ring
RO-06 | MAF-U-0012 | U | Rooftop | Mafraq | Mafraq | 32.3278 | 36.2142 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R03 | Fiber ring
RO-06 | MAF-U-0013 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3278 | 36.2189 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R03 | Fiber ring
RO-06 | MAF-U-0019 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3314 | 36.1976 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R05 | Fiber ring
RO-06 | MAF-U-0020 | U | Rooftop | Mafraq | Mafraq | 32.3314 | 36.2024 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R05 | Fiber ring
RO-06 | MAF-U-0021 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3314 | 36.2071 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R04 | Fiber ring
RO-06 | MAF-U-0022 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3314 | 36.2118 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R03 | Fiber ring
RO-06 | MAF-U-0023 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3314 | 36.2165 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R03 | Fiber ring
RO-06 | MAF-U-0031 | U | Rooftop | Mafraq | Mafraq | 32.3349 | 36.2 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R05 | Fiber ring
RO-06 | MAF-U-0032 | U | Rooftop | Mafraq | Mafraq | 32.3349 | 36.2047 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R04 | Fiber ring
RO-06 | MAF-U-0033 | U | Rooftop | Mafraq | Mafraq | 32.3349 | 36.2094 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R04 | Fiber ring
RO-06 | MAF-U-0034 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3349 | 36.2142 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R03 | Fiber ring
RO-06 | MAF-U-0043 | U | Rooftop | Mafraq | Mafraq | 32.3384 | 36.2024 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R04 | Fiber ring
RO-06 | MAF-U-0044 | U | Rooftop | Mafraq | Mafraq | 32.3384 | 36.2071 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R04 | Fiber ring
RO-06 | MAF-U-0045 | U | Rooftop | Mafraq | Mafraq | 32.3384 | 36.2118 | 30 | 3 | HUB-MAF-02 | HUB-MAF-02-R04 | Fiber ring
RO-06 | MAF-U-0056 | U | Rooftop | Mafraq | Mafraq | 32.3419 | 36.2047 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R01 | Fiber ring
RO-06 | MAF-U-0057 | U | Rooftop | Mafraq | Mafraq | 32.3419 | 36.2094 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R01 | Fiber ring
RO-06 | MAF-U-0058 | U | Rooftop | Mafraq | Mafraq | 32.3419 | 36.2142 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R02 | Fiber ring
RO-06 | MAF-U-0059 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3419 | 36.2189 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R02 | Fiber ring
RO-06 | MAF-U-0067 | U | Rooftop | Mafraq | Mafraq | 32.3454 | 36.2014 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R01 | Fiber ring
RO-06 | MAF-U-0068 | U | Rooftop | Mafraq | Mafraq | 32.3454 | 36.2071 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R01 | Fiber ring
RO-06 | MAF-U-0069 | U | Rooftop | Mafraq | Mafraq | 32.3454 | 36.2118 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R02 | Fiber ring
RO-06 | MAF-U-0070 | U | Rooftop | Mafraq | Mafraq | 32.3454 | 36.2156 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R02 | Fiber ring
RO-06 | MAF-U-0071 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3454 | 36.2213 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R02 | Fiber ring
RO-06 | MAF-U-0080 | U | Rooftop | Mafraq | Mafraq | 32.349 | 36.2047 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R01 | Fiber ring
RO-06 | MAF-U-0081 | U | Rooftop | Mafraq | Mafraq | 32.349 | 36.2094 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R01 | Fiber ring
RO-06 | MAF-U-0082 | U | Rooftop | Mafraq | Mafraq | 32.349 | 36.2142 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R01 | Fiber ring
RO-06 | MAF-U-0083 | U | Rooftop | Mafraq | Mafraq | 32.349 | 36.218 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R02 | Fiber ring
RO-06 | MAF-U-0084 | U | Monopole / greenfield | Mafraq | Mafraq | 32.349 | 36.2236 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R02 | Fiber ring
RO-06 | MAF-U-0085 | U | Monopole / greenfield | Mafraq | Mafraq | 32.349 | 36.2284 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R03 | Fiber ring
RO-06 | MAF-U-0092 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3525 | 36.2071 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R06 | Fiber ring
RO-06 | MAF-U-0093 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3525 | 36.2118 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R06 | Fiber ring
RO-06 | MAF-U-0094 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3525 | 36.2165 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R01 | Fiber ring
RO-06 | MAF-U-0095 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3525 | 36.2213 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R03 | Fiber ring
RO-06 | MAF-U-0096 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3525 | 36.226 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R03 | Fiber ring
RO-06 | MAF-U-0097 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3525 | 36.2307 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R03 | Fiber ring
RO-06 | MAF-U-0102 | U | Monopole / greenfield | Mafraq | Mafraq | 32.356 | 36.2047 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R06 | Fiber ring
RO-06 | MAF-U-0103 | U | Monopole / greenfield | Mafraq | Mafraq | 32.356 | 36.2094 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R05 | Fiber ring
RO-06 | MAF-U-0104 | U | Monopole / greenfield | Mafraq | Mafraq | 32.356 | 36.2132 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R05 | Fiber ring
RO-06 | MAF-U-0105 | U | Monopole / greenfield | Mafraq | Mafraq | 32.356 | 36.2189 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R04 | Fiber ring
RO-06 | MAF-U-0106 | U | Monopole / greenfield | Mafraq | Mafraq | 32.356 | 36.2236 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R03 | Fiber ring
RO-06 | MAF-U-0107 | U | Monopole / greenfield | Mafraq | Mafraq | 32.356 | 36.2284 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R03 | Fiber ring
RO-06 | MAF-U-0111 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3587 | 36.2071 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R05 | Fiber ring
RO-06 | MAF-U-0112 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3595 | 36.2118 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R05 | Fiber ring
RO-06 | MAF-U-0113 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3595 | 36.2165 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R04 | Fiber ring
RO-06 | MAF-U-0114 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3595 | 36.2213 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R04 | Fiber ring
RO-06 | MAF-U-0115 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3595 | 36.226 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R04 | Fiber ring
RO-06 | MAF-U-0118 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3631 | 36.2094 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R05 | Fiber ring
RO-06 | MAF-U-0119 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3631 | 36.2142 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R05 | Fiber ring
RO-06 | MAF-U-0120 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3631 | 36.2189 | 30 | 3 | HUB-MAF-05 | HUB-MAF-05-R04 | Fiber ring
RO-06 | TAF-SU-0044 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8125 | 35.5931 | 32 | 3 | HUB-TAF-02 | HUB-TAF-02-R02 | Fiber ring
RO-06 | TAF-SU-0045 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8131 | 35.6007 | 32 | 3 | HUB-TAF-02 | HUB-TAF-02-R02 | Fiber ring
RO-06 | TAF-SU-0046 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8182 | 35.5904 | 32 | 3 | HUB-TAF-02 | HUB-TAF-02-R01 | Fiber ring
RO-06 | TAF-SU-0047 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8176 | 35.5966 | 32 | 3 | HUB-TAF-02 | HUB-TAF-02-R02 | Fiber ring
RO-06 | TAF-SU-0048 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8188 | 35.6034 | 32 | 3 | HUB-TAF-02 | HUB-TAF-02-R02 | Fiber ring
RO-06 | TAF-SU-0049 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8233 | 35.587 | 32 | 3 | HUB-TAF-02 | HUB-TAF-02-R01 | Fiber ring
RO-06 | TAF-SU-0050 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8221 | 35.5924 | 32 | 3 | HUB-TAF-02 | HUB-TAF-02-R01 | Fiber ring
RO-06 | TAF-SU-0051 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8221 | 35.6266 | 32 | 3 | HUB-TAF-02 | HUB-TAF-02-R03 | Fiber ring
RO-06 | TAF-SU-0052 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8278 | 35.5815 | 32 | 3 | HUB-TAF-02 | HUB-TAF-02-R01 | Fiber ring
RO-06 | TAF-SU-0053 | SU | Rooftop | Tafilah | Tafilah | 30.8272 | 35.589 | 32 | 3 | HUB-TAF-02 | HUB-TAF-02-R01 | Fiber ring
RO-06 | TAF-SU-0054 | SU | Rooftop | Tafilah | Tafilah | 30.8284 | 35.6218 | 32 | 3 | HUB-TAF-02 | HUB-TAF-02-R03 | Fiber ring
RO-06 | TAF-SU-0055 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8335 | 35.5774 | 32 | 3 | HUB-TAF-02 | HUB-TAF-02-R06 | Fiber ring
RO-06 | TAF-SU-0056 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8335 | 35.5843 | 32 | 3 | HUB-TAF-02 | HUB-TAF-02-R06 | Fiber ring
RO-06 | TAF-SU-0058 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8386 | 35.5808 | 32 | 3 | HUB-TAF-02 | HUB-TAF-02-R06 | Fiber ring
RO-06 | TAF-U-0001 | U | Monopole / greenfield | Tafilah | Tafilah | 30.8229 | 35.6031 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R02 | Fiber ring
RO-06 | TAF-U-0002 | U | Monopole / greenfield | Tafilah | Tafilah | 30.8229 | 35.6059 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R02 | Fiber ring
RO-06 | TAF-U-0003 | U | Rooftop | Tafilah | Tafilah | 30.8256 | 35.5951 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R01 | Fiber ring
RO-06 | TAF-U-0004 | U | Rooftop | Tafilah | Tafilah | 30.8264 | 35.6007 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R01 | Fiber ring
RO-06 | TAF-U-0005 | U | Rooftop | Tafilah | Tafilah | 30.8256 | 35.6045 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R02 | Fiber ring
RO-06 | TAF-U-0006 | U | Monopole / greenfield | Tafilah | Tafilah | 30.8268 | 35.6097 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R03 | Fiber ring
RO-06 | TAF-U-0007 | U | Monopole / greenfield | Tafilah | Tafilah | 30.8256 | 35.614 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R03 | Fiber ring
RO-06 | TAF-U-0008 | U | Rooftop | Tafilah | Tafilah | 30.8295 | 35.5922 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R06 | Fiber ring
RO-06 | TAF-U-0009 | U | Rooftop | Tafilah | Tafilah | 30.8299 | 35.5984 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R06 | Fiber ring
RO-06 | TAF-U-0010 | U | Rooftop | Tafilah | Tafilah | 30.8295 | 35.6026 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R01 | Fiber ring
RO-06 | TAF-U-0011 | U | Rooftop | Tafilah | Tafilah | 30.8299 | 35.6078 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R03 | Fiber ring
RO-06 | TAF-U-0012 | U | Monopole / greenfield | Tafilah | Tafilah | 30.8291 | 35.6116 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R03 | Fiber ring
RO-06 | TAF-U-0013 | U | Monopole / greenfield | Tafilah | Tafilah | 30.8291 | 35.6163 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R03 | Fiber ring
RO-06 | TAF-U-0014 | U | Monopole / greenfield | Tafilah | Tafilah | 30.8326 | 35.5951 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R06 | Fiber ring
RO-06 | TAF-U-0015 | U | Rooftop | Tafilah | Tafilah | 30.8335 | 35.6007 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R05 | Fiber ring
RO-06 | TAF-U-0016 | U | Rooftop | Tafilah | Tafilah | 30.8335 | 35.6055 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R04 | Fiber ring
RO-06 | TAF-U-0017 | U | Rooftop | Tafilah | Tafilah | 30.8326 | 35.6093 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R04 | Fiber ring
RO-06 | TAF-U-0018 | U | Rooftop | Tafilah | Tafilah | 30.8326 | 35.614 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R04 | Fiber ring
RO-06 | TAF-U-0019 | U | Rooftop | Tafilah | Tafilah | 30.8326 | 35.6187 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R04 | Fiber ring
RO-06 | TAF-U-0020 | U | Monopole / greenfield | Tafilah | Tafilah | 30.837 | 35.5984 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R05 | Fiber ring
RO-06 | TAF-U-0021 | U | Rooftop | Tafilah | Tafilah | 30.837 | 35.6031 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R05 | Fiber ring
RO-06 | TAF-U-0022 | U | Rooftop | Tafilah | Tafilah | 30.8362 | 35.6069 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R04 | Fiber ring
RO-06 | TAF-U-0023 | U | Rooftop | Tafilah | Tafilah | 30.8362 | 35.6116 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R04 | Fiber ring
RO-06 | TAF-U-0025 | U | Monopole / greenfield | Tafilah | Tafilah | 30.8405 | 35.596 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R05 | Fiber ring
RO-06 | TAF-U-0026 | U | Monopole / greenfield | Tafilah | Tafilah | 30.8397 | 35.5998 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R05 | Fiber ring
RO-06 | TAF-U-0027 | U | Rooftop | Tafilah | Tafilah | 30.8397 | 35.6045 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R04 | Fiber ring
RO-06 | TAF-U-0031 | U | Monopole / greenfield | Tafilah | Tafilah | 30.844 | 35.5937 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R05 | Fiber ring
RO-06 | TAF-U-0032 | U | Monopole / greenfield | Tafilah | Tafilah | 30.8432 | 35.5974 | 30 | 3 | HUB-TAF-02 | HUB-TAF-02-R05 | Fiber ring
RO-07 | AMM-SU-3025 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0337 | 35.8246 | 32 | 3 | HUB-AMM-71 | HUB-AMM-71-R01 | Fiber ring
RO-07 | AMM-SU-3049 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0388 | 35.8143 | 32 | 3 | HUB-AMM-71 | HUB-AMM-71-R01 | Fiber ring
RO-07 | AMM-SU-3050 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0388 | 35.8211 | 32 | 3 | HUB-AMM-71 | HUB-AMM-71-R01 | Fiber ring
RO-07 | AMM-SU-3075 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0439 | 35.8109 | 32 | 3 | HUB-AMM-71 | HUB-AMM-71-R04 | Fiber ring
RO-07 | AMM-SU-3076 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0439 | 35.8177 | 32 | 3 | HUB-AMM-71 | HUB-AMM-71-R04 | Fiber ring
RO-07 | AMM-SU-3077 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0439 | 35.8246 | 32 | 3 | HUB-AMM-71 | HUB-AMM-71-R04 | Fiber ring
RO-07 | AMM-SU-3078 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0439 | 35.8314 | 32 | 3 | HUB-AMM-71 | HUB-AMM-71-R01 | Fiber ring
RO-07 | AMM-SU-3108 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.049 | 35.8143 | 32 | 3 | HUB-AMM-71 | HUB-AMM-71-R04 | Fiber ring
RO-07 | AMM-SU-3109 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0502 | 35.8211 | 32 | 3 | HUB-AMM-71 | HUB-AMM-71-R04 | Fiber ring
RO-07 | AMM-SU-3110 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0502 | 35.8293 | 32 | 3 | HUB-AMM-71 | HUB-AMM-71-R03 | Fiber ring
RO-07 | AMM-SU-3111 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0502 | 35.8334 | 32 | 3 | HUB-AMM-71 | HUB-AMM-71-R03 | Fiber ring
RO-07 | AMM-SU-3112 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.049 | 35.8416 | 32 | 3 | HUB-AMM-71 | HUB-AMM-71-R02 | Fiber ring
RO-07 | AMM-SU-3147 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0547 | 35.8184 | 32 | 3 | HUB-AMM-71 | HUB-AMM-71-R04 | Fiber ring
RO-07 | AMM-SU-3148 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0553 | 35.8259 | 32 | 3 | HUB-AMM-71 | HUB-AMM-71-R04 | Fiber ring
RO-07 | AMM-SU-3149 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0541 | 35.8314 | 32 | 3 | HUB-AMM-71 | HUB-AMM-71-R03 | Fiber ring
RO-07 | AMM-SU-3150 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0553 | 35.8382 | 32 | 3 | HUB-AMM-71 | HUB-AMM-71-R03 | Fiber ring
RO-07 | AMM-SU-3151 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0541 | 35.845 | 32 | 3 | HUB-AMM-71 | HUB-AMM-71-R03 | Fiber ring
RO-07 | AMM-SU-3188 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0592 | 35.828 | 32 | 3 | HUB-AMM-71 | HUB-AMM-71-R03 | Fiber ring
RO-07 | AMM-SU-3189 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0603 | 35.8362 | 32 | 3 | HUB-AMM-71 | HUB-AMM-71-R03 | Fiber ring
RO-07 | AMM-U-1666 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0309 | 35.8314 | 30 | 3 | HUB-AMM-71 | HUB-AMM-71-R01 | Fiber ring
RO-07 | AMM-U-1707 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0345 | 35.829 | 30 | 3 | HUB-AMM-71 | HUB-AMM-71-R01 | Fiber ring
RO-07 | AMM-U-1708 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0345 | 35.8337 | 30 | 3 | HUB-AMM-71 | HUB-AMM-71-R01 | Fiber ring
RO-07 | AMM-U-1709 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0349 | 35.838 | 30 | 3 | HUB-AMM-71 | HUB-AMM-71-R02 | Fiber ring
RO-07 | AMM-U-1748 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.038 | 35.8314 | 30 | 3 | HUB-AMM-71 | HUB-AMM-71-R01 | Fiber ring
RO-07 | AMM-U-1749 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.038 | 35.8361 | 30 | 3 | HUB-AMM-71 | HUB-AMM-71-R02 | Fiber ring
RO-07 | AMM-U-1750 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0388 | 35.8418 | 30 | 3 | HUB-AMM-71 | HUB-AMM-71-R02 | Fiber ring
RO-07 | AMM-U-1786 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0415 | 35.8337 | 30 | 3 | HUB-AMM-71 | HUB-AMM-71-R02 | Fiber ring
RO-07 | AMM-U-1787 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0423 | 35.8394 | 30 | 3 | HUB-AMM-71 | HUB-AMM-71-R02 | Fiber ring
RO-07 | AMM-U-1788 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0415 | 35.8432 | 30 | 3 | HUB-AMM-71 | HUB-AMM-71-R02 | Fiber ring
RO-07 | JER-SU-0068 | SU | Monopole / greenfield | Jerash | Jerash | 32.255 | 35.8826 | 32 | 3 | HUB-JER-03 | HUB-JER-03-R02 | Fiber ring
RO-07 | JER-SU-0069 | SU | Monopole / greenfield | Jerash | Jerash | 32.2538 | 35.888 | 32 | 3 | HUB-JER-03 | HUB-JER-03-R02 | Fiber ring
RO-07 | JER-SU-0070 | SU | Monopole / greenfield | Jerash | Jerash | 32.2532 | 35.8969 | 32 | 3 | HUB-JER-03 | HUB-JER-03-R03 | Fiber ring
RO-07 | JER-SU-0071 | SU | Monopole / greenfield | Jerash | Jerash | 32.2538 | 35.9044 | 32 | 3 | HUB-JER-02 | HUB-JER-02-R02 | Fiber ring
RO-07 | JER-SU-0072 | SU | Monopole / greenfield | Jerash | Jerash | 32.2589 | 35.8737 | 32 | 3 | HUB-JER-03 | HUB-JER-03-R01 | Fiber ring
RO-07 | JER-SU-0073 | SU | Monopole / greenfield | Jerash | Jerash | 32.2583 | 35.8798 | 32 | 3 | HUB-JER-03 | HUB-JER-03-R02 | Fiber ring
RO-07 | JER-SU-0074 | SU | Monopole / greenfield | Jerash | Jerash | 32.2601 | 35.886 | 32 | 3 | HUB-JER-03 | HUB-JER-03-R02 | Fiber ring
RO-07 | JER-SU-0075 | SU | Monopole / greenfield | Jerash | Jerash | 32.2589 | 35.8942 | 32 | 3 | HUB-JER-03 | HUB-JER-03-R03 | Fiber ring
RO-07 | JER-SU-0076 | SU | Monopole / greenfield | Jerash | Jerash | 32.2589 | 35.901 | 32 | 3 | HUB-JER-02 | HUB-JER-02-R01 | Fiber ring
RO-07 | JER-SU-0077 | SU | Monopole / greenfield | Jerash | Jerash | 32.2589 | 35.9078 | 32 | 3 | HUB-JER-02 | HUB-JER-02-R02 | Fiber ring
RO-07 | JER-SU-0078 | SU | Monopole / greenfield | Jerash | Jerash | 32.2577 | 35.9133 | 32 | 3 | HUB-JER-02 | HUB-JER-02-R02 | Fiber ring
RO-07 | JER-SU-0079 | SU | Rooftop | Jerash | Jerash | 32.264 | 35.8676 | 32 | 3 | HUB-JER-03 | HUB-JER-03-R01 | Fiber ring
RO-07 | JER-SU-0080 | SU | Monopole / greenfield | Jerash | Jerash | 32.264 | 35.8771 | 32 | 3 | HUB-JER-03 | HUB-JER-03-R01 | Fiber ring
RO-07 | JER-SU-0081 | SU | Monopole / greenfield | Jerash | Jerash | 32.2652 | 35.8826 | 32 | 3 | HUB-JER-03 | HUB-JER-03-R02 | Fiber ring
RO-07 | JER-SU-0082 | SU | Monopole / greenfield | Jerash | Jerash | 32.2652 | 35.9099 | 32 | 3 | HUB-JER-02 | HUB-JER-02-R02 | Fiber ring
RO-07 | JER-SU-0083 | SU | Monopole / greenfield | Jerash | Jerash | 32.2628 | 35.9167 | 32 | 3 | HUB-JER-02 | HUB-JER-02-R02 | Fiber ring
RO-07 | JER-SU-0084 | SU | Monopole / greenfield | Jerash | Jerash | 32.2691 | 35.8641 | 32 | 3 | HUB-JER-03 | HUB-JER-03-R01 | Fiber ring
RO-07 | JER-SU-0085 | SU | Monopole / greenfield | Jerash | Jerash | 32.2691 | 35.8737 | 32 | 3 | HUB-JER-03 | HUB-JER-03-R01 | Fiber ring
RO-07 | JER-SU-0086 | SU | Monopole / greenfield | Jerash | Jerash | 32.2691 | 35.9215 | 32 | 3 | HUB-JER-02 | HUB-JER-02-R02 | Fiber ring
RO-07 | JER-SU-0087 | SU | Monopole / greenfield | Jerash | Jerash | 32.2742 | 35.8703 | 32 | 3 | HUB-JER-03 | HUB-JER-03-R06 | Fiber ring
RO-07 | JER-SU-0088 | SU | Monopole / greenfield | Jerash | Jerash | 32.2754 | 35.9167 | 32 | 3 | HUB-JER-02 | HUB-JER-02-R03 | Fiber ring
RO-07 | JER-SU-0089 | SU | Monopole / greenfield | Jerash | Jerash | 32.2742 | 35.9249 | 32 | 3 | HUB-JER-02 | HUB-JER-02-R03 | Fiber ring
RO-07 | JER-SU-0090 | SU | Monopole / greenfield | Jerash | Jerash | 32.2804 | 35.8655 | 32 | 3 | HUB-JER-03 | HUB-JER-03-R06 | Fiber ring
RO-07 | JER-SU-0091 | SU | Monopole / greenfield | Jerash | Jerash | 32.2793 | 35.871 | 32 | 3 | HUB-JER-03 | HUB-JER-03-R05 | Fiber ring
RO-07 | JER-SU-0092 | SU | Monopole / greenfield | Jerash | Jerash | 32.2793 | 35.9215 | 32 | 3 | HUB-JER-02 | HUB-JER-02-R03 | Fiber ring
RO-07 | JER-SU-0093 | SU | Monopole / greenfield | Jerash | Jerash | 32.2793 | 35.9283 | 32 | 3 | HUB-JER-02 | HUB-JER-02-R03 | Fiber ring
RO-07 | JER-SU-0094 | SU | Monopole / greenfield | Jerash | Jerash | 32.2855 | 35.8621 | 32 | 3 | HUB-JER-03 | HUB-JER-03-R05 | Fiber ring
RO-07 | JER-SU-0095 | SU | Monopole / greenfield | Jerash | Jerash | 32.2855 | 35.8689 | 32 | 3 | HUB-JER-03 | HUB-JER-03-R05 | Fiber ring
RO-07 | JER-SU-0096 | SU | Monopole / greenfield | Jerash | Jerash | 32.2844 | 35.9153 | 32 | 3 | HUB-JER-02 | HUB-JER-02-R04 | Fiber ring
RO-07 | JER-SU-0097 | SU | Monopole / greenfield | Jerash | Jerash | 32.2844 | 35.9249 | 32 | 3 | HUB-JER-02 | HUB-JER-02-R03 | Fiber ring
RO-07 | JER-SU-0098 | SU | Monopole / greenfield | Jerash | Jerash | 32.2906 | 35.8655 | 32 | 3 | HUB-JER-01 | HUB-JER-01-R01 | Fiber ring
RO-07 | JER-SU-0099 | SU | Monopole / greenfield | Jerash | Jerash | 32.2906 | 35.8723 | 32 | 3 | HUB-JER-01 | HUB-JER-01-R01 | Fiber ring
RO-07 | JER-SU-0100 | SU | Rooftop | Jerash | Jerash | 32.2894 | 35.9119 | 32 | 3 | HUB-JER-02 | HUB-JER-02-R04 | Fiber ring
RO-07 | JER-SU-0101 | SU | Monopole / greenfield | Jerash | Jerash | 32.2894 | 35.9215 | 32 | 3 | HUB-JER-02 | HUB-JER-02-R03 | Fiber ring
RO-07 | JER-SU-0102 | SU | Monopole / greenfield | Jerash | Jerash | 32.2951 | 35.8682 | 32 | 3 | HUB-JER-01 | HUB-JER-01-R05 | Fiber ring
RO-07 | JER-SU-0103 | SU | Monopole / greenfield | Jerash | Jerash | 32.2945 | 35.8744 | 32 | 3 | HUB-JER-01 | HUB-JER-01-R05 | Fiber ring
RO-07 | JER-SU-0104 | SU | Monopole / greenfield | Jerash | Jerash | 32.2945 | 35.9153 | 32 | 3 | HUB-JER-02 | HUB-JER-02-R04 | Fiber ring
RO-07 | JER-SU-0105 | SU | Monopole / greenfield | Jerash | Jerash | 32.2951 | 35.9242 | 32 | 3 | HUB-JER-02 | HUB-JER-02-R03 | Fiber ring
RO-07 | JER-SU-0106 | SU | Monopole / greenfield | Jerash | Jerash | 32.2985 | 35.8723 | 32 | 3 | HUB-JER-01 | HUB-JER-01-R05 | Fiber ring
RO-07 | JER-SU-0107 | SU | Monopole / greenfield | Jerash | Jerash | 32.2996 | 35.8778 | 32 | 3 | HUB-JER-01 | HUB-JER-01-R05 | Fiber ring
RO-07 | JER-SU-0108 | SU | Monopole / greenfield | Jerash | Jerash | 32.2996 | 35.8846 | 32 | 3 | HUB-JER-01 | HUB-JER-01-R05 | Fiber ring
RO-07 | JER-SU-0109 | SU | Monopole / greenfield | Jerash | Jerash | 32.2996 | 35.8914 | 32 | 3 | HUB-JER-01 | HUB-JER-01-R04 | Fiber ring
RO-07 | JER-SU-0110 | SU | Monopole / greenfield | Jerash | Jerash | 32.2996 | 35.901 | 32 | 3 | HUB-JER-01 | HUB-JER-01-R04 | Fiber ring
RO-07 | JER-SU-0111 | SU | Monopole / greenfield | Jerash | Jerash | 32.3002 | 35.9072 | 32 | 3 | HUB-JER-01 | HUB-JER-01-R03 | Fiber ring
RO-07 | JER-SU-0112 | SU | Monopole / greenfield | Jerash | Jerash | 32.2996 | 35.9119 | 32 | 3 | HUB-JER-01 | HUB-JER-01-R03 | Fiber ring
RO-07 | JER-SU-0113 | SU | Monopole / greenfield | Jerash | Jerash | 32.3035 | 35.8826 | 32 | 3 | HUB-JER-01 | HUB-JER-01-R05 | Fiber ring
RO-07 | JER-SU-0114 | SU | Monopole / greenfield | Jerash | Jerash | 32.3053 | 35.8887 | 32 | 3 | HUB-JER-01 | HUB-JER-01-R04 | Fiber ring
RO-07 | JER-SU-0115 | SU | Monopole / greenfield | Jerash | Jerash | 32.3059 | 35.8962 | 32 | 3 | HUB-JER-01 | HUB-JER-01-R04 | Fiber ring
RO-07 | JER-SU-0116 | SU | Monopole / greenfield | Jerash | Jerash | 32.3047 | 35.9044 | 32 | 3 | HUB-JER-01 | HUB-JER-01-R04 | Fiber ring
RO-07 | JER-SU-0117 | SU | Monopole / greenfield | Jerash | Jerash | 32.3047 | 35.9085 | 32 | 3 | HUB-JER-01 | HUB-JER-01-R04 | Fiber ring
RO-07 | JER-U-0001 | U | Monopole / greenfield | Jerash | Jerash | 32.2644 | 35.8871 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R02 | Fiber ring
RO-07 | JER-U-0002 | U | Monopole / greenfield | Jerash | Jerash | 32.2652 | 35.8928 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R03 | Fiber ring
RO-07 | JER-U-0003 | U | Monopole / greenfield | Jerash | Jerash | 32.2652 | 35.8975 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R03 | Fiber ring
RO-07 | JER-U-0004 | U | Monopole / greenfield | Jerash | Jerash | 32.2636 | 35.9023 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R01 | Fiber ring
RO-07 | JER-U-0005 | U | Monopole / greenfield | Jerash | Jerash | 32.2679 | 35.881 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R01 | Fiber ring
RO-07 | JER-U-0006 | U | Monopole / greenfield | Jerash | Jerash | 32.2687 | 35.8857 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R02 | Fiber ring
RO-07 | JER-U-0007 | U | Monopole / greenfield | Jerash | Jerash | 32.2679 | 35.8914 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R03 | Fiber ring
RO-07 | JER-U-0008 | U | Monopole / greenfield | Jerash | Jerash | 32.2679 | 35.8942 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R03 | Fiber ring
RO-07 | JER-U-0009 | U | Rooftop | Jerash | Jerash | 32.2687 | 35.8999 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R01 | Fiber ring
RO-07 | JER-U-0010 | U | Monopole / greenfield | Jerash | Jerash | 32.2679 | 35.9056 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R01 | Fiber ring
RO-07 | JER-U-0011 | U | Monopole / greenfield | Jerash | Jerash | 32.2714 | 35.8777 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R01 | Fiber ring
RO-07 | JER-U-0012 | U | Rooftop | Jerash | Jerash | 32.2722 | 35.8834 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R01 | Fiber ring
RO-07 | JER-U-0013 | U | Rooftop | Jerash | Jerash | 32.2718 | 35.8876 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R04 | Fiber ring
RO-07 | JER-U-0014 | U | Monopole / greenfield | Jerash | Jerash | 32.271 | 35.8923 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R03 | Fiber ring
RO-07 | JER-U-0015 | U | Rooftop | Jerash | Jerash | 32.2714 | 35.8985 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R01 | Fiber ring
RO-07 | JER-U-0016 | U | Rooftop | Jerash | Jerash | 32.271 | 35.9023 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R01 | Fiber ring
RO-07 | JER-U-0017 | U | Rooftop | Jerash | Jerash | 32.2714 | 35.9079 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R01 | Fiber ring
RO-07 | JER-U-0018 | U | Monopole / greenfield | Jerash | Jerash | 32.2718 | 35.9113 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R02 | Fiber ring
RO-07 | JER-U-0019 | U | Monopole / greenfield | Jerash | Jerash | 32.2758 | 35.8763 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R06 | Fiber ring
RO-07 | JER-U-0020 | U | Monopole / greenfield | Jerash | Jerash | 32.2749 | 35.88 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R05 | Fiber ring
RO-07 | JER-U-0021 | U | Rooftop | Jerash | Jerash | 32.2758 | 35.8857 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R04 | Fiber ring
RO-07 | JER-U-0022 | U | Rooftop | Jerash | Jerash | 32.2749 | 35.8895 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R04 | Fiber ring
RO-07 | JER-U-0023 | U | Rooftop | Jerash | Jerash | 32.2754 | 35.8957 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R06 | Fiber ring
RO-07 | JER-U-0024 | U | Rooftop | Jerash | Jerash | 32.2758 | 35.8999 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R06 | Fiber ring
RO-07 | JER-U-0025 | U | Rooftop | Jerash | Jerash | 32.2749 | 35.9056 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R06 | Fiber ring
RO-07 | JER-U-0026 | U | Rooftop | Jerash | Jerash | 32.2741 | 35.9094 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R01 | Fiber ring
RO-07 | JER-U-0027 | U | Monopole / greenfield | Jerash | Jerash | 32.2781 | 35.8782 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R05 | Fiber ring
RO-07 | JER-U-0028 | U | Rooftop | Jerash | Jerash | 32.2793 | 35.8834 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R04 | Fiber ring
RO-07 | JER-U-0029 | U | Rooftop | Jerash | Jerash | 32.2789 | 35.8876 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R04 | Fiber ring
RO-07 | JER-U-0030 | U | Rooftop | Jerash | Jerash | 32.2793 | 35.8928 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R04 | Fiber ring
RO-07 | JER-U-0031 | U | Rooftop | Jerash | Jerash | 32.2785 | 35.8985 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R06 | Fiber ring
RO-07 | JER-U-0032 | U | Rooftop | Jerash | Jerash | 32.2793 | 35.9023 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R05 | Fiber ring
RO-07 | JER-U-0033 | U | Rooftop | Jerash | Jerash | 32.2793 | 35.907 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R05 | Fiber ring
RO-07 | JER-U-0034 | U | Monopole / greenfield | Jerash | Jerash | 32.2785 | 35.9108 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R04 | Fiber ring
RO-07 | JER-U-0035 | U | Monopole / greenfield | Jerash | Jerash | 32.2824 | 35.8758 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R05 | Fiber ring
RO-07 | JER-U-0036 | U | Rooftop | Jerash | Jerash | 32.282 | 35.8819 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R05 | Fiber ring
RO-07 | JER-U-0037 | U | Rooftop | Jerash | Jerash | 32.282 | 35.8848 | 30 | 3 | HUB-JER-03 | HUB-JER-03-R04 | Fiber ring
RO-07 | JER-U-0038 | U | Monopole / greenfield | Jerash | Jerash | 32.2828 | 35.8905 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R02 | Fiber ring
RO-07 | JER-U-0039 | U | Rooftop | Jerash | Jerash | 32.282 | 35.8961 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R02 | Fiber ring
RO-07 | JER-U-0040 | U | Rooftop | Jerash | Jerash | 32.2828 | 35.8999 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R05 | Fiber ring
RO-07 | JER-U-0041 | U | Rooftop | Jerash | Jerash | 32.282 | 35.9056 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R05 | Fiber ring
RO-07 | JER-U-0042 | U | Rooftop | Jerash | Jerash | 32.2828 | 35.9094 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R04 | Fiber ring
RO-07 | JER-U-0043 | U | Monopole / greenfield | Jerash | Jerash | 32.2828 | 35.9141 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R04 | Fiber ring
RO-07 | JER-U-0044 | U | Monopole / greenfield | Jerash | Jerash | 32.2855 | 35.8777 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R01 | Fiber ring
RO-07 | JER-U-0045 | U | Rooftop | Jerash | Jerash | 32.2863 | 35.8834 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R01 | Fiber ring
RO-07 | JER-U-0046 | U | Monopole / greenfield | Jerash | Jerash | 32.2855 | 35.8881 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R02 | Fiber ring
RO-07 | JER-U-0047 | U | Rooftop | Jerash | Jerash | 32.2855 | 35.8919 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R02 | Fiber ring
RO-07 | JER-U-0048 | U | Rooftop | Jerash | Jerash | 32.2855 | 35.8985 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R02 | Fiber ring
RO-07 | JER-U-0049 | U | Rooftop | Jerash | Jerash | 32.2847 | 35.9023 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R05 | Fiber ring
RO-07 | JER-U-0050 | U | Rooftop | Jerash | Jerash | 32.2855 | 35.9079 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R05 | Fiber ring
RO-07 | JER-U-0051 | U | Rooftop | Jerash | Jerash | 32.2855 | 35.9108 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R04 | Fiber ring
RO-07 | JER-U-0052 | U | Monopole / greenfield | Jerash | Jerash | 32.2891 | 35.8819 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R01 | Fiber ring
RO-07 | JER-U-0053 | U | Monopole / greenfield | Jerash | Jerash | 32.2891 | 35.8848 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R01 | Fiber ring
RO-07 | JER-U-0054 | U | Monopole / greenfield | Jerash | Jerash | 32.2891 | 35.8895 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R01 | Fiber ring
RO-07 | JER-U-0055 | U | Monopole / greenfield | Jerash | Jerash | 32.2891 | 35.8942 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R02 | Fiber ring
RO-07 | JER-U-0056 | U | Rooftop | Jerash | Jerash | 32.2886 | 35.8994 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R02 | Fiber ring
RO-07 | JER-U-0057 | U | Rooftop | Jerash | Jerash | 32.2899 | 35.9046 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R03 | Fiber ring
RO-07 | JER-U-0058 | U | Rooftop | Jerash | Jerash | 32.2899 | 35.9094 | 30 | 3 | HUB-JER-02 | HUB-JER-02-R05 | Fiber ring
RO-07 | JER-U-0059 | U | Monopole / greenfield | Jerash | Jerash | 32.2926 | 35.8824 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R06 | Fiber ring
RO-07 | JER-U-0060 | U | Monopole / greenfield | Jerash | Jerash | 32.2926 | 35.8871 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R06 | Fiber ring
RO-07 | JER-U-0061 | U | Monopole / greenfield | Jerash | Jerash | 32.2926 | 35.8919 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R01 | Fiber ring
RO-07 | JER-U-0062 | U | Monopole / greenfield | Jerash | Jerash | 32.2926 | 35.8985 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R03 | Fiber ring
RO-07 | JER-U-0063 | U | Monopole / greenfield | Jerash | Jerash | 32.2926 | 35.9032 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R03 | Fiber ring
RO-07 | JER-U-0064 | U | Monopole / greenfield | Jerash | Jerash | 32.293 | 35.9075 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R03 | Fiber ring
RO-07 | JER-U-0065 | U | Monopole / greenfield | Jerash | Jerash | 32.2969 | 35.8905 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R05 | Fiber ring
RO-07 | JER-U-0066 | U | Monopole / greenfield | Jerash | Jerash | 32.2961 | 35.8961 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R04 | Fiber ring
RO-07 | JER-U-0067 | U | Monopole / greenfield | Jerash | Jerash | 32.2969 | 35.8999 | 30 | 3 | HUB-JER-01 | HUB-JER-01-R03 | Fiber ring
RO-07 | KAR-SU-0082 | SU | Monopole / greenfield | Karak | Karak | 31.1796 | 35.6798 | 32 | 3 | HUB-KAR-02 | HUB-KAR-02-R01 | Fiber ring
RO-07 | KAR-SU-0085 | SU | Monopole / greenfield | Karak | Karak | 31.1836 | 35.6778 | 32 | 3 | HUB-KAR-02 | HUB-KAR-02-R01 | Fiber ring
RO-07 | KAR-SU-0086 | SU | Monopole / greenfield | Karak | Karak | 31.1847 | 35.6832 | 32 | 3 | HUB-KAR-02 | HUB-KAR-02-R01 | Fiber ring
RO-07 | KAR-SU-0088 | SU | Monopole / greenfield | Karak | Karak | 31.1886 | 35.6744 | 32 | 3 | HUB-KAR-02 | HUB-KAR-02-R01 | Fiber ring
RO-07 | KAR-SU-0089 | SU | Monopole / greenfield | Karak | Karak | 31.1898 | 35.6798 | 32 | 3 | HUB-KAR-02 | HUB-KAR-02-R05 | Fiber ring
RO-07 | KAR-SU-0090 | SU | Monopole / greenfield | Karak | Karak | 31.1898 | 35.6867 | 32 | 3 | HUB-KAR-02 | HUB-KAR-02-R05 | Fiber ring
RO-07 | KAR-SU-0093 | SU | Monopole / greenfield | Karak | Karak | 31.1937 | 35.6778 | 32 | 3 | HUB-KAR-02 | HUB-KAR-02-R05 | Fiber ring
RO-07 | KAR-SU-0094 | SU | Monopole / greenfield | Karak | Karak | 31.1937 | 35.6846 | 32 | 3 | HUB-KAR-02 | HUB-KAR-02-R05 | Fiber ring
RO-07 | KAR-SU-0097 | SU | Monopole / greenfield | Karak | Karak | 31.1988 | 35.6812 | 32 | 3 | HUB-KAR-02 | HUB-KAR-02-R05 | Fiber ring
RO-07 | KAR-SU-0098 | SU | Monopole / greenfield | Karak | Karak | 31.2012 | 35.688 | 32 | 3 | HUB-KAR-02 | HUB-KAR-02-R05 | Fiber ring
RO-07 | KAR-SU-0099 | SU | Monopole / greenfield | Karak | Karak | 31.2 | 35.6962 | 32 | 3 | HUB-KAR-02 | HUB-KAR-02-R04 | Fiber ring
RO-07 | KAR-SU-0100 | SU | Monopole / greenfield | Karak | Karak | 31.1988 | 35.7085 | 32 | 3 | HUB-KAR-02 | HUB-KAR-02-R04 | Fiber ring
RO-07 | KAR-SU-0104 | SU | Monopole / greenfield | Karak | Karak | 31.2063 | 35.6914 | 32 | 3 | HUB-KAR-02 | HUB-KAR-02-R04 | Fiber ring
RO-07 | KAR-SU-0105 | SU | Monopole / greenfield | Karak | Karak | 31.2051 | 35.7064 | 32 | 3 | HUB-KAR-02 | HUB-KAR-02-R04 | Fiber ring
RO-07 | KAR-SU-0106 | SU | Monopole / greenfield | Karak | Karak | 31.2051 | 35.7133 | 32 | 3 | HUB-KAR-02 | HUB-KAR-02-R04 | Fiber ring
RO-07 | KAR-U-0026 | U | Monopole / greenfield | Karak | Karak | 31.1789 | 35.6887 | 30 | 3 | HUB-KAR-02 | HUB-KAR-02-R01 | Fiber ring
RO-07 | KAR-U-0027 | U | Monopole / greenfield | Karak | Karak | 31.1797 | 35.6943 | 30 | 3 | HUB-KAR-02 | HUB-KAR-02-R02 | Fiber ring
RO-07 | KAR-U-0034 | U | Monopole / greenfield | Karak | Karak | 31.1824 | 35.6863 | 30 | 3 | HUB-KAR-02 | HUB-KAR-02-R01 | Fiber ring
RO-07 | KAR-U-0035 | U | Monopole / greenfield | Karak | Karak | 31.1824 | 35.691 | 30 | 3 | HUB-KAR-02 | HUB-KAR-02-R02 | Fiber ring
RO-07 | KAR-U-0036 | U | Monopole / greenfield | Karak | Karak | 31.1824 | 35.6976 | 30 | 3 | HUB-KAR-02 | HUB-KAR-02-R02 | Fiber ring
RO-07 | KAR-U-0037 | U | Rooftop | Karak | Karak | 31.1824 | 35.7024 | 30 | 3 | HUB-KAR-02 | HUB-KAR-02-R02 | Fiber ring
RO-07 | KAR-U-0038 | U | Rooftop | Karak | Karak | 31.1824 | 35.7052 | 30 | 3 | HUB-KAR-02 | HUB-KAR-02-R02 | Fiber ring
RO-07 | KAR-U-0042 | U | Monopole / greenfield | Karak | Karak | 31.1859 | 35.6887 | 30 | 3 | HUB-KAR-02 | HUB-KAR-02-R01 | Fiber ring
RO-07 | KAR-U-0043 | U | Monopole / greenfield | Karak | Karak | 31.1859 | 35.6934 | 30 | 3 | HUB-KAR-02 | HUB-KAR-02-R02 | Fiber ring
RO-07 | KAR-U-0044 | U | Rooftop | Karak | Karak | 31.1859 | 35.7 | 30 | 3 | HUB-KAR-02 | HUB-KAR-02-R02 | Fiber ring
RO-07 | KAR-U-0045 | U | Rooftop | Karak | Karak | 31.1851 | 35.7038 | 30 | 3 | HUB-KAR-02 | HUB-KAR-02-R03 | Fiber ring
RO-07 | KAR-U-0050 | U | Monopole / greenfield | Karak | Karak | 31.1894 | 35.691 | 30 | 3 | HUB-KAR-02 | HUB-KAR-02-R01 | Fiber ring
RO-07 | KAR-U-0051 | U | Monopole / greenfield | Karak | Karak | 31.1894 | 35.6976 | 30 | 3 | HUB-KAR-02 | HUB-KAR-02-R03 | Fiber ring
RO-07 | KAR-U-0052 | U | Rooftop | Karak | Karak | 31.1886 | 35.7014 | 30 | 3 | HUB-KAR-02 | HUB-KAR-02-R03 | Fiber ring
RO-07 | KAR-U-0053 | U | Rooftop | Karak | Karak | 31.1886 | 35.7061 | 30 | 3 | HUB-KAR-02 | HUB-KAR-02-R03 | Fiber ring
RO-07 | KAR-U-0056 | U | Monopole / greenfield | Karak | Karak | 31.1929 | 35.6934 | 30 | 3 | HUB-KAR-02 | HUB-KAR-02-R04 | Fiber ring
RO-07 | KAR-U-0057 | U | Monopole / greenfield | Karak | Karak | 31.1925 | 35.6986 | 30 | 3 | HUB-KAR-02 | HUB-KAR-02-R03 | Fiber ring
RO-07 | KAR-U-0058 | U | Monopole / greenfield | Karak | Karak | 31.1938 | 35.7038 | 30 | 3 | HUB-KAR-02 | HUB-KAR-02-R03 | Fiber ring
RO-07 | KAR-U-0059 | U | Monopole / greenfield | Karak | Karak | 31.1938 | 35.7085 | 30 | 3 | HUB-KAR-02 | HUB-KAR-02-R03 | Fiber ring
RO-07 | KAR-U-0061 | U | Monopole / greenfield | Karak | Karak | 31.1965 | 35.7071 | 30 | 3 | HUB-KAR-02 | HUB-KAR-02-R04 | Fiber ring
RO-07 | MA-SU-0087 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1666 | 35.7187 | 32 | 3 | HUB-MA-04 | HUB-MA-04-R01 | Fiber ring
RO-07 | MA-SU-0088 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1666 | 35.7256 | 32 | 3 | HUB-MA-04 | HUB-MA-04-R01 | Fiber ring
RO-07 | MA-SU-0089 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1666 | 35.731 | 32 | 3 | HUB-MA-04 | HUB-MA-04-R02 | Fiber ring
RO-07 | MA-SU-0090 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1666 | 35.7379 | 32 | 3 | HUB-MA-04 | HUB-MA-04-R02 | Fiber ring
RO-07 | MA-SU-0091 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1666 | 35.746 | 32 | 3 | HUB-MA-04 | HUB-MA-04-R02 | Fiber ring
RO-07 | MA-SU-0092 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1666 | 35.7515 | 32 | 3 | HUB-MA-04 | HUB-MA-04-R02 | Fiber ring
RO-07 | MA-SU-0093 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1716 | 35.7153 | 32 | 3 | HUB-MA-04 | HUB-MA-04-R01 | Fiber ring
RO-07 | MA-SU-0094 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1716 | 35.7221 | 32 | 3 | HUB-MA-04 | HUB-MA-04-R01 | Fiber ring
RO-07 | MA-SU-0095 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1716 | 35.7276 | 32 | 3 | HUB-MA-04 | HUB-MA-04-R01 | Fiber ring
RO-07 | MA-SU-0096 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1716 | 35.7426 | 32 | 3 | HUB-MA-04 | HUB-MA-04-R02 | Fiber ring
RO-07 | MA-SU-0097 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1705 | 35.7495 | 32 | 3 | HUB-MA-04 | HUB-MA-04-R02 | Fiber ring
RO-07 | MA-SU-0098 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1716 | 35.7563 | 32 | 3 | HUB-MA-04 | HUB-MA-04-R03 | Fiber ring
RO-07 | MA-SU-0099 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1767 | 35.7051 | 32 | 3 | HUB-MA-03 | HUB-MA-03-R01 | Fiber ring
RO-07 | MA-SU-0100 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1767 | 35.7187 | 32 | 3 | HUB-MA-04 | HUB-MA-04-R01 | Fiber ring
RO-07 | MA-SU-0101 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1767 | 35.7529 | 32 | 3 | HUB-MA-04 | HUB-MA-04-R03 | Fiber ring
RO-07 | MA-SU-0103 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1806 | 35.7017 | 32 | 3 | HUB-MA-03 | HUB-MA-03-R01 | Fiber ring
RO-07 | MA-SU-0104 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1818 | 35.7085 | 32 | 3 | HUB-MA-03 | HUB-MA-03-R01 | Fiber ring
RO-07 | MA-SU-0105 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1806 | 35.7153 | 32 | 3 | HUB-MA-03 | HUB-MA-03-R01 | Fiber ring
RO-07 | MA-SU-0107 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1869 | 35.7051 | 32 | 3 | HUB-MA-03 | HUB-MA-03-R01 | Fiber ring
RO-07 | MA-SU-0108 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1869 | 35.7119 | 32 | 3 | HUB-MA-03 | HUB-MA-03-R01 | Fiber ring
RO-07 | MA-SU-0111 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.192 | 35.7017 | 32 | 3 | HUB-MA-03 | HUB-MA-03-R05 | Fiber ring
RO-07 | MA-SU-0112 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.192 | 35.7085 | 32 | 3 | HUB-MA-03 | HUB-MA-03-R05 | Fiber ring
RO-07 | MA-SU-0115 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1983 | 35.6983 | 32 | 3 | HUB-MA-03 | HUB-MA-03-R05 | Fiber ring
RO-07 | MA-SU-0116 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.1983 | 35.7051 | 32 | 3 | HUB-MA-03 | HUB-MA-03-R05 | Fiber ring
RO-07 | MA-SU-0118 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.201 | 35.7085 | 32 | 3 | HUB-MA-03 | HUB-MA-03-R05 | Fiber ring
RO-07 | MA-SU-0120 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.2085 | 35.7051 | 32 | 3 | HUB-MA-03 | HUB-MA-03-R04 | Fiber ring
RO-07 | MA-SU-0121 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.2073 | 35.7119 | 32 | 3 | HUB-MA-03 | HUB-MA-03-R04 | Fiber ring
RO-07 | MA-SU-0123 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.2124 | 35.7085 | 32 | 3 | HUB-MA-01 | HUB-MA-01-R01 | Fiber ring
RO-07 | MA-SU-0124 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.2124 | 35.7153 | 32 | 3 | HUB-MA-01 | HUB-MA-01-R01 | Fiber ring
RO-07 | MA-SU-0126 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.2175 | 35.7119 | 32 | 3 | HUB-MA-01 | HUB-MA-01-R05 | Fiber ring
RO-07 | MA-SU-0127 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.2175 | 35.7187 | 32 | 3 | HUB-MA-01 | HUB-MA-01-R05 | Fiber ring
RO-07 | MA-SU-0128 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.2175 | 35.7256 | 32 | 3 | HUB-MA-01 | HUB-MA-01-R05 | Fiber ring
RO-07 | MA-SU-0129 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.2175 | 35.7324 | 32 | 3 | HUB-MA-01 | HUB-MA-01-R04 | Fiber ring
RO-07 | MA-SU-0130 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.2175 | 35.7392 | 32 | 3 | HUB-MA-01 | HUB-MA-01-R04 | Fiber ring
RO-07 | MA-SU-0131 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.2186 | 35.746 | 32 | 3 | HUB-MA-01 | HUB-MA-01-R04 | Fiber ring
RO-07 | MA-SU-0132 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.2226 | 35.7153 | 32 | 3 | HUB-MA-01 | HUB-MA-01-R05 | Fiber ring
RO-07 | MA-SU-0133 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.2226 | 35.7221 | 32 | 3 | HUB-MA-01 | HUB-MA-01-R05 | Fiber ring
RO-07 | MA-SU-0134 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.2226 | 35.729 | 32 | 3 | HUB-MA-01 | HUB-MA-01-R05 | Fiber ring
RO-07 | MA-SU-0135 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.2226 | 35.7358 | 32 | 3 | HUB-MA-01 | HUB-MA-01-R04 | Fiber ring
RO-07 | MA-SU-0136 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.2226 | 35.7426 | 32 | 3 | HUB-MA-01 | HUB-MA-01-R04 | Fiber ring
RO-07 | MA-SU-0137 | SU | Monopole / greenfield | Ma'an | Ma'an | 30.2226 | 35.7481 | 32 | 3 | HUB-MA-01 | HUB-MA-01-R04 | Fiber ring
RO-07 | MA-U-0001 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1744 | 35.7336 | 30 | 3 | HUB-MA-04 | HUB-MA-04-R02 | Fiber ring
RO-07 | MA-U-0002 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1775 | 35.7279 | 30 | 3 | HUB-MA-04 | HUB-MA-04-R01 | Fiber ring
RO-07 | MA-U-0003 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1779 | 35.7321 | 30 | 3 | HUB-MA-04 | HUB-MA-04-R05 | Fiber ring
RO-07 | MA-U-0004 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1779 | 35.7359 | 30 | 3 | HUB-MA-04 | HUB-MA-04-R01 | Fiber ring
RO-07 | MA-U-0005 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1779 | 35.7463 | 30 | 3 | HUB-MA-04 | HUB-MA-04-R03 | Fiber ring
RO-07 | MA-U-0006 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1814 | 35.7194 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R02 | Fiber ring
RO-07 | MA-U-0007 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1814 | 35.725 | 30 | 3 | HUB-MA-04 | HUB-MA-04-R05 | Fiber ring
RO-07 | MA-U-0008 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1814 | 35.7298 | 30 | 3 | HUB-MA-04 | HUB-MA-04-R05 | Fiber ring
RO-07 | MA-U-0009 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1814 | 35.7345 | 30 | 3 | HUB-MA-04 | HUB-MA-04-R04 | Fiber ring
RO-07 | MA-U-0010 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1814 | 35.7392 | 30 | 3 | HUB-MA-04 | HUB-MA-04-R03 | Fiber ring
RO-07 | MA-U-0011 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1814 | 35.7439 | 30 | 3 | HUB-MA-04 | HUB-MA-04-R03 | Fiber ring
RO-07 | MA-U-0012 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1814 | 35.7487 | 30 | 3 | HUB-MA-04 | HUB-MA-04-R03 | Fiber ring
RO-07 | MA-U-0013 | U | Monopole / greenfield | Ma'an | Ma'an | 30.185 | 35.718 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R02 | Fiber ring
RO-07 | MA-U-0014 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1846 | 35.7222 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R02 | Fiber ring
RO-07 | MA-U-0015 | U | Monopole / greenfield | Ma'an | Ma'an | 30.185 | 35.7274 | 30 | 3 | HUB-MA-04 | HUB-MA-04-R04 | Fiber ring
RO-07 | MA-U-0016 | U | Monopole / greenfield | Ma'an | Ma'an | 30.185 | 35.7321 | 30 | 3 | HUB-MA-04 | HUB-MA-04-R04 | Fiber ring
RO-07 | MA-U-0017 | U | Monopole / greenfield | Ma'an | Ma'an | 30.185 | 35.7369 | 30 | 3 | HUB-MA-04 | HUB-MA-04-R04 | Fiber ring
RO-07 | MA-U-0018 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1854 | 35.7411 | 30 | 3 | HUB-MA-04 | HUB-MA-04-R03 | Fiber ring
RO-07 | MA-U-0022 | U | Rooftop | Ma'an | Ma'an | 30.1885 | 35.7156 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R01 | Fiber ring
RO-07 | MA-U-0023 | U | Rooftop | Ma'an | Ma'an | 30.1885 | 35.7203 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R02 | Fiber ring
RO-07 | MA-U-0024 | U | Rooftop | Ma'an | Ma'an | 30.1885 | 35.725 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R02 | Fiber ring
RO-07 | MA-U-0025 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1885 | 35.7298 | 30 | 3 | HUB-MA-04 | HUB-MA-04-R04 | Fiber ring
RO-07 | MA-U-0026 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1885 | 35.7345 | 30 | 3 | HUB-MA-04 | HUB-MA-04-R04 | Fiber ring
RO-07 | MA-U-0027 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1885 | 35.7392 | 30 | 3 | HUB-MA-04 | HUB-MA-04-R04 | Fiber ring
RO-07 | MA-U-0031 | U | Monopole / greenfield | Ma'an | Ma'an | 30.192 | 35.7132 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R05 | Fiber ring
RO-07 | MA-U-0032 | U | Rooftop | Ma'an | Ma'an | 30.192 | 35.718 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R01 | Fiber ring
RO-07 | MA-U-0033 | U | Rooftop | Ma'an | Ma'an | 30.192 | 35.7227 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R02 | Fiber ring
RO-07 | MA-U-0034 | U | Rooftop | Ma'an | Ma'an | 30.192 | 35.7274 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R02 | Fiber ring
RO-07 | MA-U-0035 | U | Rooftop | Ma'an | Ma'an | 30.192 | 35.7321 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R03 | Fiber ring
RO-07 | MA-U-0039 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1955 | 35.7156 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R04 | Fiber ring
RO-07 | MA-U-0040 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1955 | 35.7203 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R03 | Fiber ring
RO-07 | MA-U-0041 | U | Rooftop | Ma'an | Ma'an | 30.1955 | 35.725 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R03 | Fiber ring
RO-07 | MA-U-0042 | U | Rooftop | Ma'an | Ma'an | 30.1955 | 35.7298 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R03 | Fiber ring
RO-07 | MA-U-0048 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1991 | 35.7132 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R04 | Fiber ring
RO-07 | MA-U-0049 | U | Monopole / greenfield | Ma'an | Ma'an | 30.1991 | 35.718 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R04 | Fiber ring
RO-07 | MA-U-0050 | U | Rooftop | Ma'an | Ma'an | 30.1991 | 35.7227 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R03 | Fiber ring
RO-07 | MA-U-0051 | U | Rooftop | Ma'an | Ma'an | 30.1991 | 35.7274 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R03 | Fiber ring
RO-07 | MA-U-0052 | U | Rooftop | Ma'an | Ma'an | 30.1991 | 35.7321 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R02 | Fiber ring
RO-07 | MA-U-0058 | U | Monopole / greenfield | Ma'an | Ma'an | 30.2026 | 35.7156 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R04 | Fiber ring
RO-07 | MA-U-0059 | U | Rooftop | Ma'an | Ma'an | 30.2026 | 35.7203 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R03 | Fiber ring
RO-07 | MA-U-0060 | U | Rooftop | Ma'an | Ma'an | 30.2034 | 35.725 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R01 | Fiber ring
RO-07 | MA-U-0061 | U | Rooftop | Ma'an | Ma'an | 30.2026 | 35.7298 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R02 | Fiber ring
RO-07 | MA-U-0062 | U | Rooftop | Ma'an | Ma'an | 30.2026 | 35.7345 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R02 | Fiber ring
RO-07 | MA-U-0063 | U | Rooftop | Ma'an | Ma'an | 30.2026 | 35.7392 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R03 | Fiber ring
RO-07 | MA-U-0067 | U | Monopole / greenfield | Ma'an | Ma'an | 30.2053 | 35.718 | 30 | 3 | HUB-MA-03 | HUB-MA-03-R04 | Fiber ring
RO-07 | MA-U-0068 | U | Rooftop | Ma'an | Ma'an | 30.2053 | 35.7227 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R01 | Fiber ring
RO-07 | MA-U-0069 | U | Rooftop | Ma'an | Ma'an | 30.2061 | 35.7274 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R02 | Fiber ring
RO-07 | MA-U-0070 | U | Rooftop | Ma'an | Ma'an | 30.2061 | 35.7321 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R02 | Fiber ring
RO-07 | MA-U-0071 | U | Monopole / greenfield | Ma'an | Ma'an | 30.2053 | 35.7369 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R03 | Fiber ring
RO-07 | MA-U-0072 | U | Monopole / greenfield | Ma'an | Ma'an | 30.2053 | 35.7416 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R03 | Fiber ring
RO-07 | MA-U-0075 | U | Monopole / greenfield | Ma'an | Ma'an | 30.2105 | 35.7203 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R01 | Fiber ring
RO-07 | MA-U-0076 | U | Monopole / greenfield | Ma'an | Ma'an | 30.2096 | 35.725 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R01 | Fiber ring
RO-07 | MA-U-0077 | U | Rooftop | Ma'an | Ma'an | 30.2088 | 35.7298 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R02 | Fiber ring
RO-07 | MA-U-0078 | U | Rooftop | Ma'an | Ma'an | 30.2088 | 35.7345 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R02 | Fiber ring
RO-07 | MA-U-0079 | U | Monopole / greenfield | Ma'an | Ma'an | 30.2096 | 35.7392 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R03 | Fiber ring
RO-07 | MA-U-0080 | U | Monopole / greenfield | Ma'an | Ma'an | 30.2105 | 35.7439 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R03 | Fiber ring
RO-07 | MA-U-0082 | U | Monopole / greenfield | Ma'an | Ma'an | 30.2132 | 35.7274 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R01 | Fiber ring
RO-07 | MA-U-0083 | U | Monopole / greenfield | Ma'an | Ma'an | 30.2136 | 35.7326 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R01 | Fiber ring
RO-07 | MA-U-0084 | U | Monopole / greenfield | Ma'an | Ma'an | 30.214 | 35.7369 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R04 | Fiber ring
RO-07 | MA-U-0085 | U | Monopole / greenfield | Ma'an | Ma'an | 30.214 | 35.7416 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R03 | Fiber ring
RO-07 | MA-U-0086 | U | Monopole / greenfield | Ma'an | Ma'an | 30.2132 | 35.7463 | 30 | 3 | HUB-MA-01 | HUB-MA-01-R03 | Fiber ring
RO-07 | MAF-SU-0128 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3149 | 36.2307 | 32 | 3 | HUB-MAF-04 | HUB-MAF-04-R02 | Fiber ring
RO-07 | MAF-SU-0129 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.32 | 36.1782 | 32 | 3 | HUB-MAF-03 | HUB-MAF-03-R01 | Fiber ring
RO-07 | MAF-SU-0130 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3194 | 36.1857 | 32 | 3 | HUB-MAF-03 | HUB-MAF-03-R02 | Fiber ring
RO-07 | MAF-SU-0136 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3212 | 36.2273 | 32 | 3 | HUB-MAF-04 | HUB-MAF-04-R01 | Fiber ring
RO-07 | MAF-SU-0137 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.32 | 36.2341 | 32 | 3 | HUB-MAF-04 | HUB-MAF-04-R02 | Fiber ring
RO-07 | MAF-SU-0138 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3251 | 36.1747 | 32 | 3 | HUB-MAF-03 | HUB-MAF-03-R01 | Fiber ring
RO-07 | MAF-SU-0139 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3239 | 36.1829 | 32 | 3 | HUB-MAF-03 | HUB-MAF-03-R02 | Fiber ring
RO-07 | MAF-SU-0140 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3251 | 36.2307 | 32 | 3 | HUB-MAF-04 | HUB-MAF-04-R01 | Fiber ring
RO-07 | MAF-SU-0141 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3251 | 36.2375 | 32 | 3 | HUB-MAF-04 | HUB-MAF-04-R02 | Fiber ring
RO-07 | MAF-SU-0142 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3302 | 36.1727 | 32 | 3 | HUB-MAF-03 | HUB-MAF-03-R01 | Fiber ring
RO-07 | MAF-SU-0143 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.329 | 36.1795 | 32 | 3 | HUB-MAF-03 | HUB-MAF-03-R01 | Fiber ring
RO-07 | MAF-SU-0144 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3302 | 36.241 | 32 | 3 | HUB-MAF-04 | HUB-MAF-04-R02 | Fiber ring
RO-07 | MAF-SU-0145 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3353 | 36.1693 | 32 | 3 | HUB-MAF-03 | HUB-MAF-03-R01 | Fiber ring
RO-07 | MAF-SU-0146 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3353 | 36.1761 | 32 | 3 | HUB-MAF-03 | HUB-MAF-03-R01 | Fiber ring
RO-07 | MAF-SU-0147 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3353 | 36.2375 | 32 | 3 | HUB-MAF-04 | HUB-MAF-04-R02 | Fiber ring
RO-07 | MAF-SU-0148 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3353 | 36.2444 | 32 | 3 | HUB-MAF-04 | HUB-MAF-04-R02 | Fiber ring
RO-07 | MAF-SU-0149 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3404 | 36.1645 | 32 | 3 | HUB-MAF-03 | HUB-MAF-03-R05 | Fiber ring
RO-07 | MAF-SU-0150 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3404 | 36.1727 | 32 | 3 | HUB-MAF-03 | HUB-MAF-03-R05 | Fiber ring
RO-07 | MAF-SU-0151 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3404 | 36.241 | 32 | 3 | HUB-MAF-04 | HUB-MAF-04-R03 | Fiber ring
RO-07 | MAF-SU-0152 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3404 | 36.2478 | 32 | 3 | HUB-MAF-04 | HUB-MAF-04-R02 | Fiber ring
RO-07 | MAF-SU-0153 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3454 | 36.1679 | 32 | 3 | HUB-MAF-03 | HUB-MAF-03-R05 | Fiber ring
RO-07 | MAF-SU-0154 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3454 | 36.1761 | 32 | 3 | HUB-MAF-03 | HUB-MAF-03-R05 | Fiber ring
RO-07 | MAF-SU-0155 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3454 | 36.2444 | 32 | 3 | HUB-MAF-04 | HUB-MAF-04-R03 | Fiber ring
RO-07 | MAF-SU-0156 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3505 | 36.1713 | 32 | 3 | HUB-MAF-03 | HUB-MAF-03-R05 | Fiber ring
RO-07 | MAF-SU-0157 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3505 | 36.241 | 32 | 3 | HUB-MAF-04 | HUB-MAF-04-R03 | Fiber ring
RO-07 | MAF-SU-0158 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3505 | 36.2478 | 32 | 3 | HUB-MAF-04 | HUB-MAF-04-R03 | Fiber ring
RO-07 | MAF-SU-0162 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3556 | 36.2444 | 32 | 3 | HUB-MAF-04 | HUB-MAF-04-R03 | Fiber ring
RO-07 | MAF-U-0007 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3278 | 36.1906 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R02 | Fiber ring
RO-07 | MAF-U-0014 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3278 | 36.2236 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R01 | Fiber ring
RO-07 | MAF-U-0015 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3278 | 36.2284 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R01 | Fiber ring
RO-07 | MAF-U-0016 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3309 | 36.183 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R02 | Fiber ring
RO-07 | MAF-U-0017 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3305 | 36.1882 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R02 | Fiber ring
RO-07 | MAF-U-0018 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3305 | 36.1929 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R02 | Fiber ring
RO-07 | MAF-U-0024 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3314 | 36.2213 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R01 | Fiber ring
RO-07 | MAF-U-0025 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3309 | 36.2255 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R01 | Fiber ring
RO-07 | MAF-U-0026 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3314 | 36.2307 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R01 | Fiber ring
RO-07 | MAF-U-0027 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3357 | 36.1811 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R01 | Fiber ring
RO-07 | MAF-U-0028 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3349 | 36.1858 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R02 | Fiber ring
RO-07 | MAF-U-0029 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3349 | 36.1906 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R03 | Fiber ring
RO-07 | MAF-U-0030 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3349 | 36.1953 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R03 | Fiber ring
RO-07 | MAF-U-0035 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3349 | 36.2189 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R05 | Fiber ring
RO-07 | MAF-U-0036 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3349 | 36.2236 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R05 | Fiber ring
RO-07 | MAF-U-0037 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3349 | 36.2284 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R05 | Fiber ring
RO-07 | MAF-U-0038 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3349 | 36.2331 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R01 | Fiber ring
RO-07 | MAF-U-0039 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3376 | 36.1835 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R01 | Fiber ring
RO-07 | MAF-U-0040 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3376 | 36.1882 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R03 | Fiber ring
RO-07 | MAF-U-0041 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3384 | 36.1929 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R03 | Fiber ring
RO-07 | MAF-U-0042 | U | Rooftop | Mafraq | Mafraq | 32.3384 | 36.1976 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R03 | Fiber ring
RO-07 | MAF-U-0046 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3384 | 36.2165 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R05 | Fiber ring
RO-07 | MAF-U-0047 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3384 | 36.2213 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R05 | Fiber ring
RO-07 | MAF-U-0048 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3384 | 36.226 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R05 | Fiber ring
RO-07 | MAF-U-0049 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3384 | 36.2307 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R04 | Fiber ring
RO-07 | MAF-U-0050 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3384 | 36.2354 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R03 | Fiber ring
RO-07 | MAF-U-0051 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3419 | 36.1801 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R05 | Fiber ring
RO-07 | MAF-U-0052 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3419 | 36.1858 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R04 | Fiber ring
RO-07 | MAF-U-0053 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3419 | 36.1906 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R04 | Fiber ring
RO-07 | MAF-U-0054 | U | Rooftop | Mafraq | Mafraq | 32.3419 | 36.1953 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R03 | Fiber ring
RO-07 | MAF-U-0055 | U | Rooftop | Mafraq | Mafraq | 32.3419 | 36.2 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R03 | Fiber ring
RO-07 | MAF-U-0060 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3419 | 36.2236 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R04 | Fiber ring
RO-07 | MAF-U-0061 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3419 | 36.2284 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R04 | Fiber ring
RO-07 | MAF-U-0062 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3419 | 36.2331 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R04 | Fiber ring
RO-07 | MAF-U-0063 | U | Monopole / greenfield | Mafraq | Mafraq | 32.345 | 36.183 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R04 | Fiber ring
RO-07 | MAF-U-0064 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3454 | 36.1882 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R04 | Fiber ring
RO-07 | MAF-U-0065 | U | Rooftop | Mafraq | Mafraq | 32.3454 | 36.1929 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R04 | Fiber ring
RO-07 | MAF-U-0066 | U | Rooftop | Mafraq | Mafraq | 32.3454 | 36.1976 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R04 | Fiber ring
RO-07 | MAF-U-0072 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3454 | 36.226 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R04 | Fiber ring
RO-07 | MAF-U-0073 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3454 | 36.2307 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R04 | Fiber ring
RO-07 | MAF-U-0074 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3454 | 36.2354 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R03 | Fiber ring
RO-07 | MAF-U-0075 | U | Monopole / greenfield | Mafraq | Mafraq | 32.349 | 36.1811 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R05 | Fiber ring
RO-07 | MAF-U-0076 | U | Monopole / greenfield | Mafraq | Mafraq | 32.349 | 36.1858 | 30 | 3 | HUB-MAF-03 | HUB-MAF-03-R04 | Fiber ring
RO-07 | MAF-U-0086 | U | Monopole / greenfield | Mafraq | Mafraq | 32.349 | 36.2331 | 30 | 3 | HUB-MAF-04 | HUB-MAF-04-R04 | Fiber ring
RO-07 | RUR-R-0001 | R | Lattice tower | Rural | Tafilah | 30.7041 | 35.5885 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0002 | R | Lattice tower | Rural | Tafilah | 30.7017 | 35.6329 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0003 | R | Lattice tower | Rural | Tafilah | 30.7066 | 35.6745 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0004 | R | Lattice tower | Rural | Tafilah | 30.709 | 35.7274 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0005 | R | Lattice tower | Rural | Tafilah | 30.7443 | 35.6064 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0006 | R | Lattice tower | Rural | Tafilah | 30.7418 | 35.6537 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0007 | R | Lattice tower | Rural | Tafilah | 30.7394 | 35.7009 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0008 | R | Lattice tower | Rural | Tafilah | 30.7418 | 35.7454 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0009 | R | Lattice tower | Rural | Tafilah | 30.7771 | 35.5913 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0010 | R | Lattice tower | Rural | Tafilah | 30.7771 | 35.6386 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0011 | R | Lattice tower | Rural | Tafilah | 30.7795 | 35.6801 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0012 | R | Lattice tower | Rural | Tafilah | 30.7746 | 35.7246 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0013 | R | Lattice tower | Rural | Tafilah | 30.7746 | 35.7718 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0014 | R | Lattice tower | Rural | Tafilah | 30.8099 | 35.6565 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0015 | R | Lattice tower | Rural | Tafilah | 30.8099 | 35.7066 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0016 | R | Lattice tower | Rural | Tafilah | 30.8123 | 35.7454 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0017 | R | Lattice tower | Rural | Tafilah | 30.8123 | 35.7955 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0018 | R | Lattice tower | Rural | Tafilah | 30.8427 | 35.6801 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0019 | R | Lattice tower | Rural | Tafilah | 30.8427 | 35.7274 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0020 | R | Lattice tower | Rural | Tafilah | 30.8476 | 35.7747 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0021 | R | Lattice tower | Rural | Tafilah | 30.8524 | 35.8219 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0022 | R | Lattice tower | Rural | Tafilah | 30.8804 | 35.6537 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0023 | R | Lattice tower | Rural | Tafilah | 30.8804 | 35.7009 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0024 | R | Lattice tower | Rural | Tafilah | 30.8852 | 35.7482 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0025 | R | Lattice tower | Rural | Tafilah | 30.8828 | 35.7926 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0026 | R | Lattice tower | Rural | Tafilah | 30.8828 | 35.8399 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0027 | R | Lattice tower | Rural | Tafilah | 30.918 | 35.5913 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0028 | R | Lattice tower | Rural | Tafilah | 30.918 | 35.6272 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0029 | R | Lattice tower | Rural | Tafilah | 30.918 | 35.6745 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0030 | R | Lattice tower | Rural | Tafilah | 30.9156 | 35.7246 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0031 | R | Lattice tower | Rural | Tafilah | 30.9156 | 35.7718 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0032 | R | Lattice tower | Rural | Tafilah | 30.9156 | 35.8248 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0034 | R | Lattice tower | Rural | Tafilah | 30.9533 | 35.6036 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0035 | R | Lattice tower | Rural | Tafilah | 30.9533 | 35.6622 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0036 | R | Lattice tower | Rural | Tafilah | 30.9508 | 35.7009 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0066 | R | Lattice tower | Rural | Karak | 31.1295 | 35.6745 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0072 | R | Lattice tower | Rural | Karak | 31.1599 | 35.6093 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0073 | R | Lattice tower | Rural | Karak | 31.1648 | 35.804 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0074 | R | Lattice tower | Rural | Karak | 31.1599 | 35.8456 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0075 | R | Lattice tower | Rural | Karak | 31.1648 | 35.8985 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0076 | R | Lattice tower | Rural | Karak | 31.2 | 35.6329 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0077 | R | Lattice tower | Rural | Karak | 31.2 | 35.769 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0078 | R | Lattice tower | Rural | Karak | 31.2 | 35.8162 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0079 | R | Lattice tower | Rural | Karak | 31.2 | 35.8749 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0080 | R | Lattice tower | Rural | Karak | 31.2 | 35.9221 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0081 | R | Lattice tower | Rural | Karak | 31.2352 | 35.6622 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0082 | R | Lattice tower | Rural | Karak | 31.2304 | 35.7038 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0083 | R | Lattice tower | Rural | Karak | 31.2377 | 35.7539 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0084 | R | Lattice tower | Rural | Karak | 31.2352 | 35.7926 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0085 | R | Lattice tower | Rural | Karak | 31.2401 | 35.8456 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0086 | R | Lattice tower | Rural | Karak | 31.2352 | 35.8871 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0087 | R | Lattice tower | Rural | Karak | 31.2729 | 35.6357 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0088 | R | Lattice tower | Rural | Karak | 31.2656 | 35.6801 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0089 | R | Lattice tower | Rural | Karak | 31.2705 | 35.7302 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0090 | R | Lattice tower | Rural | Karak | 31.268 | 35.7718 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0091 | R | Lattice tower | Rural | Karak | 31.2705 | 35.8219 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0092 | R | Lattice tower | Rural | Karak | 31.2705 | 35.8635 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0093 | R | Lattice tower | Rural | Karak | 31.2705 | 35.9221 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0094 | R | Lattice tower | Rural | Karak | 31.3057 | 35.6622 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0095 | R | Lattice tower | Rural | Karak | 31.3082 | 35.7038 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0096 | R | Lattice tower | Rural | Karak | 31.3057 | 35.7454 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0097 | R | Lattice tower | Rural | Karak | 31.3057 | 35.7926 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0100 | R | Lattice tower | Rural | Karak | 31.341 | 35.6386 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0101 | R | Lattice tower | Rural | Karak | 31.3459 | 35.6801 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0102 | R | Lattice tower | Rural | Karak | 31.341 | 35.7217 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0103 | R | Lattice tower | Rural | Karak | 31.341 | 35.7747 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0104 | R | Lattice tower | Rural | Karak | 31.3385 | 35.8191 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0107 | R | Lattice tower | Rural | Karak | 31.3713 | 35.6565 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0108 | R | Lattice tower | Rural | Karak | 31.3762 | 35.7094 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0109 | R | Lattice tower | Rural | Karak | 31.3811 | 35.751 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0110 | R | Lattice tower | Rural | Karak | 31.3762 | 35.7926 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0114 | R | Lattice tower | Rural | Karak | 31.409 | 35.6773 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0115 | R | Lattice tower | Rural | Karak | 31.4066 | 35.7274 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0116 | R | Lattice tower | Rural | Karak | 31.409 | 35.7747 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0117 | R | Lattice tower | Rural | Karak | 31.4115 | 35.8191 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0120 | R | Lattice tower | Rural | Madaba | 31.4516 | 35.6565 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0121 | R | Lattice tower | Rural | Madaba | 31.4491 | 35.7009 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0122 | R | Lattice tower | Rural | Madaba | 31.4418 | 35.751 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0127 | R | Lattice tower | Rural | Madaba | 31.482 | 35.6858 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0128 | R | Lattice tower | Rural | Madaba | 31.482 | 35.7217 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0129 | R | Lattice tower | Rural | Madaba | 31.4795 | 35.7718 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0130 | R | Lattice tower | Rural | Madaba | 31.482 | 35.8276 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0134 | R | Lattice tower | Rural | Madaba | 31.5221 | 35.6565 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0135 | R | Lattice tower | Rural | Madaba | 31.5196 | 35.7009 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0136 | R | Lattice tower | Rural | Madaba | 31.5148 | 35.7482 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0137 | R | Lattice tower | Rural | Madaba | 31.5148 | 35.8011 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0138 | R | Lattice tower | Rural | Madaba | 31.5196 | 35.8427 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0142 | R | Lattice tower | Rural | Madaba | 31.5476 | 35.6801 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0143 | R | Lattice tower | Rural | Madaba | 31.5573 | 35.7274 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0144 | R | Lattice tower | Rural | Madaba | 31.5476 | 35.7747 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0145 | R | Lattice tower | Rural | Madaba | 31.5476 | 35.8219 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0150 | R | Lattice tower | Rural | Madaba | 31.5852 | 35.6594 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0151 | R | Lattice tower | Rural | Madaba | 31.5877 | 35.7094 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0152 | R | Lattice tower | Rural | Madaba | 31.5877 | 35.7567 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0153 | R | Lattice tower | Rural | Madaba | 31.5877 | 35.804 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0154 | R | Lattice tower | Rural | Madaba | 31.5852 | 35.8427 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0159 | R | Lattice tower | Rural | Madaba | 31.6254 | 35.6357 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0160 | R | Lattice tower | Rural | Madaba | 31.6254 | 35.6773 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0161 | R | Lattice tower | Rural | Madaba | 31.6181 | 35.7274 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0162 | R | Lattice tower | Rural | Madaba | 31.6181 | 35.7747 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0163 | R | Lattice tower | Rural | Madaba | 31.6229 | 35.8162 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0169 | R | Lattice tower | Rural | Madaba | 31.6582 | 35.6622 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0170 | R | Lattice tower | Rural | Madaba | 31.6606 | 35.7009 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0171 | R | Lattice tower | Rural | Madaba | 31.6582 | 35.7454 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0179 | R | Lattice tower | Rural | Madaba | 31.691 | 35.6329 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0180 | R | Lattice tower | Rural | Madaba | 31.691 | 35.683 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0181 | R | Lattice tower | Rural | Madaba | 31.6934 | 35.7274 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0186 | R | Lattice tower | Rural | Madaba | 31.7287 | 35.6622 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0187 | R | Lattice tower | Rural | Madaba | 31.7311 | 35.7038 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0192 | R | Lattice tower | Rural | Madaba | 31.7639 | 35.6386 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0193 | R | Lattice tower | Rural | Madaba | 31.7615 | 35.683 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0194 | R | Lattice tower | Rural | Madaba | 31.7663 | 35.7274 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0195 | R | Lattice tower | Rural | Amman | 31.7663 | 35.8663 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0197 | R | Lattice tower | Rural | Amman | 31.7615 | 35.9609 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0198 | R | Lattice tower | Rural | Amman | 31.7688 | 36.0582 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0199 | R | Lattice tower | Rural | Amman | 31.7663 | 36.1055 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0200 | R | Lattice tower | Rural | Amman | 31.7663 | 36.1499 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0201 | R | Lattice tower | Rural | Balqa | 31.8016 | 35.6121 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0202 | R | Lattice tower | Rural | Balqa | 31.7967 | 35.6594 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0203 | R | Lattice tower | Rural | Madaba | 31.7992 | 35.7094 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0204 | R | Lattice tower | Rural | Madaba | 31.7992 | 35.7567 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0205 | R | Lattice tower | Rural | Madaba | 31.7967 | 35.8011 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0206 | R | Lattice tower | Rural | Amman | 31.804 | 35.8456 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0207 | R | Lattice tower | Rural | Amman | 31.8016 | 35.8928 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0208 | R | Lattice tower | Rural | Amman | 31.7992 | 35.9429 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0209 | R | Lattice tower | Rural | Amman | 31.7992 | 35.9873 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0210 | R | Lattice tower | Rural | Amman | 31.7992 | 36.0289 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0211 | R | Lattice tower | Rural | Amman | 31.7992 | 36.0875 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0212 | R | Lattice tower | Rural | Amman | 31.7992 | 36.1234 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0213 | R | Lattice tower | Rural | Balqa | 31.8344 | 35.5913 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0214 | R | Lattice tower | Rural | Balqa | 31.8344 | 35.6386 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0215 | R | Lattice tower | Rural | Balqa | 31.8344 | 35.6858 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0216 | R | Lattice tower | Rural | Amman | 31.832 | 35.7302 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0217 | R | Lattice tower | Rural | Amman | 31.8344 | 35.7803 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0218 | R | Lattice tower | Rural | Amman | 31.832 | 35.8219 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0219 | R | Lattice tower | Rural | Amman | 31.8344 | 36.0582 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0220 | R | Lattice tower | Rural | Amman | 31.8368 | 36.1055 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0221 | R | Lattice tower | Rural | Amman | 31.8344 | 36.1471 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0222 | R | Lattice tower | Rural | Balqa | 31.8745 | 35.6565 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0223 | R | Lattice tower | Rural | Balqa | 31.8648 | 35.7038 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0224 | R | Lattice tower | Rural | Amman | 31.8672 | 35.7482 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0225 | R | Lattice tower | Rural | Amman | 31.8696 | 36.0819 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0226 | R | Lattice tower | Rural | Amman | 31.8721 | 36.1263 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0227 | R | Lattice tower | Rural | Amman | 31.8745 | 36.1764 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0228 | R | Lattice tower | Rural | Amman | 31.9098 | 35.6801 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0229 | R | Lattice tower | Rural | Amman | 31.9049 | 35.7331 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0230 | R | Lattice tower | Rural | Amman | 31.9025 | 36.1026 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0231 | R | Lattice tower | Rural | Amman | 31.9049 | 36.1471 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0232 | R | Lattice tower | Rural | Amman | 31.9025 | 36.2 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0233 | R | Lattice tower | Rural | Balqa | 31.9401 | 35.6093 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0234 | R | Lattice tower | Rural | Balqa | 31.945 | 35.6565 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0235 | R | Lattice tower | Rural | Amman | 31.9401 | 35.7066 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0236 | R | Lattice tower | Rural | Amman | 31.9352 | 36.1291 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0237 | R | Lattice tower | Rural | Amman | 31.9401 | 36.1792 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0238 | R | Lattice tower | Rural | Amman | 31.9401 | 36.2208 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0239 | R | Lattice tower | Rural | Balqa | 31.9754 | 35.5913 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0240 | R | Lattice tower | Rural | Balqa | 31.9754 | 35.6272 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0241 | R | Lattice tower | Rural | Balqa | 31.9803 | 35.6801 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0242 | R | Lattice tower | Rural | Amman | 31.9705 | 36.1055 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0243 | R | Lattice tower | Rural | Amman | 31.9803 | 36.1527 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0244 | R | Lattice tower | Rural | Amman | 31.9754 | 36.1972 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0245 | R | Lattice tower | Rural | Amman | 31.9729 | 36.2444 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0246 | R | Lattice tower | Rural | Balqa | 32.0106 | 35.6121 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0247 | R | Lattice tower | Rural | Balqa | 32.0131 | 35.6594 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0248 | R | Lattice tower | Rural | Amman | 32.0082 | 36.1792 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0249 | R | Lattice tower | Rural | Amman | 32.0155 | 36.2236 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0250 | R | Lattice tower | Rural | Amman | 32.0106 | 36.2652 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0251 | R | Lattice tower | Rural | Balqa | 32.0459 | 35.5913 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0252 | R | Lattice tower | Rural | Balqa | 32.041 | 35.6329 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0253 | R | Lattice tower | Rural | Zarqa | 32.0434 | 36.1972 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0254 | R | Lattice tower | Rural | Amman | 32.0459 | 36.2416 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0255 | R | Lattice tower | Rural | Amman | 32.0459 | 36.3002 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0256 | R | Lattice tower | Rural | Balqa | 32.0811 | 35.6149 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0257 | R | Lattice tower | Rural | Balqa | 32.086 | 35.6565 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0258 | R | Lattice tower | Rural | Zarqa | 32.0762 | 36.2236 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0259 | R | Lattice tower | Rural | Zarqa | 32.0836 | 36.2681 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0260 | R | Lattice tower | Rural | Balqa | 32.1163 | 35.5913 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0261 | R | Lattice tower | Rural | Balqa | 32.1163 | 35.6386 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0262 | R | Lattice tower | Rural | Balqa | 32.1163 | 35.6858 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0263 | R | Lattice tower | Rural | Balqa | 32.1115 | 35.7274 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0264 | R | Lattice tower | Rural | Balqa | 32.1163 | 35.769 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0265 | R | Lattice tower | Rural | Balqa | 32.1139 | 35.8191 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0266 | R | Lattice tower | Rural | Zarqa | 32.1212 | 35.9637 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0267 | R | Lattice tower | Rural | Zarqa | 32.1163 | 36.0053 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0268 | R | Lattice tower | Rural | Zarqa | 32.1188 | 36.2 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0269 | R | Lattice tower | Rural | Zarqa | 32.1115 | 36.2473 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0270 | R | Lattice tower | Rural | Zarqa | 32.1188 | 36.2974 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0271 | R | Lattice tower | Rural | Balqa | 32.1516 | 35.6622 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0272 | R | Lattice tower | Rural | Balqa | 32.1467 | 35.7038 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0273 | R | Lattice tower | Rural | Balqa | 32.1467 | 35.751 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0274 | R | Lattice tower | Rural | Balqa | 32.1467 | 35.7983 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0275 | R | Lattice tower | Rural | Jerash | 32.1492 | 35.8427 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0276 | R | Lattice tower | Rural | Jerash | 32.154 | 35.89 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0277 | R | Lattice tower | Rural | Zarqa | 32.1492 | 35.9372 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0278 | R | Lattice tower | Rural | Zarqa | 32.1467 | 35.9873 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0281 | R | Lattice tower | Rural | Zarqa | 32.1467 | 36.1764 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0282 | R | Lattice tower | Rural | Zarqa | 32.1516 | 36.2236 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0285 | R | Lattice tower | Rural | Ajloun | 32.1868 | 35.6745 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0286 | R | Lattice tower | Rural | Jerash | 32.1917 | 35.7274 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0287 | R | Lattice tower | Rural | Jerash | 32.182 | 35.7747 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0288 | R | Lattice tower | Rural | Jerash | 32.1868 | 35.8162 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0289 | R | Lattice tower | Rural | Jerash | 32.1844 | 35.872 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0290 | R | Lattice tower | Rural | Jerash | 32.1868 | 35.9108 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0291 | R | Lattice tower | Rural | Zarqa | 32.182 | 35.9637 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0300 | R | Lattice tower | Rural | Ajloun | 32.2245 | 35.6594 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0301 | R | Lattice tower | Rural | Ajloun | 32.2245 | 35.7038 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0302 | R | Lattice tower | Rural | Ajloun | 32.2221 | 35.7567 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0303 | R | Lattice tower | Rural | Jerash | 32.227 | 35.7983 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0304 | R | Lattice tower | Rural | Jerash | 32.2197 | 35.8427 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0305 | R | Lattice tower | Rural | Jerash | 32.2245 | 35.89 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0306 | R | Lattice tower | Rural | Jerash | 32.227 | 35.9401 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0317 | R | Lattice tower | Rural | Ajloun | 32.2598 | 35.6357 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0318 | R | Lattice tower | Rural | Ajloun | 32.2573 | 35.6858 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0319 | R | Lattice tower | Rural | Ajloun | 32.2598 | 35.7302 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0320 | R | Lattice tower | Rural | Ajloun | 32.2549 | 35.7775 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0321 | R | Lattice tower | Rural | Jerash | 32.2573 | 35.8162 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0322 | R | Lattice tower | Rural | Mafraq | 32.2622 | 35.9637 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0326 | R | Lattice tower | Rural | Mafraq | 32.2622 | 36.1527 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0332 | R | Lattice tower | Rural | Ajloun | 32.2926 | 35.6149 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0333 | R | Lattice tower | Rural | Ajloun | 32.2975 | 35.6565 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0334 | R | Lattice tower | Rural | Ajloun | 32.2877 | 35.7038 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0335 | R | Lattice tower | Rural | Ajloun | 32.2926 | 35.804 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0336 | R | Lattice tower | Rural | Mafraq | 32.2926 | 35.993 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0337 | R | Lattice tower | Rural | Mafraq | 32.2877 | 36.0346 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0338 | R | Lattice tower | Rural | Mafraq | 32.2975 | 36.0819 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0339 | R | Lattice tower | Rural | Mafraq | 32.295 | 36.1291 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0340 | R | Lattice tower | Rural | Mafraq | 32.2926 | 36.1735 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0341 | R | Lattice tower | Rural | Mafraq | 32.2926 | 36.2709 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0342 | R | Lattice tower | Rural | Mafraq | 32.2926 | 36.3182 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0343 | R | Lattice tower | Rural | Mafraq | 32.2926 | 36.3711 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0345 | R | Lattice tower | Rural | Ajloun | 32.3278 | 35.6386 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0346 | R | Lattice tower | Rural | Ajloun | 32.3303 | 35.6773 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0347 | R | Lattice tower | Rural | Ajloun | 32.3278 | 35.8162 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0348 | R | Lattice tower | Rural | Jerash | 32.3303 | 35.8692 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0349 | R | Lattice tower | Rural | Jerash | 32.3278 | 35.9221 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0350 | R | Lattice tower | Rural | Jerash | 32.3254 | 35.9609 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0351 | R | Lattice tower | Rural | Mafraq | 32.3327 | 36.011 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0352 | R | Lattice tower | Rural | Mafraq | 32.3254 | 36.0611 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0353 | R | Lattice tower | Rural | Mafraq | 32.3229 | 36.1055 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0354 | R | Lattice tower | Rural | Mafraq | 32.3278 | 36.2888 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0355 | R | Lattice tower | Rural | Mafraq | 32.3303 | 36.3446 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0356 | R | Lattice tower | Rural | Mafraq | 32.3278 | 36.3947 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0358 | R | Lattice tower | Rural | Ajloun | 32.3631 | 35.6622 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0360 | R | Lattice tower | Rural | Ajloun | 32.3631 | 35.7983 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0361 | R | Lattice tower | Rural | Ajloun | 32.3606 | 35.8427 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0363 | R | Lattice tower | Rural | Jerash | 32.3606 | 35.9429 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0365 | R | Lattice tower | Rural | Mafraq | 32.3582 | 36.0346 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0366 | R | Lattice tower | Rural | Mafraq | 32.3631 | 36.0762 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0367 | R | Lattice tower | Rural | Mafraq | 32.3582 | 36.1291 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0368 | R | Lattice tower | Rural | Mafraq | 32.3631 | 36.2709 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0369 | R | Lattice tower | Rural | Mafraq | 32.368 | 36.3182 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0370 | R | Lattice tower | Rural | Mafraq | 32.3631 | 36.3654 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0376 | R | Lattice tower | Rural | Ajloun | 32.3983 | 35.8248 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0380 | R | Lattice tower | Rural | Mafraq | 32.3959 | 36.0138 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0381 | R | Lattice tower | Rural | Mafraq | 32.3959 | 36.0611 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0382 | R | Lattice tower | Rural | Mafraq | 32.3983 | 36.0998 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0383 | R | Lattice tower | Rural | Mafraq | 32.3959 | 36.1527 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0384 | R | Lattice tower | Rural | Mafraq | 32.3983 | 36.2028 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0385 | R | Lattice tower | Rural | Mafraq | 32.3983 | 36.2473 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0386 | R | Lattice tower | Rural | Mafraq | 32.3983 | 36.2945 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0387 | R | Lattice tower | Rural | Mafraq | 32.4032 | 36.3418 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0388 | R | Lattice tower | Rural | Irbid | 32.4335 | 35.6149 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0390 | R | Lattice tower | Rural | Irbid | 32.436 | 35.7066 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0393 | R | Lattice tower | Rural | Irbid | 32.436 | 35.8427 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0394 | R | Lattice tower | Rural | Irbid | 32.436 | 35.8957 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0399 | R | Lattice tower | Rural | Mafraq | 32.4335 | 36.132 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0400 | R | Lattice tower | Rural | Mafraq | 32.4335 | 36.1707 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0401 | R | Lattice tower | Rural | Mafraq | 32.4287 | 36.2236 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0402 | R | Lattice tower | Rural | Mafraq | 32.4335 | 36.2709 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0403 | R | Lattice tower | Rural | Mafraq | 32.4287 | 36.3182 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0404 | R | Lattice tower | Rural | Irbid | 32.4688 | 35.6386 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0405 | R | Lattice tower | Rural | Irbid | 32.4688 | 35.6858 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0406 | R | Lattice tower | Rural | Irbid | 32.4688 | 35.7217 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0407 | R | Lattice tower | Rural | Irbid | 32.4664 | 35.7775 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0408 | R | Lattice tower | Rural | Irbid | 32.4639 | 35.9164 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0409 | R | Lattice tower | Rural | Irbid | 32.4639 | 35.9637 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0410 | R | Lattice tower | Rural | Irbid | 32.4664 | 36.0081 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0411 | R | Lattice tower | Rural | Irbid | 32.4688 | 36.0639 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0412 | R | Lattice tower | Rural | Mafraq | 32.4664 | 36.1055 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0413 | R | Lattice tower | Rural | Mafraq | 32.4688 | 36.1471 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0414 | R | Lattice tower | Rural | Mafraq | 32.4639 | 36.2 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0415 | R | Lattice tower | Rural | Mafraq | 32.4688 | 36.2473 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0416 | R | Lattice tower | Rural | Irbid | 32.5016 | 35.6121 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0417 | R | Lattice tower | Rural | Irbid | 32.5065 | 35.6594 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0418 | R | Lattice tower | Rural | Irbid | 32.4992 | 35.7038 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0419 | R | Lattice tower | Rural | Irbid | 32.504 | 35.7567 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0420 | R | Lattice tower | Rural | Irbid | 32.4992 | 35.9873 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0421 | R | Lattice tower | Rural | Irbid | 32.504 | 36.0318 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0422 | R | Lattice tower | Rural | Mafraq | 32.504 | 36.132 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0423 | R | Lattice tower | Rural | Irbid | 32.5417 | 35.6357 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0424 | R | Lattice tower | Rural | Irbid | 32.5344 | 35.6801 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0425 | R | Lattice tower | Rural | Irbid | 32.5369 | 35.7302 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0426 | R | Lattice tower | Rural | Irbid | 32.5745 | 35.6622 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0427 | R | Lattice tower | Rural | Irbid | 32.5721 | 35.7066 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0428 | R | Lattice tower | Rural | Irbid | 32.5721 | 35.7539 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0429 | R | Lattice tower | Rural | Irbid | 32.6098 | 35.6858 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0430 | R | Lattice tower | Rural | Irbid | 32.6073 | 35.7302 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-07 | RUR-R-0431 | R | Lattice tower | Rural | Irbid | 32.6073 | 35.7775 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0432 | R | Lattice tower | Rural | Irbid | 32.6098 | 35.9108 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0433 | R | Lattice tower | Rural | Irbid | 32.6049 | 35.9637 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0434 | R | Lattice tower | Rural | Irbid | 32.6475 | 35.6565 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0435 | R | Lattice tower | Rural | Irbid | 32.6499 | 35.7038 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0436 | R | Lattice tower | Rural | Irbid | 32.645 | 35.7454 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0437 | R | Lattice tower | Rural | Irbid | 32.6475 | 35.8011 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0438 | R | Lattice tower | Rural | Irbid | 32.645 | 35.8399 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0439 | R | Lattice tower | Rural | Irbid | 32.645 | 35.8871 | 45 | 3 |  |  | Microwave E-band 10G
RO-07 | RUR-R-0440 | R | Lattice tower | Rural | Irbid | 32.6426 | 35.9429 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0441 | R | Lattice tower | Rural | Irbid | 32.6754 | 35.7274 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0442 | R | Lattice tower | Rural | Irbid | 32.6803 | 35.7803 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0443 | R | Lattice tower | Rural | Irbid | 32.6754 | 35.8219 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | RUR-R-0444 | R | Lattice tower | Rural | Irbid | 32.6778 | 35.8663 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-07 | SAL-SU-0086 | SU | Monopole / greenfield | Salt | Balqa | 32.0145 | 35.7372 | 32 | 3 | HUB-SAL-02 | HUB-SAL-02-R02 | Fiber ring
RO-07 | SAL-SU-0087 | SU | Monopole / greenfield | Salt | Balqa | 32.0145 | 35.7413 | 32 | 3 | HUB-SAL-02 | HUB-SAL-02-R02 | Fiber ring
RO-07 | SAL-SU-0092 | SU | Monopole / greenfield | Salt | Balqa | 32.0196 | 35.731 | 32 | 3 | HUB-SAL-02 | HUB-SAL-02-R01 | Fiber ring
RO-07 | SAL-SU-0093 | SU | Monopole / greenfield | Salt | Balqa | 32.0196 | 35.7406 | 32 | 3 | HUB-SAL-02 | HUB-SAL-02-R02 | Fiber ring
RO-07 | SAL-SU-0094 | SU | Monopole / greenfield | Salt | Balqa | 32.0202 | 35.7454 | 32 | 3 | HUB-SAL-02 | HUB-SAL-02-R02 | Fiber ring
RO-07 | SAL-SU-0095 | SU | Monopole / greenfield | Salt | Balqa | 32.0202 | 35.7522 | 32 | 3 | HUB-SAL-02 | HUB-SAL-02-R02 | Fiber ring
RO-07 | SAL-SU-0099 | SU | Monopole / greenfield | Salt | Balqa | 32.0253 | 35.7433 | 32 | 3 | HUB-SAL-02 | HUB-SAL-02-R02 | Fiber ring
RO-07 | SAL-SU-0100 | SU | Monopole / greenfield | Salt | Balqa | 32.0259 | 35.7495 | 32 | 3 | HUB-SAL-02 | HUB-SAL-02-R03 | Fiber ring
RO-07 | SAL-SU-0101 | SU | Monopole / greenfield | Salt | Balqa | 32.0259 | 35.7563 | 32 | 3 | HUB-SAL-02 | HUB-SAL-02-R03 | Fiber ring
RO-07 | SAL-SU-0104 | SU | Monopole / greenfield | Salt | Balqa | 32.0304 | 35.759 | 32 | 3 | HUB-SAL-02 | HUB-SAL-02-R03 | Fiber ring
RO-07 | SAL-SU-0107 | SU | Monopole / greenfield | Salt | Balqa | 32.0349 | 35.7645 | 32 | 3 | HUB-SAL-02 | HUB-SAL-02-R03 | Fiber ring
RO-07 | SAL-SU-0110 | SU | Monopole / greenfield | Salt | Balqa | 32.04 | 35.7583 | 32 | 3 | HUB-SAL-02 | HUB-SAL-02-R04 | Fiber ring
RO-07 | SAL-SU-0111 | SU | Monopole / greenfield | Salt | Balqa | 32.04 | 35.7652 | 32 | 3 | HUB-SAL-02 | HUB-SAL-02-R03 | Fiber ring
RO-07 | SAL-SU-0112 | SU | Monopole / greenfield | Salt | Balqa | 32.0451 | 35.6962 | 32 | 3 | HUB-SAL-03 | HUB-SAL-03-R01 | Fiber ring
RO-07 | SAL-SU-0113 | SU | Monopole / greenfield | Salt | Balqa | 32.0451 | 35.703 | 32 | 3 | HUB-SAL-03 | HUB-SAL-03-R01 | Fiber ring
RO-07 | SAL-SU-0114 | SU | Monopole / greenfield | Salt | Balqa | 32.0451 | 35.7549 | 32 | 3 | HUB-SAL-01 | HUB-SAL-01-R03 | Fiber ring
RO-07 | SAL-SU-0115 | SU | Monopole / greenfield | Salt | Balqa | 32.0451 | 35.7617 | 32 | 3 | HUB-SAL-01 | HUB-SAL-01-R03 | Fiber ring
RO-07 | SAL-SU-0116 | SU | Monopole / greenfield | Salt | Balqa | 32.0502 | 35.6996 | 32 | 3 | HUB-SAL-03 | HUB-SAL-03-R05 | Fiber ring
RO-07 | SAL-SU-0117 | SU | Monopole / greenfield | Salt | Balqa | 32.0502 | 35.7037 | 32 | 3 | HUB-SAL-03 | HUB-SAL-03-R05 | Fiber ring
RO-07 | SAL-SU-0118 | SU | Monopole / greenfield | Salt | Balqa | 32.049 | 35.7529 | 32 | 3 | HUB-SAL-01 | HUB-SAL-01-R03 | Fiber ring
RO-07 | SAL-SU-0119 | SU | Monopole / greenfield | Salt | Balqa | 32.0496 | 35.759 | 32 | 3 | HUB-SAL-01 | HUB-SAL-01-R03 | Fiber ring
RO-07 | SAL-SU-0120 | SU | Monopole / greenfield | Salt | Balqa | 32.0553 | 35.7003 | 32 | 3 | HUB-SAL-03 | HUB-SAL-03-R05 | Fiber ring
RO-07 | SAL-SU-0121 | SU | Monopole / greenfield | Salt | Balqa | 32.0553 | 35.7071 | 32 | 3 | HUB-SAL-03 | HUB-SAL-03-R05 | Fiber ring
RO-07 | SAL-SU-0122 | SU | Monopole / greenfield | Salt | Balqa | 32.0553 | 35.7153 | 32 | 3 | HUB-SAL-03 | HUB-SAL-03-R04 | Fiber ring
RO-07 | SAL-SU-0123 | SU | Monopole / greenfield | Salt | Balqa | 32.0553 | 35.7481 | 32 | 3 | HUB-SAL-01 | HUB-SAL-01-R04 | Fiber ring
RO-07 | SAL-SU-0124 | SU | Monopole / greenfield | Salt | Balqa | 32.0553 | 35.7549 | 32 | 3 | HUB-SAL-01 | HUB-SAL-01-R04 | Fiber ring
RO-07 | SAL-SU-0125 | SU | Monopole / greenfield | Salt | Balqa | 32.0609 | 35.7044 | 32 | 3 | HUB-SAL-03 | HUB-SAL-03-R05 | Fiber ring
RO-07 | SAL-SU-0126 | SU | Monopole / greenfield | Salt | Balqa | 32.0603 | 35.7119 | 32 | 3 | HUB-SAL-03 | HUB-SAL-03-R04 | Fiber ring
RO-07 | SAL-SU-0127 | SU | Rooftop | Salt | Balqa | 32.0603 | 35.7194 | 32 | 3 | HUB-SAL-03 | HUB-SAL-03-R04 | Fiber ring
RO-07 | SAL-SU-0128 | SU | Rooftop | Salt | Balqa | 32.0615 | 35.7256 | 32 | 3 | HUB-SAL-03 | HUB-SAL-03-R03 | Fiber ring
RO-07 | SAL-SU-0129 | SU | Rooftop | Salt | Balqa | 32.0615 | 35.7324 | 32 | 3 | HUB-SAL-01 | HUB-SAL-01-R05 | Fiber ring
RO-07 | SAL-SU-0130 | SU | Monopole / greenfield | Salt | Balqa | 32.0603 | 35.7392 | 32 | 3 | HUB-SAL-01 | HUB-SAL-01-R04 | Fiber ring
RO-07 | SAL-SU-0131 | SU | Monopole / greenfield | Salt | Balqa | 32.0615 | 35.746 | 32 | 3 | HUB-SAL-01 | HUB-SAL-01-R04 | Fiber ring
RO-07 | SAL-SU-0132 | SU | Monopole / greenfield | Salt | Balqa | 32.0598 | 35.7522 | 32 | 3 | HUB-SAL-01 | HUB-SAL-01-R04 | Fiber ring
RO-07 | SAL-SU-0133 | SU | Monopole / greenfield | Salt | Balqa | 32.0654 | 35.714 | 32 | 3 | HUB-SAL-03 | HUB-SAL-03-R04 | Fiber ring
RO-07 | SAL-SU-0134 | SU | Rooftop | Salt | Balqa | 32.0654 | 35.7235 | 32 | 3 | HUB-SAL-03 | HUB-SAL-03-R04 | Fiber ring
RO-07 | SAL-SU-0135 | SU | Rooftop | Salt | Balqa | 32.0643 | 35.729 | 32 | 3 | HUB-SAL-01 | HUB-SAL-01-R05 | Fiber ring
RO-07 | SAL-SU-0136 | SU | Monopole / greenfield | Salt | Balqa | 32.0666 | 35.7358 | 32 | 3 | HUB-SAL-01 | HUB-SAL-01-R04 | Fiber ring
RO-07 | SAL-SU-0137 | SU | Monopole / greenfield | Salt | Balqa | 32.0649 | 35.7433 | 32 | 3 | HUB-SAL-01 | HUB-SAL-01-R04 | Fiber ring
RO-07 | SAL-U-0003 | U | Monopole / greenfield | Salt | Balqa | 32.0239 | 35.7321 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R01 | Fiber ring
RO-07 | SAL-U-0004 | U | Monopole / greenfield | Salt | Balqa | 32.0255 | 35.7369 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R01 | Fiber ring
RO-07 | SAL-U-0008 | U | Monopole / greenfield | Salt | Balqa | 32.0282 | 35.7307 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R01 | Fiber ring
RO-07 | SAL-U-0009 | U | Monopole / greenfield | Salt | Balqa | 32.0291 | 35.7345 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R01 | Fiber ring
RO-07 | SAL-U-0010 | U | Monopole / greenfield | Salt | Balqa | 32.0291 | 35.7392 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R01 | Fiber ring
RO-07 | SAL-U-0011 | U | Monopole / greenfield | Salt | Balqa | 32.0274 | 35.7439 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R02 | Fiber ring
RO-07 | SAL-U-0017 | U | Rooftop | Salt | Balqa | 32.0326 | 35.7321 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R05 | Fiber ring
RO-07 | SAL-U-0018 | U | Rooftop | Salt | Balqa | 32.0314 | 35.7373 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R01 | Fiber ring
RO-07 | SAL-U-0019 | U | Monopole / greenfield | Salt | Balqa | 32.0326 | 35.7416 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R05 | Fiber ring
RO-07 | SAL-U-0020 | U | Monopole / greenfield | Salt | Balqa | 32.0318 | 35.7454 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R01 | Fiber ring
RO-07 | SAL-U-0021 | U | Monopole / greenfield | Salt | Balqa | 32.0318 | 35.752 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R03 | Fiber ring
RO-07 | SAL-U-0027 | U | Rooftop | Salt | Balqa | 32.0353 | 35.7288 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R05 | Fiber ring
RO-07 | SAL-U-0028 | U | Rooftop | Salt | Balqa | 32.0361 | 35.7345 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R05 | Fiber ring
RO-07 | SAL-U-0029 | U | Rooftop | Salt | Balqa | 32.0353 | 35.7402 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R05 | Fiber ring
RO-07 | SAL-U-0030 | U | Rooftop | Salt | Balqa | 32.0353 | 35.743 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R04 | Fiber ring
RO-07 | SAL-U-0031 | U | Monopole / greenfield | Salt | Balqa | 32.0353 | 35.7477 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R04 | Fiber ring
RO-07 | SAL-U-0032 | U | Monopole / greenfield | Salt | Balqa | 32.0361 | 35.7534 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R03 | Fiber ring
RO-07 | SAL-U-0038 | U | Rooftop | Salt | Balqa | 32.0396 | 35.7321 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R05 | Fiber ring
RO-07 | SAL-U-0039 | U | Rooftop | Salt | Balqa | 32.0396 | 35.7369 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R04 | Fiber ring
RO-07 | SAL-U-0040 | U | Rooftop | Salt | Balqa | 32.0388 | 35.7425 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R04 | Fiber ring
RO-07 | SAL-U-0041 | U | Monopole / greenfield | Salt | Balqa | 32.0388 | 35.7454 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R04 | Fiber ring
RO-07 | SAL-U-0042 | U | Monopole / greenfield | Salt | Balqa | 32.0392 | 35.7515 | 30 | 3 | HUB-SAL-02 | HUB-SAL-02-R04 | Fiber ring
RO-07 | SAL-U-0043 | U | Rooftop | Salt | Balqa | 32.0432 | 35.7061 | 30 | 3 | HUB-SAL-03 | HUB-SAL-03-R01 | Fiber ring
RO-07 | SAL-U-0044 | U | Rooftop | Salt | Balqa | 32.0423 | 35.7099 | 30 | 3 | HUB-SAL-03 | HUB-SAL-03-R01 | Fiber ring
RO-07 | SAL-U-0045 | U | Rooftop | Salt | Balqa | 32.0423 | 35.7146 | 30 | 3 | HUB-SAL-03 | HUB-SAL-03-R02 | Fiber ring
RO-07 | SAL-U-0046 | U | Rooftop | Salt | Balqa | 32.0432 | 35.7203 | 33 | 3 | HUB-SAL-03 | HUB-SAL-03-R02 | Fiber ring
RO-07 | SAL-U-0047 | U | Rooftop | Salt | Balqa | 32.0423 | 35.7241 | 33 | 3 | HUB-SAL-03 | HUB-SAL-03-R02 | Fiber ring
RO-07 | SAL-U-0048 | U | Rooftop | Salt | Balqa | 32.0423 | 35.7307 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R01 | Fiber ring
RO-07 | SAL-U-0049 | U | Rooftop | Salt | Balqa | 32.0423 | 35.7345 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R01 | Fiber ring
RO-07 | SAL-U-0050 | U | Rooftop | Salt | Balqa | 32.0423 | 35.7383 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R02 | Fiber ring
RO-07 | SAL-U-0051 | U | Rooftop | Salt | Balqa | 32.0427 | 35.7444 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R02 | Fiber ring
RO-07 | SAL-U-0052 | U | Monopole / greenfield | Salt | Balqa | 32.0423 | 35.7477 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R02 | Fiber ring
RO-07 | SAL-U-0053 | U | Monopole / greenfield | Salt | Balqa | 32.0419 | 35.7529 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R02 | Fiber ring
RO-07 | SAL-U-0054 | U | Rooftop | Salt | Balqa | 32.0451 | 35.7085 | 30 | 3 | HUB-SAL-03 | HUB-SAL-03-R01 | Fiber ring
RO-07 | SAL-U-0055 | U | Rooftop | Salt | Balqa | 32.0459 | 35.7123 | 30 | 3 | HUB-SAL-03 | HUB-SAL-03-R01 | Fiber ring
RO-07 | SAL-U-0056 | U | Rooftop | Salt | Balqa | 32.0459 | 35.718 | 30 | 3 | HUB-SAL-03 | HUB-SAL-03-R02 | Fiber ring
RO-07 | SAL-U-0057 | U | Rooftop | Salt | Balqa | 32.0451 | 35.7227 | 30 | 3 | HUB-SAL-03 | HUB-SAL-03-R02 | Fiber ring
RO-07 | SAL-U-0058 | U | Rooftop | Salt | Balqa | 32.0463 | 35.7279 | 30 | 3 | HUB-SAL-03 | HUB-SAL-03-R02 | Fiber ring
RO-07 | SAL-U-0059 | U | Rooftop | Salt | Balqa | 32.0459 | 35.7312 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R01 | Fiber ring
RO-07 | SAL-U-0060 | U | Rooftop | Salt | Balqa | 32.0463 | 35.7373 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R01 | Fiber ring
RO-07 | SAL-U-0061 | U | Rooftop | Salt | Balqa | 32.0463 | 35.7411 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R02 | Fiber ring
RO-07 | SAL-U-0062 | U | Monopole / greenfield | Salt | Balqa | 32.0459 | 35.7463 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R02 | Fiber ring
RO-07 | SAL-U-0063 | U | Monopole / greenfield | Salt | Balqa | 32.0467 | 35.751 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R03 | Fiber ring
RO-07 | SAL-U-0064 | U | Monopole / greenfield | Salt | Balqa | 32.0502 | 35.7109 | 30 | 3 | HUB-SAL-03 | HUB-SAL-03-R05 | Fiber ring
RO-07 | SAL-U-0065 | U | Rooftop | Salt | Balqa | 32.0494 | 35.7146 | 30 | 3 | HUB-SAL-03 | HUB-SAL-03-R01 | Fiber ring
RO-07 | SAL-U-0066 | U | Rooftop | Salt | Balqa | 32.0494 | 35.7194 | 30 | 3 | HUB-SAL-03 | HUB-SAL-03-R03 | Fiber ring
RO-07 | SAL-U-0067 | U | Rooftop | Salt | Balqa | 32.0494 | 35.726 | 30 | 3 | HUB-SAL-03 | HUB-SAL-03-R03 | Fiber ring
RO-07 | SAL-U-0068 | U | Rooftop | Salt | Balqa | 32.0494 | 35.7298 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R01 | Fiber ring
RO-07 | SAL-U-0069 | U | Rooftop | Salt | Balqa | 32.0498 | 35.734 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R01 | Fiber ring
RO-07 | SAL-U-0070 | U | Rooftop | Salt | Balqa | 32.0498 | 35.7388 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R01 | Fiber ring
RO-07 | SAL-U-0071 | U | Monopole / greenfield | Salt | Balqa | 32.0494 | 35.7449 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R02 | Fiber ring
RO-07 | SAL-U-0072 | U | Monopole / greenfield | Salt | Balqa | 32.0494 | 35.7487 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R03 | Fiber ring
RO-07 | SAL-U-0073 | U | Rooftop | Salt | Balqa | 32.0529 | 35.717 | 30 | 3 | HUB-SAL-03 | HUB-SAL-03-R04 | Fiber ring
RO-07 | SAL-U-0074 | U | Rooftop | Salt | Balqa | 32.0529 | 35.7236 | 30 | 3 | HUB-SAL-03 | HUB-SAL-03-R03 | Fiber ring
RO-07 | SAL-U-0075 | U | Rooftop | Salt | Balqa | 32.0529 | 35.7279 | 30 | 3 | HUB-SAL-03 | HUB-SAL-03-R03 | Fiber ring
RO-07 | SAL-U-0076 | U | Rooftop | Salt | Balqa | 32.0537 | 35.7321 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R05 | Fiber ring
RO-07 | SAL-U-0077 | U | Rooftop | Salt | Balqa | 32.0529 | 35.7359 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R05 | Fiber ring
RO-07 | SAL-U-0078 | U | Monopole / greenfield | Salt | Balqa | 32.0521 | 35.7416 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R01 | Fiber ring
RO-07 | SAL-U-0079 | U | Monopole / greenfield | Salt | Balqa | 32.0529 | 35.7473 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R03 | Fiber ring
RO-07 | SAL-U-0080 | U | Rooftop | Salt | Balqa | 32.0564 | 35.726 | 30 | 3 | HUB-SAL-03 | HUB-SAL-03-R03 | Fiber ring
RO-07 | SAL-U-0081 | U | Rooftop | Salt | Balqa | 32.0564 | 35.7288 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R05 | Fiber ring
RO-07 | SAL-U-0082 | U | Rooftop | Salt | Balqa | 32.0564 | 35.7336 | 30 | 3 | HUB-SAL-01 | HUB-SAL-01-R05 | Fiber ring
RO-08 | AJL-SU-0041 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3098 | 35.744 | 32 | 3 | HUB-AJL-02 | HUB-AJL-02-R01 | Fiber ring
RO-08 | AJL-SU-0042 | SU | Rooftop | Ajloun | Ajloun | 32.3086 | 35.7495 | 32 | 3 | HUB-AJL-02 | HUB-AJL-02-R01 | Fiber ring
RO-08 | AJL-SU-0043 | SU | Rooftop | Ajloun | Ajloun | 32.3092 | 35.757 | 32 | 3 | HUB-AJL-02 | HUB-AJL-02-R01 | Fiber ring
RO-08 | AJL-SU-0044 | SU | Rooftop | Ajloun | Ajloun | 32.3098 | 35.7645 | 32 | 3 | HUB-AJL-02 | HUB-AJL-02-R01 | Fiber ring
RO-08 | AJL-SU-0045 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3155 | 35.7317 | 32 | 3 | HUB-AJL-03 | HUB-AJL-03-R01 | Fiber ring
RO-08 | AJL-SU-0046 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3137 | 35.7392 | 32 | 3 | HUB-AJL-02 | HUB-AJL-02-R01 | Fiber ring
RO-08 | AJL-SU-0047 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3161 | 35.746 | 32 | 3 | HUB-AJL-02 | HUB-AJL-02-R01 | Fiber ring
RO-08 | AJL-SU-0048 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3161 | 35.7529 | 32 | 3 | HUB-AJL-02 | HUB-AJL-02-R01 | Fiber ring
RO-08 | AJL-SU-0049 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3155 | 35.7604 | 32 | 3 | HUB-AJL-02 | HUB-AJL-02-R02 | Fiber ring
RO-08 | AJL-SU-0050 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3149 | 35.7679 | 32 | 3 | HUB-AJL-02 | HUB-AJL-02-R02 | Fiber ring
RO-08 | AJL-SU-0051 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3212 | 35.729 | 32 | 3 | HUB-AJL-03 | HUB-AJL-03-R01 | Fiber ring
RO-08 | AJL-SU-0052 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.32 | 35.7413 | 32 | 3 | HUB-AJL-03 | HUB-AJL-03-R01 | Fiber ring
RO-08 | AJL-SU-0053 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3206 | 35.7638 | 32 | 3 | HUB-AJL-02 | HUB-AJL-02-R02 | Fiber ring
RO-08 | AJL-SU-0054 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3206 | 35.7706 | 32 | 3 | HUB-AJL-02 | HUB-AJL-02-R02 | Fiber ring
RO-08 | AJL-SU-0055 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.32 | 35.7781 | 32 | 3 | HUB-AJL-02 | HUB-AJL-02-R02 | Fiber ring
RO-08 | AJL-SU-0056 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3251 | 35.7269 | 32 | 3 | HUB-AJL-03 | HUB-AJL-03-R01 | Fiber ring
RO-08 | AJL-SU-0057 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3251 | 35.731 | 32 | 3 | HUB-AJL-03 | HUB-AJL-03-R01 | Fiber ring
RO-08 | AJL-SU-0058 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3263 | 35.7392 | 32 | 3 | HUB-AJL-03 | HUB-AJL-03-R01 | Fiber ring
RO-08 | AJL-SU-0059 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3251 | 35.7747 | 32 | 3 | HUB-AJL-02 | HUB-AJL-02-R02 | Fiber ring
RO-08 | AJL-SU-0060 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3296 | 35.7297 | 32 | 3 | HUB-AJL-03 | HUB-AJL-03-R01 | Fiber ring
RO-08 | AJL-SU-0061 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.329 | 35.7768 | 32 | 3 | HUB-AJL-02 | HUB-AJL-02-R02 | Fiber ring
RO-08 | AJL-SU-0062 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3353 | 35.7256 | 32 | 3 | HUB-AJL-03 | HUB-AJL-03-R04 | Fiber ring
RO-08 | AJL-SU-0063 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3353 | 35.731 | 32 | 3 | HUB-AJL-03 | HUB-AJL-03-R04 | Fiber ring
RO-08 | AJL-SU-0064 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3364 | 35.7734 | 32 | 3 | HUB-AJL-01 | HUB-AJL-01-R02 | Fiber ring
RO-08 | AJL-SU-0065 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3398 | 35.7283 | 32 | 3 | HUB-AJL-03 | HUB-AJL-03-R04 | Fiber ring
RO-08 | AJL-SU-0066 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3415 | 35.7358 | 32 | 3 | HUB-AJL-03 | HUB-AJL-03-R03 | Fiber ring
RO-08 | AJL-SU-0067 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3404 | 35.7781 | 32 | 3 | HUB-AJL-01 | HUB-AJL-01-R03 | Fiber ring
RO-08 | AJL-SU-0068 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3454 | 35.7338 | 32 | 3 | HUB-AJL-03 | HUB-AJL-03-R04 | Fiber ring
RO-08 | AJL-SU-0069 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3454 | 35.7406 | 32 | 3 | HUB-AJL-03 | HUB-AJL-03-R03 | Fiber ring
RO-08 | AJL-SU-0070 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3443 | 35.7665 | 32 | 3 | HUB-AJL-01 | HUB-AJL-01-R03 | Fiber ring
RO-08 | AJL-SU-0071 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3454 | 35.7747 | 32 | 3 | HUB-AJL-01 | HUB-AJL-01-R03 | Fiber ring
RO-08 | AJL-SU-0072 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3517 | 35.7358 | 32 | 3 | HUB-AJL-03 | HUB-AJL-03-R03 | Fiber ring
RO-08 | AJL-SU-0073 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3505 | 35.744 | 32 | 3 | HUB-AJL-01 | HUB-AJL-01-R04 | Fiber ring
RO-08 | AJL-SU-0074 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3511 | 35.7488 | 32 | 3 | HUB-AJL-01 | HUB-AJL-01-R04 | Fiber ring
RO-08 | AJL-SU-0075 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3494 | 35.7563 | 32 | 3 | HUB-AJL-01 | HUB-AJL-01-R04 | Fiber ring
RO-08 | AJL-SU-0076 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3505 | 35.7631 | 32 | 3 | HUB-AJL-01 | HUB-AJL-01-R03 | Fiber ring
RO-08 | AJL-SU-0077 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3517 | 35.7699 | 32 | 3 | HUB-AJL-01 | HUB-AJL-01-R03 | Fiber ring
RO-08 | AJL-SU-0078 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3544 | 35.7392 | 32 | 3 | HUB-AJL-01 | HUB-AJL-01-R04 | Fiber ring
RO-08 | AJL-SU-0079 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3544 | 35.746 | 32 | 3 | HUB-AJL-01 | HUB-AJL-01-R04 | Fiber ring
RO-08 | AJL-SU-0080 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3544 | 35.7529 | 32 | 3 | HUB-AJL-01 | HUB-AJL-01-R04 | Fiber ring
RO-08 | AJL-SU-0081 | SU | Monopole / greenfield | Ajloun | Ajloun | 32.3544 | 35.7597 | 32 | 3 | HUB-AJL-01 | HUB-AJL-01-R03 | Fiber ring
RO-08 | AJL-U-0001 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3204 | 35.7468 | 30 | 3 | HUB-AJL-02 | HUB-AJL-02-R04 | Fiber ring
RO-08 | AJL-U-0002 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3208 | 35.752 | 30 | 3 | HUB-AJL-02 | HUB-AJL-02-R04 | Fiber ring
RO-08 | AJL-U-0003 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3204 | 35.7562 | 30 | 3 | HUB-AJL-02 | HUB-AJL-02-R01 | Fiber ring
RO-08 | AJL-U-0004 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3243 | 35.7449 | 30 | 3 | HUB-AJL-03 | HUB-AJL-03-R02 | Fiber ring
RO-08 | AJL-U-0005 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3243 | 35.7496 | 30 | 3 | HUB-AJL-02 | HUB-AJL-02-R04 | Fiber ring
RO-08 | AJL-U-0006 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3235 | 35.7534 | 30 | 3 | HUB-AJL-02 | HUB-AJL-02-R04 | Fiber ring
RO-08 | AJL-U-0007 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3243 | 35.7591 | 30 | 3 | HUB-AJL-02 | HUB-AJL-02-R03 | Fiber ring
RO-08 | AJL-U-0008 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3243 | 35.7638 | 30 | 3 | HUB-AJL-02 | HUB-AJL-02-R03 | Fiber ring
RO-08 | AJL-U-0009 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3278 | 35.7406 | 30 | 3 | HUB-AJL-03 | HUB-AJL-03-R02 | Fiber ring
RO-08 | AJL-U-0010 | U | Rooftop | Ajloun | Ajloun | 32.3286 | 35.7463 | 30 | 3 | HUB-AJL-03 | HUB-AJL-03-R02 | Fiber ring
RO-08 | AJL-U-0011 | U | Rooftop | Ajloun | Ajloun | 32.3278 | 35.752 | 30 | 3 | HUB-AJL-02 | HUB-AJL-02-R04 | Fiber ring
RO-08 | AJL-U-0012 | U | Rooftop | Ajloun | Ajloun | 32.3286 | 35.7558 | 30 | 3 | HUB-AJL-02 | HUB-AJL-02-R04 | Fiber ring
RO-08 | AJL-U-0013 | U | Monopole / greenfield | Ajloun | Ajloun | 32.327 | 35.7605 | 30 | 3 | HUB-AJL-02 | HUB-AJL-02-R03 | Fiber ring
RO-08 | AJL-U-0014 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3278 | 35.7662 | 30 | 3 | HUB-AJL-02 | HUB-AJL-02-R03 | Fiber ring
RO-08 | AJL-U-0015 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3322 | 35.7392 | 30 | 3 | HUB-AJL-03 | HUB-AJL-03-R01 | Fiber ring
RO-08 | AJL-U-0016 | U | Rooftop | Ajloun | Ajloun | 32.3322 | 35.7439 | 30 | 3 | HUB-AJL-03 | HUB-AJL-03-R02 | Fiber ring
RO-08 | AJL-U-0017 | U | Rooftop | Ajloun | Ajloun | 32.3314 | 35.7477 | 30 | 3 | HUB-AJL-03 | HUB-AJL-03-R02 | Fiber ring
RO-08 | AJL-U-0018 | U | Rooftop | Ajloun | Ajloun | 32.3309 | 35.7539 | 30 | 3 | HUB-AJL-02 | HUB-AJL-02-R04 | Fiber ring
RO-08 | AJL-U-0019 | U | Rooftop | Ajloun | Ajloun | 32.3305 | 35.7581 | 30 | 3 | HUB-AJL-02 | HUB-AJL-02-R03 | Fiber ring
RO-08 | AJL-U-0020 | U | Rooftop | Ajloun | Ajloun | 32.3305 | 35.7629 | 30 | 3 | HUB-AJL-02 | HUB-AJL-02-R03 | Fiber ring
RO-08 | AJL-U-0021 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3305 | 35.7676 | 30 | 3 | HUB-AJL-02 | HUB-AJL-02-R03 | Fiber ring
RO-08 | AJL-U-0022 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3341 | 35.7369 | 30 | 3 | HUB-AJL-03 | HUB-AJL-03-R04 | Fiber ring
RO-08 | AJL-U-0023 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3345 | 35.7421 | 30 | 3 | HUB-AJL-03 | HUB-AJL-03-R03 | Fiber ring
RO-08 | AJL-U-0024 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3357 | 35.7463 | 30 | 3 | HUB-AJL-03 | HUB-AJL-03-R02 | Fiber ring
RO-08 | AJL-U-0025 | U | Rooftop | Ajloun | Ajloun | 32.3349 | 35.7501 | 30 | 3 | HUB-AJL-03 | HUB-AJL-03-R02 | Fiber ring
RO-08 | AJL-U-0026 | U | Rooftop | Ajloun | Ajloun | 32.3357 | 35.7558 | 30 | 3 | HUB-AJL-01 | HUB-AJL-01-R01 | Fiber ring
RO-08 | AJL-U-0027 | U | Rooftop | Ajloun | Ajloun | 32.3357 | 35.7605 | 30 | 3 | HUB-AJL-01 | HUB-AJL-01-R02 | Fiber ring
RO-08 | AJL-U-0028 | U | Rooftop | Ajloun | Ajloun | 32.3357 | 35.7652 | 30 | 3 | HUB-AJL-01 | HUB-AJL-01-R02 | Fiber ring
RO-08 | AJL-U-0029 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3392 | 35.7392 | 30 | 3 | HUB-AJL-03 | HUB-AJL-03-R03 | Fiber ring
RO-08 | AJL-U-0030 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3384 | 35.7449 | 30 | 3 | HUB-AJL-03 | HUB-AJL-03-R03 | Fiber ring
RO-08 | AJL-U-0031 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3384 | 35.7477 | 30 | 3 | HUB-AJL-03 | HUB-AJL-03-R03 | Fiber ring
RO-08 | AJL-U-0032 | U | Rooftop | Ajloun | Ajloun | 32.3384 | 35.7543 | 30 | 3 | HUB-AJL-01 | HUB-AJL-01-R01 | Fiber ring
RO-08 | AJL-U-0033 | U | Rooftop | Ajloun | Ajloun | 32.3384 | 35.7591 | 30 | 3 | HUB-AJL-01 | HUB-AJL-01-R02 | Fiber ring
RO-08 | AJL-U-0034 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3384 | 35.7629 | 30 | 3 | HUB-AJL-01 | HUB-AJL-01-R02 | Fiber ring
RO-08 | AJL-U-0035 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3419 | 35.7501 | 30 | 3 | HUB-AJL-01 | HUB-AJL-01-R01 | Fiber ring
RO-08 | AJL-U-0036 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3427 | 35.7558 | 30 | 3 | HUB-AJL-01 | HUB-AJL-01-R01 | Fiber ring
RO-08 | AJL-U-0037 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3419 | 35.7614 | 30 | 3 | HUB-AJL-01 | HUB-AJL-01-R02 | Fiber ring
RO-08 | AJL-U-0038 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3454 | 35.7496 | 30 | 3 | HUB-AJL-01 | HUB-AJL-01-R01 | Fiber ring
RO-08 | AJL-U-0039 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3454 | 35.7529 | 30 | 3 | HUB-AJL-01 | HUB-AJL-01-R01 | Fiber ring
RO-08 | AJL-U-0040 | U | Monopole / greenfield | Ajloun | Ajloun | 32.3463 | 35.7581 | 30 | 3 | HUB-AJL-01 | HUB-AJL-01-R01 | Fiber ring
RO-08 | AMM-SU-2340 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8579 | 35.9577 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R02 | Fiber ring
RO-08 | AMM-SU-2341 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8579 | 35.9645 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R02 | Fiber ring
RO-08 | AMM-SU-2342 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8579 | 35.9713 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R02 | Fiber ring
RO-08 | AMM-SU-2343 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8567 | 35.9781 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R03 | Fiber ring
RO-08 | AMM-SU-2351 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8624 | 35.8389 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R02 | Fiber ring
RO-08 | AMM-SU-2352 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8612 | 35.8443 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R03 | Fiber ring
RO-08 | AMM-SU-2353 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8618 | 35.8505 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R03 | Fiber ring
RO-08 | AMM-SU-2367 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.863 | 35.9474 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R01 | Fiber ring
RO-08 | AMM-SU-2368 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.863 | 35.9543 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R01 | Fiber ring
RO-08 | AMM-SU-2369 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8612 | 35.9618 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R02 | Fiber ring
RO-08 | AMM-SU-2370 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8618 | 35.9679 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R02 | Fiber ring
RO-08 | AMM-SU-2371 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8618 | 35.9734 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R02 | Fiber ring
RO-08 | AMM-SU-2372 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.863 | 35.9816 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R03 | Fiber ring
RO-08 | AMM-SU-2380 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8669 | 35.8293 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R02 | Fiber ring
RO-08 | AMM-SU-2381 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8669 | 35.8362 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R02 | Fiber ring
RO-08 | AMM-SU-2382 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8681 | 35.8416 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R03 | Fiber ring
RO-08 | AMM-SU-2383 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8669 | 35.8484 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R03 | Fiber ring
RO-08 | AMM-SU-2384 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8669 | 35.8553 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R03 | Fiber ring
RO-08 | AMM-SU-2397 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8681 | 35.944 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R01 | Fiber ring
RO-08 | AMM-SU-2398 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8669 | 35.9522 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R01 | Fiber ring
RO-08 | AMM-SU-2399 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8669 | 35.959 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R01 | Fiber ring
RO-08 | AMM-SU-2400 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8669 | 35.9645 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R02 | Fiber ring
RO-08 | AMM-SU-2401 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8657 | 35.9713 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R03 | Fiber ring
RO-08 | AMM-SU-2402 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8681 | 35.9781 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R03 | Fiber ring
RO-08 | AMM-SU-2403 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8669 | 35.985 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R03 | Fiber ring
RO-08 | AMM-SU-2411 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.872 | 35.8177 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R01 | Fiber ring
RO-08 | AMM-SU-2412 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.872 | 35.8232 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R02 | Fiber ring
RO-08 | AMM-SU-2413 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.872 | 35.8327 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R02 | Fiber ring
RO-08 | AMM-SU-2414 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.872 | 35.8396 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R02 | Fiber ring
RO-08 | AMM-SU-2415 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8732 | 35.845 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R03 | Fiber ring
RO-08 | AMM-SU-2416 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.872 | 35.8532 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R04 | Fiber ring
RO-08 | AMM-SU-2417 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8726 | 35.858 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R01 | Fiber ring
RO-08 | AMM-SU-2418 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8732 | 35.8655 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R01 | Fiber ring
RO-08 | AMM-SU-2419 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.872 | 35.8723 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R02 | Fiber ring
RO-08 | AMM-SU-2420 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8726 | 35.8798 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R02 | Fiber ring
RO-08 | AMM-SU-2421 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8732 | 35.886 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R02 | Fiber ring
RO-08 | AMM-SU-2422 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.872 | 35.8942 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R02 | Fiber ring
RO-08 | AMM-SU-2429 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.872 | 35.942 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R01 | Fiber ring
RO-08 | AMM-SU-2430 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8732 | 35.9474 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R07 | Fiber ring
RO-08 | AMM-SU-2431 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8726 | 35.9536 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R07 | Fiber ring
RO-08 | AMM-SU-2432 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.872 | 35.9611 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R01 | Fiber ring
RO-08 | AMM-SU-2433 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8726 | 35.9672 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R01 | Fiber ring
RO-08 | AMM-SU-2434 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.872 | 35.9747 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R03 | Fiber ring
RO-08 | AMM-SU-2435 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8732 | 35.9816 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R04 | Fiber ring
RO-08 | AMM-SU-2436 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8732 | 35.9884 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R03 | Fiber ring
RO-08 | AMM-SU-2443 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8759 | 35.8143 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R01 | Fiber ring
RO-08 | AMM-SU-2444 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8765 | 35.8205 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R01 | Fiber ring
RO-08 | AMM-SU-2445 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8771 | 35.8293 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R01 | Fiber ring
RO-08 | AMM-SU-2446 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8771 | 35.8362 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R02 | Fiber ring
RO-08 | AMM-SU-2447 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8783 | 35.8416 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R03 | Fiber ring
RO-08 | AMM-SU-2448 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8783 | 35.8484 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R04 | Fiber ring
RO-08 | AMM-SU-2449 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8759 | 35.8553 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R04 | Fiber ring
RO-08 | AMM-SU-2450 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8759 | 35.8621 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R01 | Fiber ring
RO-08 | AMM-SU-2451 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8783 | 35.8689 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R01 | Fiber ring
RO-08 | AMM-SU-2452 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8771 | 35.8744 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R02 | Fiber ring
RO-08 | AMM-SU-2453 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8759 | 35.8826 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R02 | Fiber ring
RO-08 | AMM-SU-2454 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8783 | 35.8894 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R03 | Fiber ring
RO-08 | AMM-SU-2455 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8771 | 35.8949 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R03 | Fiber ring
RO-08 | AMM-SU-2462 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8759 | 35.944 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R07 | Fiber ring
RO-08 | AMM-SU-2463 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8777 | 35.9502 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R06 | Fiber ring
RO-08 | AMM-SU-2464 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8759 | 35.9577 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R06 | Fiber ring
RO-08 | AMM-SU-2465 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8771 | 35.9645 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R06 | Fiber ring
RO-08 | AMM-SU-2466 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8771 | 35.9727 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R05 | Fiber ring
RO-08 | AMM-SU-2467 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8771 | 35.9795 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R04 | Fiber ring
RO-08 | AMM-SU-2468 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8783 | 35.985 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R04 | Fiber ring
RO-08 | AMM-SU-2469 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8771 | 35.9918 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R04 | Fiber ring
RO-08 | AMM-SU-2476 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.881 | 35.8109 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R01 | Fiber ring
RO-08 | AMM-SU-2477 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.881 | 35.8177 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R01 | Fiber ring
RO-08 | AMM-SU-2478 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8822 | 35.8259 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R01 | Fiber ring
RO-08 | AMM-SU-2479 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8834 | 35.8314 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R07 | Fiber ring
RO-08 | AMM-SU-2480 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8834 | 35.8382 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R01 | Fiber ring
RO-08 | AMM-SU-2481 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8822 | 35.8464 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R04 | Fiber ring
RO-08 | AMM-SU-2482 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8816 | 35.8512 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R04 | Fiber ring
RO-08 | AMM-SU-2483 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8822 | 35.8587 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R01 | Fiber ring
RO-08 | AMM-SU-2484 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.881 | 35.8655 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R01 | Fiber ring
RO-08 | AMM-SU-2485 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8828 | 35.8717 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R01 | Fiber ring
RO-08 | AMM-SU-2486 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8816 | 35.8798 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R02 | Fiber ring
RO-08 | AMM-SU-2487 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8822 | 35.886 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R03 | Fiber ring
RO-08 | AMM-SU-2488 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8822 | 35.8914 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R03 | Fiber ring
RO-08 | AMM-SU-2497 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8822 | 35.9529 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R06 | Fiber ring
RO-08 | AMM-SU-2498 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8834 | 35.9611 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R06 | Fiber ring
RO-08 | AMM-SU-2499 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8834 | 35.9679 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R06 | Fiber ring
RO-08 | AMM-SU-2500 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8822 | 35.9761 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R05 | Fiber ring
RO-08 | AMM-SU-2501 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8822 | 35.9816 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R05 | Fiber ring
RO-08 | AMM-SU-2502 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8828 | 35.9877 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R04 | Fiber ring
RO-08 | AMM-SU-2503 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8822 | 35.9938 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R04 | Fiber ring
RO-08 | AMM-SU-2510 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8884 | 35.8143 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R07 | Fiber ring
RO-08 | AMM-SU-2511 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8873 | 35.8225 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R07 | Fiber ring
RO-08 | AMM-SU-2512 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8884 | 35.828 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R07 | Fiber ring
RO-08 | AMM-SU-2513 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8873 | 35.8362 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R06 | Fiber ring
RO-08 | AMM-SU-2514 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8879 | 35.8409 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R05 | Fiber ring
RO-08 | AMM-SU-2515 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8867 | 35.8491 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R04 | Fiber ring
RO-08 | AMM-SU-2516 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8873 | 35.8553 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R04 | Fiber ring
RO-08 | AMM-SU-2517 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8873 | 35.8621 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R05 | Fiber ring
RO-08 | AMM-SU-2518 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8873 | 35.8689 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R05 | Fiber ring
RO-08 | AMM-SU-2519 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8861 | 35.8757 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R01 | Fiber ring
RO-08 | AMM-SU-2520 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8884 | 35.8826 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R03 | Fiber ring
RO-08 | AMM-SU-2521 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8879 | 35.8901 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R03 | Fiber ring
RO-08 | AMM-SU-2522 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8884 | 35.8962 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R03 | Fiber ring
RO-08 | AMM-SU-2530 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8879 | 35.9638 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R06 | Fiber ring
RO-08 | AMM-SU-2531 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8873 | 35.9713 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R05 | Fiber ring
RO-08 | AMM-SU-2532 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8873 | 35.9781 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R05 | Fiber ring
RO-08 | AMM-SU-2533 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8873 | 35.985 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R05 | Fiber ring
RO-08 | AMM-SU-2534 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8873 | 35.9918 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R04 | Fiber ring
RO-08 | AMM-SU-2543 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8924 | 35.8191 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R07 | Fiber ring
RO-08 | AMM-SU-2544 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8924 | 35.8259 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R06 | Fiber ring
RO-08 | AMM-SU-2545 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8924 | 35.8327 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R06 | Fiber ring
RO-08 | AMM-SU-2546 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8924 | 35.8368 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R05 | Fiber ring
RO-08 | AMM-SU-2547 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8924 | 35.8437 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R05 | Fiber ring
RO-08 | AMM-SU-2548 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8918 | 35.8525 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R05 | Fiber ring
RO-08 | AMM-SU-2549 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8924 | 35.8587 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R05 | Fiber ring
RO-08 | AMM-SU-2550 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8924 | 35.8641 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R05 | Fiber ring
RO-08 | AMM-SU-2551 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8924 | 35.8723 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R04 | Fiber ring
RO-08 | AMM-SU-2552 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8918 | 35.8798 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R04 | Fiber ring
RO-08 | AMM-SU-2553 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8935 | 35.886 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R04 | Fiber ring
RO-08 | AMM-SU-2556 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8924 | 35.9747 | 32 | 3 | HUB-AMM-73 | HUB-AMM-73-R05 | Fiber ring
RO-08 | AMM-SU-2570 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8986 | 35.8211 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R06 | Fiber ring
RO-08 | AMM-SU-2571 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8974 | 35.8293 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R06 | Fiber ring
RO-08 | AMM-SU-2572 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8974 | 35.8362 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R05 | Fiber ring
RO-08 | AMM-SU-2573 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8974 | 35.843 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R05 | Fiber ring
RO-08 | AMM-SU-2574 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.898 | 35.8478 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R05 | Fiber ring
RO-08 | AMM-SU-2578 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.898 | 35.8751 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R04 | Fiber ring
RO-08 | AMM-SU-2579 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.898 | 35.8833 | 32 | 3 | HUB-AMM-20 | HUB-AMM-20-R04 | Fiber ring
RO-08 | AMM-SU-2597 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9025 | 35.8259 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R06 | Fiber ring
RO-08 | AMM-SU-2598 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9031 | 35.8321 | 32 | 3 | HUB-AMM-37 | HUB-AMM-37-R06 | Fiber ring
RO-08 | AMM-SU-2786 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9585 | 36.0314 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R01 | Fiber ring
RO-08 | AMM-SU-2787 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9591 | 36.0403 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R02 | Fiber ring
RO-08 | AMM-SU-2788 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9585 | 36.0478 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R02 | Fiber ring
RO-08 | AMM-SU-2789 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9585 | 36.0519 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R02 | Fiber ring
RO-08 | AMM-SU-2797 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9648 | 36.0293 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R01 | Fiber ring
RO-08 | AMM-SU-2798 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9636 | 36.0375 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R01 | Fiber ring
RO-08 | AMM-SU-2799 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9636 | 36.0444 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R02 | Fiber ring
RO-08 | AMM-SU-2807 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9699 | 36.0328 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R01 | Fiber ring
RO-08 | AMM-SU-2808 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9699 | 36.0396 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R01 | Fiber ring
RO-08 | AMM-SU-2809 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9681 | 36.0471 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R02 | Fiber ring
RO-08 | AMM-SU-2810 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9687 | 36.0519 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R02 | Fiber ring
RO-08 | AMM-SU-2811 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9699 | 36.0601 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R02 | Fiber ring
RO-08 | AMM-SU-2819 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9738 | 36.0362 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R05 | Fiber ring
RO-08 | AMM-SU-2820 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9738 | 36.0416 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R01 | Fiber ring
RO-08 | AMM-SU-2821 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9738 | 36.0512 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R03 | Fiber ring
RO-08 | AMM-SU-2822 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9738 | 36.058 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R03 | Fiber ring
RO-08 | AMM-SU-2831 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9795 | 36.0334 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R05 | Fiber ring
RO-08 | AMM-SU-2832 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9789 | 36.0396 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R04 | Fiber ring
RO-08 | AMM-SU-2833 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9795 | 36.0457 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R04 | Fiber ring
RO-08 | AMM-SU-2834 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9777 | 36.0532 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R03 | Fiber ring
RO-08 | AMM-SU-2842 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.984 | 36.028 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R05 | Fiber ring
RO-08 | AMM-SU-2843 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.984 | 36.0375 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R04 | Fiber ring
RO-08 | AMM-SU-2844 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.984 | 36.0416 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R04 | Fiber ring
RO-08 | AMM-SU-2845 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.984 | 36.0512 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R03 | Fiber ring
RO-08 | AMM-SU-2846 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9852 | 36.0566 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R03 | Fiber ring
RO-08 | AMM-SU-2855 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 31.9891 | 36.0341 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R04 | Fiber ring
RO-08 | AMM-SU-2856 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9879 | 36.0396 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R04 | Fiber ring
RO-08 | AMM-SU-2857 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9897 | 36.0471 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R04 | Fiber ring
RO-08 | AMM-SU-2858 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.9879 | 36.0532 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R03 | Fiber ring
RO-08 | AMM-SU-2859 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9879 | 36.0601 | 32 | 3 | HUB-AMM-50 | HUB-AMM-50-R03 | Fiber ring
RO-08 | AMM-SU-2932 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0145 | 35.9884 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R01 | Fiber ring
RO-08 | AMM-SU-2933 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.014 | 35.9945 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R01 | Fiber ring
RO-08 | AMM-SU-2934 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0134 | 36.002 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R01 | Fiber ring
RO-08 | AMM-SU-2935 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.014 | 36.0095 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R02 | Fiber ring
RO-08 | AMM-SU-2956 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0202 | 35.9925 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R01 | Fiber ring
RO-08 | AMM-SU-2957 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0208 | 35.9986 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R01 | Fiber ring
RO-08 | AMM-SU-2958 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0202 | 36.0048 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R02 | Fiber ring
RO-08 | AMM-SU-2982 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0247 | 35.9898 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R01 | Fiber ring
RO-08 | AMM-SU-2983 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0235 | 35.9952 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R01 | Fiber ring
RO-08 | AMM-SU-2984 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0235 | 36.002 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R02 | Fiber ring
RO-08 | AMM-SU-2985 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0235 | 36.0089 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R02 | Fiber ring
RO-08 | AMM-SU-3009 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0298 | 35.985 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R05 | Fiber ring
RO-08 | AMM-SU-3010 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0298 | 35.9904 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R05 | Fiber ring
RO-08 | AMM-SU-3011 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0286 | 35.9986 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R01 | Fiber ring
RO-08 | AMM-SU-3012 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.031 | 36.0055 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R03 | Fiber ring
RO-08 | AMM-SU-3013 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0298 | 36.0136 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R03 | Fiber ring
RO-08 | AMM-SU-3033 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0361 | 35.9816 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R05 | Fiber ring
RO-08 | AMM-SU-3034 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0355 | 35.9891 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R05 | Fiber ring
RO-08 | AMM-SU-3035 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0361 | 35.9952 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R04 | Fiber ring
RO-08 | AMM-SU-3036 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0355 | 36.0014 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R04 | Fiber ring
RO-08 | AMM-SU-3037 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0349 | 36.0102 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R03 | Fiber ring
RO-08 | AMM-SU-3038 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0349 | 36.0143 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R03 | Fiber ring
RO-08 | AMM-SU-3041 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0361 | 36.1386 | 32 | 3 | HUB-AMM-84 | HUB-AMM-84-R02 | Fiber ring
RO-08 | AMM-SU-3042 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0337 | 36.1454 | 32 | 3 | HUB-AMM-84 | HUB-AMM-84-R02 | Fiber ring
RO-08 | AMM-SU-3060 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0412 | 35.985 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R05 | Fiber ring
RO-08 | AMM-SU-3061 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0406 | 35.9911 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R05 | Fiber ring
RO-08 | AMM-SU-3062 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.04 | 36 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R04 | Fiber ring
RO-08 | AMM-SU-3063 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.04 | 36.0041 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R04 | Fiber ring
RO-08 | AMM-SU-3064 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0388 | 36.0123 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R03 | Fiber ring
RO-08 | AMM-SU-3067 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.04 | 36.127 | 32 | 3 | HUB-AMM-84 | HUB-AMM-84-R02 | Fiber ring
RO-08 | AMM-SU-3068 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0388 | 36.1352 | 32 | 3 | HUB-AMM-84 | HUB-AMM-84-R02 | Fiber ring
RO-08 | AMM-SU-3069 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0388 | 36.142 | 32 | 3 | HUB-AMM-84 | HUB-AMM-84-R03 | Fiber ring
RO-08 | AMM-SU-3090 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0463 | 35.9884 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R04 | Fiber ring
RO-08 | AMM-SU-3091 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0451 | 35.9938 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R04 | Fiber ring
RO-08 | AMM-SU-3092 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0445 | 36.0027 | 32 | 3 | HUB-AMM-21 | HUB-AMM-21-R04 | Fiber ring
RO-08 | AMM-SU-3100 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0451 | 36.1304 | 32 | 3 | HUB-AMM-84 | HUB-AMM-84-R02 | Fiber ring
RO-08 | AMM-SU-3101 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0451 | 36.1386 | 32 | 3 | HUB-AMM-84 | HUB-AMM-84-R03 | Fiber ring
RO-08 | AMM-SU-3102 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0451 | 36.1467 | 32 | 3 | HUB-AMM-84 | HUB-AMM-84-R03 | Fiber ring
RO-08 | AMM-SU-3116 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0513 | 35.8689 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R01 | Fiber ring
RO-08 | AMM-SU-3139 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0496 | 36.1345 | 32 | 3 | HUB-AMM-84 | HUB-AMM-84-R01 | Fiber ring
RO-08 | AMM-SU-3140 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.049 | 36.142 | 32 | 3 | HUB-AMM-84 | HUB-AMM-84-R03 | Fiber ring
RO-08 | AMM-SU-3141 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.049 | 36.1488 | 32 | 3 | HUB-AMM-84 | HUB-AMM-84-R03 | Fiber ring
RO-08 | AMM-SU-3153 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0553 | 35.8601 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R01 | Fiber ring
RO-08 | AMM-SU-3154 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0553 | 35.8669 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R01 | Fiber ring
RO-08 | AMM-SU-3155 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0541 | 35.8723 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R01 | Fiber ring
RO-08 | AMM-SU-3156 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0541 | 35.8792 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R02 | Fiber ring
RO-08 | AMM-SU-3157 | SU | Rooftop | Amman-Zarqa Metro | Amman | 32.0541 | 35.886 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R02 | Fiber ring
RO-08 | AMM-SU-3178 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0553 | 36.1331 | 32 | 3 | HUB-AMM-84 | HUB-AMM-84-R04 | Fiber ring
RO-08 | AMM-SU-3179 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0553 | 36.1372 | 32 | 3 | HUB-AMM-84 | HUB-AMM-84-R04 | Fiber ring
RO-08 | AMM-SU-3180 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0553 | 36.1454 | 32 | 3 | HUB-AMM-84 | HUB-AMM-84-R04 | Fiber ring
RO-08 | AMM-SU-3181 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0564 | 36.1522 | 32 | 3 | HUB-AMM-84 | HUB-AMM-84-R03 | Fiber ring
RO-08 | AMM-SU-3192 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0592 | 35.8553 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R01 | Fiber ring
RO-08 | AMM-SU-3193 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0603 | 35.8635 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R04 | Fiber ring
RO-08 | AMM-SU-3194 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0603 | 35.8703 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R04 | Fiber ring
RO-08 | AMM-SU-3195 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0603 | 35.8744 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R01 | Fiber ring
RO-08 | AMM-SU-3196 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0598 | 35.8819 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R02 | Fiber ring
RO-08 | AMM-SU-3197 | SU | Rooftop | Amman-Zarqa Metro | Amman | 32.0592 | 35.8894 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R02 | Fiber ring
RO-08 | AMM-SU-3215 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0603 | 36.0396 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R01 | Fiber ring
RO-08 | AMM-SU-3216 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0592 | 36.0464 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R02 | Fiber ring
RO-08 | AMM-SU-3217 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0603 | 36.1352 | 32 | 3 | HUB-AMM-84 | HUB-AMM-84-R04 | Fiber ring
RO-08 | AMM-SU-3218 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0603 | 36.1433 | 32 | 3 | HUB-AMM-84 | HUB-AMM-84-R04 | Fiber ring
RO-08 | AMM-SU-3219 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0609 | 36.1495 | 32 | 3 | HUB-AMM-84 | HUB-AMM-84-R04 | Fiber ring
RO-08 | AMM-SU-3227 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0654 | 35.8601 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R04 | Fiber ring
RO-08 | AMM-SU-3228 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0643 | 35.8655 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R04 | Fiber ring
RO-08 | AMM-SU-3229 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0643 | 35.8723 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R03 | Fiber ring
RO-08 | AMM-SU-3230 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0654 | 35.8792 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R02 | Fiber ring
RO-08 | AMM-SU-3231 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0654 | 35.8846 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R02 | Fiber ring
RO-08 | AMM-SU-3232 | SU | Rooftop | Amman-Zarqa Metro | Amman | 32.0643 | 35.8928 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R02 | Fiber ring
RO-08 | AMM-SU-3247 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0643 | 36.0362 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R01 | Fiber ring
RO-08 | AMM-SU-3248 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0666 | 36.043 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R01 | Fiber ring
RO-08 | AMM-SU-3256 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0694 | 35.8621 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R03 | Fiber ring
RO-08 | AMM-SU-3257 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0694 | 35.8689 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R03 | Fiber ring
RO-08 | AMM-SU-3258 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0705 | 35.8771 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R03 | Fiber ring
RO-08 | AMM-SU-3259 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0705 | 35.8812 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R03 | Fiber ring
RO-08 | AMM-SU-3274 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0711 | 36.0266 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R01 | Fiber ring
RO-08 | AMM-SU-3275 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0705 | 36.0314 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R01 | Fiber ring
RO-08 | AMM-SU-3276 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0705 | 36.0382 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R01 | Fiber ring
RO-08 | AMM-SU-3277 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0705 | 36.045 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R02 | Fiber ring
RO-08 | AMM-SU-3286 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0756 | 35.8669 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R03 | Fiber ring
RO-08 | AMM-SU-3287 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0744 | 35.8723 | 32 | 3 | HUB-AMM-74 | HUB-AMM-74-R03 | Fiber ring
RO-08 | AMM-SU-3301 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0744 | 36.0225 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R01 | Fiber ring
RO-08 | AMM-SU-3302 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0756 | 36.028 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R05 | Fiber ring
RO-08 | AMM-SU-3303 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0768 | 36.0362 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R05 | Fiber ring
RO-08 | AMM-SU-3304 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0756 | 36.0416 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R01 | Fiber ring
RO-08 | AMM-SU-3327 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0813 | 36.0184 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R05 | Fiber ring
RO-08 | AMM-SU-3328 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0813 | 36.0252 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R05 | Fiber ring
RO-08 | AMM-SU-3329 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0807 | 36.0314 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R05 | Fiber ring
RO-08 | AMM-SU-3330 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0807 | 36.0382 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R04 | Fiber ring
RO-08 | AMM-SU-3331 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0801 | 36.0457 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R03 | Fiber ring
RO-08 | AMM-SU-3351 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0858 | 36.0239 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R05 | Fiber ring
RO-08 | AMM-SU-3352 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0858 | 36.0307 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R05 | Fiber ring
RO-08 | AMM-SU-3353 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.087 | 36.0362 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R04 | Fiber ring
RO-08 | AMM-SU-3354 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0864 | 36.0423 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R04 | Fiber ring
RO-08 | AMM-SU-3372 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0915 | 36.0252 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R04 | Fiber ring
RO-08 | AMM-SU-3373 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0921 | 36.0328 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R04 | Fiber ring
RO-08 | AMM-SU-3374 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0921 | 36.0396 | 32 | 3 | HUB-AMM-58 | HUB-AMM-58-R04 | Fiber ring
RO-08 | AMM-U-0430 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8943 | 35.8942 | 30 | 3 | HUB-AMM-20 | HUB-AMM-20-R04 | Fiber ring
RO-08 | AMM-U-0443 | U | Rooftop | Amman-Zarqa Metro | Amman | 31.8974 | 35.8876 | 30 | 3 | HUB-AMM-20 | HUB-AMM-20-R04 | Fiber ring
RO-08 | AMM-U-0981 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9683 | 36.0261 | 30 | 3 | HUB-AMM-50 | HUB-AMM-50-R01 | Fiber ring
RO-08 | AMM-U-1008 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9723 | 36.027 | 30 | 3 | HUB-AMM-50 | HUB-AMM-50-R01 | Fiber ring
RO-08 | AMM-U-1033 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.975 | 36.0256 | 30 | 3 | HUB-AMM-50 | HUB-AMM-50-R05 | Fiber ring
RO-08 | AMM-U-1061 | U | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9789 | 36.0237 | 30 | 3 | HUB-AMM-50 | HUB-AMM-50-R05 | Fiber ring
RO-08 | AMM-U-1480 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0137 | 36.0129 | 30 | 3 | HUB-AMM-21 | HUB-AMM-21-R02 | Fiber ring
RO-08 | AMM-U-1523 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0169 | 36.0157 | 30 | 3 | HUB-AMM-21 | HUB-AMM-21-R02 | Fiber ring
RO-08 | AMM-U-1566 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0212 | 36.0124 | 30 | 3 | HUB-AMM-21 | HUB-AMM-21-R02 | Fiber ring
RO-08 | AMM-U-1567 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0212 | 36.0171 | 30 | 3 | HUB-AMM-21 | HUB-AMM-21-R03 | Fiber ring
RO-08 | AMM-U-1607 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0255 | 36.0157 | 30 | 3 | HUB-AMM-21 | HUB-AMM-21-R03 | Fiber ring
RO-08 | AMM-U-1814 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0423 | 36.1173 | 30 | 3 | HUB-AMM-84 | HUB-AMM-84-R01 | Fiber ring
RO-08 | AMM-U-1815 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0415 | 36.122 | 30 | 3 | HUB-AMM-84 | HUB-AMM-84-R02 | Fiber ring
RO-08 | AMM-U-1840 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0451 | 36.1197 | 30 | 3 | HUB-AMM-84 | HUB-AMM-84-R01 | Fiber ring
RO-08 | AMM-U-1841 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0459 | 36.1234 | 30 | 3 | HUB-AMM-84 | HUB-AMM-84-R01 | Fiber ring
RO-08 | AMM-U-1842 | U | Rooftop | Amman-Zarqa Metro | Balqa | 32.0494 | 35.8753 | 30 | 3 | HUB-AMM-74 | HUB-AMM-74-R01 | Fiber ring
RO-08 | AMM-U-1843 | U | Rooftop | Amman-Zarqa Metro | Amman | 32.0494 | 35.88 | 30 | 3 | HUB-AMM-74 | HUB-AMM-74-R01 | Fiber ring
RO-08 | AMM-U-1857 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0494 | 36.1173 | 30 | 3 | HUB-AMM-84 | HUB-AMM-84-R01 | Fiber ring
RO-08 | AMM-U-1858 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0494 | 36.1211 | 30 | 3 | HUB-AMM-84 | HUB-AMM-84-R01 | Fiber ring
RO-08 | AMM-U-1859 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0494 | 36.1268 | 30 | 3 | HUB-AMM-84 | HUB-AMM-84-R01 | Fiber ring
RO-08 | AMM-U-1874 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0529 | 36.1206 | 30 | 3 | HUB-AMM-84 | HUB-AMM-84-R05 | Fiber ring
RO-08 | AMM-U-1875 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0529 | 36.1234 | 30 | 3 | HUB-AMM-84 | HUB-AMM-84-R05 | Fiber ring
RO-08 | AMM-U-1891 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0564 | 36.122 | 30 | 3 | HUB-AMM-84 | HUB-AMM-84-R05 | Fiber ring
RO-08 | AMM-U-1892 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0564 | 36.1258 | 30 | 3 | HUB-AMM-84 | HUB-AMM-84-R05 | Fiber ring
RO-08 | AMM-U-1909 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.06 | 36.1301 | 30 | 3 | HUB-AMM-84 | HUB-AMM-84-R05 | Fiber ring
RO-08 | AMM-U-1910 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0635 | 36.0511 | 30 | 3 | HUB-AMM-58 | HUB-AMM-58-R02 | Fiber ring
RO-08 | AMM-U-1932 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.067 | 36.0497 | 30 | 3 | HUB-AMM-58 | HUB-AMM-58-R02 | Fiber ring
RO-08 | AMM-U-1933 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.067 | 36.0525 | 30 | 3 | HUB-AMM-58 | HUB-AMM-58-R02 | Fiber ring
RO-08 | AMM-U-1955 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0701 | 36.0516 | 30 | 3 | HUB-AMM-58 | HUB-AMM-58-R02 | Fiber ring
RO-08 | AMM-U-1979 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0741 | 36.0478 | 30 | 3 | HUB-AMM-58 | HUB-AMM-58-R02 | Fiber ring
RO-08 | AMM-U-1980 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0741 | 36.0525 | 30 | 3 | HUB-AMM-58 | HUB-AMM-58-R03 | Fiber ring
RO-08 | AMM-U-2004 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0768 | 36.0511 | 30 | 3 | HUB-AMM-58 | HUB-AMM-58-R03 | Fiber ring
RO-08 | AMM-U-2005 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0768 | 36.0559 | 30 | 3 | HUB-AMM-58 | HUB-AMM-58-R03 | Fiber ring
RO-08 | AMM-U-2027 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0807 | 36.053 | 30 | 3 | HUB-AMM-58 | HUB-AMM-58-R03 | Fiber ring
RO-08 | AMM-U-2049 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0855 | 36.0511 | 30 | 3 | HUB-AMM-58 | HUB-AMM-58-R03 | Fiber ring
RO-08 | AMM-U-2050 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0846 | 36.0549 | 30 | 3 | HUB-AMM-58 | HUB-AMM-58-R03 | Fiber ring
RO-08 | AMM-U-2070 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0882 | 36.0525 | 30 | 3 | HUB-AMM-58 | HUB-AMM-58-R04 | Fiber ring
RO-08 | AQB-SU-0184 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4284 | 34.9863 | 32 | 3 | HUB-AQB-04 | HUB-AQB-04-R01 | Fiber ring
RO-08 | AQB-SU-0185 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4335 | 34.9829 | 32 | 3 | HUB-AQB-04 | HUB-AQB-04-R01 | Fiber ring
RO-08 | AQB-SU-0186 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4335 | 34.9897 | 32 | 3 | HUB-AQB-04 | HUB-AQB-04-R02 | Fiber ring
RO-08 | AQB-SU-0187 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4386 | 34.9863 | 32 | 3 | HUB-AQB-04 | HUB-AQB-04-R01 | Fiber ring
RO-08 | AQB-SU-0188 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4437 | 34.9897 | 32 | 3 | HUB-AQB-04 | HUB-AQB-04-R01 | Fiber ring
RO-08 | AQB-SU-0189 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4487 | 34.9863 | 32 | 3 | HUB-AQB-04 | HUB-AQB-04-R01 | Fiber ring
RO-08 | AQB-SU-0190 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4476 | 34.9917 | 32 | 3 | HUB-AQB-04 | HUB-AQB-04-R01 | Fiber ring
RO-08 | AQB-SU-0191 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4538 | 34.9897 | 32 | 3 | HUB-AQB-04 | HUB-AQB-04-R03 | Fiber ring
RO-08 | AQB-SU-0192 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4533 | 34.9958 | 32 | 3 | HUB-AQB-04 | HUB-AQB-04-R01 | Fiber ring
RO-08 | AQB-SU-0193 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4601 | 34.9917 | 32 | 3 | HUB-AQB-04 | HUB-AQB-04-R03 | Fiber ring
RO-08 | AQB-SU-0194 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4589 | 34.9999 | 32 | 3 | HUB-AQB-04 | HUB-AQB-04-R02 | Fiber ring
RO-08 | AQB-SU-0195 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4589 | 35.0067 | 32 | 3 | HUB-AQB-04 | HUB-AQB-04-R02 | Fiber ring
RO-08 | AQB-SU-0196 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4634 | 34.9876 | 32 | 3 | HUB-AQB-04 | HUB-AQB-04-R03 | Fiber ring
RO-08 | AQB-SU-0197 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.464 | 35.002 | 32 | 3 | HUB-AQB-04 | HUB-AQB-04-R03 | Fiber ring
RO-08 | AQB-SU-0198 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4679 | 35.0054 | 32 | 3 | HUB-AQB-04 | HUB-AQB-04-R02 | Fiber ring
RO-08 | AQB-SU-0199 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4742 | 35.0033 | 32 | 3 | HUB-AQB-04 | HUB-AQB-04-R03 | Fiber ring
RO-08 | AQB-SU-0200 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4736 | 35.0095 | 32 | 3 | HUB-AQB-04 | HUB-AQB-04-R02 | Fiber ring
RO-08 | AQB-SU-0201 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4781 | 35.0122 | 32 | 3 | HUB-AQB-04 | HUB-AQB-04-R02 | Fiber ring
RO-08 | HWY-HW-0073 | HW | Lattice tower | Highway | Karak | 31.23 | 35.9547 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-08 | HWY-HW-0074 | HW | Lattice tower | Highway | Tafilah | 30.7158 | 35.8166 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-08 | HWY-HW-0075 | HW | Lattice tower | Highway | Amman | 31.7883 | 36.1833 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-08 | HWY-HW-0076 | HW | Lattice tower | Highway | Amman | 31.7757 | 36.2545 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-08 | HWY-HW-0077 | HW | Lattice tower | Highway | Amman | 31.7599 | 36.3256 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-08 | HWY-HW-0078 | HW | Lattice tower | Highway | Amman | 31.744 | 36.3968 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-08 | HWY-HW-0079 | HW | Lattice tower | Highway | Amman | 31.733 | 36.4675 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-08 | HWY-HW-0080 | HW | Lattice tower | Highway | Amman | 31.7632 | 36.534 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-08 | HWY-HW-0081 | HW | Lattice tower | Highway | Zarqa | 31.7885 | 36.5987 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-08 | HWY-HW-0082 | HW | Lattice tower | Highway | Zarqa | 31.8139 | 36.667 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-08 | HWY-HW-0083 | HW | Lattice tower | Highway | Zarqa | 31.8425 | 36.7317 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-08 | IRB-SU-0497 | SU | Rooftop | Irbid | Irbid | 32.4823 | 35.8785 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R01 | Fiber ring
RO-08 | IRB-SU-0506 | SU | Rooftop | Irbid | Irbid | 32.488 | 35.8812 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R01 | Fiber ring
RO-08 | IRB-SU-0507 | SU | Monopole / greenfield | Irbid | Irbid | 32.488 | 35.8894 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R01 | Fiber ring
RO-08 | IRB-SU-0508 | SU | Monopole / greenfield | Irbid | Irbid | 32.4868 | 35.8962 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R01 | Fiber ring
RO-08 | IRB-SU-0519 | SU | Monopole / greenfield | Irbid | Irbid | 32.4919 | 35.8792 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R01 | Fiber ring
RO-08 | IRB-SU-0520 | SU | Monopole / greenfield | Irbid | Irbid | 32.4931 | 35.886 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R01 | Fiber ring
RO-08 | IRB-SU-0521 | SU | Monopole / greenfield | Irbid | Irbid | 32.4931 | 35.8928 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R01 | Fiber ring
RO-08 | IRB-SU-0522 | SU | Monopole / greenfield | Irbid | Irbid | 32.4919 | 35.8996 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R02 | Fiber ring
RO-08 | IRB-SU-0523 | SU | Monopole / greenfield | Irbid | Irbid | 32.4931 | 35.9051 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R02 | Fiber ring
RO-08 | IRB-SU-0534 | SU | Monopole / greenfield | Irbid | Irbid | 32.4982 | 35.8744 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R04 | Fiber ring
RO-08 | IRB-SU-0535 | SU | Monopole / greenfield | Irbid | Irbid | 32.4982 | 35.8826 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R04 | Fiber ring
RO-08 | IRB-SU-0536 | SU | Rooftop | Irbid | Irbid | 32.4982 | 35.8894 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R01 | Fiber ring
RO-08 | IRB-SU-0537 | SU | Monopole / greenfield | Irbid | Irbid | 32.4982 | 35.8949 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R02 | Fiber ring
RO-08 | IRB-SU-0538 | SU | Monopole / greenfield | Irbid | Irbid | 32.4976 | 35.9024 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R02 | Fiber ring
RO-08 | IRB-SU-0539 | SU | Monopole / greenfield | Irbid | Irbid | 32.4982 | 35.9099 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R02 | Fiber ring
RO-08 | IRB-SU-0553 | SU | Monopole / greenfield | Irbid | Irbid | 32.5033 | 35.8778 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R04 | Fiber ring
RO-08 | IRB-SU-0554 | SU | Rooftop | Irbid | Irbid | 32.5033 | 35.886 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R03 | Fiber ring
RO-08 | IRB-SU-0555 | SU | Rooftop | Irbid | Irbid | 32.5044 | 35.8928 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R03 | Fiber ring
RO-08 | IRB-SU-0556 | SU | Monopole / greenfield | Irbid | Irbid | 32.5021 | 35.8996 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R02 | Fiber ring
RO-08 | IRB-SU-0557 | SU | Monopole / greenfield | Irbid | Irbid | 32.5033 | 35.9065 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R02 | Fiber ring
RO-08 | IRB-SU-0566 | SU | Monopole / greenfield | Irbid | Irbid | 32.5084 | 35.8826 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R04 | Fiber ring
RO-08 | IRB-SU-0567 | SU | Monopole / greenfield | Irbid | Irbid | 32.5084 | 35.8894 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R03 | Fiber ring
RO-08 | IRB-SU-0568 | SU | Rooftop | Irbid | Irbid | 32.5084 | 35.8962 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R03 | Fiber ring
RO-08 | IRB-SU-0569 | SU | Monopole / greenfield | Irbid | Irbid | 32.5084 | 35.9017 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R03 | Fiber ring
RO-08 | IRB-SU-0579 | SU | Monopole / greenfield | Irbid | Irbid | 32.5134 | 35.8914 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R03 | Fiber ring
RO-08 | IRB-SU-0580 | SU | Monopole / greenfield | Irbid | Irbid | 32.5134 | 35.8983 | 32 | 3 | HUB-IRB-12 | HUB-IRB-12-R03 | Fiber ring
RO-08 | IRB-U-0075 | U | Monopole / greenfield | Irbid | Irbid | 32.5111 | 35.8786 | 30 | 3 | HUB-IRB-12 | HUB-IRB-12-R04 | Fiber ring
RO-08 | KAR-SU-0074 | SU | Monopole / greenfield | Karak | Karak | 31.165 | 35.7249 | 32 | 3 | HUB-KAR-01 | HUB-KAR-01-R02 | Fiber ring
RO-08 | KAR-SU-0075 | SU | Monopole / greenfield | Karak | Karak | 31.1644 | 35.731 | 32 | 3 | HUB-KAR-01 | HUB-KAR-01-R02 | Fiber ring
RO-08 | KAR-SU-0077 | SU | Monopole / greenfield | Karak | Karak | 31.1683 | 35.7221 | 32 | 3 | HUB-KAR-01 | HUB-KAR-01-R02 | Fiber ring
RO-08 | KAR-SU-0078 | SU | Rooftop | Karak | Karak | 31.1695 | 35.729 | 32 | 3 | HUB-KAR-01 | HUB-KAR-01-R02 | Fiber ring
RO-08 | KAR-SU-0079 | SU | Monopole / greenfield | Karak | Karak | 31.1706 | 35.7358 | 32 | 3 | HUB-KAR-01 | HUB-KAR-01-R02 | Fiber ring
RO-08 | KAR-SU-0080 | SU | Monopole / greenfield | Karak | Karak | 31.1745 | 35.7256 | 32 | 3 | HUB-KAR-01 | HUB-KAR-01-R02 | Fiber ring
RO-08 | KAR-SU-0081 | SU | Monopole / greenfield | Karak | Karak | 31.1745 | 35.7338 | 32 | 3 | HUB-KAR-01 | HUB-KAR-01-R03 | Fiber ring
RO-08 | KAR-SU-0083 | SU | Monopole / greenfield | Karak | Karak | 31.1796 | 35.7304 | 32 | 3 | HUB-KAR-01 | HUB-KAR-01-R03 | Fiber ring
RO-08 | KAR-SU-0084 | SU | Monopole / greenfield | Karak | Karak | 31.1796 | 35.7358 | 32 | 3 | HUB-KAR-01 | HUB-KAR-01-R03 | Fiber ring
RO-08 | KAR-SU-0087 | SU | Monopole / greenfield | Karak | Karak | 31.1836 | 35.7324 | 32 | 3 | HUB-KAR-01 | HUB-KAR-01-R03 | Fiber ring
RO-08 | KAR-SU-0091 | SU | Monopole / greenfield | Karak | Karak | 31.1904 | 35.7297 | 32 | 3 | HUB-KAR-01 | HUB-KAR-01-R03 | Fiber ring
RO-08 | KAR-SU-0092 | SU | Monopole / greenfield | Karak | Karak | 31.1898 | 35.7358 | 32 | 3 | HUB-KAR-01 | HUB-KAR-01-R03 | Fiber ring
RO-08 | KAR-SU-0095 | SU | Monopole / greenfield | Karak | Karak | 31.1955 | 35.7256 | 32 | 3 | HUB-KAR-01 | HUB-KAR-01-R04 | Fiber ring
RO-08 | KAR-SU-0096 | SU | Monopole / greenfield | Karak | Karak | 31.1949 | 35.7324 | 32 | 3 | HUB-KAR-01 | HUB-KAR-01-R04 | Fiber ring
RO-08 | KAR-SU-0101 | SU | Monopole / greenfield | Karak | Karak | 31.2012 | 35.7153 | 32 | 3 | HUB-KAR-01 | HUB-KAR-01-R04 | Fiber ring
RO-08 | KAR-SU-0102 | SU | Monopole / greenfield | Karak | Karak | 31.2006 | 35.7228 | 32 | 3 | HUB-KAR-01 | HUB-KAR-01-R04 | Fiber ring
RO-08 | KAR-SU-0103 | SU | Monopole / greenfield | Karak | Karak | 31.1988 | 35.729 | 32 | 3 | HUB-KAR-01 | HUB-KAR-01-R04 | Fiber ring
RO-08 | KAR-SU-0107 | SU | Monopole / greenfield | Karak | Karak | 31.2039 | 35.7187 | 32 | 3 | HUB-KAR-01 | HUB-KAR-01-R04 | Fiber ring
RO-08 | KAR-U-0017 | U | Monopole / greenfield | Karak | Karak | 31.171 | 35.718 | 30 | 3 | HUB-KAR-01 | HUB-KAR-01-R01 | Fiber ring
RO-08 | KAR-U-0024 | U | Monopole / greenfield | Karak | Karak | 31.1749 | 35.7151 | 30 | 3 | HUB-KAR-01 | HUB-KAR-01-R01 | Fiber ring
RO-08 | KAR-U-0025 | U | Monopole / greenfield | Karak | Karak | 31.1761 | 35.7203 | 30 | 3 | HUB-KAR-01 | HUB-KAR-01-R01 | Fiber ring
RO-08 | KAR-U-0031 | U | Rooftop | Karak | Karak | 31.178 | 35.7132 | 30 | 3 | HUB-KAR-01 | HUB-KAR-01-R01 | Fiber ring
RO-08 | KAR-U-0032 | U | Rooftop | Karak | Karak | 31.1789 | 35.717 | 30 | 3 | HUB-KAR-01 | HUB-KAR-01-R01 | Fiber ring
RO-08 | KAR-U-0033 | U | Monopole / greenfield | Karak | Karak | 31.1797 | 35.7227 | 30 | 3 | HUB-KAR-01 | HUB-KAR-01-R02 | Fiber ring
RO-08 | KAR-U-0039 | U | Rooftop | Karak | Karak | 31.1816 | 35.7109 | 30 | 3 | HUB-KAR-01 | HUB-KAR-01-R01 | Fiber ring
RO-08 | KAR-U-0040 | U | Rooftop | Karak | Karak | 31.1824 | 35.7146 | 30 | 3 | HUB-KAR-01 | HUB-KAR-01-R01 | Fiber ring
RO-08 | KAR-U-0041 | U | Monopole / greenfield | Karak | Karak | 31.1832 | 35.7203 | 30 | 3 | HUB-KAR-01 | HUB-KAR-01-R01 | Fiber ring
RO-08 | KAR-U-0046 | U | Rooftop | Karak | Karak | 31.1851 | 35.7085 | 30 | 3 | HUB-KAR-01 | HUB-KAR-01-R05 | Fiber ring
RO-08 | KAR-U-0047 | U | Monopole / greenfield | Karak | Karak | 31.1859 | 35.7142 | 30 | 3 | HUB-KAR-01 | HUB-KAR-01-R05 | Fiber ring
RO-08 | KAR-U-0048 | U | Monopole / greenfield | Karak | Karak | 31.1859 | 35.7189 | 30 | 3 | HUB-KAR-01 | HUB-KAR-01-R04 | Fiber ring
RO-08 | KAR-U-0049 | U | Monopole / greenfield | Karak | Karak | 31.1859 | 35.7236 | 30 | 3 | HUB-KAR-01 | HUB-KAR-01-R03 | Fiber ring
RO-08 | KAR-U-0054 | U | Monopole / greenfield | Karak | Karak | 31.1894 | 35.7118 | 30 | 3 | HUB-KAR-01 | HUB-KAR-01-R05 | Fiber ring
RO-08 | KAR-U-0055 | U | Monopole / greenfield | Karak | Karak | 31.1902 | 35.7156 | 30 | 3 | HUB-KAR-01 | HUB-KAR-01-R05 | Fiber ring
RO-08 | KAR-U-0060 | U | Monopole / greenfield | Karak | Karak | 31.1938 | 35.7132 | 30 | 3 | HUB-KAR-01 | HUB-KAR-01-R05 | Fiber ring
RO-08 | MAD-SU-0136 | SU | Monopole / greenfield | Madaba | Madaba | 31.7294 | 35.8177 | 32 | 3 | HUB-MAD-01 | HUB-MAD-01-R03 | Fiber ring
RO-08 | MAD-SU-0137 | SU | Monopole / greenfield | Madaba | Amman | 31.7294 | 35.8246 | 32 | 3 | HUB-MAD-01 | HUB-MAD-01-R03 | Fiber ring
RO-08 | MAD-SU-0140 | SU | Monopole / greenfield | Madaba | Madaba | 31.734 | 35.8136 | 32 | 3 | HUB-MAD-01 | HUB-MAD-01-R03 | Fiber ring
RO-08 | MAD-SU-0141 | SU | Monopole / greenfield | Madaba | Madaba | 31.7345 | 35.8211 | 32 | 3 | HUB-MAD-01 | HUB-MAD-01-R03 | Fiber ring
RO-08 | MAD-SU-0142 | SU | Monopole / greenfield | Madaba | Amman | 31.7345 | 35.8293 | 32 | 3 | HUB-MAD-01 | HUB-MAD-01-R03 | Fiber ring
RO-08 | MAD-SU-0146 | SU | Monopole / greenfield | Madaba | Madaba | 31.7402 | 35.7897 | 32 | 3 | HUB-MAD-01 | HUB-MAD-01-R05 | Fiber ring
RO-08 | MAD-SU-0147 | SU | Monopole / greenfield | Madaba | Madaba | 31.7396 | 35.7972 | 32 | 3 | HUB-MAD-01 | HUB-MAD-01-R05 | Fiber ring
RO-08 | MAD-SU-0148 | SU | Monopole / greenfield | Madaba | Madaba | 31.7396 | 35.8041 | 32 | 3 | HUB-MAD-01 | HUB-MAD-01-R04 | Fiber ring
RO-08 | MAD-SU-0149 | SU | Monopole / greenfield | Madaba | Madaba | 31.7396 | 35.8109 | 32 | 3 | HUB-MAD-01 | HUB-MAD-01-R04 | Fiber ring
RO-08 | MAD-SU-0150 | SU | Monopole / greenfield | Madaba | Madaba | 31.7396 | 35.8177 | 32 | 3 | HUB-MAD-01 | HUB-MAD-01-R04 | Fiber ring
RO-08 | MAD-SU-0153 | SU | Monopole / greenfield | Madaba | Madaba | 31.7447 | 35.7952 | 32 | 3 | HUB-MAD-01 | HUB-MAD-01-R05 | Fiber ring
RO-08 | MAD-SU-0154 | SU | Rooftop | Madaba | Madaba | 31.7447 | 35.7993 | 32 | 3 | HUB-MAD-01 | HUB-MAD-01-R04 | Fiber ring
RO-08 | MAD-SU-0155 | SU | Monopole / greenfield | Madaba | Madaba | 31.7447 | 35.8061 | 32 | 3 | HUB-MAD-01 | HUB-MAD-01-R04 | Fiber ring
RO-08 | MAD-SU-0156 | SU | Monopole / greenfield | Madaba | Madaba | 31.7441 | 35.815 | 32 | 3 | HUB-MAD-01 | HUB-MAD-01-R04 | Fiber ring
RO-08 | MAD-SU-0157 | SU | Monopole / greenfield | Madaba | Madaba | 31.751 | 35.7904 | 32 | 3 | HUB-MAD-01 | HUB-MAD-01-R05 | Fiber ring
RO-08 | MAD-SU-0158 | SU | Monopole / greenfield | Madaba | Madaba | 31.7498 | 35.7972 | 32 | 3 | HUB-MAD-01 | HUB-MAD-01-R04 | Fiber ring
RO-08 | MAD-U-0066 | U | Rooftop | Madaba | Madaba | 31.7216 | 35.7983 | 30 | 3 | HUB-MAD-01 | HUB-MAD-01-R02 | Fiber ring
RO-08 | MAD-U-0067 | U | Rooftop | Madaba | Madaba | 31.7216 | 35.803 | 30 | 3 | HUB-MAD-01 | HUB-MAD-01-R02 | Fiber ring
RO-08 | MAD-U-0068 | U | Rooftop | Madaba | Madaba | 31.7216 | 35.8068 | 30 | 3 | HUB-MAD-01 | HUB-MAD-01-R02 | Fiber ring
RO-08 | MAD-U-0076 | U | Rooftop | Madaba | Madaba | 31.726 | 35.7959 | 30 | 3 | HUB-MAD-01 | HUB-MAD-01-R01 | Fiber ring
RO-08 | MAD-U-0077 | U | Rooftop | Madaba | Madaba | 31.726 | 35.8007 | 30 | 3 | HUB-MAD-01 | HUB-MAD-01-R01 | Fiber ring
RO-08 | MAD-U-0078 | U | Rooftop | Madaba | Madaba | 31.7251 | 35.8044 | 30 | 3 | HUB-MAD-01 | HUB-MAD-01-R02 | Fiber ring
RO-08 | MAD-U-0079 | U | Rooftop | Madaba | Madaba | 31.726 | 35.8101 | 30 | 3 | HUB-MAD-01 | HUB-MAD-01-R02 | Fiber ring
RO-08 | MAD-U-0080 | U | Monopole / greenfield | Madaba | Madaba | 31.7251 | 35.8148 | 30 | 3 | HUB-MAD-01 | HUB-MAD-01-R02 | Fiber ring
RO-08 | MAD-U-0085 | U | Rooftop | Madaba | Madaba | 31.7287 | 35.7945 | 30 | 3 | HUB-MAD-01 | HUB-MAD-01-R01 | Fiber ring
RO-08 | MAD-U-0086 | U | Rooftop | Madaba | Madaba | 31.7295 | 35.7983 | 30 | 3 | HUB-MAD-01 | HUB-MAD-01-R01 | Fiber ring
RO-08 | MAD-U-0087 | U | Rooftop | Madaba | Madaba | 31.7287 | 35.8021 | 30 | 3 | HUB-MAD-01 | HUB-MAD-01-R01 | Fiber ring
RO-08 | MAD-U-0088 | U | Rooftop | Madaba | Madaba | 31.7287 | 35.8077 | 30 | 3 | HUB-MAD-01 | HUB-MAD-01-R02 | Fiber ring
RO-08 | MAD-U-0089 | U | Monopole / greenfield | Madaba | Madaba | 31.7295 | 35.8125 | 30 | 3 | HUB-MAD-01 | HUB-MAD-01-R03 | Fiber ring
RO-08 | MAD-U-0094 | U | Rooftop | Madaba | Madaba | 31.7322 | 35.7959 | 30 | 3 | HUB-MAD-01 | HUB-MAD-01-R01 | Fiber ring
RO-08 | MAD-U-0095 | U | Rooftop | Madaba | Madaba | 31.7322 | 35.7997 | 30 | 3 | HUB-MAD-01 | HUB-MAD-01-R01 | Fiber ring
RO-08 | MAD-U-0096 | U | Rooftop | Madaba | Madaba | 31.733 | 35.8054 | 30 | 3 | HUB-MAD-01 | HUB-MAD-01-R01 | Fiber ring
RO-08 | MAD-U-0097 | U | Rooftop | Madaba | Madaba | 31.7322 | 35.8101 | 30 | 3 | HUB-MAD-01 | HUB-MAD-01-R03 | Fiber ring
RO-08 | MAD-U-0100 | U | Monopole / greenfield | Madaba | Madaba | 31.7357 | 35.7936 | 30 | 3 | HUB-MAD-01 | HUB-MAD-01-R05 | Fiber ring
RO-08 | MAD-U-0101 | U | Monopole / greenfield | Madaba | Madaba | 31.7357 | 35.7983 | 30 | 3 | HUB-MAD-01 | HUB-MAD-01-R05 | Fiber ring
RO-08 | MAD-U-0102 | U | Monopole / greenfield | Madaba | Madaba | 31.7357 | 35.804 | 30 | 3 | HUB-MAD-01 | HUB-MAD-01-R05 | Fiber ring
RO-08 | MAF-SU-0159 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3556 | 36.1693 | 32 | 3 | HUB-MAF-01 | HUB-MAF-01-R01 | Fiber ring
RO-08 | MAF-SU-0160 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3556 | 36.1761 | 32 | 3 | HUB-MAF-01 | HUB-MAF-01-R01 | Fiber ring
RO-08 | MAF-SU-0163 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3607 | 36.1713 | 32 | 3 | HUB-MAF-01 | HUB-MAF-01-R05 | Fiber ring
RO-08 | MAF-SU-0164 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3601 | 36.1788 | 32 | 3 | HUB-MAF-01 | HUB-MAF-01-R05 | Fiber ring
RO-08 | MAF-SU-0165 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3619 | 36.1863 | 32 | 3 | HUB-MAF-01 | HUB-MAF-01-R05 | Fiber ring
RO-08 | MAF-SU-0166 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3658 | 36.1829 | 32 | 3 | HUB-MAF-01 | HUB-MAF-01-R05 | Fiber ring
RO-08 | MAF-SU-0167 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3646 | 36.1898 | 32 | 3 | HUB-MAF-01 | HUB-MAF-01-R05 | Fiber ring
RO-08 | MAF-SU-0168 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3646 | 36.1966 | 32 | 3 | HUB-MAF-01 | HUB-MAF-01-R04 | Fiber ring
RO-08 | MAF-SU-0170 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3703 | 36.187 | 32 | 3 | HUB-MAF-01 | HUB-MAF-01-R05 | Fiber ring
RO-08 | MAF-SU-0171 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3709 | 36.1932 | 32 | 3 | HUB-MAF-01 | HUB-MAF-01-R04 | Fiber ring
RO-08 | MAF-SU-0172 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3709 | 36.2 | 32 | 3 | HUB-MAF-01 | HUB-MAF-01-R04 | Fiber ring
RO-08 | MAF-SU-0173 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.3697 | 36.2068 | 32 | 3 | HUB-MAF-01 | HUB-MAF-01-R04 | Fiber ring
RO-08 | MAF-SU-0176 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.376 | 36.2034 | 32 | 3 | HUB-MAF-01 | HUB-MAF-01-R04 | Fiber ring
RO-08 | MAF-SU-0177 | SU | Monopole / greenfield | Mafraq | Mafraq | 32.376 | 36.2102 | 32 | 3 | HUB-MAF-01 | HUB-MAF-01-R04 | Fiber ring
RO-08 | MAF-U-0077 | U | Monopole / greenfield | Mafraq | Mafraq | 32.349 | 36.1906 | 30 | 3 | HUB-MAF-01 | HUB-MAF-01-R02 | Fiber ring
RO-08 | MAF-U-0078 | U | Monopole / greenfield | Mafraq | Mafraq | 32.349 | 36.1953 | 30 | 3 | HUB-MAF-01 | HUB-MAF-01-R02 | Fiber ring
RO-08 | MAF-U-0079 | U | Rooftop | Mafraq | Mafraq | 32.349 | 36.2 | 30 | 3 | HUB-MAF-01 | HUB-MAF-01-R02 | Fiber ring
RO-08 | MAF-U-0087 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3525 | 36.1835 | 30 | 3 | HUB-MAF-01 | HUB-MAF-01-R01 | Fiber ring
RO-08 | MAF-U-0088 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3525 | 36.1882 | 30 | 3 | HUB-MAF-01 | HUB-MAF-01-R01 | Fiber ring
RO-08 | MAF-U-0089 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3525 | 36.1929 | 30 | 3 | HUB-MAF-01 | HUB-MAF-01-R02 | Fiber ring
RO-08 | MAF-U-0090 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3525 | 36.1986 | 30 | 3 | HUB-MAF-01 | HUB-MAF-01-R02 | Fiber ring
RO-08 | MAF-U-0091 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3525 | 36.2024 | 30 | 3 | HUB-MAF-01 | HUB-MAF-01-R03 | Fiber ring
RO-08 | MAF-U-0098 | U | Monopole / greenfield | Mafraq | Mafraq | 32.356 | 36.1849 | 30 | 3 | HUB-MAF-01 | HUB-MAF-01-R01 | Fiber ring
RO-08 | MAF-U-0099 | U | Monopole / greenfield | Mafraq | Mafraq | 32.356 | 36.1896 | 30 | 3 | HUB-MAF-01 | HUB-MAF-01-R01 | Fiber ring
RO-08 | MAF-U-0100 | U | Monopole / greenfield | Mafraq | Mafraq | 32.356 | 36.1953 | 30 | 3 | HUB-MAF-01 | HUB-MAF-01-R02 | Fiber ring
RO-08 | MAF-U-0101 | U | Monopole / greenfield | Mafraq | Mafraq | 32.356 | 36.2 | 30 | 3 | HUB-MAF-01 | HUB-MAF-01-R03 | Fiber ring
RO-08 | MAF-U-0108 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3595 | 36.1929 | 30 | 3 | HUB-MAF-01 | HUB-MAF-01-R01 | Fiber ring
RO-08 | MAF-U-0109 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3595 | 36.1976 | 30 | 3 | HUB-MAF-01 | HUB-MAF-01-R03 | Fiber ring
RO-08 | MAF-U-0110 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3595 | 36.2024 | 30 | 3 | HUB-MAF-01 | HUB-MAF-01-R03 | Fiber ring
RO-08 | MAF-U-0116 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3631 | 36.199 | 30 | 3 | HUB-MAF-01 | HUB-MAF-01-R03 | Fiber ring
RO-08 | MAF-U-0117 | U | Monopole / greenfield | Mafraq | Mafraq | 32.3631 | 36.2047 | 30 | 3 | HUB-MAF-01 | HUB-MAF-01-R03 | Fiber ring
RO-08 | RUR-R-0033 | R | Lattice tower | Rural | Karak | 30.9156 | 35.872 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0037 | R | Lattice tower | Rural | Karak | 30.9533 | 35.7482 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0038 | R | Lattice tower | Rural | Karak | 30.9533 | 35.804 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0039 | R | Lattice tower | Rural | Karak | 30.9484 | 35.8456 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0040 | R | Lattice tower | Rural | Karak | 30.9533 | 35.8871 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0041 | R | Lattice tower | Rural | Karak | 30.9837 | 35.5856 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0042 | R | Lattice tower | Rural | Karak | 30.9837 | 35.6329 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0043 | R | Lattice tower | Rural | Karak | 30.9885 | 35.6858 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0044 | R | Lattice tower | Rural | Karak | 30.9934 | 35.7274 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0045 | R | Lattice tower | Rural | Karak | 30.9885 | 35.769 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0046 | R | Lattice tower | Rural | Karak | 30.9885 | 35.8276 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0047 | R | Lattice tower | Rural | Karak | 30.9885 | 35.8635 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0048 | R | Lattice tower | Rural | Karak | 31.0287 | 35.6093 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0049 | R | Lattice tower | Rural | Karak | 31.0287 | 35.6565 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-08 | RUR-R-0050 | R | Lattice tower | Rural | Karak | 31.0262 | 35.7009 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0051 | R | Lattice tower | Rural | Karak | 31.0238 | 35.7454 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0052 | R | Lattice tower | Rural | Karak | 31.0238 | 35.7926 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0053 | R | Lattice tower | Rural | Karak | 31.0238 | 35.8399 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0054 | R | Lattice tower | Rural | Karak | 31.0238 | 35.8985 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0055 | R | Lattice tower | Rural | Karak | 31.0566 | 35.6357 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0056 | R | Lattice tower | Rural | Karak | 31.059 | 35.7803 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0057 | R | Lattice tower | Rural | Karak | 31.059 | 35.8162 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0058 | R | Lattice tower | Rural | Karak | 31.059 | 35.8635 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0059 | R | Lattice tower | Rural | Karak | 31.0894 | 35.6093 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0060 | R | Lattice tower | Rural | Karak | 31.0943 | 35.6565 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0061 | R | Lattice tower | Rural | Karak | 31.0894 | 35.751 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0062 | R | Lattice tower | Rural | Karak | 31.0943 | 35.804 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0063 | R | Lattice tower | Rural | Karak | 31.0992 | 35.8456 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0064 | R | Lattice tower | Rural | Karak | 31.0918 | 35.89 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0065 | R | Lattice tower | Rural | Karak | 31.1246 | 35.6329 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0067 | R | Lattice tower | Rural | Karak | 31.1271 | 35.7246 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0068 | R | Lattice tower | Rural | Karak | 31.1246 | 35.7747 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0069 | R | Lattice tower | Rural | Karak | 31.1271 | 35.8248 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0070 | R | Lattice tower | Rural | Karak | 31.1246 | 35.8692 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0071 | R | Lattice tower | Rural | Karak | 31.1246 | 35.9164 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0118 | R | Lattice tower | Rural | Amman | 31.409 | 35.872 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0119 | R | Lattice tower | Rural | Amman | 31.4066 | 35.9164 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0123 | R | Lattice tower | Rural | Madaba | 31.4418 | 35.7983 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0124 | R | Lattice tower | Rural | Amman | 31.4467 | 35.8512 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0125 | R | Lattice tower | Rural | Amman | 31.4418 | 35.8928 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0126 | R | Lattice tower | Rural | Amman | 31.4467 | 35.9344 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0131 | R | Lattice tower | Rural | Amman | 31.4868 | 35.8692 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0132 | R | Lattice tower | Rural | Amman | 31.4844 | 35.9193 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0133 | R | Lattice tower | Rural | Amman | 31.482 | 35.9694 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0139 | R | Lattice tower | Rural | Amman | 31.5172 | 35.8871 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0140 | R | Lattice tower | Rural | Amman | 31.5172 | 35.9344 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0141 | R | Lattice tower | Rural | Amman | 31.5123 | 35.9873 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-08 | RUR-R-0146 | R | Lattice tower | Rural | Amman | 31.5524 | 35.8692 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0147 | R | Lattice tower | Rural | Amman | 31.5476 | 35.9164 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0148 | R | Lattice tower | Rural | Amman | 31.5524 | 35.958 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0149 | R | Lattice tower | Rural | Amman | 31.5524 | 36.0166 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-08 | RUR-R-0155 | R | Lattice tower | Rural | Amman | 31.5852 | 35.8928 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0156 | R | Lattice tower | Rural | Amman | 31.5901 | 35.9372 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0157 | R | Lattice tower | Rural | Amman | 31.5877 | 35.993 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-08 | RUR-R-0158 | R | Lattice tower | Rural | Amman | 31.5901 | 36.0374 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0164 | R | Lattice tower | Rural | Amman | 31.6229 | 35.8692 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0165 | R | Lattice tower | Rural | Amman | 31.6181 | 35.9164 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0166 | R | Lattice tower | Rural | Amman | 31.6229 | 35.9665 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-08 | RUR-R-0167 | R | Lattice tower | Rural | Amman | 31.6205 | 36.0138 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0168 | R | Lattice tower | Rural | Amman | 31.6181 | 36.0582 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0172 | R | Lattice tower | Rural | Amman | 31.6582 | 35.804 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-08 | RUR-R-0173 | R | Lattice tower | Rural | Amman | 31.6582 | 35.8456 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0174 | R | Lattice tower | Rural | Amman | 31.6533 | 35.8928 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0175 | R | Lattice tower | Rural | Amman | 31.6557 | 35.9429 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0176 | R | Lattice tower | Rural | Amman | 31.6582 | 35.9873 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-08 | RUR-R-0177 | R | Lattice tower | Rural | Amman | 31.6631 | 36.0346 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0178 | R | Lattice tower | Rural | Amman | 31.6582 | 36.0875 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0182 | R | Lattice tower | Rural | Amman | 31.6983 | 35.8692 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0183 | R | Lattice tower | Rural | Amman | 31.6934 | 35.9164 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0184 | R | Lattice tower | Rural | Amman | 31.6934 | 36.0582 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0185 | R | Lattice tower | Rural | Amman | 31.6934 | 36.1112 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0188 | R | Lattice tower | Rural | Amman | 31.7287 | 35.8928 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0189 | R | Lattice tower | Rural | Amman | 31.7311 | 35.9372 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-08 | RUR-R-0190 | R | Lattice tower | Rural | Amman | 31.7311 | 36.0847 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0191 | R | Lattice tower | Rural | Amman | 31.7287 | 36.1234 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0196 | R | Lattice tower | Rural | Amman | 31.759 | 35.9164 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0279 | R | Lattice tower | Rural | Mafraq | 32.1565 | 36.0346 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0280 | R | Lattice tower | Rural | Mafraq | 32.154 | 36.1263 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-08 | RUR-R-0283 | R | Lattice tower | Rural | Mafraq | 32.1516 | 36.2766 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0284 | R | Lattice tower | Rural | Mafraq | 32.1516 | 36.3238 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0292 | R | Lattice tower | Rural | Mafraq | 32.1917 | 36.011 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0293 | R | Lattice tower | Rural | Mafraq | 32.1893 | 36.0582 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0294 | R | Lattice tower | Rural | Mafraq | 32.1868 | 36.1112 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0295 | R | Lattice tower | Rural | Mafraq | 32.1893 | 36.1527 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-08 | RUR-R-0296 | R | Lattice tower | Rural | Mafraq | 32.1868 | 36.2 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0297 | R | Lattice tower | Rural | Mafraq | 32.1868 | 36.2529 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0298 | R | Lattice tower | Rural | Mafraq | 32.1868 | 36.2974 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0299 | R | Lattice tower | Rural | Mafraq | 32.1868 | 36.3446 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0307 | R | Lattice tower | Rural | Mafraq | 32.227 | 35.9873 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0308 | R | Lattice tower | Rural | Mafraq | 32.2221 | 36.0403 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0309 | R | Lattice tower | Rural | Mafraq | 32.2221 | 36.0762 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0310 | R | Lattice tower | Rural | Mafraq | 32.227 | 36.1291 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0311 | R | Lattice tower | Rural | Mafraq | 32.2197 | 36.1792 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-08 | RUR-R-0312 | R | Lattice tower | Rural | Mafraq | 32.2221 | 36.2293 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0313 | R | Lattice tower | Rural | Mafraq | 32.2221 | 36.2652 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0314 | R | Lattice tower | Rural | Mafraq | 32.2221 | 36.3238 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0315 | R | Lattice tower | Rural | Mafraq | 32.2221 | 36.3711 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0316 | R | Lattice tower | Rural | Irbid | 32.2598 | 35.5885 | 45 | 2 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0323 | R | Lattice tower | Rural | Mafraq | 32.2598 | 36.0138 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0324 | R | Lattice tower | Rural | Mafraq | 32.2598 | 36.0582 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0325 | R | Lattice tower | Rural | Mafraq | 32.2598 | 36.1026 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0327 | R | Lattice tower | Rural | Mafraq | 32.2549 | 36.1972 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0328 | R | Lattice tower | Rural | Mafraq | 32.2573 | 36.2473 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0329 | R | Lattice tower | Rural | Mafraq | 32.2573 | 36.2945 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0330 | R | Lattice tower | Rural | Mafraq | 32.2573 | 36.3475 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0331 | R | Lattice tower | Rural | Mafraq | 32.2622 | 36.389 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0344 | R | Lattice tower | Rural | Irbid | 32.3278 | 35.5913 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-08 | RUR-R-0357 | R | Lattice tower | Rural | Irbid | 32.3655 | 35.6121 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-08 | RUR-R-0359 | R | Lattice tower | Rural | Irbid | 32.3582 | 35.7038 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0362 | R | Lattice tower | Rural | Irbid | 32.3655 | 35.89 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-08 | RUR-R-0364 | R | Lattice tower | Rural | Irbid | 32.3582 | 35.9873 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0371 | R | Lattice tower | Rural | Irbid | 32.3983 | 35.5913 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-08 | RUR-R-0372 | R | Lattice tower | Rural | Irbid | 32.3983 | 35.6329 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0373 | R | Lattice tower | Rural | Irbid | 32.3959 | 35.683 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0374 | R | Lattice tower | Rural | Irbid | 32.4032 | 35.7274 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0375 | R | Lattice tower | Rural | Irbid | 32.3959 | 35.7775 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-08 | RUR-R-0377 | R | Lattice tower | Rural | Irbid | 32.3959 | 35.8692 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-08 | RUR-R-0378 | R | Lattice tower | Rural | Irbid | 32.3959 | 35.9136 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0379 | R | Lattice tower | Rural | Irbid | 32.3959 | 35.9609 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0389 | R | Lattice tower | Rural | Irbid | 32.4335 | 35.6622 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0391 | R | Lattice tower | Rural | Irbid | 32.4335 | 35.7454 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0392 | R | Lattice tower | Rural | Irbid | 32.4287 | 35.7983 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-08 | RUR-R-0395 | R | Lattice tower | Rural | Irbid | 32.4311 | 35.9372 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0396 | R | Lattice tower | Rural | Irbid | 32.4287 | 35.9873 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-08 | RUR-R-0397 | R | Lattice tower | Rural | Irbid | 32.4287 | 36.0346 | 45 | 3 |  |  | Microwave E-band 10G
RO-08 | RUR-R-0398 | R | Lattice tower | Rural | Irbid | 32.4311 | 36.079 | 45 | 3 |  |  | Fiber (backbone add/drop spur)
RO-08 | SAL-SU-0083 | SU | Monopole / greenfield | Salt | Balqa | 32.0134 | 35.7153 | 32 | 3 | HUB-SAL-04 | HUB-SAL-04-R01 | Fiber ring
RO-08 | SAL-SU-0084 | SU | Monopole / greenfield | Salt | Balqa | 32.014 | 35.7215 | 32 | 3 | HUB-SAL-04 | HUB-SAL-04-R02 | Fiber ring
RO-08 | SAL-SU-0085 | SU | Monopole / greenfield | Salt | Balqa | 32.0145 | 35.7276 | 32 | 3 | HUB-SAL-04 | HUB-SAL-04-R02 | Fiber ring
RO-08 | SAL-SU-0088 | SU | Monopole / greenfield | Salt | Balqa | 32.0208 | 35.7051 | 32 | 3 | HUB-SAL-04 | HUB-SAL-04-R01 | Fiber ring
RO-08 | SAL-SU-0089 | SU | Monopole / greenfield | Salt | Balqa | 32.0196 | 35.7119 | 32 | 3 | HUB-SAL-04 | HUB-SAL-04-R01 | Fiber ring
RO-08 | SAL-SU-0090 | SU | Monopole / greenfield | Salt | Balqa | 32.0208 | 35.7187 | 32 | 3 | HUB-SAL-04 | HUB-SAL-04-R01 | Fiber ring
RO-08 | SAL-SU-0091 | SU | Monopole / greenfield | Salt | Balqa | 32.0208 | 35.7256 | 32 | 3 | HUB-SAL-04 | HUB-SAL-04-R02 | Fiber ring
RO-08 | SAL-SU-0096 | SU | Monopole / greenfield | Salt | Balqa | 32.0241 | 35.7024 | 32 | 3 | HUB-SAL-04 | HUB-SAL-04-R01 | Fiber ring
RO-08 | SAL-SU-0097 | SU | Monopole / greenfield | Salt | Balqa | 32.0247 | 35.7071 | 32 | 3 | HUB-SAL-04 | HUB-SAL-04-R01 | Fiber ring
RO-08 | SAL-SU-0098 | SU | Monopole / greenfield | Salt | Balqa | 32.0259 | 35.7153 | 32 | 3 | HUB-SAL-04 | HUB-SAL-04-R01 | Fiber ring
RO-08 | SAL-SU-0102 | SU | Monopole / greenfield | Salt | Balqa | 32.0298 | 35.6996 | 32 | 3 | HUB-SAL-04 | HUB-SAL-04-R05 | Fiber ring
RO-08 | SAL-SU-0103 | SU | Monopole / greenfield | Salt | Balqa | 32.0304 | 35.7058 | 32 | 3 | HUB-SAL-04 | HUB-SAL-04-R05 | Fiber ring
RO-08 | SAL-SU-0105 | SU | Monopole / greenfield | Salt | Balqa | 32.0349 | 35.6962 | 32 | 3 | HUB-SAL-04 | HUB-SAL-04-R05 | Fiber ring
RO-08 | SAL-SU-0106 | SU | Monopole / greenfield | Salt | Balqa | 32.0349 | 35.7017 | 32 | 3 | HUB-SAL-04 | HUB-SAL-04-R05 | Fiber ring
RO-08 | SAL-SU-0108 | SU | Monopole / greenfield | Salt | Balqa | 32.0406 | 35.6921 | 32 | 3 | HUB-SAL-04 | HUB-SAL-04-R05 | Fiber ring
RO-08 | SAL-SU-0109 | SU | Monopole / greenfield | Salt | Balqa | 32.0388 | 35.6983 | 32 | 3 | HUB-SAL-04 | HUB-SAL-04-R05 | Fiber ring
RO-08 | SAL-U-0001 | U | Monopole / greenfield | Salt | Balqa | 32.0239 | 35.7227 | 30 | 3 | HUB-SAL-04 | HUB-SAL-04-R02 | Fiber ring
RO-08 | SAL-U-0002 | U | Monopole / greenfield | Salt | Balqa | 32.0239 | 35.7274 | 30 | 3 | HUB-SAL-04 | HUB-SAL-04-R02 | Fiber ring
RO-08 | SAL-U-0005 | U | Rooftop | Salt | Balqa | 32.0282 | 35.7165 | 30 | 3 | HUB-SAL-04 | HUB-SAL-04-R01 | Fiber ring
RO-08 | SAL-U-0006 | U | Rooftop | Salt | Balqa | 32.0282 | 35.7194 | 30 | 3 | HUB-SAL-04 | HUB-SAL-04-R02 | Fiber ring
RO-08 | SAL-U-0007 | U | Rooftop | Salt | Balqa | 32.0286 | 35.7246 | 30 | 3 | HUB-SAL-04 | HUB-SAL-04-R02 | Fiber ring
RO-08 | SAL-U-0012 | U | Monopole / greenfield | Salt | Balqa | 32.0318 | 35.7076 | 30 | 3 | HUB-SAL-04 | HUB-SAL-04-R05 | Fiber ring
RO-08 | SAL-U-0013 | U | Rooftop | Salt | Balqa | 32.0326 | 35.7132 | 30 | 3 | HUB-SAL-04 | HUB-SAL-04-R04 | Fiber ring
RO-08 | SAL-U-0014 | U | Rooftop | Salt | Balqa | 32.0326 | 35.718 | 30 | 3 | HUB-SAL-04 | HUB-SAL-04-R03 | Fiber ring
RO-08 | SAL-U-0015 | U | Rooftop | Salt | Balqa | 32.0318 | 35.7217 | 30 | 3 | HUB-SAL-04 | HUB-SAL-04-R03 | Fiber ring
RO-08 | SAL-U-0016 | U | Rooftop | Salt | Balqa | 32.0318 | 35.7265 | 30 | 3 | HUB-SAL-04 | HUB-SAL-04-R03 | Fiber ring
RO-08 | SAL-U-0022 | U | Monopole / greenfield | Salt | Balqa | 32.0361 | 35.7061 | 30 | 3 | HUB-SAL-04 | HUB-SAL-04-R04 | Fiber ring
RO-08 | SAL-U-0023 | U | Rooftop | Salt | Balqa | 32.0361 | 35.7109 | 30 | 3 | HUB-SAL-04 | HUB-SAL-04-R04 | Fiber ring
RO-08 | SAL-U-0024 | U | Rooftop | Salt | Balqa | 32.0353 | 35.7156 | 30 | 3 | HUB-SAL-04 | HUB-SAL-04-R04 | Fiber ring
RO-08 | SAL-U-0025 | U | Rooftop | Salt | Balqa | 32.0353 | 35.7194 | 30 | 3 | HUB-SAL-04 | HUB-SAL-04-R03 | Fiber ring
RO-08 | SAL-U-0026 | U | Rooftop | Salt | Balqa | 32.0361 | 35.725 | 30 | 3 | HUB-SAL-04 | HUB-SAL-04-R03 | Fiber ring
RO-08 | SAL-U-0033 | U | Rooftop | Salt | Balqa | 32.0388 | 35.7085 | 30 | 3 | HUB-SAL-04 | HUB-SAL-04-R04 | Fiber ring
RO-08 | SAL-U-0034 | U | Rooftop | Salt | Balqa | 32.0396 | 35.7132 | 30 | 3 | HUB-SAL-04 | HUB-SAL-04-R04 | Fiber ring
RO-08 | SAL-U-0035 | U | Rooftop | Salt | Balqa | 32.0388 | 35.717 | 30 | 3 | HUB-SAL-04 | HUB-SAL-04-R04 | Fiber ring
RO-08 | SAL-U-0036 | U | Rooftop | Salt | Balqa | 32.0388 | 35.7217 | 30 | 3 | HUB-SAL-04 | HUB-SAL-04-R03 | Fiber ring
RO-08 | SAL-U-0037 | U | Rooftop | Salt | Balqa | 32.0396 | 35.7274 | 30 | 3 | HUB-SAL-04 | HUB-SAL-04-R03 | Fiber ring
RO-08 | TAF-SU-0057 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8335 | 35.6279 | 32 | 3 | HUB-TAF-01 | HUB-TAF-01-R02 | Fiber ring
RO-08 | TAF-SU-0059 | SU | Rooftop | Tafilah | Tafilah | 30.8397 | 35.6232 | 32 | 3 | HUB-TAF-01 | HUB-TAF-01-R02 | Fiber ring
RO-08 | TAF-SU-0060 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8397 | 35.63 | 32 | 3 | HUB-TAF-01 | HUB-TAF-01-R02 | Fiber ring
RO-08 | TAF-SU-0061 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8436 | 35.6279 | 32 | 3 | HUB-TAF-01 | HUB-TAF-01-R03 | Fiber ring
RO-08 | TAF-SU-0062 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8487 | 35.6245 | 32 | 3 | HUB-TAF-01 | HUB-TAF-01-R03 | Fiber ring
RO-08 | TAF-SU-0063 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8487 | 35.63 | 32 | 3 | HUB-TAF-01 | HUB-TAF-01-R03 | Fiber ring
RO-08 | TAF-SU-0064 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8538 | 35.6211 | 32 | 3 | HUB-TAF-01 | HUB-TAF-01-R03 | Fiber ring
RO-08 | TAF-SU-0065 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8544 | 35.6273 | 32 | 3 | HUB-TAF-01 | HUB-TAF-01-R03 | Fiber ring
RO-08 | TAF-SU-0066 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8601 | 35.6027 | 32 | 3 | HUB-TAF-01 | HUB-TAF-01-R05 | Fiber ring
RO-08 | TAF-SU-0067 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8601 | 35.6095 | 32 | 3 | HUB-TAF-01 | HUB-TAF-01-R04 | Fiber ring
RO-08 | TAF-SU-0068 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8589 | 35.6177 | 32 | 3 | HUB-TAF-01 | HUB-TAF-01-R04 | Fiber ring
RO-08 | TAF-SU-0069 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.8577 | 35.6232 | 32 | 3 | HUB-TAF-01 | HUB-TAF-01-R03 | Fiber ring
RO-08 | TAF-SU-0070 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.864 | 35.6007 | 32 | 3 | HUB-TAF-01 | HUB-TAF-01-R04 | Fiber ring
RO-08 | TAF-SU-0071 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.864 | 35.6075 | 32 | 3 | HUB-TAF-01 | HUB-TAF-01-R04 | Fiber ring
RO-08 | TAF-SU-0072 | SU | Monopole / greenfield | Tafilah | Tafilah | 30.864 | 35.6143 | 32 | 3 | HUB-TAF-01 | HUB-TAF-01-R04 | Fiber ring
RO-08 | TAF-U-0024 | U | Rooftop | Tafilah | Tafilah | 30.8362 | 35.6163 | 30 | 3 | HUB-TAF-01 | HUB-TAF-01-R02 | Fiber ring
RO-08 | TAF-U-0028 | U | Rooftop | Tafilah | Tafilah | 30.8397 | 35.6093 | 30 | 3 | HUB-TAF-01 | HUB-TAF-01-R01 | Fiber ring
RO-08 | TAF-U-0029 | U | Rooftop | Tafilah | Tafilah | 30.8397 | 35.614 | 30 | 3 | HUB-TAF-01 | HUB-TAF-01-R01 | Fiber ring
RO-08 | TAF-U-0030 | U | Monopole / greenfield | Tafilah | Tafilah | 30.8397 | 35.6187 | 30 | 3 | HUB-TAF-01 | HUB-TAF-01-R02 | Fiber ring
RO-08 | TAF-U-0033 | U | Monopole / greenfield | Tafilah | Tafilah | 30.8432 | 35.6022 | 30 | 3 | HUB-TAF-01 | HUB-TAF-01-R01 | Fiber ring
RO-08 | TAF-U-0034 | U | Monopole / greenfield | Tafilah | Tafilah | 30.8432 | 35.6069 | 30 | 3 | HUB-TAF-01 | HUB-TAF-01-R01 | Fiber ring
RO-08 | TAF-U-0035 | U | Monopole / greenfield | Tafilah | Tafilah | 30.844 | 35.6126 | 30 | 3 | HUB-TAF-01 | HUB-TAF-01-R01 | Fiber ring
RO-08 | TAF-U-0036 | U | Monopole / greenfield | Tafilah | Tafilah | 30.8449 | 35.6163 | 30 | 3 | HUB-TAF-01 | HUB-TAF-01-R02 | Fiber ring
RO-08 | TAF-U-0037 | U | Monopole / greenfield | Tafilah | Tafilah | 30.8467 | 35.5951 | 30 | 3 | HUB-TAF-01 | HUB-TAF-01-R01 | Fiber ring
RO-08 | TAF-U-0038 | U | Monopole / greenfield | Tafilah | Tafilah | 30.848 | 35.605 | 30 | 3 | HUB-TAF-01 | HUB-TAF-01-R05 | Fiber ring
RO-08 | TAF-U-0039 | U | Monopole / greenfield | Tafilah | Tafilah | 30.8476 | 35.6102 | 30 | 3 | HUB-TAF-01 | HUB-TAF-01-R05 | Fiber ring
RO-08 | TAF-U-0040 | U | Monopole / greenfield | Tafilah | Tafilah | 30.8476 | 35.6149 | 30 | 3 | HUB-TAF-01 | HUB-TAF-01-R01 | Fiber ring
RO-08 | TAF-U-0041 | U | Monopole / greenfield | Tafilah | Tafilah | 30.8519 | 35.6022 | 30 | 3 | HUB-TAF-01 | HUB-TAF-01-R05 | Fiber ring
RO-08 | TAF-U-0042 | U | Monopole / greenfield | Tafilah | Tafilah | 30.8519 | 35.6069 | 30 | 3 | HUB-TAF-01 | HUB-TAF-01-R05 | Fiber ring
RO-08 | TAF-U-0043 | U | Monopole / greenfield | Tafilah | Tafilah | 30.8511 | 35.6126 | 30 | 3 | HUB-TAF-01 | HUB-TAF-01-R04 | Fiber ring
RO-09 | AMM-SU-2219 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8223 | 35.9474 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R01 | Fiber ring
RO-09 | AMM-SU-2220 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8262 | 35.9304 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R01 | Fiber ring
RO-09 | AMM-SU-2221 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8273 | 35.9372 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R01 | Fiber ring
RO-09 | AMM-SU-2222 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8256 | 35.9447 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R01 | Fiber ring
RO-09 | AMM-SU-2223 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8262 | 35.9508 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R02 | Fiber ring
RO-09 | AMM-SU-2224 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8273 | 35.9577 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R02 | Fiber ring
RO-09 | AMM-SU-2225 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8273 | 35.9645 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R02 | Fiber ring
RO-09 | AMM-SU-2226 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8262 | 35.9699 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R02 | Fiber ring
RO-09 | AMM-SU-2227 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8324 | 35.9133 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R02 | Fiber ring
RO-09 | AMM-SU-2228 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8313 | 35.9201 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R02 | Fiber ring
RO-09 | AMM-SU-2229 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8324 | 35.9269 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R02 | Fiber ring
RO-09 | AMM-SU-2230 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8324 | 35.9338 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R01 | Fiber ring
RO-09 | AMM-SU-2231 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8318 | 35.9399 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R01 | Fiber ring
RO-09 | AMM-SU-2232 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8324 | 35.9474 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R01 | Fiber ring
RO-09 | AMM-SU-2233 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8324 | 35.9543 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R02 | Fiber ring
RO-09 | AMM-SU-2234 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8313 | 35.9624 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R02 | Fiber ring
RO-09 | AMM-SU-2235 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8313 | 35.9665 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R02 | Fiber ring
RO-09 | AMM-SU-2236 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8313 | 35.9734 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R03 | Fiber ring
RO-09 | AMM-SU-2237 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8318 | 35.9877 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R02 | Fiber ring
RO-09 | AMM-SU-2238 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8364 | 35.8949 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R02 | Fiber ring
RO-09 | AMM-SU-2239 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8375 | 35.9031 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R01 | Fiber ring
RO-09 | AMM-SU-2240 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8375 | 35.9099 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R02 | Fiber ring
RO-09 | AMM-SU-2241 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8364 | 35.9153 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R02 | Fiber ring
RO-09 | AMM-SU-2242 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8364 | 35.9249 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R02 | Fiber ring
RO-09 | AMM-SU-2243 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.837 | 35.9297 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R03 | Fiber ring
RO-09 | AMM-SU-2244 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8375 | 35.9372 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R06 | Fiber ring
RO-09 | AMM-SU-2245 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8375 | 35.944 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R06 | Fiber ring
RO-09 | AMM-SU-2246 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8364 | 35.9508 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R06 | Fiber ring
RO-09 | AMM-SU-2247 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8364 | 35.9563 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R01 | Fiber ring
RO-09 | AMM-SU-2248 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8364 | 35.9659 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R03 | Fiber ring
RO-09 | AMM-SU-2249 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8358 | 35.9706 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R03 | Fiber ring
RO-09 | AMM-SU-2250 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.837 | 35.9775 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R03 | Fiber ring
RO-09 | AMM-SU-2251 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8375 | 35.985 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R01 | Fiber ring
RO-09 | AMM-SU-2252 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.837 | 35.9911 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R02 | Fiber ring
RO-09 | AMM-SU-2253 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8352 | 35.9986 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R02 | Fiber ring
RO-09 | AMM-SU-2254 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8364 | 36.0061 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R02 | Fiber ring
RO-09 | AMM-SU-2255 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8414 | 35.8805 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R02 | Fiber ring
RO-09 | AMM-SU-2256 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8414 | 35.8846 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R02 | Fiber ring
RO-09 | AMM-SU-2257 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8414 | 35.8914 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R03 | Fiber ring
RO-09 | AMM-SU-2258 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8414 | 35.901 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R01 | Fiber ring
RO-09 | AMM-SU-2259 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8414 | 35.9078 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R01 | Fiber ring
RO-09 | AMM-SU-2260 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8414 | 35.9119 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R01 | Fiber ring
RO-09 | AMM-SU-2261 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8414 | 35.9215 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R02 | Fiber ring
RO-09 | AMM-SU-2262 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8414 | 35.9269 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R03 | Fiber ring
RO-09 | AMM-SU-2263 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.842 | 35.9331 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R03 | Fiber ring
RO-09 | AMM-SU-2264 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8414 | 35.9392 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R06 | Fiber ring
RO-09 | AMM-SU-2265 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8414 | 35.9488 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R05 | Fiber ring
RO-09 | AMM-SU-2266 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8414 | 35.9529 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R05 | Fiber ring
RO-09 | AMM-SU-2267 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8426 | 35.9611 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R04 | Fiber ring
RO-09 | AMM-SU-2268 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8414 | 35.9679 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R03 | Fiber ring
RO-09 | AMM-SU-2269 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.842 | 35.9754 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R03 | Fiber ring
RO-09 | AMM-SU-2270 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8414 | 35.9829 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R01 | Fiber ring
RO-09 | AMM-SU-2271 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8426 | 35.9884 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R01 | Fiber ring
RO-09 | AMM-SU-2272 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8414 | 35.9938 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R02 | Fiber ring
RO-09 | AMM-SU-2273 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8414 | 36.002 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R02 | Fiber ring
RO-09 | AMM-SU-2274 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8414 | 36.0075 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R03 | Fiber ring
RO-09 | AMM-SU-2275 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.842 | 36.015 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R03 | Fiber ring
RO-09 | AMM-SU-2276 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8465 | 35.8703 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R01 | Fiber ring
RO-09 | AMM-SU-2277 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8465 | 35.8757 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R02 | Fiber ring
RO-09 | AMM-SU-2278 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8465 | 35.8812 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R02 | Fiber ring
RO-09 | AMM-SU-2279 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8465 | 35.888 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R03 | Fiber ring
RO-09 | AMM-SU-2280 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8465 | 35.8976 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R03 | Fiber ring
RO-09 | AMM-SU-2281 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8477 | 35.9031 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R01 | Fiber ring
RO-09 | AMM-SU-2282 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8465 | 35.9113 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R01 | Fiber ring
RO-09 | AMM-SU-2283 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8471 | 35.916 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R01 | Fiber ring
RO-09 | AMM-SU-2284 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8471 | 35.9242 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R03 | Fiber ring
RO-09 | AMM-SU-2285 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8477 | 35.9304 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R03 | Fiber ring
RO-09 | AMM-SU-2286 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8471 | 35.9365 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R03 | Fiber ring
RO-09 | AMM-SU-2287 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8465 | 35.9427 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R05 | Fiber ring
RO-09 | AMM-SU-2288 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8465 | 35.9508 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R05 | Fiber ring
RO-09 | AMM-SU-2289 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8454 | 35.9577 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R04 | Fiber ring
RO-09 | AMM-SU-2290 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8465 | 35.9659 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R04 | Fiber ring
RO-09 | AMM-SU-2291 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8465 | 35.9727 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R04 | Fiber ring
RO-09 | AMM-SU-2292 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8471 | 35.9775 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R03 | Fiber ring
RO-09 | AMM-SU-2293 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8465 | 35.9863 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R01 | Fiber ring
RO-09 | AMM-SU-2294 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8465 | 35.9904 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R01 | Fiber ring
RO-09 | AMM-SU-2295 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8477 | 35.9986 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R02 | Fiber ring
RO-09 | AMM-SU-2296 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8477 | 36.0055 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R03 | Fiber ring
RO-09 | AMM-SU-2297 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8465 | 36.0123 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R03 | Fiber ring
RO-09 | AMM-SU-2298 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8465 | 36.0177 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R03 | Fiber ring
RO-09 | AMM-SU-2299 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8516 | 35.8587 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R01 | Fiber ring
RO-09 | AMM-SU-2300 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8528 | 35.8655 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R01 | Fiber ring
RO-09 | AMM-SU-2301 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8516 | 35.8737 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R02 | Fiber ring
RO-09 | AMM-SU-2302 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8516 | 35.8778 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R02 | Fiber ring
RO-09 | AMM-SU-2303 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8504 | 35.886 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R03 | Fiber ring
RO-09 | AMM-SU-2304 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8528 | 35.8928 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R03 | Fiber ring
RO-09 | AMM-SU-2305 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8528 | 35.8996 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R07 | Fiber ring
RO-09 | AMM-SU-2306 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8528 | 35.9065 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R07 | Fiber ring
RO-09 | AMM-SU-2307 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8516 | 35.9133 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R07 | Fiber ring
RO-09 | AMM-SU-2308 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8516 | 35.9201 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R01 | Fiber ring
RO-09 | AMM-SU-2309 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8516 | 35.9283 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R03 | Fiber ring
RO-09 | AMM-SU-2310 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8528 | 35.9338 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R04 | Fiber ring
RO-09 | AMM-SU-2311 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8522 | 35.9399 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R04 | Fiber ring
RO-09 | AMM-SU-2312 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8504 | 35.9474 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R05 | Fiber ring
RO-09 | AMM-SU-2313 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8516 | 35.9529 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R05 | Fiber ring
RO-09 | AMM-SU-2314 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8516 | 35.9624 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R04 | Fiber ring
RO-09 | AMM-SU-2315 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8516 | 35.9665 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R04 | Fiber ring
RO-09 | AMM-SU-2316 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8516 | 35.9734 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R04 | Fiber ring
RO-09 | AMM-SU-2317 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8528 | 35.9816 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R07 | Fiber ring
RO-09 | AMM-SU-2318 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8516 | 35.987 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R01 | Fiber ring
RO-09 | AMM-SU-2319 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8516 | 35.9966 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R01 | Fiber ring
RO-09 | AMM-SU-2320 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8528 | 36.002 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R01 | Fiber ring
RO-09 | AMM-SU-2321 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8516 | 36.0089 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R03 | Fiber ring
RO-09 | AMM-SU-2322 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8516 | 36.0157 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R03 | Fiber ring
RO-09 | AMM-SU-2323 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8516 | 36.0225 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R04 | Fiber ring
RO-09 | AMM-SU-2324 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8567 | 35.8498 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R01 | Fiber ring
RO-09 | AMM-SU-2325 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8567 | 35.8566 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R01 | Fiber ring
RO-09 | AMM-SU-2326 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8555 | 35.8621 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R01 | Fiber ring
RO-09 | AMM-SU-2327 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8567 | 35.8703 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R01 | Fiber ring
RO-09 | AMM-SU-2328 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8573 | 35.8751 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R01 | Fiber ring
RO-09 | AMM-SU-2329 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8579 | 35.8826 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R04 | Fiber ring
RO-09 | AMM-SU-2330 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8573 | 35.8887 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R03 | Fiber ring
RO-09 | AMM-SU-2331 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8567 | 35.8962 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R03 | Fiber ring
RO-09 | AMM-SU-2332 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8579 | 35.9031 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R07 | Fiber ring
RO-09 | AMM-SU-2333 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8567 | 35.9099 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R06 | Fiber ring
RO-09 | AMM-SU-2334 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8555 | 35.9167 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R06 | Fiber ring
RO-09 | AMM-SU-2335 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8567 | 35.9249 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R05 | Fiber ring
RO-09 | AMM-SU-2336 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8567 | 35.9317 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R04 | Fiber ring
RO-09 | AMM-SU-2337 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8561 | 35.9365 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R04 | Fiber ring
RO-09 | AMM-SU-2338 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8567 | 35.9427 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R04 | Fiber ring
RO-09 | AMM-SU-2339 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8579 | 35.9508 | 32 | 3 | HUB-AMM-55 | HUB-AMM-55-R05 | Fiber ring
RO-09 | AMM-SU-2344 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8579 | 35.985 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R07 | Fiber ring
RO-09 | AMM-SU-2345 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8567 | 35.9918 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R07 | Fiber ring
RO-09 | AMM-SU-2346 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8567 | 36 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R06 | Fiber ring
RO-09 | AMM-SU-2347 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8567 | 36.0055 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R05 | Fiber ring
RO-09 | AMM-SU-2348 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8567 | 36.0123 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R04 | Fiber ring
RO-09 | AMM-SU-2349 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8567 | 36.0191 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R04 | Fiber ring
RO-09 | AMM-SU-2350 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8567 | 36.0259 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R04 | Fiber ring
RO-09 | AMM-SU-2354 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.863 | 35.8587 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R05 | Fiber ring
RO-09 | AMM-SU-2355 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8612 | 35.8662 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R05 | Fiber ring
RO-09 | AMM-SU-2356 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8606 | 35.8723 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R05 | Fiber ring
RO-09 | AMM-SU-2357 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8624 | 35.8785 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R04 | Fiber ring
RO-09 | AMM-SU-2358 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8618 | 35.886 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R04 | Fiber ring
RO-09 | AMM-SU-2359 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8624 | 35.8935 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R04 | Fiber ring
RO-09 | AMM-SU-2360 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8618 | 35.901 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R06 | Fiber ring
RO-09 | AMM-SU-2361 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.863 | 35.9065 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R06 | Fiber ring
RO-09 | AMM-SU-2362 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8612 | 35.914 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R06 | Fiber ring
RO-09 | AMM-SU-2363 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8606 | 35.9201 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R05 | Fiber ring
RO-09 | AMM-SU-2364 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8618 | 35.9283 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R05 | Fiber ring
RO-09 | AMM-SU-2365 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8606 | 35.9338 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R04 | Fiber ring
RO-09 | AMM-SU-2366 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8618 | 35.9406 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R04 | Fiber ring
RO-09 | AMM-SU-2373 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.863 | 35.9884 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R07 | Fiber ring
RO-09 | AMM-SU-2374 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8618 | 35.9938 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R07 | Fiber ring
RO-09 | AMM-SU-2375 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8618 | 36.002 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R06 | Fiber ring
RO-09 | AMM-SU-2376 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8618 | 36.0089 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R05 | Fiber ring
RO-09 | AMM-SU-2377 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8618 | 36.0157 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R05 | Fiber ring
RO-09 | AMM-SU-2378 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.863 | 36.0225 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R04 | Fiber ring
RO-09 | AMM-SU-2379 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.863 | 36.0293 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R04 | Fiber ring
RO-09 | AMM-SU-2385 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8669 | 35.8621 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R05 | Fiber ring
RO-09 | AMM-SU-2386 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8681 | 35.8689 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R05 | Fiber ring
RO-09 | AMM-SU-2387 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8669 | 35.8744 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R05 | Fiber ring
RO-09 | AMM-SU-2388 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8669 | 35.8839 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R04 | Fiber ring
RO-09 | AMM-SU-2389 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8681 | 35.8894 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R04 | Fiber ring
RO-09 | AMM-SU-2390 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8663 | 35.8955 | 32 | 3 | HUB-AMM-31 | HUB-AMM-31-R04 | Fiber ring
RO-09 | AMM-SU-2391 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8669 | 35.9044 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R06 | Fiber ring
RO-09 | AMM-SU-2392 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8657 | 35.9099 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R06 | Fiber ring
RO-09 | AMM-SU-2393 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8669 | 35.9153 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R05 | Fiber ring
RO-09 | AMM-SU-2394 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8675 | 35.9242 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R05 | Fiber ring
RO-09 | AMM-SU-2395 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8669 | 35.9304 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R05 | Fiber ring
RO-09 | AMM-SU-2396 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8669 | 35.9372 | 32 | 3 | HUB-AMM-30 | HUB-AMM-30-R05 | Fiber ring
RO-09 | AMM-SU-2404 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8669 | 35.9918 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R07 | Fiber ring
RO-09 | AMM-SU-2405 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8675 | 35.9979 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R06 | Fiber ring
RO-09 | AMM-SU-2406 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8681 | 36.0055 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R06 | Fiber ring
RO-09 | AMM-SU-2407 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8669 | 36.0109 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R05 | Fiber ring
RO-09 | AMM-SU-2408 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8675 | 36.0184 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R05 | Fiber ring
RO-09 | AMM-SU-2409 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8669 | 36.0259 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R04 | Fiber ring
RO-09 | AMM-SU-2410 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8669 | 36.0341 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R03 | Fiber ring
RO-09 | AMM-SU-2437 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8732 | 35.9952 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R06 | Fiber ring
RO-09 | AMM-SU-2438 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.872 | 36.002 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R06 | Fiber ring
RO-09 | AMM-SU-2439 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.872 | 36.0089 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R05 | Fiber ring
RO-09 | AMM-SU-2440 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.872 | 36.0157 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R05 | Fiber ring
RO-09 | AMM-SU-2441 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.872 | 36.0211 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R02 | Fiber ring
RO-09 | AMM-SU-2442 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.872 | 36.0307 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R02 | Fiber ring
RO-09 | AMM-SU-2470 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8771 | 35.9973 | 32 | 3 | HUB-AMM-16 | HUB-AMM-16-R06 | Fiber ring
RO-09 | AMM-SU-2471 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8771 | 36.0055 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R01 | Fiber ring
RO-09 | AMM-SU-2472 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8783 | 36.0123 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R01 | Fiber ring
RO-09 | AMM-SU-2473 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8771 | 36.0191 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R02 | Fiber ring
RO-09 | AMM-SU-2474 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8765 | 36.0266 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R02 | Fiber ring
RO-09 | AMM-SU-2475 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8771 | 36.0341 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R03 | Fiber ring
RO-09 | AMM-SU-2504 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8834 | 36.002 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R01 | Fiber ring
RO-09 | AMM-SU-2505 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.8822 | 36.0089 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R01 | Fiber ring
RO-09 | AMM-SU-2506 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.881 | 36.0157 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R02 | Fiber ring
RO-09 | AMM-SU-2507 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.881 | 36.0225 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R02 | Fiber ring
RO-09 | AMM-SU-2508 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8816 | 36.0287 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R03 | Fiber ring
RO-09 | AMM-SU-2509 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8822 | 36.0362 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R03 | Fiber ring
RO-09 | AMM-SU-2535 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8884 | 35.9986 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R01 | Fiber ring
RO-09 | AMM-SU-2536 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8884 | 36.0055 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R01 | Fiber ring
RO-09 | AMM-SU-2537 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8879 | 36.013 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R01 | Fiber ring
RO-09 | AMM-SU-2538 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8884 | 36.0191 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R02 | Fiber ring
RO-09 | AMM-SU-2539 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8884 | 36.0259 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R03 | Fiber ring
RO-09 | AMM-SU-2540 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8861 | 36.0328 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R03 | Fiber ring
RO-09 | AMM-SU-2541 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8873 | 36.0396 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R03 | Fiber ring
RO-09 | AMM-SU-2542 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8929 | 35.7979 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R02 | Fiber ring
RO-09 | AMM-SU-2559 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8929 | 35.9952 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R08 | Fiber ring
RO-09 | AMM-SU-2560 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8924 | 36.002 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R08 | Fiber ring
RO-09 | AMM-SU-2561 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8935 | 36.0089 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R08 | Fiber ring
RO-09 | AMM-SU-2562 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8935 | 36.0157 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R08 | Fiber ring
RO-09 | AMM-SU-2563 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8924 | 36.0211 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R01 | Fiber ring
RO-09 | AMM-SU-2564 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8924 | 36.028 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R04 | Fiber ring
RO-09 | AMM-SU-2565 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8918 | 36.0355 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R04 | Fiber ring
RO-09 | AMM-SU-2566 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8912 | 36.043 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R04 | Fiber ring
RO-09 | AMM-SU-2567 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8986 | 35.787 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R02 | Fiber ring
RO-09 | AMM-SU-2568 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8974 | 35.7952 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R02 | Fiber ring
RO-09 | AMM-SU-2569 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8986 | 35.8143 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R02 | Fiber ring
RO-09 | AMM-SU-2584 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.898 | 35.9986 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R08 | Fiber ring
RO-09 | AMM-SU-2585 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8969 | 36.0048 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R07 | Fiber ring
RO-09 | AMM-SU-2586 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8963 | 36.0123 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R07 | Fiber ring
RO-09 | AMM-SU-2587 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.898 | 36.0184 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R06 | Fiber ring
RO-09 | AMM-SU-2588 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8974 | 36.0246 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R05 | Fiber ring
RO-09 | AMM-SU-2589 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.898 | 36.0321 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R05 | Fiber ring
RO-09 | AMM-SU-2590 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8974 | 36.0382 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R04 | Fiber ring
RO-09 | AMM-SU-2591 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.8986 | 36.0464 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R04 | Fiber ring
RO-09 | AMM-SU-2592 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9037 | 35.7904 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R01 | Fiber ring
RO-09 | AMM-SU-2593 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9037 | 35.7972 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R02 | Fiber ring
RO-09 | AMM-SU-2594 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9014 | 35.8041 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R02 | Fiber ring
RO-09 | AMM-SU-2595 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9031 | 35.8116 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R03 | Fiber ring
RO-09 | AMM-SU-2596 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9025 | 35.8164 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R03 | Fiber ring
RO-09 | AMM-SU-2607 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9037 | 36.002 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R07 | Fiber ring
RO-09 | AMM-SU-2608 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9025 | 36.0075 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R07 | Fiber ring
RO-09 | AMM-SU-2609 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9019 | 36.0164 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R07 | Fiber ring
RO-09 | AMM-SU-2610 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9025 | 36.0225 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R06 | Fiber ring
RO-09 | AMM-SU-2611 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9019 | 36.0293 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R05 | Fiber ring
RO-09 | AMM-SU-2612 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9025 | 36.0348 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R05 | Fiber ring
RO-09 | AMM-SU-2613 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9025 | 36.043 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R04 | Fiber ring
RO-09 | AMM-SU-2614 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9025 | 36.0498 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R04 | Fiber ring
RO-09 | AMM-SU-2615 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9076 | 35.7747 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R01 | Fiber ring
RO-09 | AMM-SU-2616 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9088 | 35.7802 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R01 | Fiber ring
RO-09 | AMM-SU-2617 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9076 | 35.7884 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R01 | Fiber ring
RO-09 | AMM-SU-2618 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9088 | 35.7938 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R01 | Fiber ring
RO-09 | AMM-SU-2619 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9076 | 35.802 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R02 | Fiber ring
RO-09 | AMM-SU-2620 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9088 | 35.8075 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R03 | Fiber ring
RO-09 | AMM-SU-2621 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9064 | 35.8143 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R03 | Fiber ring
RO-09 | AMM-SU-2622 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9088 | 35.8211 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R03 | Fiber ring
RO-09 | AMM-SU-2632 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9064 | 36.0055 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R07 | Fiber ring
RO-09 | AMM-SU-2633 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9076 | 36.0109 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R07 | Fiber ring
RO-09 | AMM-SU-2634 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9064 | 36.0191 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R06 | Fiber ring
RO-09 | AMM-SU-2635 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9076 | 36.0246 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R06 | Fiber ring
RO-09 | AMM-SU-2636 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9088 | 36.0328 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R05 | Fiber ring
RO-09 | AMM-SU-2637 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.907 | 36.0389 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R05 | Fiber ring
RO-09 | AMM-SU-2638 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9064 | 36.0464 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R05 | Fiber ring
RO-09 | AMM-SU-2639 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9127 | 35.7713 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R01 | Fiber ring
RO-09 | AMM-SU-2640 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9127 | 35.7781 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R01 | Fiber ring
RO-09 | AMM-SU-2641 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9133 | 35.7829 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R06 | Fiber ring
RO-09 | AMM-SU-2642 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9139 | 35.7904 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R06 | Fiber ring
RO-09 | AMM-SU-2643 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9133 | 35.7979 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R01 | Fiber ring
RO-09 | AMM-SU-2644 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9115 | 35.8041 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R03 | Fiber ring
RO-09 | AMM-SU-2645 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9121 | 35.8116 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R03 | Fiber ring
RO-09 | AMM-SU-2646 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9127 | 35.8164 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R04 | Fiber ring
RO-09 | AMM-SU-2656 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9121 | 36.0218 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R06 | Fiber ring
RO-09 | AMM-SU-2657 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9127 | 36.0293 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R06 | Fiber ring
RO-09 | AMM-SU-2658 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9127 | 36.0348 | 32 | 3 | HUB-AMM-78 | HUB-AMM-78-R06 | Fiber ring
RO-09 | AMM-SU-2659 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9127 | 36.0416 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R01 | Fiber ring
RO-09 | AMM-SU-2660 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9127 | 36.0512 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R02 | Fiber ring
RO-09 | AMM-SU-2661 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9166 | 35.7734 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R06 | Fiber ring
RO-09 | AMM-SU-2662 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9166 | 35.7802 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R05 | Fiber ring
RO-09 | AMM-SU-2663 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9184 | 35.7877 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R05 | Fiber ring
RO-09 | AMM-SU-2664 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9178 | 35.7925 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R05 | Fiber ring
RO-09 | AMM-SU-2665 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9178 | 35.802 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R04 | Fiber ring
RO-09 | AMM-SU-2666 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9178 | 35.8061 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R04 | Fiber ring
RO-09 | AMM-SU-2667 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9178 | 35.8157 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R04 | Fiber ring
RO-09 | AMM-SU-2678 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9184 | 36.0334 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R01 | Fiber ring
RO-09 | AMM-SU-2679 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.919 | 36.0396 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R01 | Fiber ring
RO-09 | AMM-SU-2680 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9184 | 36.0457 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R02 | Fiber ring
RO-09 | AMM-SU-2681 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9166 | 36.0532 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R02 | Fiber ring
RO-09 | AMM-SU-2682 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9229 | 35.7713 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R01 | Fiber ring
RO-09 | AMM-SU-2683 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9229 | 35.7781 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R02 | Fiber ring
RO-09 | AMM-SU-2684 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9217 | 35.7836 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R05 | Fiber ring
RO-09 | AMM-SU-2685 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9229 | 35.7918 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R05 | Fiber ring
RO-09 | AMM-SU-2686 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9217 | 35.7972 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R05 | Fiber ring
RO-09 | AMM-SU-2687 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9235 | 35.8034 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R04 | Fiber ring
RO-09 | AMM-SU-2688 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9229 | 35.8095 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R04 | Fiber ring
RO-09 | AMM-SU-2696 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9241 | 36.0293 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R01 | Fiber ring
RO-09 | AMM-SU-2697 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9241 | 36.043 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R01 | Fiber ring
RO-09 | AMM-SU-2698 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9229 | 36.0485 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R02 | Fiber ring
RO-09 | AMM-SU-2699 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.928 | 35.7652 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R01 | Fiber ring
RO-09 | AMM-SU-2700 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.928 | 35.7747 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R01 | Fiber ring
RO-09 | AMM-SU-2701 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.928 | 35.7815 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R02 | Fiber ring
RO-09 | AMM-SU-2702 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9274 | 35.7877 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R02 | Fiber ring
RO-09 | AMM-SU-2703 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.928 | 35.7952 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R05 | Fiber ring
RO-09 | AMM-SU-2704 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9268 | 35.8007 | 32 | 3 | HUB-AMM-25 | HUB-AMM-25-R04 | Fiber ring
RO-09 | AMM-SU-2712 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9268 | 36.0396 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R01 | Fiber ring
RO-09 | AMM-SU-2713 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.928 | 36.0457 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R01 | Fiber ring
RO-09 | AMM-SU-2714 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.928 | 36.0532 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R02 | Fiber ring
RO-09 | AMM-SU-2715 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9343 | 35.7631 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R01 | Fiber ring
RO-09 | AMM-SU-2716 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9331 | 35.7686 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R01 | Fiber ring
RO-09 | AMM-SU-2717 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9319 | 35.7768 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R02 | Fiber ring
RO-09 | AMM-SU-2718 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9337 | 35.7843 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R02 | Fiber ring
RO-09 | AMM-SU-2719 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9319 | 35.7904 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R02 | Fiber ring
RO-09 | AMM-SU-2720 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9319 | 35.7972 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R02 | Fiber ring
RO-09 | AMM-SU-2726 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9331 | 36.0512 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R01 | Fiber ring
RO-09 | AMM-SU-2727 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9331 | 36.058 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R02 | Fiber ring
RO-09 | AMM-SU-2728 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9382 | 35.7652 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R01 | Fiber ring
RO-09 | AMM-SU-2729 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9388 | 35.7727 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R01 | Fiber ring
RO-09 | AMM-SU-2730 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9394 | 35.7802 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R01 | Fiber ring
RO-09 | AMM-SU-2731 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9394 | 35.787 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R03 | Fiber ring
RO-09 | AMM-SU-2732 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9388 | 35.7931 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R03 | Fiber ring
RO-09 | AMM-SU-2737 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9382 | 36.045 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R04 | Fiber ring
RO-09 | AMM-SU-2738 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9382 | 36.0614 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R02 | Fiber ring
RO-09 | AMM-SU-2739 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9444 | 35.7631 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R05 | Fiber ring
RO-09 | AMM-SU-2740 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9433 | 35.7686 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R05 | Fiber ring
RO-09 | AMM-SU-2741 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9433 | 35.7781 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R04 | Fiber ring
RO-09 | AMM-SU-2742 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9444 | 35.7836 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R03 | Fiber ring
RO-09 | AMM-SU-2743 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9433 | 35.7904 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R03 | Fiber ring
RO-09 | AMM-SU-2744 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9433 | 35.7986 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R03 | Fiber ring
RO-09 | AMM-SU-2747 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9444 | 36.0362 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R04 | Fiber ring
RO-09 | AMM-SU-2748 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9433 | 36.0444 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R04 | Fiber ring
RO-09 | AMM-SU-2749 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9427 | 36.0505 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R03 | Fiber ring
RO-09 | AMM-SU-2750 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9433 | 36.058 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R03 | Fiber ring
RO-09 | AMM-SU-2751 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9489 | 35.7604 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R05 | Fiber ring
RO-09 | AMM-SU-2752 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9484 | 35.7652 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R04 | Fiber ring
RO-09 | AMM-SU-2753 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9484 | 35.772 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R04 | Fiber ring
RO-09 | AMM-SU-2754 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9484 | 35.7815 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R04 | Fiber ring
RO-09 | AMM-SU-2755 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9495 | 35.787 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R03 | Fiber ring
RO-09 | AMM-SU-2756 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9495 | 35.7938 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R03 | Fiber ring
RO-09 | AMM-SU-2760 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9495 | 36.0396 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R04 | Fiber ring
RO-09 | AMM-SU-2761 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9484 | 36.0478 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R04 | Fiber ring
RO-09 | AMM-SU-2762 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9495 | 36.0532 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R03 | Fiber ring
RO-09 | AMM-SU-2763 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9484 | 36.0614 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R03 | Fiber ring
RO-09 | AMM-SU-2764 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9535 | 35.7576 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R01 | Fiber ring
RO-09 | AMM-SU-2765 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9529 | 35.7624 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R02 | Fiber ring
RO-09 | AMM-SU-2766 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.954 | 35.7693 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R02 | Fiber ring
RO-09 | AMM-SU-2767 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.954 | 35.7775 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R04 | Fiber ring
RO-09 | AMM-SU-2768 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9535 | 35.785 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R04 | Fiber ring
RO-09 | AMM-SU-2769 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9535 | 35.7891 | 32 | 3 | HUB-AMM-67 | HUB-AMM-67-R04 | Fiber ring
RO-09 | AMM-SU-2774 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9535 | 36.0437 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R04 | Fiber ring
RO-09 | AMM-SU-2775 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9529 | 36.0505 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R03 | Fiber ring
RO-09 | AMM-SU-2776 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9529 | 36.0573 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R03 | Fiber ring
RO-09 | AMM-SU-2777 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9535 | 36.0621 | 32 | 3 | HUB-AMM-10 | HUB-AMM-10-R03 | Fiber ring
RO-09 | AMM-SU-2778 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9585 | 35.7611 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R01 | Fiber ring
RO-09 | AMM-SU-2779 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.958 | 35.7672 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R02 | Fiber ring
RO-09 | AMM-SU-2780 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9597 | 35.7734 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R02 | Fiber ring
RO-09 | AMM-SU-2781 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9597 | 35.7802 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R02 | Fiber ring
RO-09 | AMM-SU-2782 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9597 | 35.787 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R03 | Fiber ring
RO-09 | AMM-SU-2790 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 31.9642 | 35.757 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R01 | Fiber ring
RO-09 | AMM-SU-2791 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9636 | 35.7645 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R01 | Fiber ring
RO-09 | AMM-SU-2792 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9648 | 35.7699 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R02 | Fiber ring
RO-09 | AMM-SU-2793 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9648 | 35.7768 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R02 | Fiber ring
RO-09 | AMM-SU-2794 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9648 | 35.7836 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R03 | Fiber ring
RO-09 | AMM-SU-2800 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 31.9675 | 35.7529 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R01 | Fiber ring
RO-09 | AMM-SU-2801 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 31.9675 | 35.7597 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R01 | Fiber ring
RO-09 | AMM-SU-2802 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9687 | 35.7679 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R01 | Fiber ring
RO-09 | AMM-SU-2803 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9699 | 35.7734 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R01 | Fiber ring
RO-09 | AMM-SU-2804 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9699 | 35.7802 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R03 | Fiber ring
RO-09 | AMM-SU-2805 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9699 | 35.787 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R03 | Fiber ring
RO-09 | AMM-SU-2812 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 31.9732 | 35.757 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R05 | Fiber ring
RO-09 | AMM-SU-2813 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 31.975 | 35.7631 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R05 | Fiber ring
RO-09 | AMM-SU-2814 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 31.9738 | 35.7713 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R04 | Fiber ring
RO-09 | AMM-SU-2815 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9744 | 35.7761 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R04 | Fiber ring
RO-09 | AMM-SU-2816 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9726 | 35.7836 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R03 | Fiber ring
RO-09 | AMM-SU-2817 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.975 | 35.7904 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R03 | Fiber ring
RO-09 | AMM-SU-2823 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 31.9801 | 35.7529 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R05 | Fiber ring
RO-09 | AMM-SU-2824 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 31.9789 | 35.7611 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R05 | Fiber ring
RO-09 | AMM-SU-2825 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 31.9789 | 35.7679 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R05 | Fiber ring
RO-09 | AMM-SU-2826 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 31.9777 | 35.7734 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R04 | Fiber ring
RO-09 | AMM-SU-2827 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 31.9801 | 35.7802 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R04 | Fiber ring
RO-09 | AMM-SU-2828 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9801 | 35.787 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R03 | Fiber ring
RO-09 | AMM-SU-2835 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 31.9834 | 35.757 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R05 | Fiber ring
RO-09 | AMM-SU-2836 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 31.984 | 35.7645 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R05 | Fiber ring
RO-09 | AMM-SU-2837 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 31.984 | 35.7713 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R04 | Fiber ring
RO-09 | AMM-SU-2838 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 31.984 | 35.7781 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R04 | Fiber ring
RO-09 | AMM-SU-2839 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 31.9852 | 35.7836 | 32 | 3 | HUB-AMM-34 | HUB-AMM-34-R04 | Fiber ring
RO-09 | AMM-SU-2847 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 31.9891 | 35.7611 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R01 | Fiber ring
RO-09 | AMM-SU-2848 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 31.9891 | 35.7679 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R01 | Fiber ring
RO-09 | AMM-SU-2849 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 31.9891 | 35.7747 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R02 | Fiber ring
RO-09 | AMM-SU-2850 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 31.9885 | 35.7802 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R02 | Fiber ring
RO-09 | AMM-SU-2860 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 31.9942 | 35.7645 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R01 | Fiber ring
RO-09 | AMM-SU-2861 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 31.9953 | 35.7699 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R02 | Fiber ring
RO-09 | AMM-SU-2862 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 31.9942 | 35.7781 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R02 | Fiber ring
RO-09 | AMM-SU-2863 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 31.9942 | 35.785 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R02 | Fiber ring
RO-09 | AMM-SU-2873 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0004 | 35.7597 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R01 | Fiber ring
RO-09 | AMM-SU-2874 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0004 | 35.7665 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R01 | Fiber ring
RO-09 | AMM-SU-2875 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 31.9987 | 35.7727 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R02 | Fiber ring
RO-09 | AMM-SU-2876 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 31.9987 | 35.7809 | 38 | 3 | HUB-AMM-43 | HUB-AMM-43-R02 | Fiber ring
RO-09 | AMM-SU-2877 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 31.9993 | 35.7884 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R03 | Fiber ring
RO-09 | AMM-SU-2888 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0044 | 35.7576 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R01 | Fiber ring
RO-09 | AMM-SU-2889 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0049 | 35.7638 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R01 | Fiber ring
RO-09 | AMM-SU-2890 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0055 | 35.7699 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R01 | Fiber ring
RO-09 | AMM-SU-2891 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0044 | 35.7781 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R03 | Fiber ring
RO-09 | AMM-SU-2892 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0044 | 35.7836 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R03 | Fiber ring
RO-09 | AMM-SU-2893 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0038 | 35.7911 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R03 | Fiber ring
RO-09 | AMM-SU-2903 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0095 | 35.7611 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R05 | Fiber ring
RO-09 | AMM-SU-2904 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0083 | 35.7665 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R05 | Fiber ring
RO-09 | AMM-SU-2905 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0106 | 35.7734 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R04 | Fiber ring
RO-09 | AMM-SU-2906 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0106 | 35.7802 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R03 | Fiber ring
RO-09 | AMM-SU-2907 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0089 | 35.7863 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R03 | Fiber ring
RO-09 | AMM-SU-2908 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0083 | 35.7938 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R03 | Fiber ring
RO-09 | AMM-SU-2921 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0145 | 35.7645 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R05 | Fiber ring
RO-09 | AMM-SU-2922 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0145 | 35.7713 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R04 | Fiber ring
RO-09 | AMM-SU-2923 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0134 | 35.7768 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R04 | Fiber ring
RO-09 | AMM-SU-2924 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0157 | 35.7836 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R04 | Fiber ring
RO-09 | AMM-SU-2925 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0157 | 35.7904 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R04 | Fiber ring
RO-09 | AMM-SU-2943 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0208 | 35.7597 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R05 | Fiber ring
RO-09 | AMM-SU-2944 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0196 | 35.7679 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R05 | Fiber ring
RO-09 | AMM-SU-2945 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0196 | 35.7747 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R04 | Fiber ring
RO-09 | AMM-SU-2946 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0185 | 35.7802 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R04 | Fiber ring
RO-09 | AMM-SU-2968 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0253 | 35.7638 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R05 | Fiber ring
RO-09 | AMM-SU-2969 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0247 | 35.7713 | 32 | 3 | HUB-AMM-43 | HUB-AMM-43-R05 | Fiber ring
RO-09 | AMM-SU-3055 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0412 | 35.9508 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R01 | Fiber ring
RO-09 | AMM-SU-3056 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0412 | 35.9577 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R02 | Fiber ring
RO-09 | AMM-SU-3057 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.04 | 35.9631 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R02 | Fiber ring
RO-09 | AMM-SU-3059 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0406 | 35.9788 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R02 | Fiber ring
RO-09 | AMM-SU-3065 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0394 | 36.0184 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R01 | Fiber ring
RO-09 | AMM-SU-3084 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0457 | 35.9481 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R01 | Fiber ring
RO-09 | AMM-SU-3085 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0451 | 35.9529 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R01 | Fiber ring
RO-09 | AMM-SU-3086 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0457 | 35.9618 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R02 | Fiber ring
RO-09 | AMM-SU-3087 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0463 | 35.9679 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R02 | Fiber ring
RO-09 | AMM-SU-3088 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0463 | 35.9747 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R02 | Fiber ring
RO-09 | AMM-SU-3089 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0457 | 35.9809 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R03 | Fiber ring
RO-09 | AMM-SU-3093 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0445 | 36.0089 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R01 | Fiber ring
RO-09 | AMM-SU-3094 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0451 | 36.0143 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R01 | Fiber ring
RO-09 | AMM-SU-3095 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0439 | 36.0225 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R01 | Fiber ring
RO-09 | AMM-SU-3124 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0513 | 35.9372 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R01 | Fiber ring
RO-09 | AMM-SU-3125 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0513 | 35.944 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R01 | Fiber ring
RO-09 | AMM-SU-3126 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0502 | 35.9495 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R01 | Fiber ring
RO-09 | AMM-SU-3127 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0513 | 35.9577 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R01 | Fiber ring
RO-09 | AMM-SU-3128 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0496 | 35.9638 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R02 | Fiber ring
RO-09 | AMM-SU-3129 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0513 | 35.9713 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R03 | Fiber ring
RO-09 | AMM-SU-3130 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0513 | 35.9781 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R03 | Fiber ring
RO-09 | AMM-SU-3131 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0502 | 35.9836 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R03 | Fiber ring
RO-09 | AMM-SU-3132 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0513 | 35.9986 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R03 | Fiber ring
RO-09 | AMM-SU-3133 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0513 | 36.0055 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R03 | Fiber ring
RO-09 | AMM-SU-3134 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0502 | 36.0177 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R01 | Fiber ring
RO-09 | AMM-SU-3135 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0508 | 36.0252 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R01 | Fiber ring
RO-09 | AMM-SU-3136 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0496 | 36.0321 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R01 | Fiber ring
RO-09 | AMM-SU-3137 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0502 | 36.0382 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R01 | Fiber ring
RO-09 | AMM-SU-3163 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0564 | 35.9269 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R02 | Fiber ring
RO-09 | AMM-SU-3164 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0547 | 35.9344 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R02 | Fiber ring
RO-09 | AMM-SU-3165 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0564 | 35.9406 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R06 | Fiber ring
RO-09 | AMM-SU-3166 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0553 | 35.9461 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R06 | Fiber ring
RO-09 | AMM-SU-3167 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0553 | 35.9624 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R01 | Fiber ring
RO-09 | AMM-SU-3168 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0553 | 35.9679 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R03 | Fiber ring
RO-09 | AMM-SU-3169 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0553 | 35.9734 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R03 | Fiber ring
RO-09 | AMM-SU-3170 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0553 | 35.9802 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R04 | Fiber ring
RO-09 | AMM-SU-3171 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0541 | 35.9884 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R03 | Fiber ring
RO-09 | AMM-SU-3172 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0547 | 35.9945 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R03 | Fiber ring
RO-09 | AMM-SU-3173 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0541 | 36.002 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R03 | Fiber ring
RO-09 | AMM-SU-3174 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0564 | 36.0225 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R02 | Fiber ring
RO-09 | AMM-SU-3175 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0564 | 36.0293 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R02 | Fiber ring
RO-09 | AMM-SU-3176 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0564 | 36.0362 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R02 | Fiber ring
RO-09 | AMM-SU-3201 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0603 | 35.9181 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R01 | Fiber ring
RO-09 | AMM-SU-3202 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0603 | 35.9242 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R01 | Fiber ring
RO-09 | AMM-SU-3203 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0603 | 35.929 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R02 | Fiber ring
RO-09 | AMM-SU-3204 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0615 | 35.9372 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R02 | Fiber ring
RO-09 | AMM-SU-3205 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0592 | 35.944 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R06 | Fiber ring
RO-09 | AMM-SU-3206 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0615 | 35.9508 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R06 | Fiber ring
RO-09 | AMM-SU-3207 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0603 | 35.9645 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R05 | Fiber ring
RO-09 | AMM-SU-3208 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0609 | 35.9706 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R04 | Fiber ring
RO-09 | AMM-SU-3209 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0592 | 35.9781 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R04 | Fiber ring
RO-09 | AMM-SU-3210 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0603 | 35.9836 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R04 | Fiber ring
RO-09 | AMM-SU-3211 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0592 | 35.9918 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R03 | Fiber ring
RO-09 | AMM-SU-3212 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0598 | 36.0184 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R03 | Fiber ring
RO-09 | AMM-SU-3213 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0598 | 36.0266 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R02 | Fiber ring
RO-09 | AMM-SU-3214 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0592 | 36.0328 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R02 | Fiber ring
RO-09 | AMM-SU-3235 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0666 | 35.9133 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R01 | Fiber ring
RO-09 | AMM-SU-3236 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0649 | 35.9208 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R01 | Fiber ring
RO-09 | AMM-SU-3237 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0654 | 35.9283 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R02 | Fiber ring
RO-09 | AMM-SU-3238 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0654 | 35.9324 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R02 | Fiber ring
RO-09 | AMM-SU-3239 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0666 | 35.9406 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R03 | Fiber ring
RO-09 | AMM-SU-3240 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0666 | 35.9474 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R06 | Fiber ring
RO-09 | AMM-SU-3241 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0666 | 35.9543 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R05 | Fiber ring
RO-09 | AMM-SU-3242 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.066 | 35.9611 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R05 | Fiber ring
RO-09 | AMM-SU-3243 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0666 | 35.9679 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R04 | Fiber ring
RO-09 | AMM-SU-3244 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0654 | 35.9734 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R04 | Fiber ring
RO-09 | AMM-SU-3245 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.066 | 36.0218 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R02 | Fiber ring
RO-09 | AMM-SU-3246 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0654 | 36.028 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R02 | Fiber ring
RO-09 | AMM-SU-3249 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0654 | 36.1386 | 32 | 3 | HUB-AMM-18 | HUB-AMM-18-R01 | Fiber ring
RO-09 | AMM-SU-3250 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0649 | 36.1515 | 32 | 3 | HUB-AMM-18 | HUB-AMM-18-R01 | Fiber ring
RO-09 | AMM-SU-3260 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0699 | 35.8901 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R01 | Fiber ring
RO-09 | AMM-SU-3261 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0705 | 35.8962 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R02 | Fiber ring
RO-09 | AMM-SU-3262 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0694 | 35.9031 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R01 | Fiber ring
RO-09 | AMM-SU-3263 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0694 | 35.9099 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R01 | Fiber ring
RO-09 | AMM-SU-3264 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0705 | 35.9153 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R06 | Fiber ring
RO-09 | AMM-SU-3265 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0705 | 35.9249 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R01 | Fiber ring
RO-09 | AMM-SU-3266 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0717 | 35.9304 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R03 | Fiber ring
RO-09 | AMM-SU-3267 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0705 | 35.9385 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R03 | Fiber ring
RO-09 | AMM-SU-3268 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0694 | 35.944 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R03 | Fiber ring
RO-09 | AMM-SU-3269 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0699 | 35.9502 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R06 | Fiber ring
RO-09 | AMM-SU-3270 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0705 | 35.9563 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R05 | Fiber ring
RO-09 | AMM-SU-3271 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0699 | 35.9638 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R05 | Fiber ring
RO-09 | AMM-SU-3272 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0711 | 35.972 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R04 | Fiber ring
RO-09 | AMM-SU-3273 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0705 | 36.0177 | 32 | 3 | HUB-AMM-26 | HUB-AMM-26-R03 | Fiber ring
RO-09 | AMM-SU-3278 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0717 | 36.142 | 32 | 3 | HUB-AMM-18 | HUB-AMM-18-R01 | Fiber ring
RO-09 | AMM-SU-3279 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0694 | 36.1488 | 32 | 3 | HUB-AMM-18 | HUB-AMM-18-R01 | Fiber ring
RO-09 | AMM-SU-3288 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0756 | 35.8805 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R01 | Fiber ring
RO-09 | AMM-SU-3289 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0762 | 35.8853 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R01 | Fiber ring
RO-09 | AMM-SU-3290 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0756 | 35.8914 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R02 | Fiber ring
RO-09 | AMM-SU-3291 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0744 | 35.8996 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R02 | Fiber ring
RO-09 | AMM-SU-3292 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.075 | 35.9072 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R06 | Fiber ring
RO-09 | AMM-SU-3293 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0756 | 35.9119 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R06 | Fiber ring
RO-09 | AMM-SU-3294 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0744 | 35.9201 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R06 | Fiber ring
RO-09 | AMM-SU-3295 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0756 | 35.9283 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R04 | Fiber ring
RO-09 | AMM-SU-3296 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0756 | 35.9351 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R04 | Fiber ring
RO-09 | AMM-SU-3297 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0762 | 35.9399 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R04 | Fiber ring
RO-09 | AMM-SU-3298 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.075 | 35.9467 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R03 | Fiber ring
RO-09 | AMM-SU-3299 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.075 | 35.9549 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R05 | Fiber ring
RO-09 | AMM-SU-3300 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0744 | 35.9611 | 32 | 3 | HUB-AMM-32 | HUB-AMM-32-R05 | Fiber ring
RO-09 | AMM-SU-3305 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0756 | 36.1386 | 32 | 3 | HUB-AMM-18 | HUB-AMM-18-R01 | Fiber ring
RO-09 | AMM-SU-3306 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0756 | 36.1467 | 32 | 3 | HUB-AMM-18 | HUB-AMM-18-R02 | Fiber ring
RO-09 | AMM-SU-3307 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0762 | 36.1529 | 32 | 3 | HUB-AMM-18 | HUB-AMM-18-R02 | Fiber ring
RO-09 | AMM-SU-3314 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0795 | 35.8689 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R01 | Fiber ring
RO-09 | AMM-SU-3315 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0795 | 35.8757 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R01 | Fiber ring
RO-09 | AMM-SU-3316 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0807 | 35.8839 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R01 | Fiber ring
RO-09 | AMM-SU-3317 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0807 | 35.888 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R01 | Fiber ring
RO-09 | AMM-SU-3318 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0807 | 35.8949 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R02 | Fiber ring
RO-09 | AMM-SU-3319 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0819 | 35.9031 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R02 | Fiber ring
RO-09 | AMM-SU-3320 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0807 | 35.9085 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R06 | Fiber ring
RO-09 | AMM-SU-3321 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0795 | 35.9167 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R06 | Fiber ring
RO-09 | AMM-SU-3322 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0795 | 35.9235 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R05 | Fiber ring
RO-09 | AMM-SU-3323 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0807 | 35.9317 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R05 | Fiber ring
RO-09 | AMM-SU-3324 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0807 | 35.9385 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R04 | Fiber ring
RO-09 | AMM-SU-3325 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0795 | 35.944 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R04 | Fiber ring
RO-09 | AMM-SU-3326 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0795 | 35.9508 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R03 | Fiber ring
RO-09 | AMM-SU-3332 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0795 | 36.1352 | 32 | 3 | HUB-AMM-18 | HUB-AMM-18-R01 | Fiber ring
RO-09 | AMM-SU-3333 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0807 | 36.1406 | 32 | 3 | HUB-AMM-18 | HUB-AMM-18-R01 | Fiber ring
RO-09 | AMM-SU-3334 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0795 | 36.1488 | 32 | 3 | HUB-AMM-18 | HUB-AMM-18-R02 | Fiber ring
RO-09 | AMM-SU-3341 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0846 | 35.8655 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R05 | Fiber ring
RO-09 | AMM-SU-3342 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0846 | 35.8723 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R05 | Fiber ring
RO-09 | AMM-SU-3343 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0846 | 35.8792 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R05 | Fiber ring
RO-09 | AMM-SU-3344 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0846 | 35.886 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R01 | Fiber ring
RO-09 | AMM-SU-3345 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0846 | 35.8928 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R02 | Fiber ring
RO-09 | AMM-SU-3346 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.087 | 35.8996 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R03 | Fiber ring
RO-09 | AMM-SU-3347 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.087 | 35.9065 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R02 | Fiber ring
RO-09 | AMM-SU-3348 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.087 | 35.9133 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R05 | Fiber ring
RO-09 | AMM-SU-3349 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0858 | 35.9188 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R05 | Fiber ring
RO-09 | AMM-SU-3350 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0858 | 35.9351 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R04 | Fiber ring
RO-09 | AMM-SU-3355 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0852 | 36.1311 | 32 | 3 | HUB-AMM-18 | HUB-AMM-18-R03 | Fiber ring
RO-09 | AMM-SU-3356 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0846 | 36.1386 | 32 | 3 | HUB-AMM-18 | HUB-AMM-18-R03 | Fiber ring
RO-09 | AMM-SU-3357 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0858 | 36.1454 | 32 | 3 | HUB-AMM-18 | HUB-AMM-18-R02 | Fiber ring
RO-09 | AMM-SU-3363 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0897 | 35.8689 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R05 | Fiber ring
RO-09 | AMM-SU-3364 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0909 | 35.8771 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R04 | Fiber ring
RO-09 | AMM-SU-3365 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0909 | 35.8839 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R04 | Fiber ring
RO-09 | AMM-SU-3366 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0909 | 35.8908 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R03 | Fiber ring
RO-09 | AMM-SU-3367 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0909 | 35.8976 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R03 | Fiber ring
RO-09 | AMM-SU-3368 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0897 | 35.9031 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R03 | Fiber ring
RO-09 | AMM-SU-3369 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0897 | 35.9099 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R03 | Fiber ring
RO-09 | AMM-SU-3370 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0897 | 35.9167 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R05 | Fiber ring
RO-09 | AMM-SU-3371 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0897 | 35.9235 | 32 | 3 | HUB-AMM-53 | HUB-AMM-53-R05 | Fiber ring
RO-09 | AMM-SU-3375 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0909 | 36.1338 | 32 | 3 | HUB-AMM-18 | HUB-AMM-18-R03 | Fiber ring
RO-09 | AMM-SU-3376 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0909 | 36.142 | 32 | 3 | HUB-AMM-18 | HUB-AMM-18-R02 | Fiber ring
RO-09 | AMM-SU-3377 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.096 | 35.8669 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R04 | Fiber ring
RO-09 | AMM-SU-3378 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.096 | 35.8737 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R04 | Fiber ring
RO-09 | AMM-SU-3379 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.096 | 35.8805 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R04 | Fiber ring
RO-09 | AMM-SU-3380 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.096 | 35.8873 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R04 | Fiber ring
RO-09 | AMM-SU-3381 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.096 | 35.8942 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R04 | Fiber ring
RO-09 | AMM-SU-3382 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.096 | 35.901 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R03 | Fiber ring
RO-09 | AMM-SU-3383 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0972 | 35.9065 | 32 | 3 | HUB-AMM-68 | HUB-AMM-68-R03 | Fiber ring
RO-09 | AMM-SU-3385 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0948 | 36.1386 | 32 | 3 | HUB-AMM-18 | HUB-AMM-18-R03 | Fiber ring
RO-09 | AMM-SU-3386 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0948 | 36.1454 | 32 | 3 | HUB-AMM-18 | HUB-AMM-18-R02 | Fiber ring
RO-09 | AMM-U-2043 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0811 | 36.1291 | 30 | 3 | HUB-AMM-18 | HUB-AMM-18-R03 | Fiber ring
RO-09 | AMM-U-2065 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0846 | 36.1263 | 30 | 3 | HUB-AMM-18 | HUB-AMM-18-R03 | Fiber ring
RO-09 | HWY-HW-0084 | HW | Lattice tower | Highway | Amman | 31.9962 | 36.3333 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0085 | HW | Lattice tower | Highway | Amman | 31.9772 | 36.4034 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0086 | HW | Lattice tower | Highway | Amman | 31.9623 | 36.4763 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0087 | HW | Lattice tower | Highway | Zarqa | 31.9458 | 36.5509 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0088 | HW | Lattice tower | Highway | Zarqa | 31.9277 | 36.62 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0089 | HW | Lattice tower | Highway | Zarqa | 31.9127 | 36.6892 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0090 | HW | Lattice tower | Highway | Zarqa | 31.8978 | 36.7583 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0091 | HW | Lattice tower | Highway | Zarqa | 31.93 | 36.8769 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0092 | HW | Lattice tower | Highway | Mafraq | 31.9793 | 36.9231 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0093 | HW | Lattice tower | Highway | Mafraq | 32.0286 | 36.9729 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0094 | HW | Lattice tower | Highway | Mafraq | 32.081 | 37.0155 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0095 | HW | Lattice tower | Highway | Mafraq | 32.1302 | 37.0616 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0096 | HW | Lattice tower | Highway | Mafraq | 32.1763 | 37.1078 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0097 | HW | Lattice tower | Highway | Mafraq | 32.315 | 36.4632 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0098 | HW | Lattice tower | Highway | Mafraq | 32.307 | 36.5362 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0099 | HW | Lattice tower | Highway | Mafraq | 32.2983 | 36.609 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0100 | HW | Lattice tower | Highway | Mafraq | 32.2848 | 36.6844 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0101 | HW | Lattice tower | Highway | Mafraq | 32.2744 | 36.7526 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0102 | HW | Lattice tower | Highway | Mafraq | 32.2608 | 36.8244 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0103 | HW | Lattice tower | Highway | Mafraq | 32.2441 | 36.8962 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0104 | HW | Lattice tower | Highway | Mafraq | 32.2306 | 36.968 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0105 | HW | Lattice tower | Highway | Mafraq | 32.2202 | 37.0398 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0106 | HW | Lattice tower | Highway | Mafraq | 32.2178 | 37.1795 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0107 | HW | Lattice tower | Highway | Mafraq | 32.238 | 37.2504 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0108 | HW | Lattice tower | Highway | Mafraq | 32.2598 | 37.3194 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0109 | HW | Lattice tower | Highway | Mafraq | 32.2816 | 37.3884 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0110 | HW | Lattice tower | Highway | Mafraq | 32.3034 | 37.4611 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0111 | HW | Lattice tower | Highway | Mafraq | 32.3252 | 37.5265 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0112 | HW | Lattice tower | Highway | Mafraq | 32.347 | 37.5955 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0113 | HW | Lattice tower | Highway | Mafraq | 32.372 | 37.6645 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0114 | HW | Lattice tower | Highway | Mafraq | 32.3867 | 37.7326 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0115 | HW | Lattice tower | Highway | Mafraq | 32.4084 | 37.8052 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0116 | HW | Lattice tower | Highway | Mafraq | 32.4254 | 37.876 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0117 | HW | Lattice tower | Highway | Mafraq | 32.4424 | 37.9468 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0118 | HW | Lattice tower | Highway | Mafraq | 32.4562 | 38.0177 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0119 | HW | Lattice tower | Highway | Mafraq | 32.4732 | 38.0885 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0120 | HW | Lattice tower | Highway | Mafraq | 32.4902 | 38.1593 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0121 | HW | Lattice tower | Highway | Mafraq | 32.5135 | 38.227 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0122 | HW | Lattice tower | Highway | Mafraq | 32.5453 | 38.2906 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0123 | HW | Lattice tower | Highway | Mafraq | 32.5755 | 38.3523 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0124 | HW | Lattice tower | Highway | Mafraq | 32.6089 | 38.4177 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0125 | HW | Lattice tower | Highway | Mafraq | 32.6407 | 38.4813 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0126 | HW | Lattice tower | Highway | Mafraq | 32.6724 | 38.5449 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0127 | HW | Lattice tower | Highway | Mafraq | 32.7042 | 38.6085 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0128 | HW | Lattice tower | Highway | Mafraq | 32.736 | 38.672 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0129 | HW | Lattice tower | Highway | Mafraq | 32.7678 | 38.7356 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0130 | HW | Lattice tower | Highway | Mafraq | 32.7996 | 38.7992 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0131 | HW | Lattice tower | Highway | Aqaba | 29.7725 | 35.3293 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0132 | HW | Lattice tower | Highway | Aqaba | 29.7224 | 35.3735 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0133 | HW | Lattice tower | Highway | Aqaba | 29.6697 | 35.4041 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | HWY-HW-0134 | HW | Lattice tower | Highway | Aqaba | 29.6071 | 35.415 | 45 | 2 |  |  | Fiber (backbone add/drop spur)
RO-09 | IRB-SU-0540 | SU | Monopole / greenfield | Irbid | Irbid | 32.4982 | 35.9167 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R01 | Fiber ring
RO-09 | IRB-SU-0558 | SU | Monopole / greenfield | Irbid | Irbid | 32.5021 | 35.9133 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R01 | Fiber ring
RO-09 | IRB-SU-0559 | SU | Monopole / greenfield | Irbid | Irbid | 32.5033 | 35.9201 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R02 | Fiber ring
RO-09 | IRB-SU-0570 | SU | Monopole / greenfield | Irbid | Irbid | 32.5084 | 35.9085 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R01 | Fiber ring
RO-09 | IRB-SU-0571 | SU | Monopole / greenfield | Irbid | Irbid | 32.5072 | 35.9167 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R01 | Fiber ring
RO-09 | IRB-SU-0572 | SU | Monopole / greenfield | Irbid | Irbid | 32.5084 | 35.9235 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R02 | Fiber ring
RO-09 | IRB-SU-0573 | SU | Monopole / greenfield | Irbid | Irbid | 32.5084 | 35.9304 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R02 | Fiber ring
RO-09 | IRB-SU-0581 | SU | Monopole / greenfield | Irbid | Irbid | 32.5134 | 35.9065 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R01 | Fiber ring
RO-09 | IRB-SU-0582 | SU | Monopole / greenfield | Irbid | Irbid | 32.5123 | 35.9133 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R01 | Fiber ring
RO-09 | IRB-SU-0583 | SU | Monopole / greenfield | Irbid | Irbid | 32.5134 | 35.9201 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R01 | Fiber ring
RO-09 | IRB-SU-0584 | SU | Monopole / greenfield | Irbid | Irbid | 32.5134 | 35.9269 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R02 | Fiber ring
RO-09 | IRB-SU-0585 | SU | Monopole / greenfield | Irbid | Irbid | 32.5134 | 35.9338 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R02 | Fiber ring
RO-09 | IRB-SU-0590 | SU | Monopole / greenfield | Irbid | Irbid | 32.5185 | 35.9031 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R04 | Fiber ring
RO-09 | IRB-SU-0591 | SU | Monopole / greenfield | Irbid | Irbid | 32.5185 | 35.9099 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R04 | Fiber ring
RO-09 | IRB-SU-0592 | SU | Monopole / greenfield | Irbid | Irbid | 32.5185 | 35.9153 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R04 | Fiber ring
RO-09 | IRB-SU-0593 | SU | Monopole / greenfield | Irbid | Irbid | 32.5185 | 35.9222 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R01 | Fiber ring
RO-09 | IRB-SU-0594 | SU | Monopole / greenfield | Irbid | Irbid | 32.5185 | 35.9317 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R02 | Fiber ring
RO-09 | IRB-SU-0595 | SU | Monopole / greenfield | Irbid | Irbid | 32.5185 | 35.9372 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R02 | Fiber ring
RO-09 | IRB-SU-0600 | SU | Monopole / greenfield | Irbid | Irbid | 32.523 | 35.9058 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R04 | Fiber ring
RO-09 | IRB-SU-0601 | SU | Monopole / greenfield | Irbid | Irbid | 32.5236 | 35.9133 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R04 | Fiber ring
RO-09 | IRB-SU-0602 | SU | Monopole / greenfield | Irbid | Irbid | 32.5236 | 35.9201 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R03 | Fiber ring
RO-09 | IRB-SU-0603 | SU | Monopole / greenfield | Irbid | Irbid | 32.5236 | 35.9269 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R03 | Fiber ring
RO-09 | IRB-SU-0604 | SU | Monopole / greenfield | Irbid | Irbid | 32.5236 | 35.9338 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R03 | Fiber ring
RO-09 | IRB-SU-0609 | SU | Monopole / greenfield | Irbid | Irbid | 32.5275 | 35.9099 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R04 | Fiber ring
RO-09 | IRB-SU-0610 | SU | Monopole / greenfield | Irbid | Irbid | 32.5287 | 35.9153 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R03 | Fiber ring
RO-09 | IRB-SU-0611 | SU | Monopole / greenfield | Irbid | Irbid | 32.5287 | 35.9235 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R03 | Fiber ring
RO-09 | IRB-SU-0620 | SU | Monopole / greenfield | Irbid | Irbid | 32.5332 | 35.9263 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R03 | Fiber ring
RO-09 | IRB-SU-0621 | SU | Monopole / greenfield | Irbid | Irbid | 32.5338 | 35.9338 | 32 | 3 | HUB-IRB-02 | HUB-IRB-02-R03 | Fiber ring
RO-09 | IRB-SU-0633 | SU | Monopole / greenfield | Irbid | Irbid | 32.5389 | 35.9304 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R01 | Fiber ring
RO-09 | IRB-SU-0634 | SU | Monopole / greenfield | Irbid | Irbid | 32.5389 | 35.9372 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R02 | Fiber ring
RO-09 | IRB-SU-0648 | SU | Monopole / greenfield | Irbid | Irbid | 32.544 | 35.9283 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R01 | Fiber ring
RO-09 | IRB-SU-0649 | SU | Monopole / greenfield | Irbid | Irbid | 32.544 | 35.9338 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R02 | Fiber ring
RO-09 | IRB-SU-0650 | SU | Monopole / greenfield | Irbid | Irbid | 32.544 | 35.9406 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R02 | Fiber ring
RO-09 | IRB-SU-0660 | SU | Monopole / greenfield | Irbid | Irbid | 32.5485 | 35.9242 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R01 | Fiber ring
RO-09 | IRB-SU-0661 | SU | Monopole / greenfield | Irbid | Irbid | 32.5497 | 35.931 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R02 | Fiber ring
RO-09 | IRB-SU-0669 | SU | Monopole / greenfield | Irbid | Irbid | 32.5542 | 35.9147 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R01 | Fiber ring
RO-09 | IRB-SU-0670 | SU | Monopole / greenfield | Irbid | Irbid | 32.5542 | 35.9201 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R01 | Fiber ring
RO-09 | IRB-SU-0671 | SU | Monopole / greenfield | Irbid | Irbid | 32.553 | 35.9269 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R01 | Fiber ring
RO-09 | IRB-SU-0672 | SU | Monopole / greenfield | Irbid | Irbid | 32.5542 | 35.9338 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R02 | Fiber ring
RO-09 | IRB-SU-0673 | SU | Monopole / greenfield | Irbid | Irbid | 32.5542 | 35.9406 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R02 | Fiber ring
RO-09 | IRB-SU-0680 | SU | Monopole / greenfield | Irbid | Irbid | 32.5604 | 35.9099 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R05 | Fiber ring
RO-09 | IRB-SU-0681 | SU | Monopole / greenfield | Irbid | Irbid | 32.5581 | 35.9167 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R01 | Fiber ring
RO-09 | IRB-SU-0682 | SU | Monopole / greenfield | Irbid | Irbid | 32.5587 | 35.9242 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R01 | Fiber ring
RO-09 | IRB-SU-0683 | SU | Monopole / greenfield | Irbid | Irbid | 32.5587 | 35.9297 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R02 | Fiber ring
RO-09 | IRB-SU-0684 | SU | Monopole / greenfield | Irbid | Irbid | 32.5593 | 35.9372 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R03 | Fiber ring
RO-09 | IRB-SU-0691 | SU | Rooftop | Irbid | Irbid | 32.5649 | 35.9072 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R05 | Fiber ring
RO-09 | IRB-SU-0692 | SU | Monopole / greenfield | Irbid | Irbid | 32.5655 | 35.9133 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R05 | Fiber ring
RO-09 | IRB-SU-0693 | SU | Monopole / greenfield | Irbid | Irbid | 32.5655 | 35.9201 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R04 | Fiber ring
RO-09 | IRB-SU-0694 | SU | Monopole / greenfield | Irbid | Irbid | 32.5655 | 35.9269 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R03 | Fiber ring
RO-09 | IRB-SU-0695 | SU | Monopole / greenfield | Irbid | Irbid | 32.5632 | 35.9338 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R03 | Fiber ring
RO-09 | IRB-SU-0702 | SU | Rooftop | Irbid | Irbid | 32.5694 | 35.9113 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R05 | Fiber ring
RO-09 | IRB-SU-0703 | SU | Rooftop | Irbid | Irbid | 32.5688 | 35.916 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R04 | Fiber ring
RO-09 | IRB-SU-0704 | SU | Monopole / greenfield | Irbid | Irbid | 32.5706 | 35.9235 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R03 | Fiber ring
RO-09 | IRB-SU-0705 | SU | Monopole / greenfield | Irbid | Irbid | 32.5706 | 35.9304 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R03 | Fiber ring
RO-09 | IRB-SU-0714 | SU | Monopole / greenfield | Irbid | Irbid | 32.5745 | 35.9065 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R04 | Fiber ring
RO-09 | IRB-SU-0715 | SU | Monopole / greenfield | Irbid | Irbid | 32.5745 | 35.9147 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R04 | Fiber ring
RO-09 | IRB-SU-0716 | SU | Monopole / greenfield | Irbid | Irbid | 32.5734 | 35.9201 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R03 | Fiber ring
RO-09 | IRB-SU-0717 | SU | Monopole / greenfield | Irbid | Irbid | 32.5739 | 35.9263 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R03 | Fiber ring
RO-09 | IRB-SU-0727 | SU | Monopole / greenfield | Irbid | Irbid | 32.5796 | 35.9099 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R04 | Fiber ring
RO-09 | IRB-SU-0728 | SU | Monopole / greenfield | Irbid | Irbid | 32.5796 | 35.9181 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R04 | Fiber ring
RO-09 | IRB-SU-0747 | SU | Monopole / greenfield | Irbid | Irbid | 32.5847 | 35.9133 | 32 | 3 | HUB-IRB-16 | HUB-IRB-16-R04 | Fiber ring
RO-09 | RUR-R-0098 | R | Lattice tower | Rural | Amman | 31.3057 | 35.8456 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-09 | RUR-R-0099 | R | Lattice tower | Rural | Amman | 31.3057 | 35.8871 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-09 | RUR-R-0105 | R | Lattice tower | Rural | Amman | 31.3385 | 35.8663 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-09 | RUR-R-0106 | R | Lattice tower | Rural | Amman | 31.3434 | 35.9136 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-09 | RUR-R-0111 | R | Lattice tower | Rural | Amman | 31.3762 | 35.8399 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-09 | RUR-R-0112 | R | Lattice tower | Rural | Amman | 31.3713 | 35.8928 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-09 | RUR-R-0113 | R | Lattice tower | Rural | Amman | 31.3713 | 35.9401 | 45 | 3 |  |  | Microwave 6-18 GHz XPIC 2x1G-4x1G
RO-10 | AMM-SU-2169 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.704 | 35.9781 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R01 | Fiber ring
RO-10 | AMM-SU-2170 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.704 | 35.985 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R02 | Fiber ring
RO-10 | AMM-SU-2171 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7091 | 35.9747 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R01 | Fiber ring
RO-10 | AMM-SU-2172 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7091 | 35.9816 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R02 | Fiber ring
RO-10 | AMM-SU-2173 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7091 | 35.9884 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R02 | Fiber ring
RO-10 | AMM-SU-2174 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7091 | 35.9952 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R02 | Fiber ring
RO-10 | AMM-SU-2175 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7142 | 35.9713 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R01 | Fiber ring
RO-10 | AMM-SU-2176 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7142 | 35.9781 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R01 | Fiber ring
RO-10 | AMM-SU-2177 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7142 | 35.985 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R02 | Fiber ring
RO-10 | AMM-SU-2178 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7142 | 35.9918 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R02 | Fiber ring
RO-10 | AMM-SU-2179 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7142 | 35.9986 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R03 | Fiber ring
RO-10 | AMM-SU-2180 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7142 | 36.0123 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R03 | Fiber ring
RO-10 | AMM-SU-2181 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7193 | 35.9679 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R01 | Fiber ring
RO-10 | AMM-SU-2182 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7193 | 35.9761 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R01 | Fiber ring
RO-10 | AMM-SU-2183 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7193 | 35.9816 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R01 | Fiber ring
RO-10 | AMM-SU-2184 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.7193 | 35.9884 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R02 | Fiber ring
RO-10 | AMM-SU-2185 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7193 | 35.9952 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R03 | Fiber ring
RO-10 | AMM-SU-2186 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.7204 | 36.002 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R03 | Fiber ring
RO-10 | AMM-SU-2187 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7193 | 36.0089 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R03 | Fiber ring
RO-10 | AMM-SU-2188 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7204 | 36.0157 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R03 | Fiber ring
RO-10 | AMM-SU-2189 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7244 | 35.9713 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R07 | Fiber ring
RO-10 | AMM-SU-2190 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7244 | 35.9781 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R07 | Fiber ring
RO-10 | AMM-SU-2191 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.7238 | 35.9856 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R07 | Fiber ring
RO-10 | AMM-SU-2192 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.7238 | 35.9911 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R01 | Fiber ring
RO-10 | AMM-SU-2193 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7244 | 35.9986 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R04 | Fiber ring
RO-10 | AMM-SU-2194 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.7238 | 36.0055 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R03 | Fiber ring
RO-10 | AMM-SU-2195 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.7244 | 36.0123 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R04 | Fiber ring
RO-10 | AMM-SU-2196 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7244 | 36.0191 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R04 | Fiber ring
RO-10 | AMM-SU-2197 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7294 | 35.9816 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R07 | Fiber ring
RO-10 | AMM-SU-2198 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7294 | 35.9884 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R06 | Fiber ring
RO-10 | AMM-SU-2199 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7294 | 35.9952 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R05 | Fiber ring
RO-10 | AMM-SU-2200 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7294 | 36.002 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R04 | Fiber ring
RO-10 | AMM-SU-2201 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7294 | 36.0089 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R04 | Fiber ring
RO-10 | AMM-SU-2202 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7294 | 36.0157 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R04 | Fiber ring
RO-10 | AMM-SU-2203 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7345 | 35.9713 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R07 | Fiber ring
RO-10 | AMM-SU-2204 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7345 | 35.9781 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R07 | Fiber ring
RO-10 | AMM-SU-2205 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7345 | 35.985 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R06 | Fiber ring
RO-10 | AMM-SU-2206 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7345 | 35.9918 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R06 | Fiber ring
RO-10 | AMM-SU-2207 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7345 | 36 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R05 | Fiber ring
RO-10 | AMM-SU-2208 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7345 | 36.0055 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R05 | Fiber ring
RO-10 | AMM-SU-2209 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7345 | 36.0123 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R04 | Fiber ring
RO-10 | AMM-SU-2210 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7396 | 35.9747 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R07 | Fiber ring
RO-10 | AMM-SU-2211 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7396 | 35.9816 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R06 | Fiber ring
RO-10 | AMM-SU-2212 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7396 | 35.9884 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R06 | Fiber ring
RO-10 | AMM-SU-2213 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7408 | 35.9952 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R05 | Fiber ring
RO-10 | AMM-SU-2214 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7396 | 36.002 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R05 | Fiber ring
RO-10 | AMM-SU-2215 | SU | Rooftop | Amman-Zarqa Metro | Amman | 31.7402 | 36.0082 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R05 | Fiber ring
RO-10 | AMM-SU-2216 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7447 | 35.985 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R06 | Fiber ring
RO-10 | AMM-SU-2217 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7447 | 35.9918 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R06 | Fiber ring
RO-10 | AMM-SU-2218 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.7447 | 35.9986 | 32 | 3 | HUB-AMM-80 | HUB-AMM-80-R05 | Fiber ring
RO-10 | AMM-SU-2883 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 31.9981 | 36.0737 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R01 | Fiber ring
RO-10 | AMM-SU-2884 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 31.9981 | 36.0805 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R01 | Fiber ring
RO-10 | AMM-SU-2885 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 31.9993 | 36.086 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R01 | Fiber ring
RO-10 | AMM-SU-2886 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 31.9993 | 36.0956 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R02 | Fiber ring
RO-10 | AMM-SU-2887 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 31.9981 | 36.101 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R02 | Fiber ring
RO-10 | AMM-SU-2899 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0044 | 36.0771 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R01 | Fiber ring
RO-10 | AMM-SU-2900 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0044 | 36.0853 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R01 | Fiber ring
RO-10 | AMM-SU-2901 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0032 | 36.0908 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R01 | Fiber ring
RO-10 | AMM-SU-2902 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0038 | 36.0976 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R02 | Fiber ring
RO-10 | AMM-SU-2915 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0089 | 36.0812 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R01 | Fiber ring
RO-10 | AMM-SU-2916 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0095 | 36.0887 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R01 | Fiber ring
RO-10 | AMM-SU-2917 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0083 | 36.0942 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R02 | Fiber ring
RO-10 | AMM-SU-2918 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0095 | 36.1024 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R02 | Fiber ring
RO-10 | AMM-SU-2919 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0095 | 36.1133 | 32 | 3 | HUB-AMM-17 | HUB-AMM-17-R01 | Fiber ring
RO-10 | AMM-SU-2920 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0095 | 36.1208 | 32 | 3 | HUB-AMM-17 | HUB-AMM-17-R01 | Fiber ring
RO-10 | AMM-SU-2936 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0151 | 36.0846 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R03 | Fiber ring
RO-10 | AMM-SU-2937 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0145 | 36.0921 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R03 | Fiber ring
RO-10 | AMM-SU-2938 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.014 | 36.0969 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R02 | Fiber ring
RO-10 | AMM-SU-2939 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0145 | 36.1044 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R02 | Fiber ring
RO-10 | AMM-SU-2940 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.014 | 36.1106 | 32 | 3 | HUB-AMM-17 | HUB-AMM-17-R01 | Fiber ring
RO-10 | AMM-SU-2941 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0151 | 36.1188 | 32 | 3 | HUB-AMM-17 | HUB-AMM-17-R01 | Fiber ring
RO-10 | AMM-SU-2942 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0145 | 36.1249 | 32 | 3 | HUB-AMM-17 | HUB-AMM-17-R02 | Fiber ring
RO-10 | AMM-SU-2947 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0196 | 35.7884 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R02 | Fiber ring
RO-10 | AMM-SU-2948 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0208 | 35.7938 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R02 | Fiber ring
RO-10 | AMM-SU-2959 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0196 | 36.0819 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R03 | Fiber ring
RO-10 | AMM-SU-2960 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.0185 | 36.0874 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R03 | Fiber ring
RO-10 | AMM-SU-2961 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0196 | 36.0956 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R03 | Fiber ring
RO-10 | AMM-SU-2962 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0185 | 36.101 | 32 | 3 | HUB-AMM-12 | HUB-AMM-12-R03 | Fiber ring
RO-10 | AMM-SU-2963 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0185 | 36.1078 | 32 | 3 | HUB-AMM-17 | HUB-AMM-17-R01 | Fiber ring
RO-10 | AMM-SU-2964 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0196 | 36.116 | 32 | 3 | HUB-AMM-17 | HUB-AMM-17-R01 | Fiber ring
RO-10 | AMM-SU-2965 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0196 | 36.1215 | 32 | 3 | HUB-AMM-17 | HUB-AMM-17-R01 | Fiber ring
RO-10 | AMM-SU-2966 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0196 | 36.1283 | 32 | 3 | HUB-AMM-17 | HUB-AMM-17-R02 | Fiber ring
RO-10 | AMM-SU-2967 | SU | Monopole / greenfield | Amman-Zarqa Metro | Amman | 32.0196 | 36.1352 | 32 | 3 | HUB-AMM-17 | HUB-AMM-17-R02 | Fiber ring
RO-10 | AMM-SU-2970 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0259 | 35.7768 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R01 | Fiber ring
RO-10 | AMM-SU-2971 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0235 | 35.7836 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R02 | Fiber ring
RO-10 | AMM-SU-2972 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0235 | 35.7904 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R02 | Fiber ring
RO-10 | AMM-SU-2973 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0241 | 35.7966 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R03 | Fiber ring
RO-10 | AMM-SU-2990 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0259 | 36.1113 | 32 | 3 | HUB-AMM-17 | HUB-AMM-17-R03 | Fiber ring
RO-10 | AMM-SU-2991 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0253 | 36.1188 | 32 | 3 | HUB-AMM-17 | HUB-AMM-17-R01 | Fiber ring
RO-10 | AMM-SU-2992 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0247 | 36.1249 | 32 | 3 | HUB-AMM-17 | HUB-AMM-17-R02 | Fiber ring
RO-10 | AMM-SU-2993 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0247 | 36.1317 | 32 | 3 | HUB-AMM-17 | HUB-AMM-17-R02 | Fiber ring
RO-10 | AMM-SU-2994 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0247 | 36.1386 | 32 | 3 | HUB-AMM-17 | HUB-AMM-17-R02 | Fiber ring
RO-10 | AMM-SU-2995 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0286 | 35.7665 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R01 | Fiber ring
RO-10 | AMM-SU-2996 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0286 | 35.7734 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R01 | Fiber ring
RO-10 | AMM-SU-2997 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0286 | 35.7802 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R02 | Fiber ring
RO-10 | AMM-SU-2998 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0286 | 35.787 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R02 | Fiber ring
RO-10 | AMM-SU-2999 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0298 | 35.7938 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R03 | Fiber ring
RO-10 | AMM-SU-3000 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0298 | 35.802 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R03 | Fiber ring
RO-10 | AMM-SU-3014 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0304 | 36.114 | 32 | 3 | HUB-AMM-17 | HUB-AMM-17-R03 | Fiber ring
RO-10 | AMM-SU-3015 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0298 | 36.1215 | 32 | 3 | HUB-AMM-17 | HUB-AMM-17-R03 | Fiber ring
RO-10 | AMM-SU-3016 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0286 | 36.1283 | 32 | 3 | HUB-AMM-17 | HUB-AMM-17-R02 | Fiber ring
RO-10 | AMM-SU-3017 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0349 | 35.7686 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R01 | Fiber ring
RO-10 | AMM-SU-3018 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0355 | 35.7775 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R01 | Fiber ring
RO-10 | AMM-SU-3019 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0361 | 35.7836 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R01 | Fiber ring
RO-10 | AMM-SU-3020 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0343 | 35.7911 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R03 | Fiber ring
RO-10 | AMM-SU-3021 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0361 | 35.7972 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R03 | Fiber ring
RO-10 | AMM-SU-3022 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0349 | 35.8054 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R03 | Fiber ring
RO-10 | AMM-SU-3039 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0349 | 36.1195 | 32 | 3 | HUB-AMM-17 | HUB-AMM-17-R03 | Fiber ring
RO-10 | AMM-SU-3040 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0343 | 36.1242 | 32 | 3 | HUB-AMM-17 | HUB-AMM-17-R03 | Fiber ring
RO-10 | AMM-SU-3043 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0406 | 35.774 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R06 | Fiber ring
RO-10 | AMM-SU-3044 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0406 | 35.7809 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R06 | Fiber ring
RO-10 | AMM-SU-3045 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.04 | 35.787 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R01 | Fiber ring
RO-10 | AMM-SU-3046 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0394 | 35.7931 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R04 | Fiber ring
RO-10 | AMM-SU-3047 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.04 | 35.7993 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R04 | Fiber ring
RO-10 | AMM-SU-3048 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0388 | 35.8075 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R04 | Fiber ring
RO-10 | AMM-SU-3070 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0451 | 35.7768 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R06 | Fiber ring
RO-10 | AMM-SU-3071 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0439 | 35.7836 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R06 | Fiber ring
RO-10 | AMM-SU-3072 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0451 | 35.7904 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R05 | Fiber ring
RO-10 | AMM-SU-3073 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0451 | 35.7959 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R04 | Fiber ring
RO-10 | AMM-SU-3074 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0451 | 35.8027 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R04 | Fiber ring
RO-10 | AMM-SU-3103 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0496 | 35.7795 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R06 | Fiber ring
RO-10 | AMM-SU-3104 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0502 | 35.787 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R05 | Fiber ring
RO-10 | AMM-SU-3105 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0502 | 35.7952 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R05 | Fiber ring
RO-10 | AMM-SU-3106 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0502 | 35.7993 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R05 | Fiber ring
RO-10 | AMM-SU-3107 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0502 | 35.8061 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R04 | Fiber ring
RO-10 | AMM-SU-3142 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0564 | 35.7836 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R06 | Fiber ring
RO-10 | AMM-SU-3143 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0547 | 35.7904 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R05 | Fiber ring
RO-10 | AMM-SU-3144 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0541 | 35.7972 | 32 | 3 | HUB-AMM-75 | HUB-AMM-75-R05 | Fiber ring
RO-10 | AMM-SU-3145 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0553 | 35.8027 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R01 | Fiber ring
RO-10 | AMM-SU-3146 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0553 | 35.8109 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R02 | Fiber ring
RO-10 | AMM-SU-3182 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0609 | 35.7863 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R01 | Fiber ring
RO-10 | AMM-SU-3183 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0598 | 35.7945 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R01 | Fiber ring
RO-10 | AMM-SU-3184 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0615 | 35.8007 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R01 | Fiber ring
RO-10 | AMM-SU-3185 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0603 | 35.8061 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R02 | Fiber ring
RO-10 | AMM-SU-3186 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0603 | 35.8143 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R02 | Fiber ring
RO-10 | AMM-SU-3187 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0603 | 35.8198 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R02 | Fiber ring
RO-10 | AMM-SU-3220 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0654 | 35.7891 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R01 | Fiber ring
RO-10 | AMM-SU-3221 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0649 | 35.7979 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R01 | Fiber ring
RO-10 | AMM-SU-3222 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0654 | 35.8027 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R01 | Fiber ring
RO-10 | AMM-SU-3223 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.066 | 35.8102 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R02 | Fiber ring
RO-10 | AMM-SU-3224 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0643 | 35.8177 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R02 | Fiber ring
RO-10 | AMM-SU-3225 | SU | Rooftop | Amman-Zarqa Metro | Balqa | 32.0643 | 35.8246 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R02 | Fiber ring
RO-10 | AMM-SU-3251 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0705 | 35.802 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R05 | Fiber ring
RO-10 | AMM-SU-3252 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0705 | 35.8061 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R01 | Fiber ring
RO-10 | AMM-SU-3253 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0705 | 35.813 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R03 | Fiber ring
RO-10 | AMM-SU-3254 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0705 | 35.8198 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R03 | Fiber ring
RO-10 | AMM-SU-3280 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0756 | 35.7918 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R05 | Fiber ring
RO-10 | AMM-SU-3281 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0768 | 35.7972 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R05 | Fiber ring
RO-10 | AMM-SU-3282 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.075 | 35.8047 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R04 | Fiber ring
RO-10 | AMM-SU-3283 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0756 | 35.8095 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R04 | Fiber ring
RO-10 | AMM-SU-3284 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0756 | 35.8164 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R03 | Fiber ring
RO-10 | AMM-SU-3285 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0744 | 35.8246 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R03 | Fiber ring
RO-10 | AMM-SU-3308 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0801 | 35.7945 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R05 | Fiber ring
RO-10 | AMM-SU-3309 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0807 | 35.7993 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R05 | Fiber ring
RO-10 | AMM-SU-3310 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0795 | 35.8075 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R04 | Fiber ring
RO-10 | AMM-SU-3311 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0801 | 35.8136 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R03 | Fiber ring
RO-10 | AMM-SU-3312 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0801 | 35.8205 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R03 | Fiber ring
RO-10 | AMM-SU-3335 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0846 | 35.7972 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R05 | Fiber ring
RO-10 | AMM-SU-3336 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0858 | 35.8027 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R04 | Fiber ring
RO-10 | AMM-SU-3337 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0858 | 35.8095 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R04 | Fiber ring
RO-10 | AMM-SU-3338 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0852 | 35.817 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R03 | Fiber ring
RO-10 | AMM-SU-3358 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0915 | 35.815 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R04 | Fiber ring
RO-10 | AMM-SU-3359 | SU | Monopole / greenfield | Amman-Zarqa Metro | Balqa | 32.0909 | 35.8205 | 32 | 3 | HUB-AMM-48 | HUB-AMM-48-R04 | Fiber ring
RO-10 | AMM-SU-3384 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0954 | 36.1311 | 32 | 3 | HUB-AMM-09 | HUB-AMM-09-R01 | Fiber ring
RO-10 | AMM-SU-3387 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1011 | 36.045 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R01 | Fiber ring
RO-10 | AMM-SU-3388 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1005 | 36.0525 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R02 | Fiber ring
RO-10 | AMM-SU-3389 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0999 | 36.1283 | 32 | 3 | HUB-AMM-09 | HUB-AMM-09-R01 | Fiber ring
RO-10 | AMM-SU-3390 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1011 | 36.1352 | 32 | 3 | HUB-AMM-09 | HUB-AMM-09-R02 | Fiber ring
RO-10 | AMM-SU-3391 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1011 | 36.142 | 32 | 3 | HUB-AMM-09 | HUB-AMM-09-R02 | Fiber ring
RO-10 | AMM-SU-3392 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1073 | 36.0362 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R01 | Fiber ring
RO-10 | AMM-SU-3393 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1056 | 36.0437 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R01 | Fiber ring
RO-10 | AMM-SU-3394 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1062 | 36.0505 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R02 | Fiber ring
RO-10 | AMM-SU-3395 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1062 | 36.0553 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R02 | Fiber ring
RO-10 | AMM-SU-3396 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1062 | 36.1181 | 32 | 3 | HUB-AMM-09 | HUB-AMM-09-R01 | Fiber ring
RO-10 | AMM-SU-3397 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1073 | 36.1249 | 32 | 3 | HUB-AMM-09 | HUB-AMM-09-R01 | Fiber ring
RO-10 | AMM-SU-3398 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1062 | 36.1304 | 32 | 3 | HUB-AMM-09 | HUB-AMM-09-R02 | Fiber ring
RO-10 | AMM-SU-3399 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1062 | 36.1386 | 32 | 3 | HUB-AMM-09 | HUB-AMM-09-R02 | Fiber ring
RO-10 | AMM-SU-3400 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1101 | 36.0396 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R01 | Fiber ring
RO-10 | AMM-SU-3401 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1113 | 36.0457 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R01 | Fiber ring
RO-10 | AMM-SU-3402 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1107 | 36.0525 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R01 | Fiber ring
RO-10 | AMM-SU-3403 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1113 | 36.0614 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R02 | Fiber ring
RO-10 | AMM-SU-3404 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1101 | 36.0669 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R02 | Fiber ring
RO-10 | AMM-SU-3405 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1124 | 36.1147 | 32 | 3 | HUB-AMM-09 | HUB-AMM-09-R03 | Fiber ring
RO-10 | AMM-SU-3406 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1113 | 36.1229 | 32 | 3 | HUB-AMM-09 | HUB-AMM-09-R01 | Fiber ring
RO-10 | AMM-SU-3407 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1113 | 36.1283 | 32 | 3 | HUB-AMM-09 | HUB-AMM-09-R02 | Fiber ring
RO-10 | AMM-SU-3408 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1175 | 36.043 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R04 | Fiber ring
RO-10 | AMM-SU-3409 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1175 | 36.0498 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R04 | Fiber ring
RO-10 | AMM-SU-3410 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1175 | 36.0566 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R01 | Fiber ring
RO-10 | AMM-SU-3411 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1163 | 36.0648 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R02 | Fiber ring
RO-10 | AMM-SU-3412 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1163 | 36.0717 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R03 | Fiber ring
RO-10 | AMM-SU-3418 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1163 | 36.1113 | 32 | 3 | HUB-AMM-09 | HUB-AMM-09-R03 | Fiber ring
RO-10 | AMM-SU-3419 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1163 | 36.1181 | 32 | 3 | HUB-AMM-09 | HUB-AMM-09-R03 | Fiber ring
RO-10 | AMM-SU-3420 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1163 | 36.1249 | 32 | 3 | HUB-AMM-09 | HUB-AMM-09-R02 | Fiber ring
RO-10 | AMM-SU-3421 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1215 | 36.0519 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R04 | Fiber ring
RO-10 | AMM-SU-3422 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.122 | 36.0594 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R04 | Fiber ring
RO-10 | AMM-SU-3423 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1215 | 36.0669 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R03 | Fiber ring
RO-10 | AMM-SU-3424 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1203 | 36.0737 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R03 | Fiber ring
RO-10 | AMM-SU-3429 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1215 | 36.1147 | 32 | 3 | HUB-AMM-09 | HUB-AMM-09-R03 | Fiber ring
RO-10 | AMM-SU-3430 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1203 | 36.1215 | 32 | 3 | HUB-AMM-09 | HUB-AMM-09-R03 | Fiber ring
RO-10 | AMM-SU-3431 | SU | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.1265 | 36.0553 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R04 | Fiber ring
RO-10 | AMM-SU-3432 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1265 | 36.0648 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R03 | Fiber ring
RO-10 | AMM-SU-3433 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1265 | 36.0717 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R03 | Fiber ring
RO-10 | AMM-SU-3437 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1254 | 36.1113 | 32 | 3 | HUB-AMM-09 | HUB-AMM-09-R03 | Fiber ring
RO-10 | AMM-SU-3438 | SU | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1316 | 36.0737 | 32 | 3 | HUB-AMM-08 | HUB-AMM-08-R03 | Fiber ring
RO-10 | AMM-U-1784 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.0388 | 36.1159 | 30 | 3 | HUB-AMM-17 | HUB-AMM-17-R03 | Fiber ring
RO-10 | AMM-U-1785 | U | Monopole / greenfield | Amman-Zarqa Metro | Zarqa | 32.038 | 36.1197 | 30 | 3 | HUB-AMM-17 | HUB-AMM-17-R03 | Fiber ring
RO-10 | AMM-U-2153 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1058 | 36.1126 | 30 | 3 | HUB-AMM-09 | HUB-AMM-09-R01 | Fiber ring
RO-10 | AMM-U-2162 | U | Rooftop | Amman-Zarqa Metro | Zarqa | 32.1093 | 36.1093 | 30 | 3 | HUB-AMM-09 | HUB-AMM-09-R01 | Fiber ring
RO-10 | AQB-SU-0150 | SU | Rooftop | Aqaba | Aqaba | 29.3724 | 34.9692 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R01 | Fiber ring
RO-10 | AQB-SU-0151 | SU | Rooftop | Aqaba | Aqaba | 29.3724 | 34.9733 | 35 | 3 | HUB-AQB-01 | HUB-AQB-01-R02 | Fiber ring
RO-10 | AQB-SU-0152 | SU | Rooftop | Aqaba | Aqaba | 29.3712 | 34.9815 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R02 | Fiber ring
RO-10 | AQB-SU-0153 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.3724 | 34.9897 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R02 | Fiber ring
RO-10 | AQB-SU-0154 | SU | Rooftop | Aqaba | Aqaba | 29.3775 | 34.9726 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R01 | Fiber ring
RO-10 | AQB-SU-0155 | SU | Rooftop | Aqaba | Aqaba | 29.3775 | 34.9794 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R02 | Fiber ring
RO-10 | AQB-SU-0156 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.3769 | 34.9856 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R02 | Fiber ring
RO-10 | AQB-SU-0157 | SU | Rooftop | Aqaba | Aqaba | 29.3826 | 34.976 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R01 | Fiber ring
RO-10 | AQB-SU-0158 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.3837 | 34.9815 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R02 | Fiber ring
RO-10 | AQB-SU-0159 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.3826 | 34.9897 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R03 | Fiber ring
RO-10 | AQB-SU-0160 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.3877 | 34.9713 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R01 | Fiber ring
RO-10 | AQB-SU-0161 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.3865 | 34.9781 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R01 | Fiber ring
RO-10 | AQB-SU-0162 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.3877 | 34.9863 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R02 | Fiber ring
RO-10 | AQB-SU-0163 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.3888 | 34.9917 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R03 | Fiber ring
RO-10 | AQB-SU-0164 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.3916 | 34.9747 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R01 | Fiber ring
RO-10 | AQB-SU-0165 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.3916 | 34.9815 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R01 | Fiber ring
RO-10 | AQB-SU-0166 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.3922 | 34.989 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R03 | Fiber ring
RO-10 | AQB-SU-0167 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.3927 | 34.9965 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R03 | Fiber ring
RO-10 | AQB-SU-0168 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.3978 | 34.9794 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R05 | Fiber ring
RO-10 | AQB-SU-0169 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.3972 | 34.9856 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R01 | Fiber ring
RO-10 | AQB-SU-0170 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4029 | 34.9815 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R05 | Fiber ring
RO-10 | AQB-SU-0171 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4017 | 34.9883 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R04 | Fiber ring
RO-10 | AQB-SU-0172 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4023 | 34.9958 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R03 | Fiber ring
RO-10 | AQB-SU-0173 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.408 | 34.9863 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R04 | Fiber ring
RO-10 | AQB-SU-0174 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.408 | 34.9931 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R03 | Fiber ring
RO-10 | AQB-SU-0175 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4125 | 34.9822 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R05 | Fiber ring
RO-10 | AQB-SU-0176 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4143 | 34.9883 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R04 | Fiber ring
RO-10 | AQB-SU-0177 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4131 | 34.9965 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R03 | Fiber ring
RO-10 | AQB-SU-0178 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4188 | 34.9856 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R05 | Fiber ring
RO-10 | AQB-SU-0179 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4182 | 34.9931 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R04 | Fiber ring
RO-10 | AQB-SU-0180 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4194 | 34.9986 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R04 | Fiber ring
RO-10 | AQB-SU-0181 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4233 | 34.9829 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R05 | Fiber ring
RO-10 | AQB-SU-0182 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4233 | 34.9897 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R04 | Fiber ring
RO-10 | AQB-SU-0183 | SU | Monopole / greenfield | Aqaba | Aqaba | 29.4233 | 34.9965 | 32 | 3 | HUB-AQB-01 | HUB-AQB-01-R04 | Fiber ring
RO-10 | AZR-SU-0001 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8618 | 36.8212 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R01 | Fiber ring
RO-10 | AZR-SU-0002 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8618 | 36.828 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R01 | Fiber ring
RO-10 | AZR-SU-0003 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8618 | 36.8349 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R01 | Fiber ring
RO-10 | AZR-SU-0004 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8669 | 36.8178 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R01 | Fiber ring
RO-10 | AZR-SU-0005 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8669 | 36.8246 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R01 | Fiber ring
RO-10 | AZR-SU-0006 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8669 | 36.8314 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R02 | Fiber ring
RO-10 | AZR-SU-0007 | SU | Monopole / greenfield | Azraq | Zarqa | 31.872 | 36.8144 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R01 | Fiber ring
RO-10 | AZR-SU-0008 | SU | Monopole / greenfield | Azraq | Zarqa | 31.872 | 36.8212 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R01 | Fiber ring
RO-10 | AZR-SU-0009 | SU | Monopole / greenfield | Azraq | Zarqa | 31.872 | 36.828 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R02 | Fiber ring
RO-10 | AZR-SU-0010 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8726 | 36.8349 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R02 | Fiber ring
RO-10 | AZR-SU-0011 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8771 | 36.8123 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R05 | Fiber ring
RO-10 | AZR-SU-0012 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8771 | 36.8178 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R05 | Fiber ring
RO-10 | AZR-SU-0013 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8771 | 36.8246 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R01 | Fiber ring
RO-10 | AZR-SU-0014 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8777 | 36.8321 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R02 | Fiber ring
RO-10 | AZR-SU-0015 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8771 | 36.8383 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R02 | Fiber ring
RO-10 | AZR-SU-0016 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8771 | 36.8451 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R02 | Fiber ring
RO-10 | AZR-SU-0017 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8771 | 36.8519 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R02 | Fiber ring
RO-10 | AZR-SU-0018 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8822 | 36.8075 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R05 | Fiber ring
RO-10 | AZR-SU-0019 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8822 | 36.8144 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R04 | Fiber ring
RO-10 | AZR-SU-0020 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8822 | 36.8212 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R04 | Fiber ring
RO-10 | AZR-SU-0021 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8822 | 36.828 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R04 | Fiber ring
RO-10 | AZR-SU-0022 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8822 | 36.8349 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R03 | Fiber ring
RO-10 | AZR-SU-0023 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8822 | 36.8417 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R03 | Fiber ring
RO-10 | AZR-SU-0024 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8822 | 36.8485 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R03 | Fiber ring
RO-10 | AZR-SU-0025 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8873 | 36.811 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R04 | Fiber ring
RO-10 | AZR-SU-0026 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8873 | 36.8178 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R04 | Fiber ring
RO-10 | AZR-SU-0027 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8879 | 36.8253 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R04 | Fiber ring
RO-10 | AZR-SU-0028 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8873 | 36.8314 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R03 | Fiber ring
RO-10 | AZR-SU-0029 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8873 | 36.8383 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R03 | Fiber ring
RO-10 | AZR-SU-0030 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8924 | 36.828 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R04 | Fiber ring
RO-10 | AZR-SU-0031 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8929 | 36.8355 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R03 | Fiber ring
RO-10 | AZR-SU-0032 | SU | Monopole / greenfield | Azraq | Zarqa | 31.8924 | 36.8417 | 32 | 3 | HUB-AZR-01 | HUB-AZR-01-R03 | Fiber ring
RO-10 | DEI-SU-0001 | SU | Monopole / greenfield | Deir Alla | Balqa | 32.1735 | 35.6163 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R01 | Fiber ring
RO-10 | DEI-SU-0002 | SU | Monopole / greenfield | Deir Alla | Balqa | 32.1724 | 35.6245 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R01 | Fiber ring
RO-10 | DEI-SU-0003 | SU | Monopole / greenfield | Deir Alla | Balqa | 32.1774 | 35.6129 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R01 | Fiber ring
RO-10 | DEI-SU-0004 | SU | Monopole / greenfield | Deir Alla | Balqa | 32.178 | 35.6204 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R01 | Fiber ring
RO-10 | DEI-SU-0005 | SU | Monopole / greenfield | Deir Alla | Balqa | 32.1774 | 35.6279 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R02 | Fiber ring
RO-10 | DEI-SU-0006 | SU | Monopole / greenfield | Deir Alla | Balqa | 32.1825 | 35.6095 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R01 | Fiber ring
RO-10 | DEI-SU-0007 | SU | Rooftop | Deir Alla | Balqa | 32.1825 | 35.6177 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R01 | Fiber ring
RO-10 | DEI-SU-0008 | SU | Monopole / greenfield | Deir Alla | Balqa | 32.1825 | 35.6232 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R02 | Fiber ring
RO-10 | DEI-SU-0009 | SU | Monopole / greenfield | Deir Alla | Balqa | 32.1825 | 35.63 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R02 | Fiber ring
RO-10 | DEI-SU-0010 | SU | Monopole / greenfield | Deir Alla | Balqa | 32.1876 | 35.6143 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R04 | Fiber ring
RO-10 | DEI-SU-0011 | SU | Monopole / greenfield | Deir Alla | Balqa | 32.1876 | 35.6211 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R01 | Fiber ring
RO-10 | DEI-SU-0012 | SU | Monopole / greenfield | Deir Alla | Balqa | 32.1876 | 35.6266 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R02 | Fiber ring
RO-10 | DEI-SU-0013 | SU | Monopole / greenfield | Deir Alla | Ajloun | 32.1882 | 35.6327 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R02 | Fiber ring
RO-10 | DEI-SU-0014 | SU | Monopole / greenfield | Deir Alla | Balqa | 32.1927 | 35.6095 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R04 | Fiber ring
RO-10 | DEI-SU-0015 | SU | Monopole / greenfield | Deir Alla | Balqa | 32.1927 | 35.6163 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R04 | Fiber ring
RO-10 | DEI-SU-0016 | SU | Monopole / greenfield | Deir Alla | Balqa | 32.1927 | 35.6232 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R03 | Fiber ring
RO-10 | DEI-SU-0017 | SU | Monopole / greenfield | Deir Alla | Ajloun | 32.1927 | 35.63 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R02 | Fiber ring
RO-10 | DEI-SU-0018 | SU | Monopole / greenfield | Deir Alla | Balqa | 32.1978 | 35.6143 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R04 | Fiber ring
RO-10 | DEI-SU-0019 | SU | Monopole / greenfield | Deir Alla | Balqa | 32.1966 | 35.6198 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R03 | Fiber ring
RO-10 | DEI-SU-0020 | SU | Monopole / greenfield | Deir Alla | Balqa | 32.1966 | 35.6266 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R03 | Fiber ring
RO-10 | DEI-SU-0021 | SU | Monopole / greenfield | Deir Alla | Irbid | 32.2029 | 35.6163 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R04 | Fiber ring
RO-10 | DEI-SU-0022 | SU | Monopole / greenfield | Deir Alla | Irbid | 32.2029 | 35.6232 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R03 | Fiber ring
RO-10 | DEI-SU-0023 | SU | Monopole / greenfield | Deir Alla | Ajloun | 32.2029 | 35.63 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R03 | Fiber ring
RO-10 | DEI-SU-0024 | SU | Monopole / greenfield | Deir Alla | Irbid | 32.208 | 35.6211 | 32 | 3 | HUB-DEI-01 | HUB-DEI-01-R03 | Fiber ring
RO-10 | GHO-SU-0001 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.0161 | 35.4771 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R01 | Fiber ring
RO-10 | GHO-SU-0002 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.0218 | 35.4662 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R01 | Fiber ring
RO-10 | GHO-SU-0003 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.0218 | 35.473 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R01 | Fiber ring
RO-10 | GHO-SU-0004 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.0206 | 35.4798 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R02 | Fiber ring
RO-10 | GHO-SU-0005 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.0269 | 35.4559 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R01 | Fiber ring
RO-10 | GHO-SU-0006 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.0269 | 35.4627 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R01 | Fiber ring
RO-10 | GHO-SU-0007 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.0269 | 35.4696 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R01 | Fiber ring
RO-10 | GHO-SU-0008 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.0269 | 35.4764 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R02 | Fiber ring
RO-10 | GHO-SU-0009 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.0269 | 35.4846 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R02 | Fiber ring
RO-10 | GHO-SU-0010 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.032 | 35.4662 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R04 | Fiber ring
RO-10 | GHO-SU-0011 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.032 | 35.473 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R01 | Fiber ring
RO-10 | GHO-SU-0012 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.032 | 35.4812 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R02 | Fiber ring
RO-10 | GHO-SU-0013 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.0371 | 35.4559 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R04 | Fiber ring
RO-10 | GHO-SU-0014 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.0371 | 35.4627 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R04 | Fiber ring
RO-10 | GHO-SU-0015 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.0371 | 35.4696 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R03 | Fiber ring
RO-10 | GHO-SU-0016 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.0371 | 35.4764 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R03 | Fiber ring
RO-10 | GHO-SU-0017 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.0371 | 35.4846 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R02 | Fiber ring
RO-10 | GHO-SU-0018 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.0422 | 35.4593 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R04 | Fiber ring
RO-10 | GHO-SU-0019 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.0422 | 35.4662 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R03 | Fiber ring
RO-10 | GHO-SU-0020 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.041 | 35.473 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R03 | Fiber ring
RO-10 | GHO-SU-0021 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.0422 | 35.4798 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R02 | Fiber ring
RO-10 | GHO-SU-0022 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.0473 | 35.4764 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R03 | Fiber ring
RO-10 | GHO-SU-0023 | SU | Monopole / greenfield | Ghor Safi | Karak | 31.0518 | 35.4737 | 32 | 3 | HUB-GHO-01 | HUB-GHO-01-R03 | Fiber ring
RO-10 | IRB-SU-0492 | SU | Monopole / greenfield | Irbid | Irbid | 32.4835 | 35.8457 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R01 | Fiber ring
RO-10 | IRB-SU-0493 | SU | Monopole / greenfield | Irbid | Irbid | 32.4835 | 35.8525 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R01 | Fiber ring
RO-10 | IRB-SU-0494 | SU | Monopole / greenfield | Irbid | Irbid | 32.4829 | 35.8573 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R01 | Fiber ring
RO-10 | IRB-SU-0495 | SU | Monopole / greenfield | Irbid | Irbid | 32.4817 | 35.8655 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R02 | Fiber ring
RO-10 | IRB-SU-0496 | SU | Monopole / greenfield | Irbid | Irbid | 32.4835 | 35.8717 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R02 | Fiber ring
RO-10 | IRB-SU-0498 | SU | Monopole / greenfield | Irbid | Irbid | 32.4868 | 35.828 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R01 | Fiber ring
RO-10 | IRB-SU-0499 | SU | Monopole / greenfield | Irbid | Irbid | 32.488 | 35.8362 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R01 | Fiber ring
RO-10 | IRB-SU-0500 | SU | Monopole / greenfield | Irbid | Irbid | 32.488 | 35.8402 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R01 | Fiber ring
RO-10 | IRB-SU-0501 | SU | Monopole / greenfield | Irbid | Irbid | 32.488 | 35.8498 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R01 | Fiber ring
RO-10 | IRB-SU-0502 | SU | Monopole / greenfield | Irbid | Irbid | 32.4868 | 35.8553 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R01 | Fiber ring
RO-10 | IRB-SU-0503 | SU | Monopole / greenfield | Irbid | Irbid | 32.488 | 35.8607 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R01 | Fiber ring
RO-10 | IRB-SU-0504 | SU | Monopole / greenfield | Irbid | Irbid | 32.488 | 35.8689 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R02 | Fiber ring
RO-10 | IRB-SU-0505 | SU | Monopole / greenfield | Irbid | Irbid | 32.488 | 35.8744 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R02 | Fiber ring
RO-10 | IRB-SU-0509 | SU | Monopole / greenfield | Irbid | Irbid | 32.4943 | 35.8109 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R01 | Fiber ring
RO-10 | IRB-SU-0510 | SU | Monopole / greenfield | Irbid | Irbid | 32.4931 | 35.8177 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R01 | Fiber ring
RO-10 | IRB-SU-0511 | SU | Monopole / greenfield | Irbid | Irbid | 32.4931 | 35.8246 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R01 | Fiber ring
RO-10 | IRB-SU-0512 | SU | Monopole / greenfield | Irbid | Irbid | 32.4931 | 35.83 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R01 | Fiber ring
RO-10 | IRB-SU-0513 | SU | Monopole / greenfield | Irbid | Irbid | 32.4919 | 35.8382 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R01 | Fiber ring
RO-10 | IRB-SU-0514 | SU | Monopole / greenfield | Irbid | Irbid | 32.4925 | 35.8457 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R04 | Fiber ring
RO-10 | IRB-SU-0515 | SU | Monopole / greenfield | Irbid | Irbid | 32.4919 | 35.8519 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R04 | Fiber ring
RO-10 | IRB-SU-0516 | SU | Monopole / greenfield | Irbid | Irbid | 32.4919 | 35.8587 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R01 | Fiber ring
RO-10 | IRB-SU-0517 | SU | Monopole / greenfield | Irbid | Irbid | 32.4931 | 35.8669 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R02 | Fiber ring
RO-10 | IRB-SU-0518 | SU | Monopole / greenfield | Irbid | Irbid | 32.4931 | 35.871 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R02 | Fiber ring
RO-10 | IRB-SU-0524 | SU | Monopole / greenfield | Irbid | Irbid | 32.4976 | 35.8082 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R03 | Fiber ring
RO-10 | IRB-SU-0525 | SU | Monopole / greenfield | Irbid | Irbid | 32.4982 | 35.8157 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R03 | Fiber ring
RO-10 | IRB-SU-0526 | SU | Monopole / greenfield | Irbid | Irbid | 32.497 | 35.8211 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R01 | Fiber ring
RO-10 | IRB-SU-0527 | SU | Monopole / greenfield | Irbid | Irbid | 32.4982 | 35.828 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R02 | Fiber ring
RO-10 | IRB-SU-0528 | SU | Monopole / greenfield | Irbid | Irbid | 32.4993 | 35.8348 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R02 | Fiber ring
RO-10 | IRB-SU-0529 | SU | Monopole / greenfield | Irbid | Irbid | 32.497 | 35.8416 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R04 | Fiber ring
RO-10 | IRB-SU-0530 | SU | Monopole / greenfield | Irbid | Irbid | 32.4993 | 35.8484 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R04 | Fiber ring
RO-10 | IRB-SU-0531 | SU | Monopole / greenfield | Irbid | Irbid | 32.497 | 35.8553 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R03 | Fiber ring
RO-10 | IRB-SU-0532 | SU | Monopole / greenfield | Irbid | Irbid | 32.4976 | 35.8614 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R03 | Fiber ring
RO-10 | IRB-SU-0533 | SU | Monopole / greenfield | Irbid | Irbid | 32.4982 | 35.8676 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R02 | Fiber ring
RO-10 | IRB-SU-0541 | SU | Monopole / greenfield | Irbid | Irbid | 32.5038 | 35.7979 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R01 | Fiber ring
RO-10 | IRB-SU-0542 | SU | Monopole / greenfield | Irbid | Irbid | 32.5033 | 35.8054 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R03 | Fiber ring
RO-10 | IRB-SU-0543 | SU | Monopole / greenfield | Irbid | Irbid | 32.5021 | 35.8109 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R03 | Fiber ring
RO-10 | IRB-SU-0544 | SU | Monopole / greenfield | Irbid | Irbid | 32.5021 | 35.8177 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R03 | Fiber ring
RO-10 | IRB-SU-0545 | SU | Monopole / greenfield | Irbid | Irbid | 32.5021 | 35.8246 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R02 | Fiber ring
RO-10 | IRB-SU-0546 | SU | Monopole / greenfield | Irbid | Irbid | 32.5027 | 35.8321 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R02 | Fiber ring
RO-10 | IRB-SU-0547 | SU | Monopole / greenfield | Irbid | Irbid | 32.5033 | 35.8368 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R02 | Fiber ring
RO-10 | IRB-SU-0548 | SU | Monopole / greenfield | Irbid | Irbid | 32.5033 | 35.845 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R03 | Fiber ring
RO-10 | IRB-SU-0549 | SU | Monopole / greenfield | Irbid | Irbid | 32.5021 | 35.8519 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R03 | Fiber ring
RO-10 | IRB-SU-0550 | SU | Rooftop | Irbid | Irbid | 32.5033 | 35.8573 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R03 | Fiber ring
RO-10 | IRB-SU-0551 | SU | Monopole / greenfield | Irbid | Irbid | 32.5033 | 35.8655 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R03 | Fiber ring
RO-10 | IRB-SU-0552 | SU | Monopole / greenfield | Irbid | Irbid | 32.5033 | 35.871 | 32 | 3 | HUB-IRB-20 | HUB-IRB-20-R03 | Fiber ring
RO-10 | IRB-SU-0560 | SU | Monopole / greenfield | Irbid | Irbid | 32.5084 | 35.7925 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R01 | Fiber ring
RO-10 | IRB-SU-0561 | SU | Monopole / greenfield | Irbid | Irbid | 32.5084 | 35.802 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R01 | Fiber ring
RO-10 | IRB-SU-0562 | SU | Monopole / greenfield | Irbid | Irbid | 32.5084 | 35.8075 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R02 | Fiber ring
RO-10 | IRB-SU-0563 | SU | Monopole / greenfield | Irbid | Irbid | 32.5084 | 35.8157 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R03 | Fiber ring
RO-10 | IRB-SU-0564 | SU | Monopole / greenfield | Irbid | Irbid | 32.5072 | 35.8211 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R02 | Fiber ring
RO-10 | IRB-SU-0565 | SU | Monopole / greenfield | Irbid | Irbid | 32.5095 | 35.828 | 32 | 3 | HUB-IRB-10 | HUB-IRB-10-R02 | Fiber ring
RO-10 | IRB-SU-0574 | SU | Monopole / greenfield | Irbid | Irbid | 32.514 | 35.7911 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R01 | Fiber ring
RO-10 | IRB-SU-0575 | SU | Monopole / greenfield | Irbid | Irbid | 32.5134 | 35.7986 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R01 | Fiber ring
RO-10 | IRB-SU-0576 | SU | Monopole / greenfield | Irbid | Irbid | 32.5123 | 35.8041 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R02 | Fiber ring
RO-10 | IRB-SU-0577 | SU | Monopole / greenfield | Irbid | Irbid | 32.5134 | 35.8123 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R02 | Fiber ring
RO-10 | IRB-SU-0586 | SU | Rooftop | Irbid | Irbid | 32.5174 | 35.787 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R01 | Fiber ring
RO-10 | IRB-SU-0587 | SU | Monopole / greenfield | Irbid | Irbid | 32.5185 | 35.7925 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R01 | Fiber ring
RO-10 | IRB-SU-0588 | SU | Monopole / greenfield | Irbid | Irbid | 32.5174 | 35.8007 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R02 | Fiber ring
RO-10 | IRB-SU-0589 | SU | Monopole / greenfield | Irbid | Irbid | 32.5185 | 35.8088 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R02 | Fiber ring
RO-10 | IRB-SU-0596 | SU | Monopole / greenfield | Irbid | Irbid | 32.5248 | 35.7836 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R04 | Fiber ring
RO-10 | IRB-SU-0597 | SU | Monopole / greenfield | Irbid | Irbid | 32.5224 | 35.7904 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R03 | Fiber ring
RO-10 | IRB-SU-0598 | SU | Monopole / greenfield | Irbid | Irbid | 32.5248 | 35.7972 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R03 | Fiber ring
RO-10 | IRB-SU-0599 | SU | Monopole / greenfield | Irbid | Irbid | 32.5248 | 35.8041 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R03 | Fiber ring
RO-10 | IRB-SU-0605 | SU | Monopole / greenfield | Irbid | Irbid | 32.5275 | 35.7802 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R04 | Fiber ring
RO-10 | IRB-SU-0606 | SU | Monopole / greenfield | Irbid | Irbid | 32.5275 | 35.787 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R04 | Fiber ring
RO-10 | IRB-SU-0607 | SU | Monopole / greenfield | Irbid | Irbid | 32.5287 | 35.7952 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R03 | Fiber ring
RO-10 | IRB-SU-0608 | SU | Monopole / greenfield | Irbid | Irbid | 32.5287 | 35.802 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R03 | Fiber ring
RO-10 | IRB-SU-0614 | SU | Monopole / greenfield | Irbid | Irbid | 32.5326 | 35.7768 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R04 | Fiber ring
RO-10 | IRB-SU-0615 | SU | Monopole / greenfield | Irbid | Irbid | 32.5338 | 35.7822 | 32 | 3 | HUB-IRB-14 | HUB-IRB-14-R04 | Fiber ring
RO-10 | IRB-U-0125 | U | Monopole / greenfield | Irbid | Irbid | 32.5252 | 35.8125 | 30 | 3 | HUB-IRB-14 | HUB-IRB-14-R02 | Fiber ring
RO-10 | IRB-U-0144 | U | Monopole / greenfield | Irbid | Irbid | 32.5287 | 35.8101 | 30 | 3 | HUB-IRB-14 | HUB-IRB-14-R03 | Fiber ring
RO-10 | MUT-SU-0001 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0688 | 35.6949 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R01 | Fiber ring
RO-10 | MUT-SU-0002 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0676 | 35.7017 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R02 | Fiber ring
RO-10 | MUT-SU-0003 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0676 | 35.7085 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R02 | Fiber ring
RO-10 | MUT-SU-0004 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0727 | 35.6846 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R01 | Fiber ring
RO-10 | MUT-SU-0005 | SU | Rooftop | Mutah-Mazar | Karak | 31.0727 | 35.6914 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R01 | Fiber ring
RO-10 | MUT-SU-0006 | SU | Rooftop | Mutah-Mazar | Karak | 31.0733 | 35.6976 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R02 | Fiber ring
RO-10 | MUT-SU-0007 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0727 | 35.7051 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R02 | Fiber ring
RO-10 | MUT-SU-0008 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0721 | 35.7112 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R02 | Fiber ring
RO-10 | MUT-SU-0009 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0778 | 35.6894 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R01 | Fiber ring
RO-10 | MUT-SU-0010 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0778 | 35.6935 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R01 | Fiber ring
RO-10 | MUT-SU-0011 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0766 | 35.7017 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R02 | Fiber ring
RO-10 | MUT-SU-0012 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0778 | 35.7085 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R02 | Fiber ring
RO-10 | MUT-SU-0013 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0766 | 35.7153 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R03 | Fiber ring
RO-10 | MUT-SU-0014 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0817 | 35.6846 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R01 | Fiber ring
RO-10 | MUT-SU-0015 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0817 | 35.6914 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R01 | Fiber ring
RO-10 | MUT-SU-0016 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0829 | 35.6983 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R01 | Fiber ring
RO-10 | MUT-SU-0017 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0817 | 35.7051 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R03 | Fiber ring
RO-10 | MUT-SU-0018 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0817 | 35.7119 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R03 | Fiber ring
RO-10 | MUT-SU-0019 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0829 | 35.7201 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R03 | Fiber ring
RO-10 | MUT-SU-0020 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0868 | 35.688 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R05 | Fiber ring
RO-10 | MUT-SU-0021 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0868 | 35.6949 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R05 | Fiber ring
RO-10 | MUT-SU-0022 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.088 | 35.7017 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R04 | Fiber ring
RO-10 | MUT-SU-0023 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.088 | 35.7085 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R03 | Fiber ring
RO-10 | MUT-SU-0024 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0892 | 35.7153 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R03 | Fiber ring
RO-10 | MUT-SU-0025 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0925 | 35.6839 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R05 | Fiber ring
RO-10 | MUT-SU-0026 | SU | Rooftop | Mutah-Mazar | Karak | 31.0919 | 35.6914 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R05 | Fiber ring
RO-10 | MUT-SU-0027 | SU | Rooftop | Mutah-Mazar | Karak | 31.0943 | 35.6983 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R04 | Fiber ring
RO-10 | MUT-SU-0028 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0931 | 35.7051 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R04 | Fiber ring
RO-10 | MUT-SU-0029 | SU | Rooftop | Mutah-Mazar | Karak | 31.0931 | 35.7119 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R03 | Fiber ring
RO-10 | MUT-SU-0030 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0976 | 35.6873 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R05 | Fiber ring
RO-10 | MUT-SU-0031 | SU | Rooftop | Mutah-Mazar | Karak | 31.0982 | 35.6962 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R05 | Fiber ring
RO-10 | MUT-SU-0032 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0982 | 35.7017 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R04 | Fiber ring
RO-10 | MUT-SU-0033 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.0982 | 35.7085 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R04 | Fiber ring
RO-10 | MUT-SU-0034 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.1027 | 35.6921 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R05 | Fiber ring
RO-10 | MUT-SU-0035 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.1033 | 35.6983 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R04 | Fiber ring
RO-10 | MUT-SU-0036 | SU | Monopole / greenfield | Mutah-Mazar | Karak | 31.1033 | 35.7051 | 32 | 3 | HUB-MUT-01 | HUB-MUT-01-R04 | Fiber ring
RO-10 | NOR-SU-0001 | SU | Monopole / greenfield | North Shuna | Irbid | 32.5943 | 35.6068 | 32 | 3 | HUB-NOR-01 | HUB-NOR-01-R01 | Fiber ring
RO-10 | NOR-SU-0002 | SU | Monopole / greenfield | North Shuna | Irbid | 32.5949 | 35.6123 | 32 | 3 | HUB-NOR-01 | HUB-NOR-01-R01 | Fiber ring
RO-10 | NOR-SU-0003 | SU | Monopole / greenfield | North Shuna | Irbid | 32.6 | 35.6027 | 32 | 3 | HUB-NOR-01 | HUB-NOR-01-R01 | Fiber ring
RO-10 | NOR-SU-0004 | SU | Monopole / greenfield | North Shuna | Irbid | 32.6 | 35.6109 | 32 | 3 | HUB-NOR-01 | HUB-NOR-01-R01 | Fiber ring
RO-10 | NOR-SU-0005 | SU | Monopole / greenfield | North Shuna | Irbid | 32.6 | 35.6177 | 32 | 3 | HUB-NOR-01 | HUB-NOR-01-R02 | Fiber ring
RO-10 | NOR-SU-0006 | SU | Monopole / greenfield | North Shuna | Irbid | 32.6051 | 35.5993 | 32 | 3 | HUB-NOR-01 | HUB-NOR-01-R01 | Fiber ring
RO-10 | NOR-SU-0007 | SU | Monopole / greenfield | North Shuna | Irbid | 32.6063 | 35.6061 | 32 | 3 | HUB-NOR-01 | HUB-NOR-01-R01 | Fiber ring
RO-10 | NOR-SU-0008 | SU | Monopole / greenfield | North Shuna | Irbid | 32.6051 | 35.6129 | 32 | 3 | HUB-NOR-01 | HUB-NOR-01-R02 | Fiber ring
RO-10 | NOR-SU-0009 | SU | Monopole / greenfield | North Shuna | Irbid | 32.6039 | 35.6198 | 32 | 3 | HUB-NOR-01 | HUB-NOR-01-R02 | Fiber ring
RO-10 | NOR-SU-0010 | SU | Monopole / greenfield | North Shuna | Irbid | 32.6102 | 35.6041 | 32 | 3 | HUB-NOR-01 | HUB-NOR-01-R01 | Fiber ring
RO-10 | NOR-SU-0011 | SU | Rooftop | North Shuna | Irbid | 32.6108 | 35.6102 | 32 | 3 | HUB-NOR-01 | HUB-NOR-01-R01 | Fiber ring
RO-10 | NOR-SU-0012 | SU | Monopole / greenfield | North Shuna | Irbid | 32.6096 | 35.617 | 32 | 3 | HUB-NOR-01 | HUB-NOR-01-R02 | Fiber ring
RO-10 | NOR-SU-0013 | SU | Monopole / greenfield | North Shuna | Irbid | 32.6108 | 35.6239 | 32 | 3 | HUB-NOR-01 | HUB-NOR-01-R02 | Fiber ring
RO-10 | NOR-SU-0014 | SU | Monopole / greenfield | North Shuna | Irbid | 32.6153 | 35.6061 | 32 | 3 | HUB-NOR-01 | HUB-NOR-01-R03 | Fiber ring
RO-10 | NOR-SU-0015 | SU | Monopole / greenfield | North Shuna | Irbid | 32.6153 | 35.6143 | 32 | 3 | HUB-NOR-01 | HUB-NOR-01-R02 | Fiber ring
RO-10 | NOR-SU-0016 | SU | Monopole / greenfield | North Shuna | Irbid | 32.6164 | 35.6198 | 32 | 3 | HUB-NOR-01 | HUB-NOR-01-R02 | Fiber ring
RO-10 | NOR-SU-0017 | SU | Monopole / greenfield | North Shuna | Irbid | 32.6204 | 35.6095 | 32 | 3 | HUB-NOR-01 | HUB-NOR-01-R03 | Fiber ring
RO-10 | NOR-SU-0018 | SU | Monopole / greenfield | North Shuna | Irbid | 32.6204 | 35.6177 | 32 | 3 | HUB-NOR-01 | HUB-NOR-01-R03 | Fiber ring
RO-10 | NOR-SU-0019 | SU | Monopole / greenfield | North Shuna | Irbid | 32.6254 | 35.6061 | 32 | 3 | HUB-NOR-01 | HUB-NOR-01-R03 | Fiber ring
RO-10 | NOR-SU-0020 | SU | Monopole / greenfield | North Shuna | Irbid | 32.6254 | 35.6129 | 32 | 3 | HUB-NOR-01 | HUB-NOR-01-R03 | Fiber ring
RO-10 | SOU-SU-0001 | SU | Monopole / greenfield | South Shuna | Balqa | 31.8873 | 35.6163 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R01 | Fiber ring
RO-10 | SOU-SU-0002 | SU | Monopole / greenfield | South Shuna | Balqa | 31.8873 | 35.6232 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R01 | Fiber ring
RO-10 | SOU-SU-0003 | SU | Monopole / greenfield | South Shuna | Balqa | 31.8873 | 35.6314 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R02 | Fiber ring
RO-10 | SOU-SU-0004 | SU | Monopole / greenfield | South Shuna | Balqa | 31.8924 | 35.6129 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R01 | Fiber ring
RO-10 | SOU-SU-0005 | SU | Monopole / greenfield | South Shuna | Balqa | 31.8924 | 35.6198 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R01 | Fiber ring
RO-10 | SOU-SU-0006 | SU | Monopole / greenfield | South Shuna | Balqa | 31.8924 | 35.6266 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R01 | Fiber ring
RO-10 | SOU-SU-0007 | SU | Monopole / greenfield | South Shuna | Balqa | 31.8969 | 35.6102 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R01 | Fiber ring
RO-10 | SOU-SU-0008 | SU | Monopole / greenfield | South Shuna | Balqa | 31.8974 | 35.6163 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R04 | Fiber ring
RO-10 | SOU-SU-0009 | SU | Monopole / greenfield | South Shuna | Balqa | 31.8974 | 35.6232 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R01 | Fiber ring
RO-10 | SOU-SU-0010 | SU | Monopole / greenfield | South Shuna | Balqa | 31.898 | 35.6307 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R02 | Fiber ring
RO-10 | SOU-SU-0011 | SU | Monopole / greenfield | South Shuna | Balqa | 31.8974 | 35.6382 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R02 | Fiber ring
RO-10 | SOU-SU-0012 | SU | Monopole / greenfield | South Shuna | Balqa | 31.9025 | 35.6129 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R04 | Fiber ring
RO-10 | SOU-SU-0013 | SU | Monopole / greenfield | South Shuna | Balqa | 31.9025 | 35.6198 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R04 | Fiber ring
RO-10 | SOU-SU-0014 | SU | Monopole / greenfield | South Shuna | Balqa | 31.9025 | 35.6279 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R03 | Fiber ring
RO-10 | SOU-SU-0015 | SU | Monopole / greenfield | South Shuna | Balqa | 31.9014 | 35.6334 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R02 | Fiber ring
RO-10 | SOU-SU-0016 | SU | Monopole / greenfield | South Shuna | Balqa | 31.9014 | 35.6402 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R02 | Fiber ring
RO-10 | SOU-SU-0017 | SU | Monopole / greenfield | South Shuna | Balqa | 31.9088 | 35.6095 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R04 | Fiber ring
RO-10 | SOU-SU-0018 | SU | Monopole / greenfield | South Shuna | Balqa | 31.9088 | 35.6163 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R03 | Fiber ring
RO-10 | SOU-SU-0019 | SU | Monopole / greenfield | South Shuna | Balqa | 31.9088 | 35.6232 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R03 | Fiber ring
RO-10 | SOU-SU-0020 | SU | Monopole / greenfield | South Shuna | Balqa | 31.9088 | 35.63 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R03 | Fiber ring
RO-10 | SOU-SU-0021 | SU | Monopole / greenfield | South Shuna | Balqa | 31.9088 | 35.6368 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R02 | Fiber ring
RO-10 | SOU-SU-0022 | SU | Monopole / greenfield | South Shuna | Balqa | 31.9127 | 35.6211 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R03 | Fiber ring
RO-10 | SOU-SU-0023 | SU | Monopole / greenfield | South Shuna | Balqa | 31.9127 | 35.6279 | 32 | 3 | HUB-SOU-01 | HUB-SOU-01-R03 | Fiber ring

## Indoor
Rollout | Venue | Type | n78 pRRU | n258 heads
RO-02 | Abdali Mall | mall | 248 | 10
RO-02 | The Boulevard - Abdali | mixed-use | 110 | 4
RO-02 | Galleria Mall | mall | 66 | 4
RO-02 | Al Baraka Mall | mall | 50 | 4
RO-02 | Istiklal Mall | mall | 66 | 4
RO-02 | Four Seasons Amman | hotel | 66 | 2
RO-02 | The St. Regis Amman | hotel | 88 | 2
RO-02 | The Ritz-Carlton Amman | hotel | 79 | 2
RO-02 | Fairmont Amman | hotel | 103 | 4
RO-02 | W Amman | hotel | 86 | 2
RO-02 | Amman Rotana | hotel | 125 | 4
RO-02 | InterContinental Jordan | hotel | 130 | 4
RO-02 | Amman Marriott | hotel | 89 | 2
RO-02 | Kempinski Amman | hotel | 83 | 2
RO-02 | Le Royal Amman | hotel | 105 | 2
RO-02 | Sheraton Amman | hotel | 84 | 2
RO-02 | Landmark Amman | hotel | 79 | 2
RO-02 | Crowne Plaza Amman | hotel | 83 | 2
RO-03 | Taj Lifestyle Center | mall | 164 | 6
RO-03 | Grand Hyatt Amman | hotel | 99 | 4
RO-03 | Al-Bashir Hospital | hospital | 130 | 2
RO-03 | Amman Intl Stadium / Al-Hussein Youth City | stadium | 50 | 24
RO-03 | Yarmouk University | campus | 130 | 2
RO-04 | City Mall | mall | 175 | 7
RO-04 | Mecca Mall | mall | 208 | 8
RO-04 | King Hussein Business Park | campus | 130 | 2
RO-04 | University of Jordan | campus | 270 | 2
RO-04 | Jordan University Hospital | hospital | 103 | 2
RO-04 | King Hussein Cancer Center | hospital | 119 | 2
RO-04 | Ayla Oasis / Hyatt Regency | resort | 112 | 2
RO-04 | Al Manara - Saraya Aqaba | hotel | 69 | 2
RO-04 | Kempinski Aqaba | hotel | 64 | 2
RO-04 | InterContinental Aqaba | hotel | 81 | 2
RO-04 | Movenpick Aqaba | hotel | 90 | 2
RO-04 | Aqaba Gateway / City Center | mall | 44 | 4
RO-04 | King Hussein Intl Airport (Aqaba) | airport | 25 | 6
RO-04 | Arabella Mall Irbid | mall | 55 | 4
RO-05 | Irbid City Centre | mall | 88 | 4
RO-06 | Kempinski Ishtar Dead Sea | hotel | 111 | 4
RO-06 | Movenpick Dead Sea | hotel | 109 | 4
RO-06 | Dead Sea Marriott | hotel | 80 | 2
RO-06 | Hilton Dead Sea | hotel | 90 | 2
RO-06 | Crowne Plaza Dead Sea | hotel | 126 | 4
RO-06 | King Hussein Bin Talal Convention Centre | convention | 42 | 6
RO-06 | Movenpick Petra | hotel | 52 | 2
RO-06 | Petra Marriott | hotel | 31 | 2
RO-06 | Petra Visitor Centre | venue | 9 | 2
RO-08 | JUST campus | campus | 216 | 2
RO-08 | King Abdullah University Hospital | hospital | 103 | 2
RO-10 | Queen Alia Intl Airport terminal | airport | 172 | 13
RO-10 | Tala Bay resort cluster | resort | 252 | 4